Annual Review

Title: Aawaz II Inclusion, Accountability and Reducing Modern Slavery Programme
Programme Value £ (full life): £49,142,613		Review date: 13 August 2021
Programme Code: 204605	AMP start date: 01 August 2015	AMP end date: 31 March 2024
[note] Aawaz means “voice” in Urdu.

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021
Overall Output Score	B	A	B	A	A	A
Risk Rating	Moderate	Moderate	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/49846919.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/61765454.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
Aawaz II aims to increase voice, choice and control for women, girls, boys, youth, religious minorities and marginalised groups; protect them from exploitation; and prevent discrimination and intolerance. The programme has prioritised: child labour; child and forced marriages; gender-based violence (GBV); and discrimination and intolerance to which marginalised groups are extremely vulnerable. By March 2024, Aawaz II aims to benefit at least 7 million people in Punjab and Khyber Pakhtunkhwa (KP), with engagement also at the federal level. The interventions are in two broad clusters, “institutional development” and “community empowerment”, and focus on:
[note] The programme has a special focus on “modern slavery” ‑ an umbrella term for situations in which one person or a group of persons is forcibly controlled by an individual or group for the purpose of exploitation. Aawaz II has prioritised child labour, and child and forced marriages as forms of modern slavery.

- Building the evidence base to inform actions and government policies: to prevent exploitation and abuse of marginalised groups. This includes, for example, technical support for the government’s Child Labour Survey, gathering feedback directly from marginalised groups, and surveys for measuring social attitudes and women’s well-being.
- Providing technical support for legislative and system reforms: including for digital birth registration and Civil Registration and Vital Statistics (CRVS) systems to enable children to have citizenship identity; supporting laws and policies for advancing rights of children, women and girls, transgender, and persons with disabilities. The programme is also supporting establishment of government-owned protection, response and referral systems for children, women and girls.
- Empowering communities to improve access to information, services and rights, for example, through Aawaz Aagahi Centres (AACs). These Centres provide information to marginalised groups on their rights and connect them with a range of social services.
- Providing a safe space for communities to debate and promote positive social behaviours to reduce harmful practices such as child labour, gender-based violence, child and forced marriages, and intolerance against marginalised communities.
- Pre-empting community conflicts: including through an early warning and response mechanism to identify conflicts and discrimination and facilitate community members, including youth volunteers and local influential leaders to address triggers of conflict and pre-empt escalation.
- Risk communication and psychosocial support targeted to children, women and girls who are affected or are vulnerable to violence or mental health issues as a result of the Covid pandemic.
The programme has a hybrid delivery model which draws on the skills and capability of the United Nations (UN) for institutional development, and the British Council (BC) as a contracted supplier for community empowerment. The former is called the United Nations Joint Programme (UNJP) which is implemented by two UN agencies – the United Nations Children’s Fund (UNICEF) and the United Nation’s Population Fund (UNFPA). UNICEF Pakistan is the Convening Agency for UNJP. The community empowerment component will be implemented in 45 districts of Punjab and KP over the life of the programme; the current phase is covering 22 districts. The role of monitoring, and consolidation of data and management frameworks is performed by the Alignment Monitoring and Results (AMAR) unit led by Development Alternatives Inc. (DAI). The programme builds on successes of its predecessor Aawaz – Voice and Accountability programme which ended in May 2018.

The review period (July 2020 to June 2021) corresponds to the first full year since the simplification of the programme’s structure, partnerships and thematic focus ahead of the 2020 annual review. This has provided the much-needed stability and focus in the strategic direction and governance arrangements for both UNJP and BC-led components. However, two factors in the broader operating context slowed down some interventions: continued impact of Covid and budget cuts. The third wave of the pandemic which began in March particularly affected British Council’s ability to deliver face-to-face activities on ground. Alongside, internal delays in allocation of the programme budget had a knock-on effect on disbursement of funds to UNJP, resulting in delays particularly in UNFPA’s activities. However, the overall progress exceeded expectations.
[note] The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of Gross National Income (GNI) as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID. The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

Summary supporting narrative for the overall score in this review
The programme has scored an ‘A’ i.e. ‘exceeded expectations’. Out of five outputs, outputs 1, 3 and 4 exceeded expectations; output 2 met expectations; whereas outputs 5 moderately did not meet expectations. During the review period, UNJP and the British Council both delivered on most of the milestones across all outputs. Most of the targets related to birth registration and community engagement exceeded expectations. 90% of the recommendations from the 2020 annual review are completed; the remaining are progressing well (see Annex A). During the review year, the programme reached a total of 20.2 million direct and 6.6 million indirect beneficiaries, with the proportion of women and girls ranging from 30% to 57% in different interventions. Key achievements included:

Child labour/child protection:
- The Child Labour Survey completed in Punjab and a draft report prepared. In KP, recruitment of survey staff is underway.
- Over 2.3 million births registered cumulatively to date. 10 programme-supported birth registration (BR) units handed over to Punjab and KP. Both provincial governments are scaling up systems modelled by these units across all districts.
- Reforms in child protection legislation and systems have progressed to next stage. A Child Protection Policy has been drafted, and Civil Registration and Vital Statistics (CRVS) national policy tabled by the Planning Commission and endorsed by the provincial governments and rules and regulations revised and notified in Punjab and submitted to the Cabinet in Khyber Pakhtunkhwa. Design of Child Protection Case Management and Referral Systems in KP, Punjab and Islamabad Capital Territory (ICT) prepared.
Child and forced marriages:
Two political economy assessments of child marriage completed in Punjab and KP. UNFPA and UN Women have signed a memorandum of understanding (MoU) to support measures for enactment of child marriage restraint laws.
Gender-based violence (GBV):
- Training provided to 19 provincial government departments (11 Punjab, 8 KP) to implement Sexual Harassment at Workplace Act 2010.
- Three roadmaps developed to support implementation of Criminal Law Amendment related to sexual violence (including rape), development of a sexual harassment framework, and strengthening the Commissions on the Status of Women.
- Establishment of multi-sectoral coordination platform for prevention and response to GBV in KP is at advance stage. A committee has been established at Planning Department and a Working Group formed within Social Welfare Department to spearhead this work.
- 4,718 individuals (57% women and girls) directly accessed programme-supported psychosocial counselling and GBV referral services.
Community outreach and social inclusion:
- 880 community forums established and operational in target districts and working as safe spaces for marginalised communities to debate and reduce harmful social practices through local social action projects.
- 455 collective community actions completed by trained village and district forums on Aawaz thematic areas (KP 148, Punjab 307).
- 90,292 individuals received information on services (KP 25,317, Punjab 64,975): 32,608 female, 56,688 male, 996 transgenders, 5,651 minority representative, and 2,551 persons with disabilities (PWDs).
- 6,770 individuals accessed services as a result of programme-supported referrals (KP 2,316, Punjab 4,454): 3,680 females, 2,955 males, 135 transgender, 183 minority representative, 378 persons with disabilities.
- 1557 conflicts pre-empted (KP 374, Punjab 1183) including 724 domestic and sexual violence. Other cases related to community conflict e.g., property disputes, family, cases of early and forced marriages, violence against transgenders, discrimination against religious minorities, child abuse, and sectarian conflicts.
While most of the milestones either met or exceeded expectations, progress remained slow in some areas, notably Child Labour Survey and finalisation of child protection law in line with the Convention on the Rights of the Children (CRC) in KP. UNFPA’s psychosocial support helpline and training of the service providers moderately fell short of targets due to a focus on preparation of roadmaps and finalisation of new partnerships to deliver the roadmaps, and subsequent delays in signing off partnerships as a result of delayed disbursement of tranche from FCDO. The British Council’s work on Knowledge, Attitudes and Practices (KAP) survey could not be initiated due to impacts of the pandemic. Progress fell short of expectation in few areas: a decline in self-assessment of district staff about programme alignment, mutual coordination and communication; procurement of FCDO-managed M&E supplier; notification of provincial coordination groups, and slower progress on final round of rapid assessments and implementation of recommendations. During the third wave of Covid in March-June, the progress considerably slowed down. While the strategic direction is more stable and predictable, the programme will need to demonstrate flexibility to operate within the constraints posed by Covid and any future implications on the programme budget.

Key lessons learnt during the year
Virtual versus in-person mode of delivery: While virtual delivery of trainings, meetings, research, and community engagement interventions reduces costs, there are significant trade-offs with quality of conversations with beneficiaries, and exclusion of those without smart digital devices. With vaccination rollout and more awareness about the behaviours of the pandemic, it is now possible to mitigate the risks of infection and manage the trade-offs by investing efforts to ensure adherence with Covid Standard Operating Procedures (SoPs) instead of reverting to virtual delivery. In some instances, costs of in-person delivery will be higher than usual (e.g. hiring larger venues to maintain social distancing), but higher quality of work outweighs the costs.

Continuous engagement with senior leadership at provincial level, in addition to line departments, is vital for continuity of legislative and system reforms. This is an important strategy to mitigate risks associated with reshuffle of senior officials within counterpart line departments, which causes disruption and delays in adoption of reforms.

Inclusive safe spaces reduce identity stigma and sensitivities. There is early evidence from village forums that transgender, religious minorities, and persons with disabilities are more likely to share their identity and problems related to their own protected characteristics (e.g. faith, disability) in local forums. This is because these forums also provide them a platform to raise collective issues facing their communities. This has enabled the programme to collect better data on protected characteristics of individuals.

Dialogue on harmful social practices at grassroots is not possible without considerations for larger community preferences. Aawaz II programme focuses on child labour, gender-based violence, child marriage and discrimination against minorities. However, discussions within village and district forums cannot be restricted to these thematic priorities as community members are also keen to find solutions to other problems such as schools, hospitals, water, roads, etc. It is important for community engagement programmes to respond to larger community issues to engage them in processes and reforms for changing social norms and behaviours.
Key recommendations
A fuller set of recommendations is set out separately under each section and output. A summary of overarching recommendations for the year ahead is provided below.
Coordination between Aawaz II and Open Societies Programme: FCDO should set up a coordination mechanism to manage risks of duplication between Aawaz II and the new Open Societies Programme (OSP) for strands of work related to legislative reforms, systems strengthening and criminal justice system for child protection. A technical working group with representation from all partners should be set up for this purpose (FCDO, October 2021).

Direction of technical assistance for birth registration systems: As the provincial governments are scaling up UNICEF-supported birth registration models, UNICEF should reset the scope of its technical assistance with a greater focus on capacity building, data quality validation, data disaggregation, and service delivery standards. Discussions with government partners and changes in workplans for this strand of work should be completed and agreed with FCDO (UNICEF, November 30, 2021).

GBV multi-sectoral coordination platform: UNFPA should pivot technical assistance to expedite the establishment of multi-sectoral GBV coordination platform in Punjab, building on experience and lessons from KP. Practical measures and deliverables for this purpose should be agreed with FCDO (UNFPA, September 30, 2021).

Transition to second phase of community engagement: The timeframe for community-based work in existing 22 districts should be extended to June 2022 to allow more time for forums and safe spaces to mature and to deliver the ambition agreed with FCDO up to the mid-term stage (BC and FCDO, November 2021). The mid-term review should be completed by April / May 2022 to guide the planning and adaptations for Phase 2 (FCDO, March 2022).

Domestic violence: Aawaz II should extend the GBV focus to domestic violence. UNFPA should conduct a scoping study to assess the need for programme’s intervention at Federal level and in Punjab and Khyber Pakhtunkhwa and adapt programme strategy and work plans accordingly (UNFPA, January 2021).

Safeguarding: British Council should initiate an expert review of safeguarding risks related to sexual exploitation, abuse and harassment (SEAH), looking particularly into types of possible triggers within the management structures of partner NGOs, mixed participation of males and females in forums and outreach teams, and participation of transgender in programme activities should be completed, and an action plan implemented to mitigate those risks (British Council, November 30, 2021).

Transition to FCDO-managed monitoring and evaluation supplier: AMAR should ensure that a detailed handover note is submitted to FCDO and the Project Completion Review (PCR) incorporates learning, especially from the execution of rapid assessments (hiring of consultants, format, methodology, quality assurance) (AMAR, November 2021).

Targets for next year should be updated in the log-frame. Those areas where a solid delivery channel has been established and milestones were exceeded, more ambitious targets should be set in consultation with implementing partners (FCDO, October 2021).

Acronyms
AACs	Aawaz Aagahi Centres
Aawaz II	Aawaz II - Inclusion, Accountability, and Reducing Modern Slavery Programme
AMAR	Alignment, Monitoring and Results Unit
AR	Annual Review
BR	Birth Registration
CLS	Child Labour Survey
CP	Child Protection
CP-CMRS	Child Protection Case Management and Referral System
CRVS	Civil Registration and Vital Statistics
CSWs	Commissions on the Status of Women
DBR	Digital Birth Registration
EAD	Economic Affairs Division – Government of Pakistan
FCDO	Foreign, Commonwealth and Development Office
GoP	Government of Pakistan
GBV	Gender-Based Violence
HMG	Her Majesty’s Government
KAP	Knowledge, Attitudes and Practices
KPCSW	Khyber Pakhtunkhwa Commission on the Status of Women
KP	Khyber Pakhtunkhwa
KPMD	Khyber Pakhtunkhwa Merged Districts
LNB	Leave No One Behind
MEL	Monitoring, Evaluation and Learning
NGO	Non-government organisation
PCSW	Punjab Commission on the Status of Women
PEA	Political Economy Assessment
PMU	Programme Management Unit
PWDs	Persons with Disabilities
SEAH	Sexual Exploitation, Abuse and Harassment
SNG II	Sub-National Governance Programme II
SRO	Senior Responsible Owner
SOPs	Standard Operating Procedures
SWD	Social Welfare Department
UN Women	United Nations Entity for Gender Equality and the Empowerment of Women
UN	United Nations
UNFPA	United Nation’s Population Fund
UNICEF	United Nations Children’s Fund
UNJP	United Nations Joint Programme
VfM	Value for Money

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
The expected impact of the programme is “a more inclusive, tolerant and peaceful Pakistan, with less modern slavery”. The intended outcome is that “Pakistani society and government institutions support increased voice, choice and control for women, girls, boys, youth, religious minorities and marginalised groups, protect them from exploitation and prevent discrimination and intolerance at all levels.” This outcome is reflected in four pillars in the Business Case: (1) institutional strengthening; (2) community engagement; (3) conflict prevention; and (4) coordination, monitoring and reporting. These pillars are expressed in five outputs as follows:

- Strengthening institutions for child protection, with a focus on child labour with effective legislative frameworks, evidence-based policies, strategies and sustainable child protection system.
- Strengthening institutions for ending gender-based violence and child marriage, supporting government institutions for effective policies and action plans for the protection of women and girls’ rights.
- Empowering marginalised communities for reducing modern slavery through enhanced citizen information, coalitions of change, leadership skills, voice and actions.
- Preventing community conflict and promoting tolerance by promoting tolerance and non-discrimination, including through early warning and response mechanisms for preventing conflicts.
- Monitoring, evaluation and learning for improved programme performance.
See Annex B for the programme’s theory of change diagram.

The FCDO team and partners reviewed the theory of change in December 2020. It remains relevant in the current operating environment. Social exclusion of marginalised groups from rights and services generally increases during pandemics (e.g. child labour, gender-based violence, child and forced marriages and discrimination). The pathways of change and assumptions hold true and therefore there were no changes in the theory of change.

Contributions towards expected outcomes and impact
A detailed assessment of programme’s performance at impact and outcome level is not feasible at this stage in the programme cycle with most of interventions led by UNFPA and British Council being in their early phase. Similarly, UNICEF’s work on development of child protection case management and referral systems is also in infancy. Institutional reforms and behaviour change activities will take time to come to fruition but during the inception phase, the programme agreed data sources for impact and outcome indicators.

At the impact level, the programme monitors Pakistan’s position on three global indices: the Global Slavery Index; the Voice and Accountability Score in the Worldwide Governance Indicators; and the Global Gender Gap Index. The fourth indicator aims to measure change in the prevalence of child labour, early marriages, and GBV in Punjab and Khyber Pakhtunkhwa using secondary data sources such as the Pakistan Demographic and Health Survey. New data against the baseline is available for the first three indicators and suggests mixed progress:

- Pakistan’s ranking on the Global Slavery Index improved two places in 2018, dropping to the 8th highest prevalence of modern slavery out of 167 countries, from the 6th position in 2016. No further data after 2018 is available yet.
  [note] Most of the modern slavery interventions under Aawaz had not started until later in 2018, and therefore, we do not see a correlation between this shift and the programme work.
- The voice and accountability ranking on the Worldwide Governance Indicators is low and has remained almost static since 2009.
  [note] The 2021 update of the WGI with data through 2020 will available in September 2021
- Pakistan remains at the bottom of the Global Gender Gap Index. It further slipped two places in 2020, ranked 153 out of 156 countries.
At the outcome level, the programme measures progress towards government’s adoption and scale up of programme-supported system reforms, legislation and other initiatives in the priority areas, total outreach, and changes in knowledge, attitudes and practices of individuals within the target communities in Punjab and Khyber Pakhtunkhwa. Progress is summarised below:

Outcome indicator 1 – adoption or scale-up of initiatives: Overachieved: The milestone for this year was that at least 5 initiatives would be scaled up or adopted. This target was achieved as UNICEF handed over 10 birth registration units to the provincial governments of Punjab and KP. Both governments have also embarked on scaling up the delivery models for birth registration. This will increase the number of children with citizenship identity and for better planning within government. Adoption of GBV multi-sectoral coordination platform is notified by the Planning and Development Department (P&D).

Outcome indicator 2 - progress on legislative reforms: Partially achieved: All legislative reforms have progressed further. Amendments to KP Child Protection Act 2010 have been submitted to the Social Welfare Department for review; this process had to be re-initiated due to change of department’s leadership. A child protection policy is being prepared in Punjab with technical assistance from UNICEF. UNFPA has signed a Memorandum of Understanding (MoU) with the Minister of Law and Justice to support implementation of Criminal Law Amendments related to sexual violence and rape.

Outcome indicator 3 - overall reach: Overachieved: The programme component of BC activities reached 11.7 million direct and approximately 4.1 million indirect beneficiaries through birth registration, psychosocial support, participation in safe spaces, radio programmes for behaviour change messages, information and referral services. This has exceeded expectation this year, mainly due to the large outreach through registration of births in KP and radio programmes in both provinces.

Outcome indicator 4 – change in knowledge, attitudes, practices: Delayed. The knowledge, attitudes and practices (KAP) survey which was scheduled last year could not be initiated during the review period owning to pandemic -related constraints. Preparatory work has now been initiated.

Overall, we assess that the programme is currently on track to achieve its intended outcomes. However, as highlighted in the 2020 annual review as well, Covid is increasing the risks of child labour due to loss of livelihoods. The incidence of violence against children and women is also increasing. Therefore, the baseline, assumptions and milestones at the impact and outcome level indicators will need to be revisited in the year ahead. Last year’s annual review predicted, “reversal of gains in Pakistan’s position on global indices cannot be ruled out.” The latest Gender Gap Index has validated this prediction as Pakistan has dropped two spots in its global ranking on this index.
[note] UNICEF and ILO estimate that millions of more children are at risk of being pushed into child labour due to Crisis, which could lead to the first rise in child labour after 20 years of progress. https://data.unicef.org/resources/Covid -and-child-labour-a-time-of-crisis-a-time-to-act
[note] According to UN Women, violence against women and girls has increased by 25-30% in many countries since March 2020. This percentage is likely to be higher in Pakistan due to strong impacts of the epidemic on economy, livelihoods, health and security. In UNICEF’s survey under Aawaz II, 34.5% of respondents believed that people were screaming at or slapping their children more because of the confinement.

Value for money (VfM): Justification for the programme to continue
The review team assessed that the programme is providing good VfM and should continue.

The major cost drivers identified in the Business Case are the costs of trainings, establishment and operational expenses of participation forums and AACs. The Business Case also expected that UN partner agencies will also use their own sources for sharing the programme costs. It recognised, however, that there are challenges in producing simple benefit-cost ratios for Aawaz II because it aims to achieve social benefits which are often unquantifiable. Therefore, it recommended a case study approach to capture social, cultural and economic benefits of select interventions.

The Business Case’s propositions about the cost drivers and the challenges in quantifying the benefits continue to be valid. During the review period, an extensive effort was made to update programme’s VfM framework in consultation with all partners. The UNJP and the British Council have provided data on a mix of quantitative and qualitative indicators. While more time is required to assess VfM of some interventions (e.g. legislative reforms and improvements to protection systems), the existing data provides some good examples of economy, efficiency, effectiveness and equity during the review year:

In terms of economy, the recent VfM analysis has estimated unit costs of major interventions. The average cost on registration of a birth is approximately £0.2 which is a significant reduction from last year when this cost was £0.56. This is in line with the expectation that a significant scale-up of BR units will translate into lower costs per beneficiary. UNICEF provided mental health and psychosocial support to 280,812 people at an average cost of £1.23. In the community empowerment component, the British Council reached 8.7 million people at a cost of 0.7 pence per person through radio talk shows and audio messages on prevention of intolerance, discrimination, child labour, child and forced marriage, and GBV, lower than the per listener cost of 1.9 pence last year. 59% of listeners reported a change in their perceptions.

In terms of efficiency, the percentage of implementing partner’s administrative cost to total budget remained within acceptable levels: UNFPA (9%), UNICEF (14%), British Council (17%). The technical support and early engagement of UNICEF with the government’s Child Labour Survey and CRVS reforms leveraged increased investments by government and multilaterals. The Government of Pakistan has allocated £135 million for CRVS reform operations with special focus on birth registration coverage. The Government of KP allocated £1.2million (PKR 264 million) for strengthening of the CRVS system. Additionally, the Govt of Punjab allocated £.42million (PKR 95.68 million) for the Child Labour Survey and Government of KP allocated £1.07million (PKR 241 million) for this purpose. Overall, 93% of all milestones were delivered on time.
[note] $188 million, converted into GBP at exchange rate of 1 US$ - 0.72 £ as of 29 July 2021.
[note] 1 £ - 225.29 PKR as of 29 July 2021.

The VfM data has documented examples of programme’s effectiveness. The work under output 1 is laying the foundation for stronger laws and systems for protecting children from modern slavery, abuse, violence, and exploitation. Cumulatively, over 2 million children have been registered, giving them an identity and access to services. The provincial governments are scaling up birth registration models tested with support from the programme. Progress towards establishing a multi-sectoral coordination mechanism is potentially a transformative step to remove operational constraints and weaknesses in GBV-related services of multiple departments. The programme has facilitated 455 collective actions, reached 11.64 million people with messages on prevention of harmful practices, and enabled 6,770 persons to access different services such as social protection, obtaining computerised national identity card and disability certificates, etc. 1557 conflicts have been pre-empted so far which otherwise might have escalated into serious disputes, violence or harm to lives to children and girls. As highlighted above, more than half of these conflicts were about domestic and sexual violence, but also included incidents of violence against transgender and minorities. 203 child and forced marriages were pre-empted.

In terms of equity, Aawaz II has a special focus on social inclusion, rights and protection of children, women and girls, minorities, persons with disabilities, and the transgender community, child and forced marriages, and discrimination. A significant proportion of beneficiaries comprises of women and girls. British Council has made a concerted effort during the review period to increase the inclusion of transgender persons, representatives of religious minorities and persons with disabilities as members of village, district and provincial forums. A breakdown of the coverage of these groups in programme interventions and results is provided in output tables.

Changes in the results framework
The results framework was updated twice during the review period: in line with recommendations of the last annual review, log-frame milestones were revised in December in a joint workshop attended by FCDO, UNJP and British Council. Few indicators which were most affected by the third wave of Covid and delays in FCDO’s tranche to UNJP were reviewed again in April. The SRO approved the changes. There has been no change in output weights or at impact and outcome levels. The log frame will be reviewed by October 2021.
[note] Outcome indicator 4, output indicators 2.1, 2.3, 3.2, 3.4, 4.1 and 4.2.
[note] Ambitious targets will be set for 3.4, 4.2 and 4.3.

Monitoring data, evidence and learning
The programme uses an independent third-party monitoring function i.e. AMAR. It provides support to FCDO for monitoring, assessments and consolidation of log-frame data and management frameworks. The partner agencies also have their own internal monitoring systems which collect and validate qualitative feedback and disaggregate data by age, sex, and location. Disaggregation of data has improved this year for transgender and disability in community engagement interventions. Progress of last year’s AR are attached in Annex A. Some highlights from the review period include:
[note] DAI leads AMAR Unit under a contract managed by UNICEF. The Unit is governed by a Board comprising of representatives from DFID and all implementing partner agencies.

- Qualitative assessments: AMAR has undertaken seven studies to assess the progress and quality of major strands of work. Four studies have been finalised and approved by FCDO and the remaining will be completed by end of July 2021. These reports confirmed the relevance of interventions with needs on ground, but also highlighted challenges and areas of improvement. Implementation of recommendations from final reports is being tracked.
- Lessons learning workshops: British Council organised four learning forums which were attended by 331 staff and young community leaders. These forums brought together NGO partners from 22 districts to share their experiences and what works to change social norms and behaviours.
- Helpdesk learning reports: FCDO commissioned three reports on best practices and lessons from other countries and projects to improve inclusivity in birth registration, GBV helplines and community forums. The South Asia Research Hub (SARH) managed the production of these reports through the Knowledge for Development (K4D) Helpdesk. The partners greatly appreciated the value of these reports and are taking steps to implement recommendations.
- Joint field visit: FCDO, UNJP and the British Council have agreed to conduct at least two joint field visits each year and engage directly with beneficiaries. During the review period, FCDO, UNICEF, UNFPA and British Council carried out two joint visits (one virtual and one in-person) in Punjab, and one virtual visit to KP. This has improved the shared understanding of programme’s objectives and interventions and opened up more opportunities for a joined-up approach.
- Quarterly technical reviews: jointly with all UN implementing partners and the British Council. These reviews tracked progress against annual review’s recommendations, due diligence, work plans and log-frame targets. The reviews also provided an opportunity for all partners to discuss risks, operational challenges and mitigation measures.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened government institutions with effective legislative frameworks, evidence-based policies, strategies and sustainable child protection system.
Output number:		1	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
1.1 Number and type of UNJP's supported legislation, policies and strategies drafted at federal and provincial level for child protection in alignment with international standards	KP: Convention on the Rights of Child (CRC)-aligned Child Protection Bill finalised in KP	A (met expectation) / Delayed. Draft shared with Social Welfare Department to be submitted to the cabinet for approval.
	KP and Punjab: Engagement strategy developed and key implementation steps on track	Completed. Implementation on track.
	CRC-aligned comprehensive child protection legal framework drafted in Punjab. Child Labour Survey (CLS) analysis and recommendations prepared in collaboration with the GoPb. Civil Registration and Vital Statistics (CRVS) National Policy finalised.	Completed
	Punjab: CRVS draft strategy and Action Plan developed and reviewed by the provincial CRVS Steering Committee.	Completed.
	KP: CRVS provincial assessment/ feasibility study initiated.	Completed
	Punjab and KP: CRVS rules and by-laws finalised.	Completed
1.2 Number and type of UNJP's supported actions for child protection systems implemented at federal and provincial level	Punjab: New unit established: 1 / Existing units functional: 3 / Handover to government: 2 / Cumulative: 6 Birth Registration Units functional	A+ (exceeded expectations) / 5 BR units handed over to the government. Scale-up in 36 districts underway.
	KP: Existing units functional: 4 / Handover: 1 / Cumulative: 5 BR units	5 units handed over to government. Scale-up across 30 districts.
	Design of the Child Protection Case Management and Referral System for KP, Punjab and Islamabad Capital Territory (ICT).	Completed
1.3 Number of children registered in KP and Punjab supported by UNJP's interventions	KP: 150,000 (girls, boys) births registered, of which, 70% are under five years of age. / Cumulative: 389,083 births registered.	A (Met expectations) / 892,965 births registered from July 2020 - May 2021 in five programme districts. / Cumulative: 1,375,454 births registered.

	Punjab: 170,000 (girls, boys) births registered, of which, 75% will be under five years of age: / Cumulative: 715,210 births registered.	159,284 births (86% of target) registered from July 2020 – May 2021 in 5 districts. / Cumulative: 1,003,430 births registered.
1.4 Progress of evidence generated on Child Labour and CRVS	Punjab: Child Labour Survey (CLS) Report drafted by the government of Punjab	B (Moderately did not meet expectation) / Completed.
	KP: 20% of CLS data collection completed	Delayed. Recruitment of survey team underway.
	Comprehensive assessment/ feasibility for Punjab completed	Completed
1.5 Number of children, parents and primary caregivers provided with community based mental health and psychosocial support (MHPSS)	7,000 children, parents and primary caregivers will be supported with community based mental health and psychosocial support	A ++ (Substantially exceeded expectations) / Punjab: 270,213 (women and girls: 50%) / KP: 10,599 (women and girls:61%)
1.6 Number of people reached with stigma prevention messages including children	5 million people reached with stigma prevention messages	A++ (Substantially exceeded expectations) / 7.36 million people (Women and girls: 52%)
1.7 A report available on the impact of confinement on violence against children	Final report completed on the impact of Covid on violence against children.	A (Met expectations) / Completed.

Supporting narrative for the score

Description of the output: This output aims to support the government on data, legislative and system reforms and institutional capacity building to promote the rights and protection of children. The major focus is on child labour as a form of modern slavery. UNICEF’s work under this output encompasses a wide range of interventions: technical support for the government’s Child Labour Survey, innovation in birth registration (BR) models and wider Civil Registration and Vital Statistics (CRVS) reforms, improvements in child rights legislation and development of an integrated Child Protection Case Management and Referral System (CP-CMRS). This output requires close engagement and coordination with a range of government departments: Planning and Development, Ministry of Human Rights and the departments of Law and Justice, Social Welfare, Labour, Local Government, and Bureaus of Statistics.

Justification for the overall score: The output scored an “A+” i.e. the performance exceeded expectations. 90% of the milestones were met, exceeded or were on an upward trajectory. Most of the targets related to birth registration substantially exceeded expectations. While Covid continued to pose challenges of mobility and availability of government officials, UNICEF delivered significant results in collaboration with government and non-government counterparts: registration of one million births in Punjab and KP; government’s ownership and scale-up of birth registration systems in both provinces, drafting of child protection policy and Case Management and Referral System in Punjab, and reaching 7.3 million people with messages on stigma prevention. In KP CRC-aligned child protection legislation is finalised, however, enactment is delayed. A brief description of progress on each indicator follows:

Indicator 1.1 – legislation, policies and strategies for child protection: This indicator scored an ‘A’ because most of the milestones either met the expectations in line with 2021 annual review, UNICEF is implementing a strategy to bolster advocacy for legislative reforms and has expanded consultation with non-government stakeholders In Punjab, a comprehensive Child Protection Bill 2021 has been drafted. The CRVS comprehensive assessment was completed in Punjab and would form the basis of a CRVS strategy and action plan for Punjab. The Government of Punjab for the first time has also notified Rules for Birth & Death Registration with special focus on marginalized and disadvantaged communities. In KP, CRVS Rules and By-laws were approved and notified by the Cabinet. A draft report of Child Labour Survey in Punjab has been prepared. However, progress in these areas in KP was mixed. The Child Labour Survey is delayed as the Government has yet to complete the recruitment of survey teams. The Child Protection Bill for KP was drafted last year and presented to the Social Welfare Department (SWD) and the KP Commission on Protection and Welfare of Children (KPCPWC). The Bill has been submitted to the SWD for presentation in the Cabinet.

Indicator 1.2 – design and scale-up of birth registration and child protection systems: This indicator scored an A+ as two out of three milestones exceeded expectations. In Punjab and KP, 11 birth registration units are functional out of which 10 have been handed over to the government. The respective governments have extended the services across 36 districts of Punjab and 30 districts of KP. In Punjab, the Local Government Department during annual review meetings highlighted that the roles of National Database and Registration Authority (NADRA) and Punjab Information and Technology Board (PITB) to manage Baldia Online app for electronic registration of births are still being negotiated, slowing down the pace of registration. UNICEF has made great achievements in legal and institutional reforms in Punjab. Assessments to inform the design of Child Protection Case Management and Referral Systems in Punjab, KP and Islamabad Capital Territory have been completed. Consultations with government and other stakeholders on the design are underway. This is potentially a transformative reform to protect children from violence, abuse and exploitation.

Indicator 1.3 – birth registration outreach: This indicator scored an A. In KP, the achievements far exceeded the target as 0.89 million children were registered against the target of 0.15 million. Punjab, however, has lagged in this area as the progress fell short of over 10,000 births in target districts. The age disaggregated data is not available to confirm if the under 5 birth target of 75% Punjab and 70% KP are met. Overall, one million children were registered against the target of 320,000 children in KP and Punjab. In KP, the key factors of success were investment in expanding the network of champions within key government departments, special registration camps, advocacy for broader CRVS reforms and a focus on resolution of technical bottlenecks in the operating systems. In Punjab, while the government has committed to scale up the model, technical bottlenecks remain due to lack of agreement on division of labour and tasks between NADRA and PITB in managing the birth registration application. Other areas of improvement include adoption of service standards at birth registration units/camps and further disaggregation of data (e.g. religion, disability).

Indicator 1.4 – evidence on child labour and protection: The data collection for the Child Labour Survey (CLS) was completed in Punjab last year. Since then, UNICEF has been providing technical support to agree technical definitions and reporting. A draft report has been prepared and presented to the concerned Technical Steering Committee. KP is lagging considerably in completing the survey. The listing and mapping exercise has been completed. The recruitment process for initiating the survey is underway. It is expected that data collection and draft report will be prepared before the next annual review.

Indicators 1.5, 1.6 and 1.7 – Covid response: These three indicators were added to the results framework in April 2020 to track progress on Covid response. The key activities were community-based mental health and psychosocial support for children and their families, and prevention of stigma associated with coronavirus infection. The commencement of these activities was delayed last year due to the delays in the annual tranche and therefore the deadline for meeting the targets was extended till June 2021. UNICEF has overachieved the targets. The number of individuals who benefitted from psychosocial and mental health support exceeded 270,000 as compared to the target of 7000. Similarly, the outreach of stigma prevention messages crossed 7 million, compared to the target of 5 million. The study on the impact of confinement on Violence Against Children in Pakistan during the time of COVID was completed and disseminated.

Value for money: The work under this output is laying the foundation for stronger laws and systems for protecting children from modern slavery, abuse, violence, and exploitation. The output has demonstrated good value for money through low unit costs and leveraging significant government resources. The average cost on registration of a birth is approximately £0.2. Continuous investment, advocacy, and collaborations with other UN agencies and World Bank to advance CRVS and birth registration reforms has leveraged £135.36 million ($188 million) from the Federal Government. The provincial governments are scaling up birth registration models across all districts which is a great example of effectiveness and sustainability. The Governments of KP and Punjab have respectively allocated £0.42 million (PKR.95.68 million) and £1.07million (PKR241 million) for the Child Labour Survey. UNICEF also provided mental health and psychosocial support to 280,812 persons (53% girls and women) at an average cost of £1.23 per person.

Recommendations for the year ahead
UNICEF should agree a roadmap with counterpart departments to fast-track the finalisation of CRC-aligned Child Protection Bill and completion of Child Labour Survey in KP and provide technical support to remove constraints to progress (UNICEF, September 30, 2021).

As the provincial governments are scaling up UNICEF-supported birth registration models, UNICEF should reset the scope of its technical assistance with a greater focus on capacity building, data quality validation, data disaggregation, and service delivery standards. Discussions with government partners and changes in workplans for this strand of work should be completed and agreed with FCDO (UNICEF, November 30, 2021).

UNICEF should expand the network of consultations on Child Protection Policies and the development of Child Protection Case Management and Referral Systems in KP, Punjab and ICT and establish a coordination mechanism with FCDO’s Open Societies Programme (OSP) to mitigate risks of duplication (UNICEF and FCDO, October 2021).

Output Title	Strengthened government institutions with effective policies and action plans for protection of women and girls’ rights and prevention and response to gender-based violence and ending child marriage. [GBV and Child Marriage; Lead: UNFPA]
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
2.1 Number and type of UNJP's supported legislation, policies and action plans in place at federal and provincial level for supporting actions (GBV and child marriage).	10 inquiry committees trained on the implementation of Sexual Harassment at Workplace Act 2010.	A (met expectation) / 19 inquiry committees in KP and Punjab trained.
	Roadmap for the implementation of Criminal Law Amendment related to sexual violence including rape, agreed and endorsed by the Ministry of Law and Justice (MoLJ).	Completed
	Mapping of existing SOPs, guidelines on sexual violence response initiated to inform draft sexual violence response framework.	Completed.

	Four dissemination events (face to face /virtual) on KP and Punjab Political Economy Assessments of Child Marriage.	Completed
	A roadmap for strengthening Commissions on the Status of Women at federal and provincial level finalized.	Completed.
	Draft reports on functional review/ assessment of gender machineries, including Women Development Departments (WDDs), Social Welfare Departments (SWDs) and Commission on Status of Welfare (CSWs) in KP and Punjab available.	Delayed. Procurement process is underway to hire the technical expert.
2.2 Number and type of initiatives to support and strengthen GBV prevention and response mechanism and systems.	Multi-sectoral Coordination Platform for GBV prevention and response established in KP.	B (moderately did not meet expectation) / P&D notified the coordination committee
	7150 women and girls (cumulative) provided with psychosocial support with a special focus on GBV.	Partially achieved. / Rozan national helpline: 4,718 (57% women and girls) / Persons with disabilities: 350
	1. Two reports on Helplines data produced to inform multi-sectoral GBV prevention and response mechanisms. / 2. SOPs for Bolo Helpline validated by the KP SWD.	Completed
	GBV Case Management Curriculum for SWDs pre-tested and finalized.	Completed
	90 health service-providers in Punjab and KP trained on Health System Response to GBV	Partially achieved. 69 service providers trained (Punjab: 54, KP: 15).
	Two consultative meetings conducted with PWDs and Departments of Health in KP and Punjab to strengthen health system response to GBV.	Completed
2.3 Level of progression of evidence products related to GBV and CM.	Final Punjab Women's Economic and Social Wellbeing Survey (WESWS) Report available.	A (met expectation) / Completed
	Dissemination/ advocacy event (hybrid/ virtual) conducted at divisional and provincial level using Punjab WESWS results.	Delayed
	Partnership arrangement between Canberra University and Punjab Bureau of Statistics (BoS) in support of ensuring the use of WESWS results secured.	Completed – the legal review confirmed for UNFPA to sign the contract with the Punjab BoS.
	Three advocacy events targeting members of the national and provincial assemblies as part of the dissemination of the PEA Reports on Child Marriage (CM).	Completed.
	Two policy briefs on health consequences of CM validated for evidence-based advocacy and policy dialogue in KP and Punjab.	Completed
[note] Speak in Urdu

Supporting narrative for the score

Description of the output: The purpose of this output is to support the government on data, legislative and system reforms and institutional capacity building for women’s rights and ending gender-based violence (GBV) and child marriage (CM). This output delivers a wide range of interventions. These include technical support in a number of areas: legislative reforms to end violence against women and girls; strengthening the role of Ombudsperson for protecting women and girls from sexual violence at workplace; development of a multi-sectoral platform for GBV response; strengthening the role and capacity of Commissions on the Status of Women at federal and provincial level, and advocacy for enactment of child marriage restraint laws; development of a national policy framework on child marriage. UNFPA also manages partnership with Rozan – a non-governmental organisation, to provide psychosocial counselling to women and girls on GBV issues in the Covid context. This work is delivered through close partnerships with government: Ministry of Law and Justice, Ministry of National Health Services, Punjab Safe Cities Authority, provincial departments of Social Welfare and Special Education, Women Empowerment KP, Women Development Department Punjab, Child Protection and Welfare Commission, KP Commission on the Status of Women, and Department of Labour.

Justification for the overall score: The output has scored a “A” i.e. met expectation. Two out of three indicators met the expectations. Major deliverables were completed related to training of inquiry committees on implementation of Sexual Harassment Act, provision of psychosocial support to over 7000 women and girls, technical support to improve the performance of GBV Helplines, and preparation of curriculum for social workers of SWD to manage cases of GBV. The P&D Department notified the multi-sectoral GBV coordination committee. However, progress fell short of expectations in the provision of online psychosocial support and trainings to the service providers. A lag in commencement of new partnerships mainly due to delayed FCDO funding, staffing gaps within UNFPA, and need for better prioritisation of interventions impacted the pace of delivery.

Indicator 2.1 – legislation, policies and strategies for tackling GBV and child marriage: This indicator scored an A as five out of six milestones were met. UNFPA completed the training of 19 inquiry committees in KP and Punjab on the implementation of the “Protection of Women from Harassment at the Workplace Act, 2010. A roadmap for the implementation of Criminal Law Amendment and mapping of existing operating procedures and guidelines on sexual violence response have been produced. UNFPA has signed a Memorandum of Understanding (MoU) with Ministry of Law and Justice to support implementation of GBV-related amendments. A partnership with UN Women is underway to build on the programme’s earlier work on child marriage and undertake advocacy for enactment of child marriage restraint laws. UNFPA is also undertaking a functional assessment of gender institutional landscape with the aim to deconflict functions and remits of Women Development Departments, Social Welfare Departments and Commissions on the Status of Women (CSW). The assessment is delayed but procurement of expertise is underway.

Indicator 2.2 – GBV prevention and response systems: This indicator scored an A as four out of six milestones were achieved. The programme-supported Rozan Helpline managed 4,718 calls on psychosocial issues. Out of these calls, 484 calls were about gender-based violence. UNFPA’s partnership with Special Talent Exchange Programme (STEP) provided psychosocial support and referrals to 350 women and girls with disabilities. Considering the magnitude of the need, UNFPA is also providing technical advice and capacity building support to improve the performance of Helplines managed by government departments. This has multiplier effects on the programme’s outreach to help victims of violence against children, women and girls and those people who need counselling. 9,795 persons (65% women and girls) benefitted from information and referral services provided by the Punjab helplines from January to June 2021. In parallel, UNFPA has achieved progress to improve health and social sector’s response to GBV. This work involved preparation of a Case Management Curriculum for social workers of the Social Welfare Department in KP. The Minister of Social Welfare KP launched the curriculum on the International Women's Day in March. Under a partnership with World Health Organisation, UNFPA is providing support to develop multi-sectoral referral pathways in KP and Punjab to strengthen health system’s response to GBV.

Indicator 2.3 – evidence on GBV and child marriage: UNFPA has produced a number of research products and policy briefs to stimulate an informed debate on prevention and response to GBV, and prevention of child marriage. Supplementary reports, based on a DFID-funded 2018 survey, are being prepared. These reports will focus on issues of minority women, male perceptions, and private-sector employers/employee’s perceptions on social and economic well-being of women and girls. In addition, UNFPA is using policy briefs based on two political economy analyses of child marriage to promote a dialogue with parliamentarians in KP and Punjab. Two policy briefs have been developed on the health consequences of child marriage and will be disseminated widely.

Value for Money: Data for a VfM assessment of this output will be available by end of next year when implementation of the three roadmaps and multi-sectoral coordination platforms has progressed. However, early information on a few interventions suggests that the value for money is on track. At an operational cost of 9%, UNFPA has built the capacity of government departments to investigate and manage GBV cases and has introduced several reforms to improve health sector’s response to GBV. Progress towards establishing a multi-sectoral coordination mechanism is potentially a transformative step to remove operational constraints and weaknesses in GBV-related services of multiple departments. Support and advocacy for enactment of child marriage restraint laws and development of a national policy framework on child marriage, if successful, will benefit millions of girls.

Recommendations for the year ahead
UNFPA should pivot technical assistance to expedite the establishment of multi-sectoral GBV coordination platform in Punjab, building on experience and lessons from KP. Practical measures and deliverables for this purpose should be agreed with FCDO (UNFPA, September 30, 2021).

The scope of disability inclusion work within this output should be reset with a stronger focus on mainstreaming approaches in provincial strands of work and scaling down federal-level standalone interventions. Provincial targets for disability-related goals and outputs should be developed and implemented (UNFPA, November 30, 2021).
3.	Aawaz II should extend the GBV focus to domestic violence. UNFPA should conduct a scoping study to assess the need for programme’s intervention at Federal level and in Punjab and Khyber Pakhtunkhwa and programme strategy and workplan adapted accordingly (UNFPA, January 2022).

4.	The existing manpower within UNFPA to deliver this component is insufficient. UNFPA should expedite the process to fill the gender expert and other positions as agreed with FCDO (UNFPA, October 30, 2021).

Output Title	Enhanced citizen information, leadership skills, voice and actions for reducing modern slavery.
Output number:		3	Output score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
3.1 Number of Aagahi Centres and Village, District and Provincial forums operational.	60 Tehsil Aagahi Centres operational / 180 community outreach teams operational / 540 village forums operational / 20 district forums operational / 2 Provincial Forums operational	A (met expectations) / 66 Tehsil Aagahi Centres operational (KP 25, Punjab 41) / 196 Community outreach teams operational (KP 75, Punjab 121) / 594 village forums operational (KP 225, Punjab 369) / 22 district forums operational (KP 9, Punjab 13) / 2 Provincial Forums operational (1 each in KP and Punjab)
3.2 Number of individuals (1) trained, and (2) taking actions to address child labour, early/forced marriage, GBV and conflict.	140 Aawaz Change Agents (ACAs) facilitators trained / 500 Aagahi Centre resource persons and outreach team members trained / 6,000 ACAs trained / 410 collective community actions taken by trained village and district forums on Aawaz thematic areas / 86 radio programmes sponsored / 4,000 radio audio insertions (short messages)	A+ (exceeded expectations) / 157 ACA facilitators trained (KP 71, Punjab 86) / 542 Aagahi Centre resource persons and outreach team members trained (KP 211, Punjab 331) / 7,535 ACAs trained (KP 3,009 Punjab 4,526) / 455 collective community actions taken by trained village and district forums on Aawaz thematic areas (KP 148, Punjab 307) / 140 radio programmes sponsored (KP 70, Punjab 70), reaching 6.7 million listeners / 6,720 radio audio insertions (KP 3,360, Punjab 3,360) reaching 11.4 million listeners
3.3 Number of people participating in community level decision-making and pursuing leadership positions.	No milestone for 2021	No milestone for 2021

3.4 Aawaz communities raise informed demands, use referrals, and access services, individually and collectively.	75,000 individuals are provided information on services / 12,000 individuals are provided referrals / 4,000 individuals access services / 700 individuals raise demands with local duty bearers	A+ (Exceeded expectations) / 90,292 individuals received information on services (KP 25,317, Punjab 64,975): 32,608 females, 56,688 males, 996 transgenders, 5,651 minority representatives, and 2,551 persons with disabilities (PWDs). / 13,519 individuals referred to services (KP 4,515, Punjab 9,004): 6,968 females, 6,218 males, 333 transgenders, 497 minority representatives, and 931 PWDs. / 6,770 individuals accessed services (KP 2,316, Punjab 4,454): 3,680 females, 2,955 males, 135 transgender, 183 minority representatives, 378 PWDs. / 1,389 individuals raised 154 demands with local duty bearers (KP 432, Punjab 957): 548 females, 781 males, 60 transgender, 56 minority representatives, and 59 PWDs.
3.5 Evidence generated, and social innovation fund established	2 researches initiated / 3 learning and sharing forums held	A (met expectations) / 2 researches initiated / 4 learning and sharing forums held

Supporting narrative for the score

Description of the output: This output aims to increase citizens’ access to information about their rights, services available to them, and provides platforms to enable them to take actions against harmful practices of child labour, gender-based violence, child marriage, and discrimination against marginalised communities. British Council (BC) manages this output and, through a grant mechanism, draws on the local experience of non-governmental organisations. This output envisages a range of interventions that complement the United Nations Joint Programme’s (UNJP) work on data, legislation and institutional reforms in programme’s thematic areas. They include establishing safe spaces in the form of village, district and provincial forums allowing community members to talk about child labour, gender-based violence, child marriage, and discrimination; agree collective actions; and channel their demands into decision-making processes. Social action projects through a network of local volunteers and Aawaz Aagahi Centres (AACs) reinforce this work by providing information on legal rights and services, and coalitions of change to reduce social acceptance of harmful practices. The BC is also collaborating closely with the Sub-National Governance (SNG II) programme for sharing platforms for citizen action and learning.

Justification for the score: The output scored an “A+” i.e. exceeded expectations. Most of the milestones for the review period exceeded the targets. Village forums, community outreach teams and district forums are functional in all target districts. The targets were overachieved. Some of these forums were set up virtually last year which provided a strong basis to use the same networks for scaling up operations. Similarly, most of the targets for trainings, provision of information on rights and services, referrals and collective community actions were overachieved. While the third wave of Covid impacted the pace and nature of delivery (virtual versus face-to-face), British Council and downstream partners were able to build on the foundational work from the last year. Availability of no objection certificates (NOCs) from government to continue programme activities also paved the way for good performance.
Indicator 3.1 – Number of Aagahi Centres and Village, District and Provincial Forums operational: This indicator exceeded the targets. Use of existing virtual networks, stability in district-level operations, and progress on partners’ registration with Economic Affairs Division (EAD) for project delivery played a major role in rapid social mobilization and establishment of new forums. These forums are vital for engaging communities to raise awareness on harmful practices, rights and services, and to escalate collective issues from village level up to district and provincial governments. British Council has made three major achievements in this respect: (1) these forums, 880 in total, are fully resourced and operational in all target districts, and providing safe spaces for marginalised communities to debate and reduce harmful social practices through local social action projects; (2) all virtual forums established previously have now been converted into in-person forums, thus increasing face-to-face interaction and quality of conversations; and (3) inclusion of marginalised communities is much more visible and is on an upward trajectory. A concerted effort has been made to include female members, as well as members from transgender community, minorities and persons with disabilities in village forums, community outreach teams, district and provincial forums.

Indicator 3.2 – Number of individuals, (1) trained, and (2) taking actions to address child labour, early/forced marriage, GBV and conflict: This indicator exceeded the targets for training of youth volunteers, collective community actions, and raising awareness through radio talk shows and short messages. Over 8000 resource persons, staff members and youth volunteers received training during the review period on prevention of and response to child labour, violence against women and girls, child marriage, and discrimination in the Covid context. There is good early evidence on the impact of these trainings. Trained community members and youth volunteers are implementing social action projects and behaviour change campaigns within their communities. 455 actions have been completed. During FCDO team’s field mission to Kasur on July 7, volunteers shared success stories of children withdrawn from labour, prevention of child marriages, and prevention of interfaith conflicts. In-person engagement is complemented by a mass awareness campaign through radio talks and messages in Urdu, Pashto and Seraiki languages. These programmes have reached an estimated 11.5 million people.

Indicator 3.3 – Number of people participating in community level decision-making and pursuing leadership positions: There was no milestone for the review period for this indicator because this work is contingent on first setting up essential participation structures and safe spaces (indicator 3.2). As these structures have now been established, milestones will be set for next year in the results framework. In addition, the programme will also encourage young leaders participating in these forums to pursue leadership positions in local governments.

Indicator 3.4 – Aawaz communities raise informed demands, use referrals, and access services, individually and collectively: This indicator looks at how the trainings, forums and awareness raising is empowering communities to demand and access rights and services. The targets were substantially overachieved. Over 90,000 individuals received information on rights and services through different platforms managed by the programme, against the target of 75,000. Of these, 13,519 individuals were referred to relevant government departments and service providers for resolution of their issues. The programme has developed district-specific directories which provide information on services related to, for example, issuance of disability certificates, training centres, shelters for GBV survivors, health and Covid treatment, referral and rehabilitation of children, birth registration certificates, family certificates, redressal in child marriage cases, etc. Additionally, information about district administration and relevant depts as well as of Civil Society Organisations (CSOs) providing relevant services is included. Of those referred, 6,770 individuals received services. 1,389 individuals raised demands with local duty bearers. Of the 154 demands raised, 68 were responded to and 86 are under process. A breakdown of these numbers is provided in the table above.

Indicator 3.5 – Evidence generation and learning: British Council has initiated two operational research studies. The first study will examine how village forums and community outreach teams are serving as the vehicle for social behaviour change. The second study is looking at factors which make citizens state-engagement more effective at grassroots. The reports will be available in December 2021 and will enrich our understanding of what works for effective voice and accountability to promote citizen rights. BC also held four events to promote mutual sharing of best practice and learning across target districts. These events unravelled the diversity in drivers of social exclusion and behaviour change, and stressed on data collection, planning and context-specific approaches to community engagement.

Vale for money: This year the programme has gathered early evidence on value for money after almost two years of investment, disrupted severely by the pandemic, in trainings, setting up safe spaces for community dialogue and their impact in terms of community actions and access to rights and services. The programme has facilitated 455 collective actions, reached 11.64 million people with messages on prevention of harmful practices, and enable 6770 persons to access different services such as social protection, obtaining computerised national identity card and disability certificates, etc. While there is scope to increase the bar on inclusion of marginalised groups, the breakdown of data validates that the programme is reaching out to marginalised women and girls, transgender, minorities, and persons with disabilities. While there is no comparable benchmark available yet, the programme is benefitting people apparently at low unit costs. We will continue to track and compare costs with these baselines in the future years.

Per capita cost of assisting people through an Aawaz Agahi Centre	£10
Per capita cost of assisting people through village forums	£5
Per capita cost of a collective demand raised by communities	£23
Per capita cost of information dissemination using radio insertions	£0.001
Per capita cost training an individual	£16
Cost of delivering an awareness message or information material	£0.05
Per listener cost through a radio programme. 59% listeners reported change in their opinion	£0.007

Recommendations

Trainings of youth volunteers and programme staff, in addition to a focus on knowledge of issues, should have a stronger emphasis on practical approaches and actions for prevention of child labour, child and forced marriages, gender-based violence, and interfaith conflicts at grassroots. Future trainings should be reoriented to achieve this goal. (British Council, on-going).

The proportion of individuals who accessed services, as a percentage of total referrals, is 50%. British Council should investigate the reasons for low uptake of referrals and adjust the programme to address any constraints. An assessment report and action plan should be shared with FCDO (British Council, October 30, 2021).

Community engagement in existing 22 districts should be extended to June 2022 to allow more time for participation structures to mature and to deliver the ambition of reaching out to 45 districts agreed with FCDO up to the mid-term stage (BC and FCDO, November 2021). The mid-term review should be completed by April / May 2022 to guide the planning and adaptations for Phase 2 (FCDO, March 2022).

British Council should revisit the sustainability strategy for community forums considering the on-ground implementation experience, constraints and opportunities. An action plan for their sustainability and responsible exit from phase 1 districts should be developed and implemented (British Council, December 31, 2021).

British Council should commission an expert review of safeguarding risks related to sexual exploitation, abuse and harassment (SEAH), looking particularly into types of possible triggers within the management structures of partner NGOs, mixed participation of males and females in forums and outreach teams, and participation of transgender in programme activities should be completed, and an action plan implemented to mitigate those risks (November 30, 2021).

Output Title	Citizens and communities better able to prevent conflict and demonstrate tolerance, including towards religious minorities.
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
4.1 Number of individuals (1) trained and (2) participating in conflict pre-emption.	1,250 individuals trained on conflict pre-emption module / 1,500 individuals participating in conflict pre-emption activities / Participatory Conflict Analysis (PCA) manual developed	A+ (exceeded expectations) / 1979 individuals trained on conflict pre-emption module (KP 773, Punjab,1206): / 933 females, 1,021 males, 13 transgenders, 73 minority representatives, and 38 persons with disabilities (PWDs). / 1,720 individuals participating in conflict pre-emption activities (KP 512, Punjab 1,208): 424 females, 1,289 males, 7 transgenders, 14 minority members, 7 PWDs. / Completed.
4.2 Number of early warnings on conflict reported to established Early Warning Systems (EWS)	1,500 early warning received	A+ (Exceeded expectations) / 2,849 warnings received (KP 672, Punjab 2,177): 1311 case of domestic and sexual violence, 1140 community conflict e.g., property disputes, family, 279 early and forced marriages, 48 cases of violence against transgenders, 29 religious minorities, 35 child abuse, 7 sectarian conflicts.
4.3 Number of conflicts pre-empted by Early Response Mechanisms (ERM).	300 conflicts pre-empted	A++ (substantially exceeded expectations) / 1557 conflicts pre-empted (KP 374, Punjab 1183): 724 domestic and sexual violence, 554 community conflict e.g., property disputes, family, 203 cases of early and forced marriages, 26 cases of violence against transgenders, 20 cases of discrimination against religious minorities, 24 child abuse cases, 4 sectarian conflicts .

Supporting narrative for the score

Description of the output: This output focuses on promoting social cohesion, tolerance and on addressing the drivers of discrimination towards marginalised communities, including against religious minorities. The British Council is the lead agency for this output. Considerable effort has been invested in training individuals on ways to identify an emerging local conflict or discrimination, and on response and pre-emption methods. The processes and methods for gathering and documenting initial information about a potential conflict or triggers are referred to as the Early Warning System (EWS). This information is then used to leverage existing community-based platforms, youth networks and influential community leaders for pre-empting conflict and promoting diversity and tolerance. These processes are referred to as Early Response Mechanism (ERM). These mechanisms provide an entry point to pre-empt conflicts on one hand, and to build a critical mass of local volunteers who actively promote peace and social harmony on the other hand.

Justification for the score: The output has scored an “A+” as progress on most of the targets for the review period exceeded expectations. As EWS and ERM rely on community forums and outreach teams to gather information about triggers of a potential conflict, and members of these forums play a vital role to resolve or pre-empt escalation of conflicts, establishment and functionality of these forums and outreach teams (output 3) have contributed directly to progress in this area.

Indicator 4.1 – Number of individuals (1) trained and (2) participating in conflict pre-emption: The British Council trained 1979 individuals (49% females) on approaches to identify tiggers and pre-empt community conflict pre-empt community conflict in target districts of Khyber Pakhtunkhwa and Punjab. Out of those trained, 1700 (25% females) participated in conflict pre-emption activities. The British Council has also developed a Participatory Conflict Analysis (PCA) manual to equip these individuals with skills to analyse local irritants and drivers of conflict.

Indicator 4.2 – Number of early warnings on conflict reported to established Early Warning Systems (EWS): The British Council has developed standard operating procedures (SOPs) for setting up EWS and ERM. Provincial partners, downstream partners and resource persons of Aawaz Aagahi Centres have been trained on these SOPs. These systems are functional in all districts and, during the review period, received more than 2800 early warnings on cases of domestic and sexual violence, property and family disputes, early and forced marriages, violence against transgenders and religious minorities, child abuse and sectarian conflicts (see the above table for actual number of cases).

Indicator 4.3 – Number of conflicts pre-empted by Early Response Mechanism (ERM): The ERM pre-empted 1557 conflicts during the review period, compared to the target of 300.
Youth volunteers, and members of village and district forums used early warnings to resolve and de-escalate conflicts through dialogue and engagement with concerned parties. Most of these cases (46.5%) were about domestic and sexual violence, but also included incidents of violence against transgender and minorities. 203 child and forced marriages were pre-empted.

Value for money: Early evidence suggests that value for money for this output is on track. The early warning system, and early response mechanism are working well to pre-empt and de-escalate conflicts. 860 conflicts have been pre-empted so far which otherwise might have escalated into serious disputes, violence or harm to lives to children and girls. As highlighted above, more than half of these conflicts were about domestic and sexual violence, but also included incidents of violence against transgender and minorities. 203 child and forced marriages were pre-empted. The average cost of pre-empting a conflict is £122, and by a crude estimate, per capita cost of averting a conflict is £40.

Recommendations

British Council should revisit the EWS-ERM approach to ensure it does not become a standalone dispute resolution mechanism and instead pivot the systems as entry points to promote inclusive and non-violent behaviours. Procedures, trainings and pre-emption dialogue and methods should be re-oriented to focus on behaviour changes aspects. (BC, October 2021).

British Council should document what works to pre-empt child and forced marriages and discrimination against minorities at grassroots, focussing on approaches and methods used in practice in EWS-ERM. A learning product should be developed and replicated in similar contexts within programme districts (BC, December 2021).
Output Title	Programme alignment, monitoring, evaluation and learning for improved performance
Output number:		5	Output score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
Indicator 5.1: Change in implementing partners' perceptions and satisfaction with programme alignment, mutual coordination and communication	At least 20% improvement over the Aawaz II baseline value	B (moderately did not meet expectations) / Overall: 3% improvement. / UNJP: 59% improvement. / British Council: -51% reduction
Indicator 5.2: Joint field visits and initiatives for synergies and collaboration on specific programme governance issues.	At least 2 (1 KP, 1 Punjab) joint visits conducted / Aawaz II web portal updated and functional / Nested strategic documents (ToC, logframe and VfM strategy) developed and implemented / 2 SSC meetings, 4 quarterly AMAR Board meetings, 4 Technical Working Group meetings, and 2 Provincial Steering Group meetings held.	B (moderately did not meet expectations) / 2 joint Punjab visits / 1 joint virtual KP visit to British Council work / Completed / Completed / Completed, except provincial steering group meetings.
Indicator 5.3: UNJP's and BC's MEL and VfM strategies are developed, annual priorities agreed with FCDO and implemented.	British Council's Monitoring plan developed and implemented. / UNJP's Revised MEL plan and targets agreed in consultation with FCDO / Aawaz II VFM strategy developed and approved by FCDO / Annual VfM analyses carried out.	A (met expectations) / Completed / Completed. / Completed. / Draft report shared with FCDO.

Indicator 5.4: Monitoring and evaluation reports produced and used for improved implementation and results	Procurement of FCDO-managed M&E supplier completed. / 7 rapid assessments produced by AMAR / Number and quality of actions implemented based on learning from monitoring and evaluation products	C (substantially did not meet expectations) / Delayed. / 4 assessments completed; data collection underway for 3 assessments for completion by end of July. / Implemented: 93% / In progress: 7%.

Supporting narrative for the score

Description of the output: This output focuses on alignment between different programme components, consolidation of management frameworks, functionality of core governance structures, and use of monitoring data and evaluation for cross-programme learning. The output is led by FCDO with support from the Alignment, Monitoring and Results (AMAR) unit but the milestones are shared and incentivise synergies and coordination among all implementing partners.

Justification for the score: The output scored an ““B” i.e. moderately did not meet expectation. Four milestones did not meet the expected progress. Implementation of governance and monitoring and evaluation mechanisms continued uninterrupted as agreed with UNJP and BC. The value for money (VfM) framework was updated and implemented. However, progress fell short of expectation in few areas: a decline in self-assessment of district staff about programme alignment, mutual coordination and communication; procurement of FCDO-managed M&E supplier; notification of provincial coordination groups, and slower progress on final round of rapid assessments and implementation of recommendations. The reasons for lagging performance are briefly explained below:

Indicator 5.1 – perceptions of implementation partners on alignment and coordination:
AMAR unit completed the third annual survey in June 2021. The staff from all Aawaz II partners including FCDO provided their feedback on effectiveness of coordination and collaboration under the programme. The findings showed an improvement of 3% in perceptions about alignment, coordination and communication. The responses from British Council staff showed deterioration of perceptions and impacted the overall trend, despite that no concerns were raised during reviews and monthly meetings. This contradiction is partially due to a methodological issue as district staff provided responses for questions which could have been better investigated. The annual review team recommends that this issue should be probed further, and if required, the methodology should be improvised and survey re-run.

Indicator 5.2 – joint field visits: A joint visit to Punjab was held virtually, whereas, a joint visit to KP had to be postponed owing to pandemic -related movement restrictions. The joint virtual visit provided FCDO team with assurance about activities on ground, but it was not a substitute for in-person visit as it was difficult to collect feedback directly from beneficiaries. An in-person joint field visit to Lahore and Kasur was took place in June 2021. FCDO’s Development Director also attended meetings in Urban Kasur. In addition, the programme benefitted enormously from joint technical reviews, advice from the Strategic Steering Committee and AMAR Board for shaping the restructuring process and Covid response. The notification of Provincial Coordination Groups, however, is still pending and is contingent on a concurrence letter from the Economic Affairs Division (EAD).

Indicator 5.3 – monitoring, evaluation and learning: The British Council developed a comprehensive monitoring, evaluation and learning (MEL) plan which was updated in April 2020 to align with Covid context. UNJP’s MEL plan was updated in line with the amendments to the Joint Programme Document (JPD) and Memorandum of Understanding (MoU). A major initiative during the review year was to revamp the VfM framework and templates led by AMAR unit in consultation with all partners. A draft VfM analysis has been prepared and is under review by FCDO. In addition, a VFM Working Group had been established and its 1st meeting was also held.

Indicator 5.4 –M&E procurement, assessment reports and learning: The procurement of FCDO-managed M&E supplier faced huge delays due to post-merger internal changes within FCDO. The procurement process is now underway and is likely to be completed by October 2021. An extension of the UNICEF-managed AMAR unit is being negotiated to cover any gap until the new supplier is on board. In the meanwhile, AMAR made good progress on assessing UNFPA's psychosocial support, UNICEF’s birth registration model and mental health and psychosocial support in KP, and British Council’s virtual forums. These reports have been approved by AMAR Board. The fifth report on Child Labour Survey is at advance stage. The remaining two assessments will be completed by end July 2021. These reports have provided data on strengths and areas of improvement in these areas. Implementation of recommendations and adaptations are being tracked. Partners have accepted and are implementing 10 out of 11 (91%) assessment recommendations. 15 out of 16 (94%) action points agreed during quarterly technical reviews, and 30 out of 32 decisions (94%) from AMAR board meetings were implemented. Provincial coordination groups in Punjab and KP have yet to be established.

Value for money: AMAR Unit has led the development of programme’s value for money (VfM) framework and aggregation of data to monitor programme’s performance. The overall trajectory of delivery and completion of log-frame targets benefits from this unit’s support. Overall, 93% of recommendations from these reports have been accepted by partners, with a quarter of them already implemented and remaining in progress. Four rapid assessments completed by AMAR unit are driving adaptations and improvements to delivery approaches. AMAR Unit’s operational cost are at 12%. During the review, it realised savings of £11,525 owing to virtual modality of delivery. Implementing partners have prepared short case studies which show positive impacts of programme’s interventions on the lives of marginalised groups. The programme will continue to track ‘intangible’ benefits that cannot be monetised by using case study approach.

Recommendations
AMAR and British Council should investigate the reasons for low satisfaction of district staff with levels of coordination, alignment, and communication. If required, the methodology should be improvised, and the survey should be re-run. British Council should agree a plan to improve engagement of district staff in relevant processes (AMAR, August 2021).

The extension and work plan of AMAR Unit should be finalised as a priority to cover the gap until the new supplier is on board (FCDO/UNICEF, August 2021).

AMAR should ensure that a detailed handover note is submitted to FCDO and the Project Completion Review (PCR) incorporates learning, especially from the execution of rapid assessments (hiring of consultants, format, methodology, quality assurance) (AMAR, on closeout).
D: RISK

The overall risk for the programme remains ‘Major’. All programme risks remain within the revised FCDO Pakistan’s risk appetite. The main risks are around “external context”, “safeguarding” and resourcing to deliver output 2. The third wave of Covid and reshuffle of senior officers within key government departments slowed down some activities during March-June but overall, most of the targets were either met or exceeded. There are risks of sexual exploitation or abuse in on-ground activities that involve direct engagement with youth, women and girls, transgender, and persons with disabilities. The programme’s focus on sensitive issues such as gender-based violence, child marriage, child labour and minority rights also entails risk of harm to staff of downstream partners from people who associate work in these areas with foreign interests or a clash with their own value systems. British Council has trained partners on safeguarding issues and has publicised procedures for reporting any safeguarding concerns. This was verified during the annual review field visit.

The programme has an extended delivery chain with a range of government and non-governmental partners There are financial & fiduciary risks in disbursements to local NGOs which are being managed through due diligence and enhanced financial reporting from the downstream partners. Both UNJP and the British Council continue to monitor risks in the evolving situation and keep the programme team informed of their impact on deliverables with proposed mitigation measures.

All partners are proactively monitoring and managing the risks by putting in place safeguarding policies, procedures for reporting concerns, staff trainings, and guidance for protection against Covid during work. All implementing partners maintain a risk register for their respective programme components which add up to a consolidated risk register maintained by FCDO. The register categorises risks and mitigation measures along all six categories in line with the new FCDO risk framework. Key risks are reviewed in monthly and quarterly reviews with UNFPA, UNICEF and British Council. In addition, the team manages programme delivery chain maps and aims to track programme delivery through regular monitoring. When needed these risks are escalated to bi-annual strategic steering committee.

Update on Partnership Principles:
The UK’s development assistance within Pakistan is underpinned by an assessment of the government’s commitment to the four Partnership Principles: commitment to reducing poverty; respecting human rights and international obligations; strengthening financial management reducing the risk of funds being misused through weak administration or corruption; and strengthening domestic accountability.

Aawaz II programme engages with the federal government as well as the provincial governments of Punjab and KP and contributes directly to improving the situation of human rights in areas of child protection, violence against women and girls, child and forced marriages, and discrimination. This is evident from the allocation of resources for the Child Labour Survey, and the political appetite for legislative reforms and capacity building on child rights, sexual violence in the workplace, domestic violence, and support of legislators for a single child marriage bill in Punjab. Concerns about human rights are raised regularly with senior counterparts within government. The programme will continue to monitor the government’s commitment and provide support for improvement in the priority policy areas.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery
Delivery against the work plan is monitored regularly using monthly meetings and in-depth technical quarterly reviews. The programme team ensured regular virtual contact with the implementing partners to ensure the dialogue on the programme delivery. Any changes due to Covid restrictions were instantly incorporated to avoid hold-ups in the execution of the work plan. The momentum of delivery within both UNJP and British Council components was steadier, compared to the previous year. The completion of the process of simplifying the delivery chain and strands of work within UNJP in May 2020 provided the much-needed stability to UNICEF and UNFPA in the future direction of institutional development activities, paving the way for better planning and mobilising new activities. British Council’s downstream partners had the contracts and necessary government permissions in place in all districts, except Faisalabad where operations could not start until March 2021. Progress in these areas provided a solid foundation for delivery at pace. Nonetheless, the third wave of Covid forced the partners to cancel some in-person activities which affected the pace and quality of delivery during March-June. In general partners delivered the commitments and targets. The programme team provided timely instructions to ensure activities are not held-up. It also kept the FCOD finance team informed of any changes in programme budgets/forecasts. This resulted in efficient management of the programme budget.

The programme has an elaborate monitoring, evaluation and learning (MEL) framework, which comprises partner’s internal monitoring and evaluation plans, a monitoring function through the AMAR unit, monthly meetings and quarterly reviews, and cross-programme learning workshops and joint field visits. AMAR has also developed a digital dashboard for consolidating monitoring data and management frameworks. A synopsis of MEL activities during the review period is provided above in Section B.

Commercial performance
There has been no change to FCDO’s Standard Administrative Agreement (SAA) with UNICEF as the convening agency for UNJP. The contract with British Council, however, was amended to reflect changes in key personnel and role profiles due to staff turnover, allowing six-weekly payments for a limited period to allow smooth flow of funds for partner grants, introduction of a clause to penalise delays in delivery of milestones, and documentation of Covid pivot into the contract provisions. These amendments faced significant delays due to a cumulative effect of changes in internal processes after DFID-FCO merger. The amendments were signed on 19 January 2021.

A key challenge during the review period was to progress FCDO’s procurement of a third-party monitoring and supplier to replace the AMAR unit. Initially, the expectation was that this process will be completed by October 2020. While the terms of reference had been developed and finalised after feedback from partners, the procurement had to be paused due to ban on new procurement following the DFID-FCO merger. To minimise a gap in monitoring activities, FCDO and UNICEF agreed a cost extension of AMAR until June 2021. The ban was lifted in March 2021. The team has initiated the process for procurement through a framework route. This is likely to be completed by October 2021. In anticipation of delays which may cause a gap in monitoring activities, a six-month (November 2021 to April 2022) no cost extension of AMAR unit with a clause to allow earlier closeout, if required, is being processed.

Financial performance
The total budget for Aawaz II is £39.5 million over six years This includes £17.25 million for institutional development through UNJP, £19.99 million for community empowerment through the British Council and its downstream partners, and £2.25 million for design and monitoring and evaluation. Of the total budget, £13.57 million (34%) has been disbursed to date (£11.16 has been spent and £2.42 million prepayment was made in June 2021). £25.9 million remains in balance until March 2024. During the review period, the programme spent £5.86 million: UNJP £2.60 million disbursed including £1.85 million prepayment and British Council £3.08 million. Last year, the programme spent £2.31 million: UNJP £1.16 million and the British Council £1.15 million. Stability in the programme’s strategic direction and availability of a longer duration to carry out activities on ground, compared to the last year, improved the financial performance. The financial work plan was readjusted downwards due to pandemic affecting in-person activities. The risk of lower spending is mitigated by lowering the forecast. In case the Covid restrictions ease-off during the next financial year, the forecast will be revised.
[note] This amount is lower than £49.14 million mentioned in the table on page 1. The latter is higher because it also includes the budget of earlier two business cases which have now been closed.

A recommendation from last annual review pertaining to invoicing process and timelines has been partially achieved. The draft invoicing process and timelines have been developed in collaboration with UNJP. Recommendations: Invoicing process and timelines with UNJP should be finalised and put in place by September 2021.

Table 1: Breakdown of total programme budget, spend and balance (£)
Component	Budget (£)	Spend (£)	Balance (£)
Design/ M&E	2,258,826	248,805	2,010,022
UNJP	17,250,000	9,936,381	7,313,619
British Council	19,991,174	3,389,601	16,601,573
Total	39,500,000	13,574,787	25,925,213

UNJP and the British Council provided six-monthly and quarterly financial progress reports, respectively. However, there has been variance of over 15% in forecasting which is well above the acceptable level of 5%. This was mainly attributed to the uncertainty caused by the pandemic and the need to adjust the pace and mode of delivery (virtual versus in-person). The quality of reporting by both UNJP and BC have been very good, however, slight slippage in timelines have been noticed. The programme team has increased the frequency of follow-ups to ensure timely financial reporting.

Asset management
UNJP and British Council maintain separate asset registers. Any changes made to assets are reported to FCDO. In addition, British Council includes details of any new assets in quarterly invoices which are duly scrutinised by the programme team. UNJP did not purchase any assets during the review period. British Council purchased essential equipment for operations such as laptops, and other electronic equipment. The latest spot check due in April 2021 had to be postponed due to lockdown. The checks were completed in June and July 2021. In June 2021, the team visited the British Council’s Programme Management Unit (PMU) in Islamabad followed by another visit to Sudhaar Society’s district office and Aawaz Aagahi Centre in Kasur. The assets were properly tagged, well maintained and fully operational. There was no damage, missing or mis-reported assets. The programme team will continue to scrutinise asset procurement documentation.

The key recommendations from the audited reports tracker will be shared with the implementing partners. Regular follow-ups in monthly and quarterly meetings to ensure their redressal. All due diligence recommendations have been addressed by UNJP and are closed. Next due diligence of the UN partners is due in early next year. The programme team will start the process in January 2022.

Date of last narrative financial report	British Council – 9th July 2021, UNJP – 7th July 2021
Date of last audited annual statement	British Council – 28th April 2021, UNJP – 16th March 2021

Annex A

Progress on recommendations from the last annual review

1	Develop an action plan outlining the opportunities for communication and influencing to leverage x-HMG relationships with government and FCDO leadership for legislative and policy reforms	Partially achieved, leveraging FCDO leadership’s quarterly engagement plan.
2	Review engagement with parliamentarians, government departments and other stakeholders, and develop measures in the form of a strategy paper to accelerate legislative and system reforms	Completed
3	Conduct an assessment of inclusivity of key interventions and possibilities of further data disaggregation	Completed
4	Extend the AMAR contract till June 2021	Completed
5	Review risk and mitigation for completion of activities within the timeline and communicate the delays to FCDO	Completed
6	Develop revised VfM frameworks of UNJP and the British Council in accordance with the new requirement of output-level VfM metrics	Completed
	Conduct a full VFM assessment based on revised framework and metrics	Draft report prepared.
7	Review and update the theory of change and the results framework	Completed
8	Review engagement with stakeholders and develop an advocacy strategy paper to ramp up the momentum on legislative and system reforms	Completed
9	Increase next year's target of BR with more focus on increasing the registration of girls and children under 5years of age in KP	Completed
10	UNICEF and the British Council should coordinate at the district level interventions	Completed
11	Develop and agree on measures for fast-tracking the implementation of Covid response	Completed
12	Transfer milestones related to Covid-response to Aug-Oct 2020 quarter	Completed
13	Review and revise the roadmaps to improve the strategy for targeting minorities and other marginalised groups and coordination with UN Women	Completed.
14	Improve beneficiary data collected by the Rozan Helpline and align it with GBV indicators	Completed
15	Support government helplines to use improved data categories	Completed
16	Set targets for increasing the participation of women, members of minorities and transgender community, and PWD in village forums and network of volunteers	Completed
17	Include a feedback mechanism in monitoring system for Aawaz Aagahi Centres	Completed
18	Develop a plan outlining measures for protection of staff and forum members from cybercrime and online abuse	Completed
19	Continue engagement with GOP’s RCCE, DAFPAK’s public campaign and other behaviour change interventions	Completed
20	Prioritise implementation of EWS and ERM in the year ahead, and revise logframe with realistic milestones against all the indicators	Completed
21	Conduct training on safeguarding and procedures for reporting safeguarding incidents	Completed
22	Develop revised VfM frameworks of UNJP and the British Council in accordance with the new requirement of output-level VfM metrics	Completed
23	Update internal M&E plan in line with the amendments to JPD and Covid context	Completed
24	Review engagement with provincial government counterparts to escalate progress on setting up PCGs or utilize existing platforms	Delayed
25	Remove unspent design funds from the programme budget	Completed.
26	Separate M&E budget from the design funds and reflect in a new ARIES component	Completed.
27	Use structured PowerPoint presentation format for FCDO-UNJP monthly meetings	Completed
28	Improve forecasting capabilities to set realistic milestones for spend and workplans	Partially achieved
29	Review and agree on invoicing processes and timeline	Completed.

Annex B