## Annual Review Template

Title: Sahel Humanitarian Assistance and Protection Programme (SHAPP)
Programme Value £ : £58m		Review date: 1/12/2022
Programme Code: 300943	AMP start date: 15/12/2021	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2022
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Results Framework

A. SUMMARY AND OVERVIEW
Description of programme
The Sahel (Mauritania, Mali, Burkina Faso, Niger, Chad) is a region in crisis and one of the poorest and most fragile regions in the world, at the bottom of the ‘bottom billion’. Humanitarian needs have increased and become more complex because of growing instability, violent extremism and extreme climate change impact. The SHAPP programme aims to deliver assistance and protection for the most vulnerable people in geographic ‘hotspots’ of acute humanitarian need building on previous UK support improving the international response. It is currently estimated that SHAPP will benefit some 1.4 million people who will receive humanitarian assistance and protection interventions through bilateral funding to the Danish Refugee Council (DRC), International Committee of the Red Cross (ICRC), United Nations High Commissioner for Refugee (UNHCR), International NGO Safety Organisation (INSO) and United Nations Humanitarian Air Service (UNHAS). This fits with the UK’s stated objective of reinforcing presence and capacity in the Sahel. The programme is aligned to the UK Aid Strategy, Humanitarian Reform Policy and Humanitarian Framework as well as UK commitments stemming from the World Humanitarian Summit and the Grand Bargain.

The region is affected by state fragility and complex political transitions, Islamist extremism, violence and weak economies exacerbated by climate change and pandemic recovery. The situation in the Sahel is deteriorating at an alarming rate including with consequences for regard of Human Rights and International Humanitarian Law. The most important contextual changes since approval have been the accelerated combination and interplay between fragility (largely due to ongoing poor governance), volatility and insecurity. There has been a downgrade in French/Mali relations and a rise in anti-French sentiment across the region, culminating in the cutting of French development support and the Malian banning of French / French funded NGOs There has also been a diversification of new armed actors increasing the difficulty to negotiate access to people in greatest need. More civilians were killed in the central Sahel in the first six months of 2022 than in all of 2021. This represents a challenge for humanitarian actors who need to adapt at pace to a continuously evolving and complex operating environment.

Summary supporting narrative for the overall score in this review
The overall score for this annual review is an ‘A’. The SHAPP is in its first year and progress is on track. We expect it to continue to meet expectations. Following the start-up phases of two key components (the Sahel Regional Fund implemented by DRC; Project 21) subsequent annual reviews will focus less on process and have a greater focus on implementation - delivery and results.

The Sahel Regional Fund agreement was signed later than initially planned but the start-up phase has nevertheless progressed - key milestones have and continue to be achieved, downstream partner implementation is now expected to begin in February 2023 well in advance of the next critical lean season. Project 21, the interagency regional harmonised protection monitoring (for which UNHCR receives funding) activities are on track. Despite a deteriorating context, INSO have also delivered on expectations, continuing to expand its reach and provide the full range of services in the countries in which it operates. UNHAS maintains a vital service to support the humanitarian community in the region with reports indicating that both passenger numbers and cargo have increased since 2021 – an indication of the continued importance of this common service.

Major lessons and recommendations for the year ahead
Lessons learnt
- The principle of neutral and impartial humanitarian response continues to be critical as a means of manging and mitigating security risks – not least as the conflict and violence becomes more entrenched and operating environment more complex.
- Support to actors who can support the response through common services such as logistics and security management is as important as maintaining the presence and ability of humanitarian actors to operate safely and securely. This confirms the relevance of the funding foreseen under this programme.
- Support to regional harmonised protection monitoring has allowed the set-up to be confirmed. Over the next twelve months it must now begin to deliver more in terms of products (information, analysis) that will inform and influence others.
- Setting up a new mechanism for delivery of humanitarian aid in the region provides the opportunity to document the lessons learnt from an approach that can inform and help broader FCDO humanitarian programming. Dedicated time and space must be set aside for this.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change is that a more effective, efficient and equitable delivery of humanitarian aid for the most vulnerable people in the Sahel is made possible because the most vulnerable people (including in the hardest to reach areas) in geographic hotspots of most acute need receive prioritised humanitarian protection and assistance. Safety and security for humanitarian actors enables their access to those in need (and for those in need to humanitarian aid) whilst data and evidence informs policy and programme priorities (key enablers).

Most assumptions detailed in the business case held true, although some will require more time to be verified. The following assumptions have been identified as particularly important and therefore how they are evolving is detailed below:

Access and ability to effect HMG oversight and monitoring of partner implementation in the field,

Direct FCDO staff access to project activities remains minimal because of insecurity. Alternative measures being put in place include close engagement with partners’ teams at regional and country level; field monitoring of the Danish Refugee Council (DRC) run Sahel Regional Fund (SRF)-funded partners by DRC’s dedicated monitoring and evaluation team team; independent third-party monitoring being procured under the Sahel, Monitoring and Assurance Programme (SIMAP) Business Case, due to be operational from early 2023.

Partner ability to access not completely compromised by criminality, government admin and/or lack of acceptance of neutral and impartial humanitarian response,

The ability of humanitarian actors to access those in greatest need, and for those in need to access humanitarian aid, continues to be challenging. This is particularly the case where non-state armed groups are present and compounded where national authorities layer on additional administrative requirements. Illustrative examples of the continued challenge include: accessing towns that have been effectively enclaved by armed actors in areas of Mali and Burkina Faso; the additional complexity in the security landscape as it evolves following the arrival of the Wagner Group and departure of Operation Barkhane; insistence that UN actors use armed escorts in Niger, etc.

Conflict will not be resolved in the lifetime of the project, but geographic areas do not expand significantly and the wider region will not deteriorate significantly, further massively increasing need
The continued deterioration in the context and increasing humanitarian needs mean that this assumption will continue to need to be revisited and assessed. More civilians were killed in the central Sahel in the first six months of 2022 than in all of 2021.The recent revision and 35% increase in the Burkina Faso Humanitarian Response Plan cost (now at USD805m) is a similar indication of the trend. Key moments in the coming months that will serve to confirm trends include the future food security projections for the 2023 June-August ‘lean season’ and 2024 Humanitarian Needs Overview exercises and subsequent planning.
[note] ACLED: 10 Conflicts to Worry About in 2022: The Sahel | Mid-Year Update (acleddata.com)

Changes in context and programme
Since SHAPP was launched in December 2021, humanitarian needs have continued to increase in scale, scope, and intensity. Overall, at the start of 2022, the UN estimated that there was an additional 2.4 million people in need compared to 2021 taking the estimated total to 21.7 million. The number of people suffering from acute food insecurity across Mali, Burkina Faso, Niger, and Chad jumped from 8.3 million in 2021 to 11.8 million in 2022. As noted above, access is increasingly challenging and leads to great reliance on UNHAS to deliver aid .
[note] In October the UN revised this estimate upwards by a further 1.2 million people following a revision of needs (and the humanitarian response plan) in Burkina Faso

The Russian invasion of Ukraine has led to higher food and fuel/energy prices, pushing larger numbers of people into food insecurity. It has also reduced availability of fertilisers that has further consequences for food production and the population. The humanitarian response is also affected by these increased costs and other challenges such as reduced ability to contract the cheaper Mi8 helicopters and crew.

Despite these deteriorating trends, the fundamental nature of the crises hasn’t changed. The policy priorities and programmatic approaches set out in the business case, combining multiyear flexible funding for NGOs to provide integrated humanitarian assistance and protection in hard-to-reach areas (Sahel Regional Fund), enabling activities (UNHAS, INSO) and improving protection monitoring (Project 21), all remain highly relevant.

Monitoring: Regular contact is maintained with all partners through meetings with their regional teams in Dakar. FCDO development counsellors based in Sahel countries, joined by regional humanitarian advisors when they are visiting, also meet directly with partners’ country teams. This engagement will be complemented, for some humanitarian partners, with independent monitoring visits by a third-party organisation. Third-party monitoring visits are planned to start in the first half of 2023.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Preparatory activities for the SRF have progressed as planned and provide a solid foundation of governance and management systems and processes. Based on ongoing engagement with ICRC, INSO and UNHAS, we are confident that the work of these partners continues to be essential and delivered to good standards.

The programme is on track to deliver the expected outputs, but it is too early to fully judge on outcomes and impact. Partial information available at this point suggests no major risks around the achievement of results. The Theory of Change remains relevant and therefore there is no current concern in relation to outcomes and impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The theory of change remains valid. The SHAPP delivers vital support in assisting and protecting the most vulnerable, including through critical life-saving interventions, and in contributing to the ‘enabling environment’, meaning humanitarian actors have greater safe and secure access

Although not fully captured through an Annual Review process, SHAPP contributes to FCDO’s bilateral engagement and diplomatic influence in the region. It feeds into and complements our policy positions, demonstrating the UK’s commitment to being a principled humanitarian donor and thought leader.

The programme should therefore continue.

## C. DETAILED OUTPUT SCORING

Output Title	Prioritised protection for the most vulnerable in areas of greatest need
Output number:		1	Output Score:	N/A
Impact weighting (%):		0	Weighting revised since last AR?	N/A (1st annual review)

Indicator(s)	Milestone(s) for this review	Progress
# (number) of people assisted with protection activities	0	Activities under this output will commence in 2023
Effective beneficiary feedback mechanism	0	Activities under this output will commence in 2023

Briefly describe the output’s activities, and provide supporting narrative for the score.

No activities were planned under this output during 2022. FCDO support to ICRC was funded through the SHAPP1 project during 2022. Effective feedback mechanisms are an explicit requirement in the call for proposals launched under the newly established Sahel Regional Fund, under which projects are due to start in early 2023.

Impact weighting is 0% for this Output for the 2022 annual review, as results were not scheduled to be delivered in this timeframe, however this will return to 30% as foreseen in the overall logframe for the next annual review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As the SRF project is still in its early phase, and we are yet to sign an agreement with ICRC, we are not currently able to assess this. This be reviewed in the next annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output or milestone in 2022.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Not applicable

Output Title	Assistance for the most vulnerable in the areas of greatest need
Output number:		2	Output Score:	N/A
Impact weighting (%):		0	Weighting revised since last AR?	N/A (1st annual review)

Indicator(s)	Milestone(s) for this review	Progress
Total Number of beneficiaries receiving appropriate calculated food (package) & cash-based assistance	0	0
Number of children treated against severe acute malnutrition (cumulative indicator)	0	0
Number of people reached with non-food assistance including (i) Water, Sanitation and Hygiene, (ii) Health, (iii) Shelter and Non-Food Items, and (iv) Camp Management assistance and services (cumulative)	0	0
# people reached with livelihood opportunity creation projects	0	0

Briefly describe the output’s activities, and provide supporting narrative for the score.

No activities were planned under this output during 2022. The program components that will deliver in subsequent years against these indicators are ICRC and the SRF. The SRF was in design and preparatory phases during the review period and is due to start delivering assistance in 2023.

FCDO support to ICRC was funded through the SHAPP1 project during 2022 and will be funded from this program from January 2023.

Impact weighting is 0% for this Output for the 2022 annual review, as results were not scheduled to be delivered in this timeframe, however this will return to 40% as foreseen in the overall logframe for the next annual review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Not applicable

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output or milestone in 2022.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Not applicable

Output Title	Humanitarian aid organisations better able to fulfil their own mandates through the provision of essential safety cooperation, information and support services.
Output number:		3	Output Score:	A
Impact weighting (%):		70	Weighting revised since last AR?	N/A (1st annual review)

Indicator(s)	Milestone(s) for this review	Progress
% of NGO respondents agree that INSO services are relevant to their needs and improve their understanding of the environment and their security practices.	>75%	Burkina Faso 97%, Mali 98% / Niger 86%
Number of humanitarian air passengers transported per month	3,000 people able to access hard to reach areas through use of UNHAS flights (1,000 pax/month) during Oct-Dec period	UK specific results not available at mid-year stage. WFP will provide full details in their end of the year report
Effective setup & operation of SRF	Board, strategy, operations manual in place. First batch of concept notes submitted.	Completed

Briefly describe the output’s activities, and provide supporting narrative for the score.
This output details the support and progress that is made in supporting an ‘enabling environment’ for humanitarian actors and the response. UK resource does this in three ways:

Through supporting INSO’s central Sahel common services that provide and reinforce NGO day-to-day risk management, security briefing, training, and situational awareness. In 2022, INSO continued to adapt and, where necessary, expand its footprint across the Sahel at the request of humanitarian NGOs. Although the context deteriorated, especially in Burkina Faso and Mali, INSO continued to deliver as planned. They exceeded the planned milestone. Feedback concerning INSO continues to be positive from stakeholders.

The United Nations Humanitarian Air Service (UNHAS) run by WFP ensures that humanitarian workers and cargo can safely reach remote hard to reach locations. It also provides an evacuation service for both security and medical emergencies. UNHAS country reports (January to July) show passenger numbers for Mali and Chad averaging 1,291 and 1,096 respectively per month against targets of 1,000 passengers per month. The amount of cargo transported is also in line with targets, showing for Chad and Mali, 27.1MT and 31.3MT delivered respectively, compared to 26.7MT and 22MT in the same period last year.

The Sahel Regional Fund is on target to meet its milestones. SRF board members have now been selected through an open competitive process and have approved the programme strategy and operations manual. A first call for concept notes from INGO-led consortia has been completed with a short list of six invited to submit full proposals. Overall, the SRF has been set up efficiently and in line with agreed timelines.
This output has therefore met expectations and scores an A.

Impact weighting is 70% for this Output for the 2022 annual review, as results for output 1 &2 were not scheduled to be delivered in this timeframe, however this will return to 20% as foreseen in the overall log frame for the next annual review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
INSO: INSO continues to provide VfM. As INSO continues to both consolidate and expand its geographic footprint and increase membership numbers the benefits of common services working at scale accrue. For example, this reduced the monthly cost per NGO to £1,241 in 2022/23 from the initial £1,287 planned in the proposal. As part of the project, from April to October, INSO also provided training courses for 989 people – a third party provider would have priced these at £500-£700 per trainee. To assess effectiveness, INSO conducts annual surveys of client perception of services provided per country, in all three countries milestones were exceeded (see milestone indicator).
[note] It now has 453 members (exceeding the initial target of 437) of these 102 were local/national NGOs or Red Cross movement members.

UNHAS: The main cost drivers for UNHAS’ operations are the airplane leasing costs and maintenance, fuel and staffing. The main indicator for VfM is cost per kilometre per passenger. As WFP (responsible for managing UNHAS) does not provide mid-year reporting on the UK contribution, we have no data available to assess VfM at this stage of the year. WFP will cover VfM in their report at the end of the year. Nevertheless, participation in Steering Committees and bilateral meetings where this metric has been discussed suggest that UNHAS partners in the region compare favourably to other operations – where they do not this is because the operation includes more expensive helicopter use.

SRF: The principles set out in the Business Case to drive VfM directly informed the design of the SRF and the strategic framework of its first call for proposals. For example:
1. Multi-annual programming to increase predictability and enable organisations to plan procurement and programme activities better (economy and efficiency),
2. Focusing on hotspot areas where the needs are greatest (efficiency),
3. Selecting partners that have a shorter delivery chain and existing operational capacity in the targeted areas (efficiency – total cost transfer ratio),
4. Using delivery mechanisms that offer the best VfM e.g. preference for cash over in-kind (effectiveness)
In addition, competitive levels of overheads were negotiated and agreed with DRC and with the SRF board (7.2% on DRC activities, 0.75% on funding passed on to consortia, 7% overheads on any partner’s activities, 0% on pass-through funding from consortium leads to downstream partners). This compares favourably to some UN pooled funds (and this comparison will be further assessed) contributing to the economy dimension of the SRF’s VfM.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
For UNHAS, the milestone was amended to reflect the start of FCDO support brought forward to October 2022 ensuring UNHAS had sufficient funding to maintain operations without break until the end of 2022.

Following this review, the ‘Effective setup & operation of SRF’ indicator will no longer be utilised, as it is now completed. Outputs 1 & 2 will become more relevant for the SRF.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from Previous AR’s
As this is the first year for SHAPP, we can only refer to recommendations from the last Sahel Humanitarian Emergency Response Programme (SHERP) annual review where these are relevant. They are as follows.

INSO SHERP 2021 Recommendation: INSO experienced gaps in staffing of key positions during the reporting period, thereby affecting delivery of some activities. INSO should be asked to include HR as a risk in their reporting with future mitigation strategies reflected.

Progress: INSO now reports on staffing issues. To ensure that staff turnover does not affect the delivery of activities, INSO has improved internal mobility, allowing staff to move more easily from operational to management positions and between platforms. This has allowed useful exchanges of practice and for consistency across operations to be maintained.

UNHAS 2021 SHERP Recommendation: Environmental impact - Given that the cost of fuel is a major driver, we should continue to push UNHAS on how ‘green’ an operation it runs. More technologically advanced and modern air assets will have more efficient engines.

Progress: FCDO takes part and influences UNHAS decisions on routes and fleet composition. Our priority is to improve cost effectiveness, but this is often also a means of reducing the environmental impact. For instance, we challenged the proposed deployment of helicopters where they were not critically needed. However, what we have also seen is that the Russia/Ukraine war has resulted in reduced availability of the former Soviet era helicopter and reliance on other types. These appear to be more expensive to lease but we have not yet determined if this has a ‘greener’ impact on the environment.

Lessons learned from this review period:
- The Sahel Regional Fund provides a clear opportunity to be more efficient in the utilisation of our funds in the Sahel and, to a different degree, challenge the system to change and improve.
- Managing potential and perceived conflicts of interest for the SRF relating to NGO management of the fund and board membership has taken time but is clearly important and will need to continue to be checked over time.
- The start-up phase for the fund was six months although there was an initial FCDO ambition to have this for three months. Retrospectively, the six-month period was necessary to allow for effective set up and foundations for the SRF. This included recruitment of fund management staff, open and transparent selection of board members, development of full set of SRF processes, templates, tools and programmatic strategy, call for concept notes, call for proposals. The typical lead time to setup a UN country-based pooled fund is one year.
- The SRF continues to generate a series of lessons learnt that are being documented with the intent of sharing them for broader FCDO learning. These include lessons on setting-up time, management of board members’ conflict of interest, collective work on proposal evaluation and funding allocation decisions.
Recommendations for year ahead: FCDO to engage with WFP focal point in Rome to see if they can pick up key questions with UNHAS from an institutional perspective. This includes fuel efficiency of aircraft, and also ensuring UNHAS dimension their fleets and country operations not just based on user demand and funding availability, but primarily on critical humanitarian access needs.

Output Title	Regional harmonised interagency protection monitoring system for the Sahel - Project 21 (P21)
Output number:		4	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	N/A (1st annual review)

Indicator(s)	Milestone(s) for this review	Progress
# of stakeholders citing P21 in their publicly available documents	6	8
# of training sessions on P21 methodology and tools	10	16
# of joint reports and dashboards disseminated	18	26

Briefly describe the output’s activities, and provide supporting narrative for the score.
Project 21 is an inter-agency harmonised protection monitoring mechanism in the Sahel countries of Burkina Faso, Chad, Mali and Niger. It has the intent to further the centrality of protection through investing in data, evidence and analysis contributing to more comprehensive analysis for evidence-based advocacy, protection programming and humanitarian response planning.

Project 21 has moderately exceeded the projected milestones for key activities. This output therefore scores an ‘A+’.

Impact weighting is 30% for this Output for the 2022 annual review, as results for output 1 &2 were not scheduled to be delivered in this timeframe, however this will return to 10% as foreseen in the overall log frame for the next annual review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The SHAPP business case made clear that we would use the set-up phase of SHAPP to work with UNHCR and FCDO central teams to develop and define VfM metrics for this component.

Economy: The main cost drivers of this project are staff costs and operational and coordination costs. We agreed that P21 staff would be recruited based on competitive and transparent processes that aims at securing the highest human resources quality and technical expertise. On the operational and coordination processes, UNHCR should avoid unnecessary start-up costs for field operations by simplifying the management of P21 governance structures and reducing the related costs. The following metric was agreed upon: % of Project 21 meetings organized in conjunction with existing coordination mechanism to reduce P21 logistical, administrative and governance costs.

As of November 2022, this is 70% for regional meetings & 80% (estimated) for country level meetings. This is performing quite highly, and we expect this to continue in the new year.

Efficiency: Timeliness of P21 publications is crucial for the efficiency of the project. This is alongside ensuring there is a low staff turnover rate for P21. The following metric was agreed upon: UNHCR Project 21 staff retention rate (%).

As of November 2022, UNHCR are meeting this VfM metric, as 100% of P21 staff have been retained so far.

Effectiveness: A key measure of effectiveness is the number of visits and downloads of protection data and analytical products on P21’s online dashboard. This reflects how effective and useful relevant stakeholders find P21’s online dashboard. The following metric was agreed upon: Number of visits and downloads of protection data and analytical products on P21 online dashboard.

From April 1st – Sept 30th 2022, there were 1254 visits. This is performing well, and we will continue to monitor this as the project continues.

Equity: P21 aims to provide a better evidence base to ensure that there is a better understanding of the specific needs of different groups, for example, gender and children. In practice a balance needs to be struck between the ambition to be comprehensive and ‘survey fatigue’. Nevertheless, the following metric was agreed upon: % of Project 21 questions that target gender and child protection issues.

As of November 2022, 16% of questions target gender issues (26 out of 163 in 2 questionnaires) whilst 25% target child protection issues (40 out of 163 in 2 questionnaires).

P21 have identified the need to address and make sure that there is a better gender balance between respondents.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first year of the Project 21 project. Funding for P21 has been agreed upon until 2025, which will enable UNHCR and downstream partners to effectively plan and forecast for the next few years. Nevertheless, there remain a number of lessons learnt including:

1. Implementing partners remain under strain in a similar way to other humanitarian actors, including because operational costs have increased due to rising cost of managing insecurity alongside global trends for fuel prices.
2. P21 will only maximise effectiveness if it achieves ‘buy-in’ from the full range of stakeholders and, critically, those who generate the raw data. To do so it must consistently demonstrate the added value that it provides.
Recommendation:
1. Ensure that benefits of multi-year funding are passed on from UNHCR to downstream partners.
2. Consider broader context factors when discussing forecasts and expenditure to determine likely effects and risks of a volatile national and regional operating context.
3. Following initial set-up phase ensure that there is a continuous drive for delivery of quality products relevant to stakeholders contributing to collective ‘buy-in’.
D: RISK [½ to 1 page]

Strategy & Context - We have a receptive appetite for these risks. The trend is complex emergencies and needs increasing in scale, scope, and intensity. There is growing insecurity in the region, including two coups in close succession in Burkina Faso and significant violence in Mali, Burkina Faso, Niger and Chad - particularly in border areas. Accessing people in greatest need is of concern, and our support to UNHAS and INSO helps to enable access to insecure areas. Mitigation measures remain our continued monitoring of the context, and early funding to partners enabling early planning and response. Overall, the risk level – severe – is unchanged.

Policy & Programming - We have a receptive appetite for these risks. There are risks that partner programmes, or specific areas of assistance may be under-funded, and they may not have sufficient staffing and technical capacity to deliver the programme. In mitigation we work with experienced multilateral and NGO partners, who have their own agreed risk management and delivery monitoring systems in place. They use their experience, and both global and in-country technical and management staff to deliver and oversee the implementation of their assistance plans.  Overall, the risk level is unchanged at moderate.

Safeguarding - We have a cautious appetite for safeguarding risk. The programme has an extremely low tolerance for safeguarding risks related to exploitation and Protection against Sexual Exploitation and Abuse (PSEA). The impact of this risk remains severe. We have mitigation in place with partners through due diligence assessments and delivery chain risk mapping and require partners to report any SEAH allegations to us as soon as they occur. Partners have hotline systems and grievance procedures in place. Allegations of SEAH in Burkina Faso in 2021 indicated that these needed reinforcing. The UK funded a PSEA coordinator role, deployed through a Standby Partnership, who worked with the Humanitarian Coordinator, local and international partners to improve systems and raise PSEA awareness among partners and beneficiaries.

We have a moderate tolerance for safeguarding risks relating to the security of our delivery partners. We accept that crime and insecurity risks are increasing for both partners and beneficiaries in the Sahel.  To mitigate this risk, agencies have needed to reroute supplies and take extra security measures, leading to increased costs and impacting VfM. We accept that some frontline staff of our delivery partners may be exposed to increased physical risk. Mitigation is difficult. We conduct due diligence assessments on partners to ensure they have suitable security management processes and contingency plans in place, and that they conduct ‘do no harm’ analysis to keep beneficiaries safe. The overall risk rating has risen to severe since the Business Case was approved.

Public Service Delivery and Operations – We have a minimal appetite for these risks. Increased instability and travel restrictions restricted the ability of staff to access programme locations to conduct monitoring, for example in Burkina Faso.  Following the lifting of Covid-19 travel restrictions, we resumed direct monitoring, but travel for HMG staff to areas where we need partners to work is challenging. Development Counsellors engagement with partners in-country contributes to our understanding and monitoring. The overall operational risk level remains moderate.

Financial & Fiduciary – We have a minimal appetite for fiduciary risks. We conduct due diligence of partners and work with them to ensure fiduciary and other controls are in place to minimise the risk of the diversion of funds before they reach beneficiaries. Increased instability in the Sahel could lead to an environment where fraud can take place more easily. There are specific aid diversion risks from armed non-state actors, particularly around Lake Chad and areas of the Central Sahel. This will be mitigated through having partners conduct do-no-harm analyses prior to their intervention, particularly for cash transfer programming. We engage with partners regularly and assess them to still have the experience and capability to identify and manage programmes in a high-risk environment. The overall risk level remains moderate.

Reputational – We have a minimal appetite for reputational risks. As set out above, we have robust controls in place to mitigate the delivery, operational, safeguarding, and fiduciary risks of our programme in the Sahel and the potential impact on our reputation. Given the presence of proscribed organisations in the region, there is a particular reputational risk relating to partner adherence to UK counter-terrorism legislation and policy, though this is an issue of perception as these should adhere to the principles of a ‘genuinely benign’ meeting and be classed as such. A ‘genuinely benign’ meeting is interpreted as a meeting at which the terrorist activities of the group are not promoted or encouraged. For example, a meeting designed to encourage a designated group to engage in a peace process or facilitate delivery of humanitarian aid where this does not involve knowingly transferring assets to a designated organisation. In mitigation, we have conducted due diligence on partners and all agreements with them specify the requirement that all partners abide by UK counter-terrorism regulations. This overall risk is classed as moderate.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

SHAPP funds are currently channelled through UNHCR, DRC, WFP (UNHAS) and INSO, with plans for a partnership with ICRC. FCDO has a contribution agreement with WFP (UNHAS), an MoU with UNHCR and Accountable Grant Agreements with DRC and INSO. DRC provides quarterly reports, with the FCDO team having in-person meetings with them to ensure the project is monitored and supported effectively in the beginning stages – the frequency of these will depend on project activities but are never less than once a month and during the set-up phase have been more often. UNHCR provides quarterly updates via virtual and in person meetings with the SRO and PRO, alongside email exchanges and updates as relevant updates. A more in-depth report is provided mid-year and annually. INSO provides FCDO specific reporting in April and October covering both results and expenditure, to which FCDO provides feedback by email and meetings. WFP (for UNHAS) provides semi-annual reporting and FCDO undertakes monitoring meetings at the regional and country levels, for example Development Counsellors participate in country-level quarterly steering group meetings.

Due Diligence Assessments (DDAs) have been conducted on DRC and UNHCR. A follow up DDA for DRC will take place in early 2023 once consortia lead partners and projects have been finalised. Following the UNHCR DDA, several risks were identified. These related to safeguarding, downstream delivery, financial stability, ability to deliver and governance and internal control. FCDO engages with UNHCR on these regularly, and UNHCR provides quarterly updates regarding agreed actions to ensure these risks are mitigated and addressed. INSO, UNHAS and ICRC DDA’s were undertaken in 2020 & 2021 as part of SHERP & SHAPP1. DDA’s last 3 years, and so subsequent DDA’s will have to be undertaken under SHAPP.

The Sahel Regional Fund project has now been set up, with spending occurring under the localisation component and the Fund Management Unit component. The first narrative and financial reports were sent in on September 30th, 2022, covering activities done between June and August 2022. The report and ongoing discussions showed that the project is progressing at a good pace, and we expect the main implementing partners to be in place by January 2023, with activities beginning by February 2023.

Under the Sahel Regional Fund, DRC have provided a draft delivery chain map, which maps the flow of funds. This will be updated with additional details after the lead consortium partners and implementing partners have been selected. For P21, UNHCR partners with DRC through a bipartite Project Partnership Agreement. UNHCR have also provided a delivery chain map which covers all their downstream partners. INSO uses its own staff to deliver all information, security, and training services; it does not have any downstream partners. UNHAS also directly delivers its own programme, contracting goods and services as required.

VfM is an important component of our programme management. Earlier this year, the Sahel & Security Department (SSD) economic adviser conducted a workshop with UNHCR to aid them in understanding FCDO’s VfM requirements, and to help them in forming specific criteria for the Project 21 project. Following the mid-year report and a meeting with UNHCR, it is clear to see that they are following the criteria to ensure VfM remains an important factor in their implementation. FCDO worked with DRC to ensure the VfM framework they provided in their proposal was suitable, however this framework will be reviewed and adapted following the selection of downstream partners. INSO provided detailed financial figures and results allowing a clear picture of VfM to be determined. UNHAS has shared data on their costs and results providing more assurance on their performance and that VfM is being delivered.

During the annual review interview process, interviews were conducted with DRC, International Council of Voluntary Agencies (independent observer) & UNHCR. DRC and UNHCR’s feedback on FCDO performance was positive, with focus being placed upon FCDO’s flexibility and support. From a self-assessment standpoint, it has been a good year with multiple agreements being signed and efficient work being done to move projects from their start up phases to delivery phases. In the next year, we will look to pro-actively support our partners to ensure our projects are delivering for those most in need, with special focus on the SRF.

Date of last narrative financial report	21/11/2022	Date of last audited annual statement	NA