## Annual Review Template

Title: Tax and Economic Governance
Programme Value £ (full life): £16,500,000		Review date: 20/08/2021
Programme Code: [AMP ID#] 300212	AMP start date: 20/08/2018	AMP end date: 31/07/2024

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/40109555.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/49850290.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

FCDO’s Tax and Economic Governance (TEG) programme aims to contribute to more inclusive economic growth by strengthening revenue collection, public investment and debt management, and supporting medium to long term fiscal planning. Fundamentally the programme is about strengthening how money is raised by government and how that money is managed to support economic stability and inclusive growth. Support is justified by two main aspects. First, there is evidence that the sharp drop in economic growth since 2016 and the spike in public debt, both resulting in reversed poverty gains, were largely caused by inefficiencies in public management (in particular, public investment and debt management). Second, the extractives sector (in particular Liquefied Natural Gas (LNG)) presents both enormous opportunities but also enormous challenges to economic governance. Mozambique needs to avoid the ‘resource curse’ which some analysts argue is already unfolding, with imbalances in the economy and a pattern of growth that doesn’t sufficiently benefit the poor. TEG seeks to respond to these challenges and opportunities through targeted technical support, combined with investment in reforms and high-level policy dialogue. The past year has presented numerous challenges to the country, including the Covid pandemic, and resulting economic slowdown, and the escalating conflict in the North of Mozambique, with knock-on impacts to future gas extraction. Income inequality also remains high in Mozambique, and the recent series of shocks to the economy have had a disproportionate impact on the poorest (most recently Covid, which has pushed an estimated 2 million people into poverty). The programme is therefore even more important, against a backdrop of rising spending needs, high debt and lower revenue prospects.
[note] https://www.wider.unu.edu/sites/default/files/Publications/Working-paper/PDF/wp2021-94-impact-COVID-19-consumption-poverty-Mozambique.pdf

TEG builds on previous UK technical and financial support to the Mozambique Revenue Authority (MRA) and to the Ministry of Economy and Finance (MEF). The programme plays an important role in delivering progress against the ‘resilient and productive economies’ pillar of the FCDO country business plan (in particular the macroeconomic management outcome), as well as supporting the broader foundations for all other pillars of the country plan in a range of ways. This includes supporting service delivery objectives under the human development pillar (by strengthening the way money is collected and managed); improving debt and fiscal risk transparency (which supports the open societies pillar); supporting improved revenue generation and climate smart investment (contributing to the cleaner, greener planet and humanitarian pillar); and helping tackle underlying drivers of conflict by enabling a more inclusive growth path (supporting the upstream threats pillar).

The programme is made up of 3 components:
[note] Note, the component numbers below don’t correspond exactly to the output numbers in the logframe

1. Tax Reform for Inclusive Development (TEDI) (£8m): Technical assistance and investment in reforms to strengthen revenue administration and policy. This component is delivered through a contracted service provider (Cowater International) and benefits both Mozambique MRA and MEF. (TEDI activities support TEG output 1).
2. Governance for Inclusive Growth’ (GEDI) (£7m): Technical assistance (mainly to MEF), and policy analysis, implemented through a World Bank Trust Fund initiated under this programme. GEDI focuses on three areas: (1) strengthening analysis and planning for inclusive growth; (2) strengthening public investment management (PIM); and (3) strengthening debt and fiscal risks management. A fourth area focuses on communication and wider partner engagement around policies and reforms. (GEDI activities support TEG outputs 2 and 3).
3. Monitoring, diagnostic and evidence (£1.5m): activities in support of the programme objectives, managed by FCDO. (Activities support primarily TEG output 3). During this reporting year no activities were planned under this output (in the coming years this component will fund the mid-term review and some targeted analysis/research work, including FCDO’s updated Fiduciary Risk Assessment).

Summary supporting narrative for the overall score in this review

Despite the challenges presented by the Covid pandemic, the programme has continued to make good progress over the last year, and an overall score of A is justified. Output milestones have been met across all indicators. The GEDI component continues to support incremental improvements across its intervention areas, although some are progressing more than others. And the TEDI tax component has successfully moved from inception to implementation stage in a challenging context. Some of the key programme highlights are noted below and elaborated further in the output sections.

- One of the first countries in sub-Saharan African to develop an SOE (State Owned Enterprise) debt database. Lack of debt transparency, particularly for SOEs, was one of the factors that led to the hidden loans crisis in 2016. GEDI has supported steady improvements in debt data, and Mozambique is now one of the first countries in sub-Saharan Africa to produce an SOE debt database.
- TEDI is the first project to provide substantial long-term technical assistance support, across multiple thematic areas, to the MRA through a third-part provider. The UK opted for this approach because of the importance of long-term sustained relationships with GoM (Government of Mozambique) for systems strengthening and because of the potential synergies with other technical assistance (mostly from the IMF) based on short-term, non-resident TA missions. This approach of developing relationships with government counterparts and building consensus around priority activities is important for securing buy-in and will lead to better outcomes in the long term (even if it means some delays in the short term, for example the delays to the MOU signing until all aspects of the workplan were agreed).
- Greater coverage of fiscal risks reports. Through GEDI support, the government’s fiscal risk reports now contain a much more holistic coverage of risks that may affect the government budget, including analysis of natural disasters, contingent liabilities and pensions.
  [note] Contingent liabilities are government’s obligations that need to be paid if certain events occur (e.g. a government backed loan). Because the costs of contingent liabilities are often invisible until they come to pass, they represent a potential drain on future government finances and a risk to stability. Hence, the inclusion of contingent liabilities in fiscal risk reports is important for giving a holistic view of government finances.
- The programme helped to unlock large amounts of WB (World Bank) funding. The Government needed to complete certain actions as part of accessing WB funding. These required actions were aligned with some of the activities under the GEDI programme, to help further incentivise implementation of GEDI’s objectives. The technical support through GEDI was critical in helping the government meet these requirements and unlock large amounts of funding. This included GEDI support to required government actions for the Covid response fund (US$100m) and contributing to the actions linked to the overall WB allocation to Mozambique (there is a 20% reduction, amounting to US$200m, if certain actions are not met – GEDI support helped to ensure all actions were achieved).
Major lessons and recommendations for the year ahead

The bullets below highlight some lessons and challenges from the last year.

- Technical engagement with government to underpin legislation. Work under public investment management and debt supported innovation at a technical level before formal legislation was adopted. Closely working with government to develop and test changes before amending legislation meant that improvements were appropriate, understood and had buy-in.
- An incremental, medium-long term approach to change is necessary. Debt, fiscal risk management and tax reforms are an iterative process, with each iteration providing greater understanding and buy-in by the authorities, eventually leading to innovations being codified in legislation and regular practice. This approach of building up trust and understanding is critical for taking advantage of reform windows when they arise. With GEDI support, the GoM has taken many steps to strengthen the regulatory framework for economic management, focusing on addressing vulnerabilities from SOE debt and guarantees, which were at the heart of the 2016 debt crisis. On the audit component under TEDI, Cowater started with small interventions to build credibility and already has more requests for technical assistance. The approach of the project speaks to the need to start small and operate flexibly, building up acceptance with the authorities at different levels.
- A challenging macro and fiscal context may slow reform implementation in some areas. For example, the continued fiscal consolidation has resulted in lower investment spending over recent years, and as a result the newly appraised projects (that have gone through the proper process, as supported by GEDI) are not yet incorporated into the public budget due to a lack of domestic financing. The result is a more gradual improvement in capital spending quality, the main objective of the reform.
- Covid has presented a range of challenges, but the project has adapted well. Travel restrictions meant delays to international consultants, and home working has presented challenges due to connectivity and availability of government counterparts. Despite these challenges the project has adapted and shifted some activities online to ensure delivery can continue.
- Another challenge is sufficient government capacity to engage. In some areas of support the technical engagement has been challenging due to overstretched government counterparts. And some of the new work on audit recommends more staff for a large taxpayer's unit, to reach programme outcomes.
The table below summarises broad recommendations for the programme over the coming year (with output-specific recommendations in section C).

Recommendations
In this reporting year the logframe changes were finalised close to the annual review, due to uncertainty over the programme budget. In the next reporting year, the logframe should be reviewed early in the reporting year, by October 2021. This should focus on setting milestones as well as strengthening indicators in certain areas. This will be done in tandem with a theory of change revision, given the TEDI sectors/workplan are now finalised (responsibility FCDO, with inputs from WB and Cowater).
Senior UK engagement with government on the critical programme areas should be increased over the coming year. Some engagement has occurred, particularly on the TEDI component due to the signing of the MOU. The TEDI steering committee (chaired by the permanent secretary of MEF) is another opportunity for engagement with senior MEF and MRA staff. There is scope for more engagement with government on GEDI activities (debt, public investment and fiscal risks), to discuss bottlenecks and help push progress (responsibility FCDO).
Improve the communications of project research and analysis. The project has funded some important research/analysis that lays out recommendations for medium-long term inclusive growth in Mozambique. These address a significant knowledge/research gap in Mozambique and should be disseminated widely. The GEDI team are developing a project website, and the World Bank with FCDO will run a dissemination event on the Country Economic Memorandum (responsibility World Bank and FCDO).
The project should continue to integrate considerations related to climate resilience and GESI (Gender Equality and Social Inclusion). TEDI has a workstream on including GESI within its tax policy work and GEDI is commencing work on integrating climate and geospatial analysis into public investment planning (to make public investment more equitable and climate sensitive) and could explore integration of gender considerations into public investment planning too. In addition, the World Bank and FCDO could consider inclusion of GESI climate issues in the launch event for the country economic memorandum (responsibility World Bank, Cowater and FCDO).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

At the impact level, the programme aims to foster ‘Improvements in inclusive growth and wider access to services that have been held back by inefficiencies in resource management and taxation’. This is underpinned by the outcome of ‘Strengthened Government of Mozambique capacity and processes demonstrated through improved revenue administration and more effective and transparent management of public resources’ and by more detailed outputs relating to revenue mobilisation capacity; reform on economic management (public investment management, fiscal risks and debt management); and policy analysis/evidence on inclusive growth. Increased inequality and a growth path based too narrowly on extractives presents a range of risks to Mozambique (including reversal in poverty reduction, and social/political tension in the north of the country). National development planning and fiscal/tax policy can play an important role in mitigating these risks by promoting a more inclusive growth path that benefits everyone in the country. This has become increasingly important over the last reporting year.
[note] Inequality appears to have increased due to the Covid19 shock, according to UNU WIDER (https://www.wider.unu.edu/sites/default/files/Publications/Working-paper/PDF/wp2021-94-impact-COVID-19-consumption-poverty-Mozambique.pdf)

This theory of change remains valid, and in some of the longer running output areas under GEDI there is evidence of improved government practice. This includes improved analysis and transparency (on debt and fiscal risks), an improved legal framework and improved staff capacity. The challenge for the GEDI component over the coming years will be to translate some of the output changes to outcome improvements, which requires continuing to build capacity, identifying windows for reform and secure commitment at senior levels of government. A key aspect of this is to continue to build our understanding of the political economy of the areas the project operates in, and for the UK to engage with the government more regularly to understand and raise issues (including through the ICCT and bilateral engagements). The upcoming World Bank budget support is also a key opportunity to incentivise reforms by linking required prior actions to programme areas.
[note] International Covid Crisis Taskforce – a group between senior government and heads of donor missions, to discuss and unblock critical challenges in the ongoing Covid pandemic. The UK is an active member in the taskforce.

On the TEDI component of the project, it is too early to assess the link between project activities/outputs and outcomes. Now that the workplan and sectors have been finalised (and the contract amendment is soon to be finalised) the theory of change will be updated during the first quarter of the next reporting year. However, the experience so far strongly aligns to the theory of change assumption/approach of working closely with government at technical levels to build buy-in for the programme and raising issues up to senior leadership when required (including through the steering committee).

More broadly, after the next annual review there will be an in-depth mid-term review of the programme (in the 2022/23 reporting year). This will give an independent assessment of the programme, including achievement of outputs and the extent to which those outputs are translating into real outcome/impact change.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress is on track to achieve the expected outcomes, although it is too early to make a detailed assessment under the TEDI component, given that the project has only recently moved to the implementation phase. Under GEDI, the project is delivering well against interim outcome targets, which it looks set to achieve by the end of the project.

Outcome indicators were updated this year to reflect the progress being made. For outcome indicator 1, the milestone for the public investment target was increased. For outcome indicator 2 the milestone was changed to refer to the SOE level database (rather than the central debt database), but with a higher target. This hasn’t drastically changed the overall VfM (Value for Money) of the programme – arguably the VfM has increased, given the increases in the outcome targets. Outcome indicator 1 will be assessed from next year onwards, given outputs in this area only started this year. Similarly, on outcome indicator 4, the expected influence on national strategies and policies will be assessed from next year onwards, building on new TEDI tax policy work and GEDI outputs on inclusive growth (e.g. once the national development strategy is finalised it will be possible to assess the extent to which it was influenced by the GEDI research recommendations).

Table 2: Progress on outcome indicators
Indicators (*)	Milestones for this review	Target (2024)	Progress
1. % of new projects funded through the budget or through state-owned enterprises that have been selected through the public investment management system.	50% of new projects funded through the budget or through state-owned enterprises that have been selected through the public investment management system.	50% of new projects funded through the budget have been selected through the public investment management system.	Partially met. This year, all new public investment projects went through the public investment management system. However, they were not included in the budget due to the lack of funds available.
2. Share of majority state-owned enterprises (SOEs) included in the Government of Mozambique's debt database	75% of SOEs are included in SOE debt database	60% of SOEs included in the GoM's debt database	Exceeded – all SOEs included in the SOE debt database.
3. Number of annual tax audits performed on largest extractive operations and on other extractive operations (to a good standard and based on adequate risk assessment).	N/A	All of the largest extractive operations audited annually plus analysis-based selection of other companies audited each year	Given that TEDI (which includes the extractives and audit work) only recently moved to the inception phase, this outcome will be assessed from the next reporting year onwards.
4. Evidence of national development strategies and policies (including tax policies) adopted that draw on policy analysis and are broadly consistent with inclusive growth and fiscal sustainability.	N/A	More analysis informed policies and strategies that consider inclusive growth	As above, this will be monitored from next year onwards now that the tax component has commenced. GEDI has published some important research/analysis this year, with the aim of influencing policy from next year onwards.

It is important to note that the logframe targets are a partial and imperfect measure of progress (given the complex nature of economic governance programmes, particularly in challenging contexts like Mozambique). Whilst progress has been positive on the logframe indicators, the challenge for the GEDI programme will be moving from the improvements in systems, legislation, transparency and capacity to changes in the way debt, fiscal risks and public investment is managed. The latter relies on political understanding and buy-in, so the flexible and demand led approach of the programme is vital. As part of the logframe revision we will improve the outcome indicators to bridge the gap between output changes and higher level outcomes/impacts. This will improve our assessment of programme trajectory.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis carried out on output/outcome progress, the programme continues to represent good value for money and should continue in its current form. The relevance of the activities has increased in a challenging macroeconomic and fiscal context, and the progress of the programme so far justifies continuation. The programme is addressing some of the key weaknesses in revenue and economic governance, showing progress against some of the weaknesses that led to the 2016 hidden loan crisis. Improvements in these areas takes time, and there’s a need to continue the programme to achieve sustainable change across all project output areas. As noted above, TEG is critical for delivering against the outcome targets in the country business plan.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened Revenue Authority capacity to increase the levels and efficiency of domestic revenue collection and reduce taxpayers’ compliance costs.
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 An efficient, risk-based and customer-centric revenue system that is effectively and equitably administered to enhance voluntary compliance,	Training on 2 modules (File Review & Audit Case Planning and Risk Analysis) delivered to 25 Auditors (40% women)	Met. Planned training delivered to 35 auditors of which 14 women (40%).
1.2 Capacity is strengthened to efficiently, effectively and equitably administer the extractives industry tax regime	Transfer Pricing (TP) training on Extractives Industry TP concepts applied to Mozambique delivered to the whole tax extractive unit and relevant staff (18 people).	Met. Three TP training sessions covering different TP aspects was delivered to 18 staff
1.3 Improved effectiveness, equity, transparency and coherence of tax policy, as measured by number of discrete pieces of analysis, policy notes or technical assistance reports with a focus on tax policy, inclusive growth and natural resource management completed and disseminated to encourage evidence-based decision-making and improve skills and capacity of a Tax Policy Unit	1 delivered (baseline study on VAT reform).	Met. VAT baseline study completed summarising the key features of a typical VAT regime and the features of VAT challenges in Mozambique.
1.3 Mozambican tax policy and administration demonstrates a responsiveness to GESI priorities	GESI and tax webinar delivered to GoM, private sector, and civil society	Met. TEDI delivered a presentation about GESI in taxation for a Mozambican Women’s Day event

Briefly describe the output’s activities and provide supporting narrative for the score.
This output relates to the work under the TEDI project. During the review period, TEDI completed its inception phase, the signature of the Memorandum of Understanding (MoU) with the government and started the implementation of the activities agreed under the approved inception work-plan. The output selected four main areas of intervention: tax audit, taxation of extractives, tax policy reform and Gender Equality and Social Inclusion (GESI). Below is the summary of the key activities delivered during the review period:
- Tax audit: taxpayers audit is crucial to recover revenues missed through normal taxpayers’ tax declarations. Well performed tax audits (and the associated penalisations for non-compliance) are also important for tax education of economic agents and improvements in voluntary tax compliance. During the review period, TEDI delivered technical training on key aspects of effective tax audits (including file review & audit case planning and risk analysis). Over the next period, TEDI will explore MRA appetite to work on building the systems for risk analysis and for risk-based selection of taxpayers to be audited and the creation of specialised sector audit teams (starting with the financial sector).
- Taxation of extractives: the extractive sector presents the largest opportunity for increased revenue collection in the medium to long-term after the major Liquefied Natural Gas (LNG) projects start production. The activities under the review period focused on Transfer Pricing (TP) training which is crucial for proper assessment of taxable incomes. TP consists of companies manipulating the prices of traded goods to reduce taxable amounts in specific jurisdictions and is a serious risk in the extractives sector. Going forward, TEDI will focus on on-the-job mentoring and support around TP, strengthening an extractives contracts database, providing access to data to support the unit to assess minerals pricing, supporting revision of the legislation and providing demand led support to the department as required.
- Tax policy: tax policy has important impacts on the level of tax raised, on business activities, on incentives (consumer/business behaviour) and on income distribution. As such, tax policy reforms should be underpinned by strong analyses of all these aspects. To date, MRA de facto leads on tax policy reforms with a clear focus on tax revenues analysis. TEDI is supporting MEF to build their capacity to gradually exercise their lead mandate on tax policy analysis and reforms, ensuring adequate analysis of the revenue, economic and distributional impacts of tax policy. Among others, TEDI has been requested to advise on the review of VAT and of the Simplified Tax for Small Taxpayers (ISPC). The former is expected to inform GoM negotiations of a critical new IMF programme.
- GESI: TEDI is one of the first initiatives looking to build GoM’s capacity to systematically embed GESI thinking in tax reform. Over the past year, the focus has been put on developing some internal analysis to inform future work. These analyses are informing: i) the ongoing work on awareness raising (the MRA invitation for TEDI to do a presentation on GESI at the National Women’s’ Day is a positive indication of the GoM’s appetite to further explore this area with TEDI support); and ii) the preparation of GESI training modules to be delivered in the next period (e.g. Mainstreaming GESI on income taxes and taxing informality). TEDI will also look at how the complexity of the VAT and ISPC tax reductions/exemptions systems is making the benefits inaccessible for many of the intended low-income group beneficiaries and how to improve these systems. The GESI intervention plan is still being scoped and over the next period a baseline study will be conducted to further inform the development of the plan of activities.

TEDI also supported the acquisition of IT equipment for both MEF and MRA (laptops, internet modems, printers, etc.) which are important for the tax auditors work (many auditors were using personal laptops) and important for flexible adjustment to remote working under the COVID-19 context. Another key purchase was supporting consultations across the country with extractive companies over new tax forms (designed to better inform MRA’s risk analysis).

This tax component of TEG remains on-track to deliver its expected results despite the delays in the completion of the inception phase. To reduce delays in the future, the project is looking to improve the ways of working with GoM including the adoption of a mutual performance assessment mechanism with performance indicators for both GoM and the service provider – the monitoring will be led by the project’s Steering Committee, which had its first meeting on August 16th. It is important to note that although the final MOU was signed in March 2021 (later than anticipated), the bulk of the inception phase was completed in the previous year, by June 2020. The MoU signing took longer due to delays in the audit workplan, but the extractives and tax policy workplans were developed quickly. While the audit work-plan was being finalized, TEDI moved ahead with various activities of the tax policy and extractives areas where the workplan had been agreed (e.g. tendering and recruitment of the two resident tax policy advisers and scoping mineral price databases).

Overall, the TEDI work-plan was successful in matching GoM demand with the service provider understanding of the relevance of the reforms needed. Nevertheless, there are opportunities to improve the prioritisation and delivery of activities. The work-plan under tax audit could be more ambitious in terms of strengthening the systems for taxpayers’ risk analysis and strategic selection of taxpayers to be audited – this is central to increase the efficiency of audits, revenue returns and voluntary compliance. However, this will depend to some extent on the budget available. The work on tax policy reform will need to properly consider the type of engagement needed between MEF and MRA with a view to gradually building MEF capabilities while making adequate use of MRA experience and procedures on the revenue aspects of tax reform. Another key priority is to build on the discussions from the first steering committee, held on August 16th (see previous paragraph and recommendations at the end of this output discussion).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The VfM for this output at economy level is strongly underpinned by the capacity of the implementer and the project team, whose fee rates thresholds are defined by the FCDO International Multi-Disciplinary (IMDP) framework and with senior consultant rates capped at about 10%-15% lower than the rates for some similar contracts. This combination of a relatively small, highly skilled and experienced team, alongside competitive fee rates, offers strong VfM. Section E details the key savings made by the project so far. At efficiency level, the agreement on the work-plan and signature of the MoU took longer than expected. Nevertheless, the longer discussions are perceived as important to build the required technical understanding and buy-in of the work-plan to ensure greater efficiency during implementation; and this did not prevent the project moving ahead with various elements of the work-plan that had been agreed. It is expected that the Steering Committee (SC), very recently established, will help reduce delays and increase the project’s efficiency through the implementation of a joint (GoM-FCDO) platform for monitoring of progress and for performance assessment. As the implementation of the work-plan started in the last quarter of the reporting period, it is too early to define or measure VfM indicators at effectiveness, cost-effectiveness or equity level.

As part of the ongoing contract amendment, the project is discussing the Monitoring and Learning (MEL) strategy, including the agreement on a set of VfM indicators to be monitored from next year. This will include equity indicators to reflect the work under the GESI component of the project (e.g. potentially, indicators to reflect how the GESI work will contribute to level the playing field for micro, small and medium businesses and improve the balance of tax burden vs fiscal transfers on disadvantaged and vulnerable groups).

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output designation remains unchanged. The output indicators were revised to reflect the activities of the implementation work-plan as the project started the implementation phase during the reporting year. In the next period, FCDO and Cowater will revisit the MEL strategy and the theory of change following the ongoing contract amendment. This may lead to a revision of the output and its indicators in the next period. The current version of the logframe does not include milestones for the next annual review and these will be defined in the next few months.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Table 3. Progress on previous AR recommendations and follow-up actions for next year.
Recommendation	Progress and follow-up
Ensuring strong engagement with GoM at technical and senior level and bringing in FCDO senior management support as required.	TEDI continued to build relationships at Director level and with staff that are benefitting from training. The FCDO technical team has reached out to the MRA president in January when TEDI was receiving conflicting information about the process to approve the work-plan. This proved instrumental for the subsequent approval of the work-plan. The MoU signature was a good opportunity to brief the Minister of economy and finances about the project and to confirm his openness to further discuss the project if needed. / The Acting Development Director for BHC Maputo attended the first SC meeting on 16th August, chaired by the MEF Permanent Secretary. This forum will allow senior representatives from FCDO and GoM to track progress, discuss and resolve issues before escalating to the minister or the President of MRA, if necessary.
FCDO to ensure support and facilitation to the tax donor coordination efforts to promote constructive engagement.	FCDO organized the last tax donors group meeting to present the TEDI approved work-plan. The TEDI SC includes (as observers) the most active donors working on tax (IMF, Switzerland and WB). / FCDO will continue to participate in the tax donors’ group and ensure it updates the group on TEDI activities at least twice a year.
FCDO to finalise the logframe indicators and milestones and to consider revision of the indicators weighting	Logframe revised. The indicators weightings remain unchanged. Another logframe revision may be needed after the completion of the contract amendment. FCDO and the service provider will define the milestones for next AR by October 2021.
Recommendations for the year ahead linked to this output
The main recommendation for the next period is for TEDI to use the SC as a key platform for strategic dialogue on the programme. The SC will also be important to help pursue the other two key recommendations: to explore the appetite for tax audit systems strengthening; and to explore how to more effectively manage MEF and MRA joint engagement on tax policy reform. (Responsibility – FCDO and Cowater).

Output Title	Strengthened Government of Mozambique systems, policies and reforms for economic management, focussed on PIM, fiscal risks and debt management
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Improved debt management processes and capacity and more robust debt and credit risk analysis that feed into stronger fiscal planning	i/ Support preparation and publication of 2020 annual debt report with SOE coverage and LNG / ii/ Provide adviser(s) to work with the back and middle offices to prepare 2022-24 MTDS (Medium Term Debt Strategy)	i/ met – the 2020 debt report was published on time, including SOE coverage, and the report was good quality. / ii/ met - GEDI has supported the preparation of the 2022-24 MTDS, primarily the required data collection/cleansing to underpin the strategy.
2.2 Public investment appraisal and management practices and processes standardised and in use	• Update annual PIM guidelines, including timelines and their alignment with the budget formulation calendar / • Provide on-demand TA on process improvements; CCSPP capacity; project appraisal/evaluation (IGEPE and DNPED).	Met – the programme has supported the regulatory framework for PIM in Mozambique as well as the development and roll out of an electronic platform for public investment (called ‘e-SNIP’)
2.3 Strengthened capacity and processes for management of debt and fiscal risks of SOEs	• On-demand TA and capacity building to utilize CRA (Credit Risk Assessment), produce fiscal and credit risk reports	Met - ongoing capacity building leading to improved fiscal and credit risk reports

Briefly describe the output’s activities, and provide supporting narrative for the score

This output, which represents the majority of the GEDI component’s activities, continues to demonstrate steady incremental progress on some of the most pressing economic governance challenges in Mozambique.

On debt (indicator 2.1) the project continues to provide important support to improve debt management and capacity, an area of huge importance for Mozambique. Assistance has included support to validate the debt database and migrate to a new system. This data cleansing is an important pre-requisite for development of a medium-term debt strategy, which will commence in the next reporting year. There were delays to the data cleansing as support from MEFMI (Macroeconomic and Financial Management Institute of Eastern and Southern Africa) was planned in person but was eventually done remotely due to Covid travel restrictions. Practical support has also been given to digitise loan agreements and create close working between the relevant government Ministries/agencies. The project also supported the development and publication of the 2020 debt report (published on time and giving a clearer picture on the debt situation in Mozambique). These reports are important for a range of stakeholders (government, donors, investors) and are also part of the World Bank’s SDFP (Sustainable Development Financing Policy) for Mozambique, which informs IDA allocations to Mozambique. The debt report was published before the deadline and received press attention. The team also fed into a pilot exercise to improve the World Bank’s Debt Reporting System, and Mozambique is one of the first countries in sub-Saharan Africa to produce an SOE debt database. This is an important foundation to address some of the factors that led to the hidden loans scandal in 2016. Many of the improvements made have been consolidated into legislation to institutionalise good practices. There have been some practical challenges in terms of essential hardware/connectivity – the project has supported internet connection for critical activities and is linking in with other projects to improve hardware and MEF intranet.
[note] As an IDA country currently in debt distress, Mozambique is subject to the SDFP. PPAs (Policy and Performance Actions) are designed as a programmatic engagement with Mozambique over the period of the IDA19 cycle. Satisfactory implementation of PPAs will release the set asides from the countries’ IDA allocations (which affects up to 20% of the allocation). Under the existing SDFP, the GoM committed to "publishing the 2020 annual debt report with SOE and LNG debt coverage by May 31, 2020", which was achieved, and hence the project supported the release of the IDA set aside.
[note] IDA, International Development Association, is the part of the World Bank that supports the world’s poorest countries.
[note] https://datahelpdesk.worldbank.org/knowledgebase/articles/381934-what-is-the-external-debt-reporting-system-drs

On PIM (indicator 2.2) the programme continues to build on progress made in the previous reporting year. This has included the development/roll out of the ‘e-SNIP’ platform, which tracks public investment throughout the project lifecycle. GEDI has also supported a PIM decree (decreto 52/2020) requiring appraisal of any investment project before inclusion in the budget (see outcome section above). Building on this, and other PIM decrees, the programme also supported the revision of the public finance law and its regulations. The next phase of PIM improvements will be supported by a sub-contracted firm (Cambridge Resources International). This will include the development of climate-sensitive investment standards, bringing geographical information system capabilities to the e-SNIP platform and expanding public investment support to the major SOEs in Mozambique. The team will explore whether the planning stage of public investment can be improved further to incorporate GESI analysis. Work is behind schedule as the WB had to re-launch the tender, but now that the contract is place work is underway. Overall progress on PIM is continuing well – the challenge over the coming years for this work will be ensuring the range of technical improvements translate to more efficient, fairer and greener public investments.
[note] Through the new SISTAFE law regulations and the e-SNIP platform.
[note] This work could be very impactful, given regional inequalities and the previous pattern of investment spending focused in urban areas (particularly in and around Maputo). The spatial and sectoral allocation patterns vs distribution of the poorest in the country will allow advice to MEF on prioritisation of pro-poor public investments.

On fiscal risks (indicator 2.3) output targets have been met, with some concrete results over the last 12 months. Fiscal risk reports have now been developed and published 3 years in a row, with GEDI support, and can be considered as institutionalised. Each year they have improved, with the latest including sections on fiscal risks related to natural disasters, contingent liabilities and pensions. Having a broader coverage of fiscal risks is key to ensuring that the impact of any shocks doesn’t fall disproportionately on the poor. Continued inequality and the series of recent shocks highlights the need for more inclusive fiscal policy that mitigates risks for the poorest. GEDI also supported the preparation of 7 fiscal risk reports for key SOEs, accounting for over 80% of all SOE assets and nearly all SOE external debt. Similar to the debt reports, this activity is aligned to the SDFP actions and the GEDI support helped the government achieve the milestone, paving the way for full release of IDA funding for the 2022 financial year (if actions are not met there is a 20% set aside of US$200m). The next step will be to expand the number of reports to cover 10 SOEs. These reports improve government’s ability to exercise oversight of the entire public debt portfolio, and hence the expansion to cover more SOEs is essential. Although the reports aren’t made public, they feed into the GoM fiscal risk report which will be published later this year. Full publication of all credit risk reports is something to be explored.

A broad challenge across this output is to capitalise on these legislative, transparency and capacity improvements to ensure real change in the way debt and fiscal risks are managed. This requires political commitment and expansion of tools to cover the whole public sector (e.g. public private partnerships).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM for this output at economy level is underpinned by the capacity of the WB as implementer. For example, procurement follows the WB’s robust processes which involve going out to competition via tender (which can mean a longer procurement process but gives the UK confidence in the outcome). The standard ‘indirect rate’ of 17% for trust funds is in line with the level expected in the business case. Given the limited breakdown of spending under World Bank trust funds (according to centrally agreed rules) it is difficult to do any thorough VfM analysis at the economy level beyond this (e.g. comparing consultancy day rates with other similar projects). Where possible the project utilizes local rather than international consultants to save on costs and travel.
[note] Charged as a percentage of staff costs (both permanent and short-term consultants).

At the efficiency level, the winning sub-contractors to support the second stage of the reforms are the incumbents, allowing the team to build on past relationships and facilitate a swift upgrade of e-SNIP I. This upgrade will make the system more user-friendly and accommodate several changes requested by the authorities. The update was not envisaged in the ToR, but it will not represent an additional cost to the program, and hence represents a more efficient delivery of outputs.

Effectiveness. The link between the GEDI activities and wider WB programming (Covid response, the broader IDA allocation and the upcoming budget support) has meant the results achieved have helped to unlock much larger sums of money (hundreds of millions of dollars). More broadly, the results achieved have the potential to improve the way debt is managed in Mozambique (which, given the size of debt, would be a huge impact). However, these outcome/impact changes will take more time. To assess outcome change, and GEDI contribution, the team will strengthen the logframe and use a broader set of indicators during the mid-term review to assess progress (including selected indicators from the World Bank’s ‘Debt Management Performance Assessment’ and the IMF ‘Public Investment Management Assessment’).
[note] This tool contains a range of indicators to measure debt management performance, including debt reporting, domestic/external borrowing, guarantees, and the coordination of debt with broader fiscal and monetary policy.
[note] This assessment contains a range of indicators across the public investment cycle, from planning, to allocation to implementation. The team will select indicators from the tool to give a more in depth assessment of progress and identify areas where further action should be prioritised.

Equity – assessing the impact on different beneficiary groups (to determine any equity VFM gains) is challenging given the nature of the outputs (improved debt management, for example, is an important foundation for broader fiscal goals such as service delivery, but it’s difficult to breakdown these outcome improvements by beneficiary group). The inclusion of geospatial analysis of public investment in next year's work plan could help to target investment more equitably in the country. Assessing the spread of investment and how this changes over time (and comparing this to levels of income/poverty in different regions) will give some evidence of equity gains in future years.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The GEDI workplan is agreed with government on a six-monthly basis, to ensure the programme is demand-led. The logframe indicators are based on the December/January report, however, the logframe wasn’t changed until the scale of the budget cuts were known (and therefore the milestones were added within six months of the annual review). These changes were agreed with the Development Director and recorded in the change frame tab of the update logframe spreadsheet.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous AR recommendations	Progress
In case the WB confirms the resumption of a medium-term budget support programme, it is important to include debt, fiscal risks and public investment management in the results framework to steer progress. Explore with the IMF the possibility of including some of these in the negotiation of a new IMF programme. Responsible: WB and MEF.	On track. The prior actions under the macro-fiscal pillar of the emergency budget support operation (including on debt reports, the publication of credit risk methodologies, and the passing of a PIM decree) were supported by GEDI. The programme is also informing the first programmatic DPF (Development Policy Financing) series since the hidden debt crisis, the Mozambique Programmatic Green, Resilient and Inclusive Recovery DPF (more than US$300 million), currently under preparation.
Continue to support the roll-out of PIM and seek to mobilise other donors’ support (in particular to the roll-out of training) and GoM financial contribution. Seek to integrate PIM in the revised Public Finance Administration System (SISTAFE) law and/or regulation to crystallise the PIM system in the public finances system and in alignment with the decentralisation process. With the inclusion of disaster risk consideration in the PIM decree, this will be a key feature to include in the next iteration of the e-SNIP. Continue discussions on how to extend e-SNIP to the SOE sector. Responsible: WB, MEF, CEDSIF, IGEPE.	Achieved and on track. PIM improvements have been integrated into the revised SISTAFE law and regulations. The workplan for 2021/22 will support inclusion of climate sensitive investment standards and disaster proofing public investments within e-SNIP. The EU have supported the roll out of training.
Ensure the MTDS is prepared, published and feeds into the MTFF process. Ensure the continuation of regular publication of the annual debt reports with a maximum time lag of six-months as required by international good practice. Responsible: MEF and WB.	On the MTDS: delayed, due to the prerequisite data gathering required. The 2021/22 workplan will include support on the MTDS and linking to the MTFF remains important. / On the debt reports: achieved, debt reports now published in line with the calendar.
Recommendations for the year ahead linked to this output
Support improved coverage of debt in the MTFF, and link MTDS to MTFF. Currently the MTFF document is light on detail when it comes to debt – there isn’t a section on overall level and composition of debt, and how the budget relates to this. The new MTDS will be an opportunity to develop a forward plan on debt, and then link this to the budget. Responsibility, WB.
The number of SOE risk reports should be expanded to ensure a broader coverage of government debt exposure. Responsibility, WB.
[note] Public Financial Administration System.

Output Title	Timely and relevant policy analysis and evidence conducted that feeds into fiscal planning and national debate and contributes to government policies and stakeholder partnerships and positions on inclusive growth
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Processes implemented in support of strengthened and more credible MTFF including use of more robust analysis and stronger institutional coordination and integration.	- Preparation of fiscal risks section and integration into MTFF. / - Formal training on MTFF, combined with on-the-job training	Achieved – support has been provided to develop a fiscal risks section (now in the MTFF), and training given to Ministry of Finance staff to improve the MTFF.
3.2 Number of discrete pieces of analysis, policy notes or technical assistance reports with a focus on inclusive growth and natural resource management completed and disseminated, aligned where possible with timing and relevance for national planning processes.	3 pieces of analysis/policy notes or reports	Partially achieved - three pieces of analysis were completed over the last year: the World Bank CEM (Country Economic Memorandum); a fiscal incidence analysis; and a study on the impact of Covid-19 on LNG in Mozambique). Full dissemination is needed in the next reporting year.

Briefly describe the output’s activities and provide supporting narrative for the score.

The GEDI programme has continued to support the government on the MTFF to ensure a more robust basis for fiscal planning. The quality of the document has improved, including a section on fiscal risks, more robust macroeconomic projections and different macro-fiscal scenarios. There is scope for further enhancement to the document and a programme of work has been set out for the coming year. One of the challenges has been the level of clarity over government demand for support in this area (partly due to the lead department being stretched). It will be important to get a clear sense of demand before embarking on the next activities in this area. More broadly, the next challenge with the MTFF will be to create stronger links with the budget and build a more multi-year approach to budgeting. GEDI’s incremental approach is sensible, building on outputs/engagement as the programme develops.

Against output 3.2, the programme has completed three pieces of analysis/reports on inclusive growth and natural resource management. Firstly, the CEM, which is the most substantial piece of analysis under this output and contains chapters on the current growth model; the impact of the resource boom on the economy; the spatial pattern of growth in Mozambique; the challenges/opportunities in the services sector; and finally, the governance and corruption challenges facing the private sector. The CEM fills an important gap in Mozambique, with no other document giving the same level of independent, rigorous analysis on the medium-long term development issues in the country. FCDO gave comments on the draft CEM which led to some improvements in coverage of gender and climate issues (although it would have been better to have built in gender analysis earlier in the process). Because of Covid the launch for the CEM was delayed and will now be launched virtually in the next reporting year. Already the CEM has been used to inform the government’s 2022-24 National Development Strategy, currently under development. As well as influencing government policy, the analysis in the CEM is critical for shaping the World Bank’s programming in country, including the upcoming DPF series and the country partnership framework. Over the last year the team also prepared a technical note on the impact of Covid 19 on LNG (Liquid Natural Gas) and presented it to the IMF and ENH (Empresa Nacional de Hidrocarbonetos). The note showed the debt position of ENH and total fiscal revenues from LNG is a pre and post Covid world. Lastly, a fiscal incidence analysis was carried out that shows the impact of taxes and transfers on poverty and inequality in Mozambique (Mozambique’s first tax incident analysis under the Commitment to Equity methodology). The next step for this work will be dissemination with government to inform tax policy scenario analysis (and continued link up with the TEDI tax policy work).
[note] The State-Owned Enterprise that owns a share of the Total Area 1 LNG project.

Given the cuts to the programme budget in the next financial year, activities related to indicator 3.2 over the year ahead are likely to focus on getting most value out of the research conducted this year, rather than funding additional policy notes. This will ensure that technical assistance across other outputs can continue. Furthermore, the WB are exploring whether analysis/research could be carried out under different projects/instruments (including important analytical work on the wage bill and pensions).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As above, the VfM at economy level is underpinned by the WB’s systems/standards, including on procurement and management overheads.

At the efficiency level, the comparative advantage that the WB has on PFM and economic governance programming means that project can deliver strongly on outputs (including building on established relationships with government, a wide network on consultants for TA, and strong in-house capacity to support research/analysis). The CEM, which was the key research output for this year, was delivered through a mix of in-house staff and consultants, which is cheaper than a fully consultant delivered report (given the daily cost of salaried staff is lower than short term consultants).

At the effectiveness level, work under outputs 2 and 3 have influenced the distribution of large sums of finance for Mozambique. The progress made under these outputs supported the completion of prior actions for US$100m of emergency support from the WB to the Government of Mozambique. Other outcomes related to improved fiscal planning and implementation of recommendations from research/analysis should be visible from 2022 onwards. Early indications are that the CEM will influence the governments national development plan and the WB’s country framework, both of which influence the allocation of substantial amounts of money.

At the equity level, there are no examples of how the benefits of this output have been distributed. However, the fiscal incidence analysis sets an important baseline on how different groups are affected by the tax system. Repeating this analysis in 2-3 years will give evidence on whether the programmes tax policy work is starting to take effect (particularly on VAT reform). The programme’s work on inclusive growth analysis should also translate to government policy/planning, although it’s too early to assess any impact (this will be picked up in the mid-term review).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As above for outputs 1 and 2, the milestones for this output were added within six months of the annual review, due to the uncertainty over budget/programme activity. However, the final indicators were based on the January WB results framework, and hence were more than six months before the review. For the next reporting year, the WB will reduce the scale of some activities under this output in response to budget reductions, but the overall output/outcomes are still achievable.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous AR recommendations	Progress
GEDI should consider adding fiscal rules to the macro-fiscal framework. In the absence of a fiscal responsibility law and clear medium-term fiscal targets in Mozambique, it will be important to build these rules into the macro-fiscal framework and use them to articulate the dialogue on fiscal discipline. Responsible: WB.	Not yet completed. Work is ongoing to further develop the MTFF, including the inclusion of fiscal rules (part of the 2021 workplan). This recommendation should be assessed under next annual review as well.
GEDI should provide technical support to implement the Minister of Finance instructions to separate the MTFF – led by DNPED – and the Medium-Term Budget Framework (MTBF) – led by the Budget Directorate (DNPO). Responsible: WB.	Completed. Under the new law/procedures for planning and budgeting the MTFF and MTEF (Medium term expenditure framework) processes are being undertaken separately for the first time in 2021. GEDI supported this transition. The next stage will be strengthening the link between the documents and ensuring the MTFF feeds into the budget process (which needs to move from short to medium term budgeting).
FCDO should ensure the WB and Cowater teams coordinate well to ensure synergies between the two components of TEG (GEDI and TEDI) are identified and activities are coherently planned for more effective results. This could include exploring the space for TEDI to add support to revenue forecasting and how to link it with GEDI work on the MTFF/MTBF. Responsible: FCDO, WB, Cowater.	Ongoing. Coordination between WB and Cowater has been good, particularly on tax policy (where some work undertaken by GEDI on tax incidence analysis is useful for the Cowater tax policy workstream).
Recommendations for the year ahead linked to this output
Early in the next reporting year the CEM should be launched to ensure the report reaches a wide audience (GoM, private sector, NGOs and academia) and has an impact on policy. This will tie into the plans to improve GEDI communication of outputs, including the development of a project website. The UK should also continue to raise the recommendations of the CEM in senior engagements with government. Responsible: WB and FCDO.
Clear demand from senior government is required for further MTFF enhancement, including better linking MTFF to the budget and shifting towards a more genuine medium-term fiscal and budget planning. The WB team will be working with government to assess the level of demand for the 2021/22 workplan, and to push for convening of a macro-fiscal working group (including relevant government ministries and the central bank, for more joined up macro-fiscal planning). These actions will help to enhance the sustainability of any support. Responsible: WB.

D: RISK

Overview of risk management

The FCDO team maintain the overall risk matrix for the project, drawing on discussions/reports from partners, interaction with government and other stakeholders.

The highest risks to the project remain related to strategy and context, as anticipated at the outset. As highlighted in the theory of change section, maintaining a good understanding of the political economy and engaging at various levels to test and encourage buy-in is critical.

A key emerging risk under ‘public service delivery and operations’ relate to the recent budget cuts, which will affect all components of the project. This reduction leaves little flexibility for TEDI to respond to emerging relevant procurement needs over the coming financial year, but it is not evident that it will have a major impact on the programme capacity to deliver its results.

On policy and programme delivery, risks remain largely moderate and stable, given the quality of the implementing partners. One new area of risk under this category is related to Cowater staff changes (due to programme budget cuts and underperformance of one of the consultants). The budget cuts led to the decision to change the team leader (but keep the existing team leader on as an advisor, on a 50% basis). This measure is sensible and will be monitored. An ongoing risk over the last year has been the Covid-19 pandemic which has impacted the programme in a wide range of ways, from cutting short time in-country for key experts, lack of in-person engagement with counterparts and absences of counterpart staff. Cases have risen in recent months and the slow roll out of vaccines means that Covid will remain a significant risk over the coming year and beyond. The partners have adapted as much as possible (shifting engagements/activities online and getting international consultants out to Mozambique when travel windows have allowed), which has helped to reduce the impact, but a hit to overall activity has been unavoidable.

Fiduciary, and reputational risks remained moderate. Both the World Bank and Cowater have strong safeguard and financial controls in place. Cowater’s Finance, Risk and Assurance Manager directly oversees the financial management of the project and liaises with FCDO on reporting and accountability requirements. Safeguarding risks remain moderate/minor and stable, given the nature of the project (which involves mostly office-based work in Maputo).

Update on Partnership Principles

Both the technical assistance and the support to GoM investment components of the programme are designed to not use GoM financial systems. However, over the duration of the programme, a gradual use of GoM financial systems with appropriate fiduciary controls may be considered. In that case Partnership Principles should be part of the programme management and monitoring.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

To date, FCDO has disbursed a total of £4,495,901.39, of which £1,495,397 to Cowater, £3,000,000 to the World Bank Trust Fund, and a total of £504.39 from the diagnostic and Monitoring component.

As shown in the table below, in this reporting period (July 2020 to June 2021), FCDO disbursed a total of £989,443.10 to Cowater against a budget of £1,546,137.18. This represents an underspend of £556,694.08 which translates into an execution rate of 63.99%. This is due to the pre-implementation phase discussions regarding the workplan taking longer than expected. Since the start of the implementation phase, Cowater has been demonstrating consistently little forecast variance against actual spend. As an example, just in the last trimester the execution rate against the forecast was of 101% (£371,523 forecasted against £375,629 actual). Based on this analysis we expect this level of execution to continue being demonstrated throughout next review period.

Beside a small contribution from the World Bank (£36,258 in this FY), FCDO is the sole contributing partner to the Trust Fund. During this reporting period FCDO disbursed £1,000,000 to the World Bank, of which the WB spent a total of £572,416. There was a considerable increase in the execution rate in the previous reporting period when compared to the first year of implementation, from 41% to 90%, however, in this reporting period the execution rate decreased to 57%. This was mainly due to procurement delays on the PIM (public investment management) component, but now that work has been awarded, we expect to see an increase in spending during the next reporting year.

FCDO Programme Annual budget execution to date
Component	Budget	Execution	% Execution
300212-101 (Tax)	£1,546,137.18 (Budget Jul 2020 to Jun 2021) / £1,941,388.58 (cumulative)	£989,443.10 (disbursements for period July 2020 to June 2021) * / £1,517,491.90 (cumulative)	63.99% (FY20/21) / 78.16% (Cumulative)
300212-102 (Economic Governance)	£1,000,000 (July 2020 to June 2021) / £3,000,000 (cumulative)	£572,416 (Disbursements FY 20/21) / £1,794,410 (cumulative)	57.24% / (FY 20/21) / 59.81% (cumulative)
300212-103 (Diagnostic)	£508.50 (payment FY 20/21)	£504.39 (FY 20/21	99%

(*) During this reporting period an additional £27,909.68 were disbursed. This amount refers to 25% Payment by Results of the previous period (2019/20).

The working relationship with Cowater and the World Bank have been positive. Both implementing partners have met the FCDO Programme Team on a regular basis throughout the period to discuss workplan, progress and finances, and have provided their quarterly/mid-year/annual reports on time. They have demonstrated adaptability in the face of challenges presented by Covid and budget changes, coming up with practical solutions to minimise disruption to the project. The World Bank has been an important partner on broader macroeconomic issues, for example providing presentations to FCDO’s deputy chief economist, and regularly discussing economic issues with the team.

Cowater’s commercial and financial performance remains very good. They maintain an efficient management structure with strong financial and administrative systems in place. A timely comprehensive monthly financial update is provided, and variances tend to be small. In addition to this, Cowater held regular meetings with FCDO to discuss issues such as the quarterly and annual reporting structures, internal policies, procurement systems and to agree changes that require FCDO approval. They also provided detailed bi-weekly updates on progress of activities which helped FCDO and Cowater work together to manage risks and resolve challenges promptly.

Regarding VFM, Cowater adopted cost control strategies, input optimization measures and output maximization approaches during the reporting period to maximize VFM at economy and efficiency levels.

Some examples of the adopted strategies on key interventions are:

-	Negotiating and reduction of hotel rates from $190 to $150. The total saving during the reporting period was equivalent to £5,650.
-	Competitive procurement of IT and Office Equipment for MEF saved around £3,595.62.
-	The use of a shared office space in Maputo reduces other expenses like electricity, water, internet, etc. Between January 2020 and June 2021 this has saved the project £14,568.
-	Sharing of TA resources across FCDO projects saved the project £1,751.
-	The Strategic Communications Advisor role has been merged with the Office Manager role with effect from June 2021 which have saved the project approximately £1,000.

The Key cost drivers of the programme during the year were fees and the MRA procurement fund. Overall, the cumulative monetary economy and efficiency savings amounted to approximately £284,188. A performance-based payment by results mechanism is in place to ensure performance, including KPIs (Key Performance Indicators) on quality and timeliness of agreed reporting and inception deliverables, accuracy of financial forecasting, and evidenced capacity to mobilise timely adequate technical assistance staff. During the review period, Cowater has satisfactorily met all KPIs. A new set of KPIs will be agreed as part of the ongoing contract amendment to be monitored from the next period. FCDO are currently implementing a contract management process to track supplier performance and identify opportunities for greater achievement of VfM. Cowater are fully engaged in this process.
In terms of audits and asset monitoring and control, the World Bank provides a Single Audit report annually. For the reporting period the report will be available in September 2021. Regarding the Tax component, the first audit started in early 2021 and was finalised in July (no significant issues were raised).
The programme maintains an updated asset registry, which has been shared and reviewed by FCDO. A physical asset spot check has not been undertaken during this review period given the current pandemic situation, however we will look to conduct this as soon as circumstances allow.
The team at FCDO are in regular contact with government counterparts, particularly in relation to the TEDI component to ensure the programme is demand led and that any potential barriers to implementation can be overcome. A wide range of Directors and technical staff in the relevant directorates were interviewed as part of this annual review. The review also involved analysing relevant Ministry of Finance documentation, other public financial management assessments and implementing partners annual reports.

Figure 1: Delivery Chain Map

FCDO Funds

Cowater International
WB Trust Fund for GEDI

Implementing Partners
- Mozambique Revenue Authority (MRA)
- Ministry of Economy & Finance (MEF)

WB implemented activities
(direct WB spend or sub-contracted services)

Consortium Partners
1. MAP Consultoria
2. Glasshouse Initiatives

Date of last narrative financial report	WB Economic Governance component – GEDI annual report (July 2021) / Tax Component - TEDI Financial Report (July 2021)	Date of last audited annual statement	The WB TF Single Audit report 2019/20 (September 2020) / The Cowater audit was finalised in July 2021.