## Annual Review Template

Title: Tax and Economic Governance
Programme Value £ (full life): £16,500,000		Review date: 20/08/2022
Programme Code: [AMP ID#] 300212	AMP start date: 20/08/2018	AMP end date: 31/07/2024

Summary of Programme Performance
Year	2019	2020	2021	2022
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/40109555.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/49850290.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

FCDO’s Tax and Economic Governance (TEG) programme contributes to more inclusive economic growth by strengthening revenue collection, public investment and debt management, and supporting medium to long term fiscal planning. Fundamentally, the programme is about strengthening how taxes are raised by government and how public spending is managed to support economic stability and growth that is distributed fairly across society. The programme achieves this through provision of technical assistance (short and long term experts, training and capacity building) and purchase of goods and services for government as required (equipment, software and travel).

Support is justified by two main challenges. First, there is evidence that the sharp drop in economic growth since 2016 and the spike in public debt, both resulting in reversed poverty gains, were largely caused by inefficiencies in public management (in particular, public investment and debt management). Second, the extractives sector (in particular Liquefied Natural Gas (LNG)) presents both enormous opportunities but also enormous challenges to economic governance. Mozambique needs to avoid the ‘resource curse’ which some analysts argue is already unfolding, with imbalances in the economy and a pattern of growth that doesn’t sufficiently benefit the poor. TEG seeks to respond to these challenges and opportunities through targeted technical support, combined with investment in reforms and high-level policy dialogue.

TEG plays an important role in delivering progress against the ‘strengthening economic partnerships’ pillar of the FCDO country business plan (in particular the macroeconomic management outcome), as well as supporting the broader foundations for all other pillars of the country plan in a range of ways. This includes supporting service delivery objectives under the women and girls pillar (by strengthening the way money is collected and managed); improving debt and fiscal risk transparency (which supports the freedom and democracy pillar); supporting improved revenue generation and climate smart investment (contributing to the cleaner, greener planet and humanitarian pillar); and helping tackle underlying drivers of conflict by enabling a more inclusive growth path (supporting defence and security partnerships pillar).

The programme is made up of 3 components:
[note] Note, the component numbers below don’t correspond exactly to the output numbers in the logframe

1. Tax Reform for Inclusive Development (TEDI) (£8m): Technical assistance and investment in reforms to strengthen revenue administration and policy. This component is delivered through a contracted service provider (Cowater International) and benefits both MRA (Mozambique Revenue Authority) and MEF (Ministry of Economy and Finance). TEDI activities support output 1 of the logframe.
2. Governance for Inclusive Growth (GEDI) (£7m): Technical assistance (mainly to MEF), and policy analysis, implemented through a World Bank-Executed Trust Fund initiated under this programme. GEDI focuses on three main areas: strengthening analysis and planning for inclusive growth; strengthening public investment management (PIM); and strengthening debt and fiscal risks management. GEDI activities support outputs 2 and 3 of the logframe.
3. Monitoring, diagnostic and evidence (£1.5m): activities in support of the programme objectives, managed by FCDO. Spend on this component was reduced over the last year but included the development of a fiduciary risk assessment and support for the launch of the Pemba urbanisation plan. Activities primarily support output 3 of the logframe.

Summary supporting narrative for the overall score in this review

Despite a reduction in the budget, the programme continues to make good progress across the majority of output areas and an overall score of A is well justified. GEDI, the longest running component, continues to make steady progress, including some impressive outcome change over the last year. TEDI is gradually building confidence and demand with government counterparts, as evidenced by the project scale-up requested by GoM (Government of Mozambique) and by the successful mobilisation of additional donor funding from Sweden. In some areas, such as tax policy, certain activities have been slower than hoped. This is to be expected in a complex, political programme of this nature, and TEG is designed with this in mind, with flexibility built in to respond to challenges. On tax policy, TEDI has used FCDO senior management to engaged with MEF at high-level and address some of the barriers, and over the next year we will focus on more systematic tax policy improvements, rather than reactive analytical work.

Feedback from government on the programme performance has been very positive, with lead Directors commenting on the helpful approach of the programme and the importance of the long term engagement. Some of the key programme highlights are noted below and elaborated further in the output sections.

- For the first time, all new public investment projects in the 2022 budget come from a published pre-appraised pipeline. The project has supported improvements in the way public investment projects are designed and managed, including a system called E-SNIP (Electronic National Public Investment System). All new projects for the budget now go through pre-appraisal on this system. This is a crucial step toward tackling poor investment decisions, such as those at the heart of the 2016 hidden debt crisis.
- TEG has supported many of the improvements that helped the return of an IMF (International Monetary Fund) programme in Mozambique. This return of an IMF programme marks a turnaround from the 2016 debt scandal (after which the IMF ended their programme) and shows the progress that has been made on economic governance. The IMF programme document specifically mentions many of the improvements that the TEG project supported, such as the work on debt transparency, fiscal risk management and VAT (Value Added Tax) reform.
The programme helped the GoM to complete a series of ‘prior actions’ required to secure US$300m of World Bank budget support. The government had a range of actions to complete before World Bank budget support could be agreed, and the GEDI project supported the government to achieve these. This budget support will assist the government in strengthening its institutions, delivery services and initiating the necessary economic transformation for a more inclusive growth model. Further, GEDI contributed to the actions linked to the overall IDA (International Development Association’s) allocation to Mozambique: 20% of the total budget (amounting to US$200m) is contingent on certain actions being completed (the ‘set aside’). GEDI support helped to ensure all actions were achieved.
[note] IDA is the part of the World Bank that supports the world's poorest countries to reduce poverty by providing grants, and zero to low-interest loans to boost economic growth, lessen inequality, and improve living conditions.
[note] This is part of the World Bank’s SDFP (Sustainable Development Financing Policy).
- Support to the government to expand the coverage of SOE (State Owned Enterprise) credit risk reports. If SOEs borrow or make a loan guarantee, it’s the government that has to pay. Hence, a lack of understanding on SOEs means the government doesn’t have a clear picture of overall public sector risk (one of the weaknesses that led to the 2016 debt crisis). 12 SOEs credit risk reports are now being produced, accounting for over 80% of all SOE assets and nearly all SOE external debt stock.
- TEDI is well established as the main project on tax in Mozambique, and feedback from GoM stakeholders on programme implementation and performance has been overwhelmingly positive. Progress across several areas has followed careful relationship building with government and a flexible, demand led approach. This is complemented by FCDO taking on leadership of the tax donor working group. The strength of TEDI’s delivery modality, relevance of thematic areas of intervention, and good progress to date has leveraged £6million of co-financing from Sweden, approved in early July 2022.
- TEDI contributed to a 145% increase (from c. $31.5m to c. $77.3m) in tax revenue collection from the mining sector over the first six months of 2022, through its support in the dissemination of new tax declaration forms. These extra funds are vital for delivery of public services in Mozambique.
- The programme has supported building new specialised tax audit teams in sectors with high revenue potential, starting with the financial sector. This will help ensure stronger revenue collection, and more funds available for public services.
- TEDI’s work on GESI (Gender Equality and Social Inclusion) is increasing awareness and generating demands from GoM on how to ensure revenue generation supports women and disadvantaged groups. This includes embedding GESI perspectives in taxpayers’ education and registration, and analysis of tax policy reforms’ impacts on different income groups.
Major lessons and recommendations for the year ahead

- Importance of allowing time to achieve meaningful, sustainable change. In several output areas the progress witnessed is the result of support through two or more annual budget cycles (for example, supporting the government on the annual debt report, three years in a row).
- Embedded advisors and regular partner engagement with government is crucial for longer term change. Accompanied on the job support helps to build professional trust, embed learning and institutionalise change, leading to more sustainable change. It also means the programme is able to take advantage of reform windows when they arise. Regular engagement between delivery partners, FCDO and government is important, including to address programme blockages.
- A range of delivery mechanisms is needed to address problems. Technical assistance (TA) in the form of training, on-the-job support and system improvements is important (and the main area of spend for the project). However not all problems can be solved through the use of TA, and the procurement fund under TEDI has been important for addressing challenges, for example through the provision of equipment like laptops, or for travel to ensure capacity is improved at provincial level.
- Uncertainty over FCDO budgets has made it difficult to plan and execute. The programme partners have delivered strongly despite this uncertainty and going forward the team will continue to have regular discussions with partners on budgets to ensure the most impactful work is prioritised.
- Low government capacity remains a key challenge. In some areas of support technical engagement has been challenging e.g., work on tax policy has moved slower than other areas as the team in MEF leads on a wide range of areas and is often stretched. There has been challenges also to retain the tax policy lead adviser position due to a mismatch of expectations on both GoM and the technical advisers’ side. A new adviser for the position has been recruited towards the end of the period and is building on lessons learned from previous experiences to improve the ways of working. Recommendations for the year ahead are contained in section C, corresponding to each of the outputs. One broad recommendation across all components is included below.

Recommendations
#1 Engagement from FCDO at senior levels has been useful to unlock bottlenecks, for example, getting MEF agreement to assign staff to work on tax policy. This should be maintained and scaled-up as needed. (Responsibility, FCDO).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

At the impact level, the programme aims to foster ‘Improvements in inclusive growth and wider access to services that have been held back by inefficiencies in resource management and taxation’. This is underpinned by the outcome of ‘Strengthened Government of Mozambique capacity and processes demonstrated through improved revenue administration and more effective and transparent management of public resources’ and by more detailed outputs relating to revenue mobilisation capacity; reform on economic management (public investment management, fiscal risks and debt management); and policy analysis/evidence on inclusive growth. Increased inequality and a growth path based too narrowly on extractives presents a range of risks to Mozambique (including reversal in poverty reduction, and social/political tension in the north of the country). National development planning and fiscal/tax policy can play an important role in mitigating these risks by promoting a more inclusive growth path that benefits everyone in the country. This has become increasingly important over the last few reporting years, with more people being pushed into poverty as a result of economic shocks.
[note] Inequality appears to have increased due to the Covid19 shock, according to UNU WIDER (https://www.wider.unu.edu/sites/default/files/Publications/Working-paper/PDF/wp2021-94-impact-COVID-19-consumption-poverty-Mozambique.pdf)

This theory of change remains valid, and in some of the longer running output areas under GEDI there is evidence of improved government practice. This includes improvements in the way public investment decisions are made, increased transparency (on debt and fiscal risks), and improved staff capacity. Progress affirms the theory of change, highlighting the need for long term engagement, government buy in and a flexible approach to respond to government demand. The challenge for the GEDI component over the coming years will be to build capacity more broadly across government, to ensure improvements can be implemented at sector and provincial level.

On the TEDI component of the programme, with just over more than one year since the start of implementation, it is too early to assess the link between project activities/outputs and outcomes. However, some early examples show how the project is supporting increased revenue collection (such as the support on extractive tax forms, as described below). More broadly, the experience so far confirms central elements of the TEDI delivery approach. In particular, the relevance of long-term TA delivered by an in-country team, complemented by a procurement fund, as well as the importance of gradually building buy-in for the project and confidence in the partnership. GoM is visibly looking to TEDI for support in more strategic and sensitive areas (e.g. risk management of taxpayers).

In the next reporting year, FCDO will commission an independent mid-term review of the programme (budget dependent). This will include a more in-depth assessment of the programme’s theory of change validity and the extent to which outputs are translating into real and sustainable change. This will help shape decisions for the remaining 2 years of the project.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress is on track to achieve the expected outcomes. There have been some impressive examples of outcome-level change over the last year, including all public investments going through the proper pre-appraisal before approval, an expansion in fiscal risk reporting, and improvements in debt transparency. On the revenue side, in most areas it is still too early in the programme to see outcome-level change, although the programme is making steady progress, particularly in audit and extractives.

Progress on outcome indicators
Indicators (*)	Milestones for this review	Target (2024)	Progress
1. % of new projects (and % share of investment budget) funded through the budget or through state-owned enterprises that have been selected through the public investment management system.	60%	70%	100% - Substantially exceeded. For the first time, all the new debt-financed public investment projects included in the 2022 budget (approved by Parliament in November 2021) were previously pre-appraised on E-SNIP.
2. Share of majority state-owned enterprises (SOEs) included in the Government of Mozambique's debt database	80% of SOEs are included in SOE debt database (and 30% in central government database)	60% of SOEs included in the GoM's debt database. SOE debt records are centralized through a shared application between central government and IGEPE.	Partially met – 100% of SOEs included in the SOE debt database, but migration to central government database not yet started.
3. Number of annual tax audits performed on largest extractive operations and on other extractive operations (to a good standard and based on adequate risk assessment).	N/A	All of the largest extractive operations audited annually plus analysis-based selection of other companies audited each year	Progress on this outcome will be monitored from next year onwards (after 1 full year of implementation the work is still at output stage).
4. Evidence of national strategies, policies and budgets (including tax policies) adopted that draw on policy analysis and are broadly consistent with inclusive growth and fiscal sustainability.	N/A	CEM (Country Economic Memorandum) findings support National Development Strategy preparation (2022); Credit Risks Assessments on SOEs are prepared, increasingly informing on-lending and guarantee issuances to SOEs (2021 onwards); at least 1 tax policy/law/regulation/GoM policy note is introduced or reviewed benefitting from TEDI analysis including GESI specific considerations.	Met. The CEM findings have been fed into the national development plan; 12 credit risk reports for SOEs were produced, informing the budget and debt strategy; 1 tax regulation was revised as a result of TEDI’s analysis (the decree on Reference Pricing Regulation – more details under output 1).
[note] The new regulation has been accepted by the MRA and is currently in the process of intra-government discussions. As per our logframe, TEDI counts draft tax policies as tax policies can take a long time to be approved by parliament and TEDI does not have an influence on this process.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme continues to provide strong evidence that it should continue, demonstrating delivery of outputs and outcome change in some of the most challenging areas of economic governance. The programme demonstrates the importance of a patient, long term approach for achieving change, and further work over the next 2-3 years will help to embed improvements and ensure sustainable change in economic governance. The programme supports delivery across a range of other objectives in the country plan.

The challenging context also highlights the need for the programme, with the fragile economic recovery from Covid hit by the recent hike in fuel and food prices (partly due to Russia’s invasion of Ukraine). The fiscal situation remains tight, with spending needs far greater than available resources, and debt still at high levels. The recent series of shocks that have hit Mozambique have had a disproportionate impact on the poorest, with a reversal in some of the hard-fought gains in poverty reduction over the last 2 decades.

On the upside, the IMF agreed a new 3-year programme of support in early 2022, followed by approval of a new World Bank budget support instrument. The recommencement of IMF and non-emergency budget support programmes after 6 years reflects the improvements the government has made on financial management, and the support from TEG has been an important part of these improvements. These programmes come at a critical time and will help to create space for spending on vital public services such as education, health and social protection. They also create space for more in-depth engagement with government on further reform on macro-fiscal issues and provide an important signal to donors and investors on the improvements made in economic governance that will help to stimulate additional finance.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened Revenue Authority capacity to increase the levels and efficiency of domestic revenue collection and reduce taxpayers’ compliance costs.
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Improved capacity of the audit function - measured by: a) number of specialised sector audit teams created (disaggregated by sector); and b) number of audits initiated and/or completed by specialised sector audit teams created	a) 1 sector specialised audit team created. B) and c) N/A for this period.	Met. a) 1 Financial Sector Audit team established. / B: n/a
1.2 Capacity is strengthened to efficiently, effectively and equitably administer the extractives industry tax regime - measured by the number of instruments (e.g. guidelines, databases) to strengthen extractive taxation functions that are developed with TEDI support;	Procurement of and training on the mineral reference price database completed	Partly met. TEDI assessed the feasibility of databases and provided written advice to MRA on two of them. The decision on what database to purchase is awaiting MRA board discussion and approval.
1.3 Number of trainings/capacity building activities on GESI delivered to MRA and/or MEF, with % trainees/beneficiaries reporting improved GESI understanding/awareness (disaggregated by sex)	≥50% male/female trainees reporting improved GESI understanding/awareness as applied to domestic revenue mobilisation	Exceeded. 96% male/ 86% women reporting improved GESI understanding/awareness

Briefly describe the output’s activities and provide supporting narrative for the score.
The output 1 indicators focus on TEDI’s support to the tax audit and taxation of extractives functions and on embedding GESI in tax policy and administration. Of the three output indicators, one was met, one partly met (with important progress and reason for delay largely outside the project control), and one exceeded – therefore a score of A is appropriate. The output milestones cover only part of the activities delivered as part of this taxation workstream and significant progress has been made in other aspects. This section summarises the most important.

The review period covers the first full year of implementation of project activities after the completion of the inception phase and signature of the Memorandum of Understanding with GoM in March 2021. Over the year, the activities delivered in partnership with MRA and MEF included provision of trainings, peer to peer thematic visits (to Ugandan Ministry of Finance and Revenue Authority), IT equipment (laptops, printers, internet modems), studies, tax policy and tax legislation analyses. Below is additional detail of the main activities delivered in each of the intervention areas:

Tax audits (output 1.1). Well-performed tax audits (and the associated penalties for non-compliance) are important to recover missed revenues, for tax education of economic agents and improvements in voluntary tax compliance. During the review period, TEDI delivered training on specialised audits in strategic sectors starting with the financial sector, a growing sector that accounts for 5% of GDP. Going forward, TEDI will help MRA to establish and properly capacitate specialised teams of auditors following the delivery of trainings for other priority sectors (including, telecommunications, construction, hospitality & tourism, and petroleum (distribution)). The team will also support the MRA in strengthening their audit case management processes and risk management procedures to introduce more risk-based audits, better target non-compliance, and improve revenues.

Taxation of extractives (output 1.2). The extractive sector presents the largest opportunity for increased revenue collection in the medium to long-term, after the major LNG projects start production. The activities under the review period focused on building MRA capacity to minimise inappropriate Transfer Pricing (TP) from companies and associated tax revenue losses. TEDI delivered specialised training on TP, conducted legislation analysis to support TP management, assessed international price benchmarking databases and provided recommendations on feasible options for Mozambique. Despite this important progress, the logframe milestone is behind schedule because an additional review was required to ensure GoM’s legal authority to select a specific database (which TEDI has been conducting). The resulting draft regulation has been accepted by the direct counterpart (MRA’s Extractives Unit) but needs to follow additional steps of consultations with other GoM departments. TEDI also supported MRA’s dissemination of the new extractive sector’s tax declaration form in the provinces. MRA reported a massive increase of 145% from large mining companies’ revenue, partly due to the introduction of the new form. The forms are also helping to collect more detailed extractive sector information that will feed into both risk management and tax policy analyses. In the next year, the focus will be on strengthening the TP work; building an extractives contracts database to facilitate the verification of tax obligations and inform tax audits of major extractive projects; and reviewing the mining and petroleum regulations to ensure harmonisation with tax regulations where interpretations remain dubious.
[note] TP occurs when companies trade goods or services with affiliated companies. Transfer mispricing occurs when one company sells to a related company at an in/deflated price to move profits to a lower-tax jurisdiction. Governments can address transfer mispricing by passing laws and regulations that request companies to apply the “arm’s-length” principle where related-party transactions are treated as if they were transactions on an open market. For this, countries require adequate legislation and adequate open market reference prices, and these are two aspects that are being supported by TEDI.

GESI (output 1.3). TEDI delivered a GESI Baseline Study, surveying 467 taxpayers including women, youth, people with disabilities operating in the formal and informal sector. The study presents how marginalised groups experience the tax system, including taxpayer compliance, business registration and accessibility to simplified tax regimes. This represents one of the first studies on the intersection between taxation and GESI issues in Mozambique and, together with the awareness sessions delivered, is contributing to a better understanding of the topic from a broad range of stakeholders in the Mozambican society. As a result, two GESI-specific interventions have been identified for the next year: to help MRA review its taxpayers’ education strategy and improving the taxpayers’ registry process to better suit women and small businesses.

More broadly, there has been strong progress in building TEDI governance mechanisms, which include: (1) a Steering Committee (SC) chaired by MEF’s Permanent Secretary (PS), with senior representatives from MEF and MRA departments supported by the programme, alongside a representative from FCDO senior leadership team; and (2) discussions to build a platform for coordination between tax donors and GoM following the confirmation of the UK as the chair of the tax donors working group in February. Both of these developments help ensure senior government buy-in and broader UK influence on taxation.

Over the last year the project has also attracted additional finance from Sweden, which will support a scale up of activity. The scale-up adds 15 months to the project duration and increases the team of local consultants and the in-country presence of international consultants.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM for this output at economy level is strongly underpinned by the capacity of the implementer and the project team, whose fee rate thresholds are defined by the FCDO International Multi-Disciplinary (IMDP) framework. Under this framework senior consultant rates are capped at about 10%-15% lower than the rates for some similar contracts. Section E details the key savings made by the project during the review period.

At efficiency level, the format of the project, based largely on long-term advisers with presence in-country, continues to be an efficient method to deliver long-term technical assistance in a context of a low starting base of institutional capabilities. The COVID19 pandemic and UK ODA (Official Development Assistance) budget reductions meant a smaller in-country presence of international experts than initially envisaged, but this was smoothed by the recruitment of one additional national technical adviser which also generated financial savings. Another important source of efficiency gains were the partnerships built with the African Tax Administration Forum (ATAF) and Her Majesty’s Revenue and Customs (HMRC) for the delivery of training, with fees covered by these respective institutions.

With little more than one year of implementation of activities, it is too soon to assess the VfM at effectiveness and cost-effectiveness levels. Nevertheless, the evidence from MRA that TEDI support in disseminating the new tax forms has directly contributed to a 145% increase in revenues, already signals good returns for the money invested.

With regards to equity, TEDI’s approach of ensuring its technical assistance and equipment reaches all provinces, and the build-up of GESI awareness in taxation for a broad range of stakeholders is strengthening the basis for improved equity of the tax system in Mozambique. Over the next year the GESI work will be expanded, moving from the baseline work to more concrete changes on tax policy and administration.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was revised during the last year to reflect the contract amendment completed in September 2021, for the move from inception to implementation and a reduction in the 20/21 TEDI budget as a result of the overall ODA budget reduction. The changes focused on more precise definition of the output and its indicators. The areas of focus were maintained but the tax policy analysis indicator was moved to output 3 (merged with economic governance analytical products). The output weighting remains the same (30%). As the scale-up of the project and detailed work-plan are expected to be approved in the next SC of September, a revision of the logframe will be required in the next period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation from last year	Progress and follow-up
The main recommendation for the next period is for TEDI to use the SC as a key platform for strategic dialogue on the programme. The SC will also be important to help pursue the other two key recommendations: to explore the appetite for tax audit systems strengthening; and to explore how to more effectively manage MEF and MRA joint engagement on tax policy reform. (Responsibility – FCDO and Cowater).	The first two SC meetings happened in the review year. In the 2nd meeting, the SC discussed and approved an initial scale-up proposal that included tax audit systems strengthening which is confirmed in the more detailed scale-up work-plan. MEF and MRA joint engagement on tax policy has been initiated (through shared training, a community of practice) but more effective mechanisms for coordination and exchange of information are to be explored and developed. FCDO has and will continue to raise this to the MEF PS and (together with Cowater) at directors’ level.
Lessons learned: The understanding of the project’s major challenges and opportunities remains broadly the same. These are focused on ensuring strong relationship building with counterparts, the importance of regular face-to-face engagements and the importance of FCDO TEG team and senior management to escalate issues to GoM senior level as needed and in consultation with Cowater.
Recommendations for the year ahead
#2 The new major recommendation is for FCDO as the new chair of the tax donors’ group to seek to formalise a mechanism for coordination on tax reform issues with both MRA and MEF that ensures greater engagement with GoM at senior level. Responsibility, FCDO.
#3 FCDO will work with Cowater to present the innovative GESI work to other teams in FCDO, to share the approach and findings. Responsibility, FCDO (through the tax and PFM community of practice).

Output Title	Strengthened Government of Mozambique systems, policies and reforms for economic management, focussed on PIM, fiscal risks and debt management
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Improved debt management processes and capacity and more robust debt and credit risk analysis that feed into stronger fiscal planning	i/ MTDS 2021-2024 produced with program support / ii/ Annual Debt Report 2021, featuring SOEs and PPP (Public-Private Partnership) sections produced with program support / iii/ Annual Borrowing Plan produced with program support (Domestic and External) / iv/ Internal DeMPA exercise conducted to inform future reforms	i/ met – MTDS 2022-2024 produced and published, with support from GEDI. / ii/ met – report published on time with chapters on SOE, LNG and PPPs (Public-Private Partnership). / iii/ met – annual borrowing plan produced, with support from the programme. / iv/ not met – preparatory work carried out for a DeMPA assessment, which will be carried out next year.
2.2 Public investment appraisal and management practices and processes standardised and in use	i/ E-SNIP successfully handed over and hosted at CEDSIF / ii/ E-SNIP integrated with other relevant platforms / iii/ Estimates of Conversion Factors for Non-Tradable goods and update of the Social Discount Rate completed / iv/ Disaster resilience standards developed and built into E-SNIP	i/ met – system now handed over to CEDSIF, including training to ensure smooth transition. / ii/ met – E-SNIP now integrated with systems on budgeting, spatial development and aid management. / iii/ Met – conversion factors and social discount rate completed and disseminated. / iv/ Met - disaster/climate resilience and mitigation sections have been incorporated into the E-SNIP.
2.3 Strengthened capacity and processes for management of debt and fiscal risks of SOEs	i/ Credit risk reports produced for 12 major SOEs / ii/ Fiscal risks report 2022 issued on time and with improved contents on risks stemming from SOEs, debt, and Covid-19	i/ Met – 12 reports produced / ii/ Met – report issued on time with new/improved contents on SOEs, debt, and PPPs.
[note] DeMPA is (Debt Management Performance Assessment) is a diagnostic tool used to evaluate a country's debt management processes and institutions. Through a comprehensive set of indicators spanning the full range of government debt management functions, the DeMPA identifies core strengths and weaknesses (https://www.worldbank.org/en/programs/debt-toolkit/dempa)
[note] Centro de desenvolvimento de sistemas de informacao de finances – finance information development centre. CEDSIF is a separate institution from the Ministry of Economy and Finance, setup to manage and modernise public finance information systems for all state and municipal bodies.

Briefly describe the output’s activities, and provide supporting narrative for the score

This output, which represents the majority of the GEDI component’s activities, continues to demonstrate steady incremental progress on some of the most pressing economic governance challenges in Mozambique. Of the ten milestones across the three indicators, nine have been met (with one delayed), justifying the overall score of A, ‘met expectations’. Activities under each of the three indicators are described below.

On debt (indicator 2.1) the project continues to provide important support to improve debt transparency and management, an area of huge importance for Mozambique. Support includes three embedded local consultants (working on the debt database), two international experts (supporting the debt reports), and training (including on the transition to a new debt management system). Areas of work over the last year include:
- Supporting the continuation and improvement of debt reports (the annual/quarterly debt reports). These documents significantly improve the transparency of public debt, and give clarity to donors, domestic markets and international investors. For the first time a PPP (Public-Private Partnerships) chapter was included in the annual debt report, covering the risks associated with 15 PPPs.
- Supporting the 2022-25 MTDS (Medium Term Debt Strategy) and 2022 annual borrowing plan. A series of workshops were organised to develop the MTDS, bringing together government, the central bank and the stock exchange. The MTDS is the first since 2015 and gives an important plan for how the government intends to borrow and manage its debt over the coming years. It helps to facilitate debt markets development and give confidence to donors and investors.
- Supporting the migration to a new debt management system, which will capture all internal and external debt, as well as contingent liabilities. One requirement for the migration to this system is to digitise all public sector loans. To achieve this, GEDI junior consultants organised, scanned and uploaded 258 boxes of paper records (a total of 1,874 documents).
Over the coming year, the team will continue to support on the areas above, with a focus on the migration to the new debt management and recording system; expanding the scope of debt reporting and embedding the improvements over recent years; and supporting a DeMPA (Debt Management Performance Assessment) exercise, to identify and address other debt management issues.

On PIM (Public Investment Management, indicator 2.2), the programme has met all targets, contributing to impressive improvements in the quality of public investment. Support is provided largely through a sub-contract with Cambridge Resource International (CRI), providing capacity building, IT and regulatory support on the following areas:
- Providing an estimate on the ‘social discount rate’, which allows benefits and costs at different times of an investment project to be compared. This is an important part of comparing public investment options.
- Support to CEDSIF (Centro de Desenvolvimento de Sistemas de Informacao de Finances) to handover and embed the E-SNIP system, through an embedded consultant. This system incorporates tools for project appraisal and evaluation, providing all information on public investment in Mozambique. The team also assisted government with integrating the system with planning and budgeting, spatial development and the aid management system (AIMS). This will help ensure that more effective public investment is linked up with the national budget, analysis of spatial development/inequality and donor investment projects.
- Developing a framework for climate-smart public investment and beginning the roll out of capacity development for its implementation. This framework helps to ensure that climate change risks are considered throughout the project cycle, and adaptation costs are included in appraisal. These changes have been incorporated into the E-SNIP platform, leveraged by the World Bank’s programmatic DPF (Development Policy Financing) series, which helped secure formal ministerial adoption.
- Capacity building with CEDSIF and MEF on planning, appraisal, management, and monitoring of public investments. Training materials were also prepared so that central government can build similar capacity among other critical stakeholders, including subnational governments.
Over the next year the priorities include the following (budget dependent): expanding the PIM framework to include SOEs; ensuring broader capacity building across government (including provincial) in the use of the E-SNIP system; support to CEDSIF to maintain the system and respond to user requests (a challenge raised during interviews); sector-specific project preparation manuals; and supporting government to develop and implement tools for identification of climate change/disaster risks. Capacity remains low with only a small number of MEF staff training in investment appraisal and risk analysis, therefore on-the-job training will be a priority in the coming year.

The work on fiscal risks (indicator 2.3) continues to show strong and steady progress, with an expansion of risk management across a wider set of areas. The programme has funded two embedded consultants, who have supported on the following:
- Continued capacity building on fiscal risk management and supporting the risk directorate on its compliance function across MEF.
- Support in the preparation of credit risk reports for 12 SOEs, accounting for over 80% of all SOE assets and nearly all SOE external debt stock. These reports are critical for understanding risks across the whole of government (SOEs have been a source of significant debt risk in recent years). This reform was aligned to an SDFP PPA (Sustainable Development Finance Policy Performance Policy Action), to incentivise implementation (in short, 20% of the World Bank’s IDA allocation to Mozambique s contingent on certain actions being completed - by linking the project to these prior actions it incentivises progress).
- Support in the preparation of the 2022 fiscal risk report (available on the MEF website), and work across departments to ensure risks associated from the government’s debt portfolio had been properly considered. The fiscal risk report had improved year on year, and now includes risks arising from SOEs, litigation and PPPs.
Over the next year GEDI will continue to support the government on the expanded fiscal risk report as well as adding 3 additional SOE credit risk reports.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM for this output at economy level is underpinned by the capacity of the WB as implementer. For example, procurement follows the WB’s robust processes which involve going out to competition via tender (which can mean a longer procurement process but gives the UK confidence in the outcome). The standard ‘indirect rate’ of 17% for trust funds is in line with the level expected in the business case.
[note] Charged as a percentage of staff costs (both permanent and short-term consultants).

At the efficiency level, the winning sub-contractors to support the second stage of the PIM reforms are the incumbents, allowing the team to build on past relationships and facilitate swift progress.

Effectiveness. The link between the GEDI activities and wider WB programming has meant the results of the programme have helped to unlock much larger sums of money, despite being a relatively small trust fund. This included supporting reform actions in the new SDFP, unlocking the 20% IDA allocation set aside for 2022. The GEDI technical assistance also helped to design a US$100m emergency DPF, and the new multiyear DPF (over US$300m). Including GEDI reform goals into the requirements for these instruments significantly helps to incentivise their implementation. More broadly, GEDI is supporting improvements in the way debt and public investment is managed in Mozambique (given the size of debt, and the scale of public investment management, even marginal improvements can have a big payoff).

Equity – assessing the impact on different beneficiary groups (to determine any equity VFM gains) is challenging given the nature of the outputs (improved debt management, for example, is an important foundation for broader fiscal goals such as service delivery, but it’s difficult to breakdown these outcome improvements by beneficiary group). The continued improvements in public investment management will support a more equitable distribution of spend, through inclusion of geospatial analysis and climate risks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The GEDI workplan is agreed with government on a six-monthly basis, to ensure the programme is demand-led. The logframe was updated in February with targets reflecting the agreed workplan. Despite reductions in the UK ODA budget leading to reductions in the 21/22 budget available for GEDI, the level of results under output 2 was maintained, given the importance of these activities (some cuts were made to output 3 instead).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous AR recommendations	Progress
Support improved coverage of debt in the MTFF, and link MTDS to MTFF. Currently the MTFF document is light on detail when it comes to debt – there isn’t a section on overall level and composition of debt, and how the budget relates to this. The new MTDS will be an opportunity to develop a forward plan on debt, and then link this to the budget. Responsibility, WB.	Achieved – the MTFF now includes a section on debt, with the departments working more closely to link up macroeconomic planning with debt management.
The number of SOE risk reports should be expanded to ensure a broader coverage of government debt exposure. Responsibility, WB.	Achieved – the number of credit risk reports was increased from 7 to 12, with further expansion planned for the coming year.
The upcoming WB DPF is a critical programme for the country, both in terms of scale of funding and the links to policy actions. Through the GEDI programme the UK is in a good position to influence and engage with the DPF (Development Policy Financing), including the prior actions, programme focus and sharing of analysis. Over the coming year the UK should request more regular engagement with the WB on the DPF, including with senior leads. Responsibility, FCDO.	Partly Achieved – there was some initial engagement on the DPF. Several GEDI priority areas are well represented in the new DPF.
Recommendations for the year ahead linked to this output
#4 IT constraints remain a challenge for MEF, which slows progress on critical areas such as the debt management database. GEDI only funds technical assistance, but in some instances providing consultants is insufficient to address the challenges faced, and the UK/WB should explore whether a small amount of TEG funds can be spent on IT equipment, to ensure progress is not delayed. Responsibility, WB and FCDO.
#5 Activities over the next year should prioritise capacity building, including at sector and decentralised levels of government. This will help to ensure improvements in fiscal risk and public investment management across all levels of government (for example, a large share of investment projects are developed and managed at the provincial level). Responsibility, WB.
#6 The work on climate-adaptive public investment management is of critical importance and has links to the work government is doing on a new climate finance strategy (a pipeline of climate-adaptive public investment projects can help attract climate finance). Links between these two workstreams should be explored in the coming year. Responsibility, FCDO.
[note] DPF is a WB general budget support vehicle for supporting sustainable, shared growth and poverty reduction through a program of policy and institutional actions (aimed at, for example, strengthening public financial management, improving the investment climate, addressing bottlenecks to improve service delivery, and diversifying the economy).

Output Title	Timely and relevant policy analysis and evidence conducted that feeds into fiscal planning and national debate and contributes to government policies and stakeholder partnerships and positions on inclusive growth
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Processes implemented in support of strengthened and more credible MTFF including use of more robust analysis and stronger institutional coordination and integration.	Provision of on demand support for preparation of MTFF.	Achieved – support has been provided on the MTFF, which has shown a marked improvement this year.
3.2 Number of discrete pieces of analysis, policy notes or technical assistance reports with a focus on inclusive growth and natural resource management completed and disseminated, aligned where possible with timing and relevance for national planning processes.	1 (Public expenditure review on SOEs and Education); 3 tax policy notes/TA reports of which at least 1 includes GESI considerations.	Achieved – public expenditure review completed, and due to be disseminated over the next reporting period; 7 tax policy notes completed, of which 2 are inclusive of GESI consideration; Fiduciary Risk Assessment completed.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 is the smallest across the programme, and the level of activity was reduced due to FCDO budget cuts. Despite these cuts, some important progress has been made, with a turnaround in the MTFF support and a substantial piece of analysis through the Public Expenditure Review.

The Medium Term Fiscal Framework (output 3.1) milestone was met, with an embedded consultant providing important support to the MTFF and the national development plan. In previous years progress has been challenging in this area, with lack of clarity in government demand and the short term capacity building missions not achieving significant progress. Given previous challenges, work was paused over the first half of the reporting year while the team worked with government to clarify demands and preferred delivery model. This led to the recruitment of a Mozambique consultant who is now embedded with the team in the Ministry. This approach has proved much more effective, and helped to ensure government buy in. There have been notable improvements in the MTFF this year, including more robust economic projections and scenarios, fiscal targets, clearer risk analysis, a section on debt dynamics and criteria for prioritising public investment. This means the government has a much stronger set of assumptions going into the national budget planning process. The consultant has also provided advice, mentoring and on-the-job training to help embed some of the improvements, and promoted greater engagement across MEF departments to ensure a more holistic MTFF. Support is also being provided on the macroeconomic aspects of the national development strategy, helping to ensure the 20-year vision draws on macro-fiscal models used for the MTFF and aligns with the government's economic transformation vision. Over the coming year support will continue on the MTFF, to embed changes and further strengthen, and more work to improve communication and coordination on macro-fiscal planning (both within MEF and with MRA/other government ministries). This could include building understanding and demand for a macro-fiscal technical working group across MEF institutions, and the Central Bank (although this has been challenging in recent years).

The target under output 3.2 was reduced slightly due to budget cuts, and the revised milestone was met, with the PER (Public Expenditure Review) and seven tax policy notes completed. As the name suggests, PERs give an assessment of how effectively and efficiently money is being spent. The sectors of SOEs and education were selected based on a combination of factors, including the country’s development program and reform priorities, spending trends, budget size and potential fiscal risks. The PER was partly funded by GEDI and the review will heavily inform the World Bank budget support programme, and policy dialogue with government. The CEM (Country Economic Memorandum) was also disseminated over the last reporting year, including through a short video in Portuguese. The GEDI team is working closely with MEF to build the recommendations from the CEM into the national developing strategy. Over the coming year the GEDI programme will continue to prioritise hands on technical assistance over analytical work, meaning this output area is likely to focus on one or two main analytical pieces next year (depending on the budget availability). This could include an updated analysis of LNG prospects in Mozambique, including economy wide impact of the gas industry and its contribution to inclusive growth. Secondly, the team might consider a paper on fiscal rules that would inform the planned fiscal responsibility law for 2023.

On tax policy, GoM requested TEDI support on three important areas: providing basic training on tax policy analysis; building a database and information exchange processes to enable this analysis; supporting reform options for specific taxes. Progress on these areas has been mixed over the last year. On the positive side, the milestone of three policy notes was exceeded, training was delivered to MEF/MRA and important support was given on options for VAT reform as part of the discussions for the new IMF programme (VAT reform was one of the more challenging areas in the programme negotiations, and TEDI support helped agreement to be reached). On the more challenging side, there has been little progress in building the database (although work is planned to start immediately in the new implementation year). This is due to several factors. Responsibility for tax policy sits with MEF, but, until June, there was no staff consistently allocated to undertake this function and benefit from TEDI’s capacity building (and the lead Directorate is already overstretched). TEDI has had to replace the consultant lead twice during the year and to function with the junior consultant for large parts of the year. It has also been difficult to find a tax policy lead who is available to work in country, which is far more effective than remote working.

Tax policy has a big impact on the level of tax raised, on business activities, on incentives (consumer/business behaviour) and on income distribution. There are huge opportunities for improvement, and the team will work closely with Cowater over the coming year to address the challenges noted above (see recommendations below).

Also under this output is work under the monitoring and evidence component of the project. Over the past year, this included an updated FRA (Fiduciary Risk Assessment). This FRA gives an assessment of Mozambique’s Public Financial Management, including fiscal transparency, anti-corruption efforts and accountability in the use of public funds. FRA’s are important for informing UK’s approach to financial aid, and the last assessment was carried out in 2017. The FRA shows that progress has been made in recent years, particularly in the areas supported through TEG, but that risks associated with financial aid remain high and the UK approach remains appropriate. The monitoring and evidence component was also used to fund the launch of the Pemba infrastructure and Urbanisation Plan. The UK supported the development of the plan through a central project, and the funding of the launch event was important for bringing together potential donors and funders for the implementation of the plan. The scale of development is Pemba is potentially huge and there are opportunities for UK investment, including in the climate resilient infrastructure projects identified in the plan.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As above, the VfM at economy level is underpinned by the WB’s systems/standards, including on procurement and management overheads.

At the efficiency level, the PER, which was the only research output for this year, was delivered through a mix of in-house staff and consultants, which is cheaper than a fully consultant delivered report (given the daily cost of salaried staff is lower than short term consultants). The work was co-financed by the World Bank and done jointly with UNICEF; this allows for broader reach of the findings, and a more in-depth piece of work (particularly important given the FCDO budget cuts). The CEM findings were shared with a large audience through a short video, which allowed broader reach and for lower cost than a traditional hotel conference room style launch.

At the effectiveness level, the CEM will influence the GoM’s national development plan and the WB’s country framework, both of which influence the allocation of substantial amounts of money.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Target 3.1 was set at a broad level this year, given the challenges in this area, and at times lack of clear/specific demands from government. Milestone for 3.2 was reduced, with the number of GEDI research outputs reduced from three to one, given the reduced budget.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous AR recommendations	Progress
Early in the next reporting year the CEM should be launched to ensure the report reaches a wide audience (GoM, private sector, NGOs and academia) and has an impact on policy. This will tie into the plans to improve GEDI communication of outputs, including the development of a project website. The UK should also continue to raise the recommendations of the CEM in senior engagements with government. Responsible: WB and FCDO.	Partly Achieved. This took longer than anticipated but the CEM was launched through a short video to reach a large audience. The project website will be functional early in the next reporting year.
Clear demand from senior government is required for further MTFF enhancement, including better linking MTFF to the budget and shifting towards a more genuine medium-term fiscal and budget planning. The WB team will be working with government to assess the level of demand for the 2021/22 workplan, and to push for convening of a macro-fiscal working group (including relevant government ministries and the central bank, for more joined up macro-fiscal planning). These actions will help to enhance the sustainability of any support. Responsible: WB.	Achieved. There has been a turnaround in this area, with the embedded advisor model bearing fruit. There are still a range of challenges to be addressed, and so support remains valid over the coming year.
GEDI should consider adding fiscal rules to the macro-fiscal framework (fiscal rules help to set limits on overspending, to ensure levels of deficit and debt remain sustainable). In the absence of a fiscal responsibility law and clear medium-term fiscal targets in Mozambique, it will be important to build these rules into the macro-fiscal framework for the national budget, to give greater transparency on fiscal discipline. Responsible: WB.	Ongoing. GEDI will be carrying out analysis of fiscal rules to inform the ongoing Sovereign Wealth Fund discussions, and the new fiscal responsibility law (which will be linked to broader World Bank programme to incentivise implementation).
Recommendations for the year ahead linked to this output
#7 The GEDI team has been developing a new website which will be important for dissemination of research products. This should be prioritised early in the reporting year. Responsibility, WB.
#8 To help improve engagement with MEF on the tax policy work, FCDO requested the MEF Permanent Secretary to appoint a group of people for the tax policy team. MEF appointed four people in June. This is expected to improve the quality of engagement but without properly addressing other challenges, it will be difficult to sustain this gain. Over the next year, the priority is to ensure consistent engagement with the tax policy team, including greater collaboration with MRA in building the database and data sharing processes. Responsibility, FCDO.
#9 To help address challenges in the tax policy component, Cowater should engage more regularly with MEF to help generate, understand and respond to demands. Trust and momentum have been built up strongly in the audit and extractives workstreams, in large part due to regular, proactive engagement with counterparts. This same approach should be applied to tax policy. Furthermore, in country presence of the tax policy lead will be far more impactful, and Cowater should try to move towards this with the tax policy lead (starting with regular country visits). Responsibility, Cowater.
#10 The FRA and PER have important links to other FCDO programmes and policy areas. For example, the PER will highlight recommendations for improving the effectiveness and efficiency of the education sector, and the FRA highlights some recommendations for system strengthening in the WASH (Water, Sanitation and Hygiene Programme) sector. Over the next year the TEG team should explore these links further and support broader work on system strengthening. Responsibility, FCDO.

D: RISK

Overview of risk management

A detailed programme risk matrix was kept updated on a quarterly basis throughout the year. Risks are updated by the programme and SRO/PRO, based on discussions with delivery partners and government.

The following is a summary of pre- and post-mitigation risk status of the 22 risks identified in the risk matrix. There are no risks outside the office risk appetite.

Summary of risks pre-mitigation
Severe	Major	Moderate	Minor
7	10	5	0
Summary of risks post-mitigation
Severe	Major	Moderate	Minor
0	4	10	8

As can be seen, despite the effective mitigation of risks, TEG remains a relatively high-risk programme given the nature of our work (addressing challenges on economic governance is political and requires long term engagement).

Summary of the main risks faced and mitigated during the year

The highest risks are related to strategy and context, and the slow pace of getting buy-in for the more strategic areas of work. Shifting GoM priorities also risk creating misalignment between initial plans and implementation. To address this, regular updates to the workplan were carried out to ensure that activities remained aligned with the objectives of the project and government. Steering Committee meetings every 6 months, and more regular senior engagement with MEF and MRA are also important for ensuring progress. Maintaining a good understanding of the technical and institutional challenges and engaging at various levels to test and encourage buy-in remains critical. Overall, the level of buy-in for the programme is strong, and trust has been built with government, allowing more challenging work to be taken on.

There are also several major risks related to policy and programme delivery. This includes difficulty securing dedicated technical counterparts within certain workstreams, frequent staff turnover in government and lack of access to data for evidence-based analysis. These risks have been addressed in several ways, including training and adapting to the requirements of each output; regular engagement with lead Directors and department leads to manage relationships; changing consultants when working relationships broke down; and focusing on embedded consultants (rather than remote) as much as possible. The quality of the implementing partners also helps to mitigate against this risk, both of whom have strong teams in place, a strong understanding of the context and good relationships with GoM.

A risk that has reduced over the last year is the Covid-19 risk, and the end of most travel restrictions has made a return to in-person working possible. Stringent and seemingly variable rules and delays in obtaining business visas continued to present challenges, making rapid and predictable deployment of international staff difficult. This was somewhat reduced by the increased experience of TEDI staff in dealing with such operational matters and a more stable workplan allowing for better scheduling of work.

A risk that has affected both reputational and programme delivery is the continued uncertainty around the overall project budget. Following UK ODA budget reductions last year there have been delays in confirming the 2022/23 budget, making it difficult to plan activities (the vast majority of work under TEG is long term, and requires engagement over several years). Implementing partners have adapted well to this uncertainty, with regular engagement with FCDO on the timing of activities/spend. The reputational risks with GoM of project reductions have so far been minimal, given the reductions have been small to date. But any further reductions would require careful management and engagement with GoM counterparts. The inclusion of Sweden in TEDI, as a result of the strong progress, is a big boost to the project and helps to mitigate against FCDO budget uncertainty.

Fiduciary risks remain low, given all procurement in the TEDI fund is being handled by the Cowater Project Management Unit in compliance with FCDO guidelines. Risks have been mitigated to the fullest extent possible. Safeguarding risks remain moderate/minor and stable, given the nature of the project (which involves mostly office-based work in Maputo).

Summary of new risks to be managed in the new implementation year

Many of the risks and mitigating actions noted above remain valid for the coming year. The main foreseeable delivery risk in the coming year is the ongoing uncertainty over the programme budget and the consequent uncertainty over expenditures and activities that can be committed to by TEDI/GEDI. The new funding from Sweden will alleviate this under the TEDI component, but requires a contract amendment, currently underway. FCDO will maintain regular contact with partners on budget availability, and prioritise activities as required.

In terms of broader political strategy and context risks, the next two years of the programme coincide with the run-up to first municipal and then presidential elections. This is likely to affect GoM priorities as well as the availability of key civil servants, many of whom also have party responsibilities. There is also an associated risk of change of counterparts and reshuffles of senior staff. The programme will continue to embed improvements at different levels (including technical level staff) to mitigate against changes in priorities/senior staff.

As noted above, a small number of risks have dominated over the last year, yet the risk register has 22 risks. The risk register will be shortened to make it more manageable and useful, dropping risks that are no longer relevant.

Update on Partnership Principles

Both the technical assistance and the support to GoM investment components of the programme are designed to not use GoM financial systems. A fiduciary risk assessment was produced under the monitoring and evidence component of the project, which highlighted that fiduciary risks had reduced in most areas, but still remained high. This confirms that our current approach is correct, however, over the duration of the programme, a gradual use of GoM financial systems with fiduciary controls may be considered.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency

Since the start of the TEG Programme (GEDI in December 2018, TEDI in January 2020 and Monitoring and evidence component in July 2018), FCDO has disbursed a total of £6.5m. Of this, £3.8m has been channelled to the World Bank under the GEDI component, £2.7m to Cowater under the TEDI component and £50k under the monitoring component, for work such as the National Fiduciary Risk Assessment.

During the reporting period, July 2021 to June 2022, FCDO disbursed a total of £1.34m to Cowater against a Budget of £1.37. In terms of variances between budget and actual spend, this represents an execution rate of 98.28%. in the previous reporting year the execution rate for TEDI was much lower, at 64%, due to it being the pre-implementation phase and discussions/agreement of the workplan took longer than expected. Now that the programme is in full implementation mode execution is much improved. Based on this analysis we expect this level of execution to continue throughout the next review period.

Regarding GEDI, FCDO has disbursed a total of £750k to the World Bank for the period July 2021 to June 2022. As seen in the table below, the funds were 100% executed, given that funding is through regular payments to the World Bank. Of the money transferred to the World Bank over 91% has been spent. The World Bank also contributed £41k of their own funds to GEDI.

TEG Programme Annual and cumulative budget execution (GBP)
Component	Budget	Execution	% Execution
300212-101 (TEDI)	£1,365,041 (July 2021 to June 2022) / £3,306,429.58 (total cumulative spend to date)	£1,341,607.38 (disbursements during period July 2021 to June 2022) * / £2,859,099 (cumulative)	98.28% (FY21/22) / 86.47% (Cumulative)
300212-102 (GEDI)	£750,000 (July 2021 to June 2022) / £3,750,000 (cumulative)	£750,000 (Disbursements during period July 2021 to June 2022) / £3,750,000 (cumulative)	100% / (FY 21/22) / 100% (cumulative)
300212-103 (Diagnostic)	£44,235 (July 2021 to June 2022)	£44,235 (Payments during period July 2021 to June 2022)	100%

(*) During the writing of this report an additional £109,738.10 were in the workflow to be paid to Cowater, which refers to June 2022 expense, and an additional £69,588.46 (25% of Payment by Results) for the period April to June 2022 are expected to be paid once the quarter goes through the Contract Performance Review.

Through regular meetings to discuss progress, finances and the workplan, FCDO have been able to maintain a close and positive working relationship with both Cowater and the WB Team, which allows the TEG team to keep on top of any issues or challenges that might arise. This is vital for ensuring a programme that is genuinely flexible and can adapt to changes in the context. The World Bank has also been an important partner on broader macroeconomic issues, regularly discussing economic issues with the team.

A quarterly payment by results assessment is in place to ensure Cowater’s satisfactory performance, including KPIs (Key Performance Indicators) on quality and timeliness of agreed reporting, implementation of deliverables and accuracy of financial forecasting. Cowater has consistently met all KPIs and maintained a positive approach to adjustments, such as responding swiftly to requests for earlier submission of forecasts and invoices. As reported in the previous Annual Review, Cowater’s commercial and financial performance remains very good. They have in place an efficient management structure with strong financial and administrative systems. They also provided detailed bi-weekly updates on progress of activities which has helped to manage risks and resolve challenges promptly.

Throughout the review period both implementing partners have provided their quarterly/mid-year/annual reports on time and have met all financial requirements, keeping variances between forecast and actuals to a minimum. They have demonstrated adaptability in the face of challenges presented by budget changes/delays and have adjusted accordingly.

To maximise VFM, the TEDI programme adopted various measures to reduce costs while preserving the quality of inputs and outputs during the reporting period July 2021 – June 2022. This includes the following examples:

- TEDI currently uses a shared office space instead of a standalone office. This has allowed the project to save £11,076 in the reporting period.
- The programme managed to negotiate short-term accommodation rates with a hotel in Maputo, yielding a cumulative saving of £3,330 over the reporting period.
- The competitive procurement of IT and Office Equipment for MRA (25 laptops) amounted to a saving of around £6,367.
- The programme continued to offer discounts on staff selling rates in compliance with the FCDO IMDP Framework rate card. The total discounts realised to FCDO this year was £40,966.
- Further savings were realised on subsistence costs for the staff travelling in-country during the reporting period, with claims at around half of the budgeted amount, yielding a cumulative saving of £4,122.

The cumulative savings amounted to approximately £68,991. These are economy and efficiency level savings. At the effectiveness level, there are examples where a small amount of funding has leveraged substantial benefits, such as the improvement in extractives revenue generation (output 1). Under the GEDI component the project has helped unlock substantial amounts of World Bank funding, through a relatively small trust fund.

In terms of audits and asset monitoring and control, the World Bank provides a Single Audit report annually. For the reporting period the report will be available in September 2022. For TEDI, in this financial year the Auditor issued an unqualified opinion with no relevant issues noted. Recommendations from the previous year have been addressed, except a finding regarding the tax regime applied by consultants. Although Cowater has no responsibility regarding the Consultants applied taxation regime they have agreed to address the finding by advising consultants of the Auditor’s recommendation.

TEDI maintains an updated asset registry, which is shared and reviewed by FCDO regularly. In December 2021 a virtual asset spot check was conducted. The assessment of assets established that the overall IT and general office equipment is maintained in good and safe conditions. No assets are purchased through the GEDI component.

The team at FCDO are in regular contact with government counterparts, particularly in relation to the TEDI component, to ensure the programme is demand-led and that any potential barriers to implementation can be overcome. A wide range of Directors and technical staff in the relevant directorates were interviewed as part of this annual review, alongside the consultants delivering the technical assistance and the GEDI/TEDI teams (17 government staff and 11 consultants covered during interviews). Feedback from counterparts was positive. For example, the MRA director of the Extractives Unit highlighted how the project adapted to overcome challenges (e.g. undertaking a legal review that was not anticipated in MRA’s initial request for support in the procurement and adoption of a price database). The review also involved analysing relevant Ministry of Finance documentation, other public financial management assessments and implementing partners annual reports.

Delivery Chain Map

FCDO Funds
WB implemented activities
(direct WB spend or sub-contracted services)

Consortium Partners
1. MAP Consultoria
2. Glasshouse Initiatives

WB Trust Fund for GEDI
Implementing Partners
- Mozambique Revenue Authority (MRA)
- Ministry of Economy & Finance (MEF)

Cowater International

Date of last narrative financial report	WB Economic Governance component – GEDI annual report (July 2021) / Tax Component - TEDI Financial Report (July 2021)	Date of last audited annual statement	Audit for the review period will be published in September 2022 / 30 June 2022