## Annual Review Template

Title: Somalia Security and Justice Programme Phase II
Programme Value £ (full life): £16.5m over 4 years rising to a total of £50m over 8 years (subject to further approvals		Review date: 09/2022
Programme Code: 300860	AMP start date: 08/10/2021	AMP end date: 31/03/2029

Summary of Programme Performance
Year	2022
Overall Output Score	A
Risk Rating	Severe

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Somalia Security and Justice Programme Phase II is designed to address several of the structural causes and proximate drivers of conflict. It is an important part of a wider HMG portfolio of stability, security and justice investments to deliver on the UK’s campaign goals. Specifically, it contributes to UK efforts to address security threats to Somalia, the region and to strengthen long-term stability by contributing to building a state that works for citizens and is underpinned by inclusive politics. SSJP II builds on an earlier security and justice programme which ran from 2016-2021. It aims to deliver tangible improvements to the accessibility, efficiency, quality and predictability of security and justice outcomes for ordinary people. This is significant from the perspective of reducing insecurity but also building confidence and trust in the State authorities (at all levels of government) and therefore contributing to wider efforts to develop a state-citizen contract in Somalia. The programme also aims to develop and pilot low-cost, hybrid approaches to improving security and justice responses, working with existing formal and informal institutions.
[note] Somalia Stability Fund, the Somalia Programme of the Conflict, Stability and Security Fund (CSSF), and the Public Resource Management in Somalia (PREMIS) programme, as well as work on counterterrorism.

At the time of this first annual review, SSJP II comprises of two components: (i) Nabadgelinta Soomaliya (Towards a Safer Somalia), delivered via UNOPS MOU, which will work in South West State and Jubaland to identify the most pressing security and justice concerns of local citizens and deliver improved responses, working through a variety of formal and informal channels; and (ii) The Somaliland Security Programme (SSP), jointly designed and funded with CSSF Somalia, delivered via a contract with Adam Smith International (ASI), focused on community policing. The current allocation of resources is 87.5% for Nabadgelinta and 12.5% for SSP. Both programmes have only commenced implementation relatively recently: SSP on 31/03/2022 and Nabadgelinta on 01/07/2022. This Annual Review is focused on the inception period of Nabadgelinta as the SSP is managed and reviewed under CSSF procedures (and is undergoing its annual review under CSSF in parallel, expected to be finalised end September 2022). FCDO anticipates adding further components to this programme to support the UN’s Joint Rule of Law programmes on policing and justice, subject to satisfactory design successor programmes and partner government support for them.

SSJP II will have greatest impact if it is able to successfully cohere with other HMG security and justice interventions. The team are already exploring connections. We anticipate working jointly with the Somalia Stability Fund to explore local accountability of security actors, land conflicts and security arrangements which sustain local reconciliation. We are also building connections to the Somalia CSSF programme, as this supports key Federal Government institutions and promotes effective planning for transition to Somali-led security arrangements, both of which Nabadgelinta will seek to influence. We anticipate that some of the work delivered through Nabadgelinta will demonstrate accepted and cost-effective local security arrangements which can inform formal, top-down planning.

Operating context: The design and inception of Nabadgelinta coincided with a watershed moment in Somalia’s post-civil war trajectory. On 15 May 2022, following a sixteen-month delay, there was a peaceful transition of power to a newly selected President. The election process followed months of often-violent political unrest in Mogadishu and elsewhere, which at times threatened to rupture Somalia’s fragile political settlement and further exacerbated underlying distrust between the country’s competing elites. At the height of the crisis in April 2021, security forces loyal to former President Mohamed Abdullahi Mohamed, (known as ‘Farmaajo’) engaged in armed clashes with troops aligned with Somalia’s political opposition. The clashes illustrated the volatility and risks associated with the government’s tenuous control over its armed security forces and the significant influence of clan loyalties over formal command and control.

The sustained political crisis and increased insecurity significantly curtailed efforts to advance security and justice reforms and to deepening federalism. In some cases, earlier progress appeared to be challenged as some within the federal government publicly dismissed political agreements such as the New Policing Model as illegitimate or irrelevant. Indeed, FGS-led security sector development priorities and investments were in direct contradiction to the federated National Security Architecture that had been endorsed in London in 2017 and which formed the basis for the subsequent Security Pact. Insecurity, particularly in the immediate runup to the May election, meant that many of Nabadgelinta’s programme partners were unable to travel freely or had only limited engagement with key stakeholders during the Inception period.

There are some signs of new opportunities to pursue reform. President Hassan Sheikh Mohamud has made early visits to several FMSs (something his predecessor had rarely done) and promised ‘no retaliation’ for those who had opposed his bid for office. He has also identified security sector reform and delivering on transition as top priorities. For much of the inception period of the programme, the team were awaiting the appointment of key Federal Government Ministers and other key positions such as the SPF Police Commissioner, which has necessarily limited opportunities for meaningful engagement. This is now a key focus of the coming months, and initial engagements led by FCDO have been positive – the programme is recognised as aligning with and supporting the President’s objective to have “a Somali society living in peace and harmony, based on public trust which is anchored on the principle of inclusiveness, mutual understanding, consensus, respect for the rule of law, and the rights of the citizens”.
[note] See https://villasomalia.gov.so/en/peace-at-home/

The formation of the new Government coincides with renewed emphasis on the transfer of responsibility for security from international partners to Somali leadership and institutions. In line with the ATMIS mandate, the first reduction in international troops (2000) is expected in December 2022. This brings new impetus to strengthening capability but also clarifying roles and responsibilities of different security institutions and ensuring that security forces act in a way which is acceptable to communities and are held accountable for their actions.

Funding context:

The Concept Note for SSJP II laid out an ambitious agenda against a proposed budget of £80m over 8 years. However, successive pressures on the ODA budget led FCDO to accelerate plans to pursue the programme as a joint donor endeavour, and it attracted significant interest from the EU and the Dutch, both of whom were planning to sign funding agreements in 2022. However, the emergence of serious allegations of fraud in connection with the Sustainable Investments in Infrastructure and Innovation (S3i) Initiative at the highest levels of UNOPS resulted in a decision of both donors to suspend the signing of new engagements with UNOPS, pending a comprehensive review of the results of an independent review of UNOPS internal control frameworks.

The review has multiple strands. The Acting Executive Director has initiated several reforms with immediate effect, including strengthening the independence and capacity of the internal audit function, revising the makeup of the Management Team to strengthen country office representation and the introduction of a revised whistle-blower policy. Preliminary findings of two KPMG-led reviews, one focused on accountability for S3i and the second on UNOPS overall governance, internal controls, risk management and cost structures, are expected in November 2022 and the process is expected to be concluded by February 2023. FCDO Somalia was permitted to honour the agreement it signed in December 2021, as the programme represented a key line of delivery under our Country Plan. However, this left UNOPS with a considerable funding gap. FCDO decided it was too risky to bring forward payments scheduled in Q4 of 22/23 to Q2, given this would only secure the programme until September 2022.

UNOPS Somalia immediately initiated a request for advance financing from its headquarters to bridge the period until 31 October 2022, when a further UK contribution could come online. The application made clear the significant political, reputational, and programme risks associated with a decision to not provide advance financing. This request was eventually approved by UNOPS headquarters and provides a measure of certainty within which the programme may operate for the first phase of its Implementation period. However, questions remain as to how the programme can be financially sustained through until Dutch and EU support comes on stream, given growing pressures on UK ODA in FY22/23.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

How this review was conducted: This first Annual Review has been undertaken by the programme team (SRO and PRO) and draws upon a series of engagements with programme partners throughout the inception phase, the end-of-inception workshop (24/06/2022) and the inception outputs which were delivered as per the programme document. Given the stage of implementation and the ongoing focus on the formation of government in Mogadishu, we have not engaged with government partners or beneficiaries in the conduct of this review.

Performance: For this first review, the programme scores an A. In summary, the programme has delivered high quality outputs in line with expectations. UNOPS, as Programme lead and fund manager, has performed strongly in the inception period. Considerable time and effort has been devoted to procuring high-quality partners, understanding and aligning to the context and establishing a one-programme approach. Nabadgelinta is now in a strong position to begin engaging in communities, identifying priority problems and working with local actors to address them.

The procurement of partners involved a thorough exploration of the market through extensive early market engagement and detailed scrutiny of proposals and bidders. Where responses to tenders did not meet expectations, UNOPS rapidly weighed their options and made several key decisions (see revisions to the lots detailed in Section C under Output 2). Contracting was completed around 5 weeks later than originally anticipated because negotiations with bidders were protracted, and this did impact on the time available for all partners to work together to deliver the agreed Inception outputs. Under pressure, the programme’s commitment to working in an integrated manner, drawing on all partners’ expertise and capability and reaching common understanding has been particularly impressive.

Time spent investing in a programme identity and common values has been well-spent, as the programme leadership have already had to jointly manage the impact of the UNOPS S3i allegations and the subsequent delays to other donors joining the programme. The programme relationships are underpinned by key agreements around governance, contract management, performance management, safeguarding and risk management. This approach, designed to drive collaborative thinking and delivery, has been informed by the lessons on the previous programme in which partners operated quite distinctly and the PCR observed that “whilst quarterly reviews brought partners together to consult and review progress, many of the partners delivered their work without full utilisation of the potential for synergies across the programme”.

Rather than extend the inception period, FCDO agreed with UNOPS to reduce some of the inception deliverables (for example, accepting that some documents would be draft, rather than final agreed versions). FCDO also agreed to grant an extension for the technical capacity assessments for all partners to relieve pressure on the other deliverables. Hence this output 2 scores a B.

Output	Score	Weight
1. Coherent, contextualised programme design completed by the end of Inception (July 2022)	A	50%
2. High-quality partnerships formed to enable coherent programme delivery	B	25%
3. Key programme management tools are established to guide the effective delivery of the programme.	A	25%

Major lessons and recommendations for the year ahead [1/2 page]

The programme has gone through a deep reflection on the Theory of Change, resulting in some insightful observations about how transformational change happens organically in Somalia.
Recommendation: The Nabadgelinta team should be invited to present this to a wider group of partners working in the security and justice space, potentially as part of a wider portfolio ‘Partner Day’. [Quarter 3]
The programme has also set out its intention to work through Islamic-based approaches, drawing on Islamic principles and engaging with religious duty bearers, following a reflection on social norms and the programme Theory of Change (see Output 3). The programme proposes further research on whether and how these approaches have been used previously to support positive security and justice outcomes, and to scope what would be required to operationalise such an approach within the programme.
Recommendation: The FCDO SRO will seek advice from LSLT as to whether FCDO should set some parameters for the approach to Islamic-based programming, particularly given that it may be necessary to engage with the Ministry of Religious Affairs. [By end of October 2022]
The dynamic context in which this programme is being implemented and its’ potential to impact on programme planning and results was very apparent, even at this early stage. For example, some district assessments could not go ahead because of dramatic changes in the security environment. Given the policy adopted by the new President to escalate military pressure on al-Shabaab, we should anticipate that the security environment will remain volatile. The landscape of international support for security and justice is also changing, with several like-minded donors reducing their resourcing for Somalia, and a shift away from state-building towards local service delivery, particularly on justice.
Recommendation: FCDO Somalia and the programme leadership need to regularly review the context for threats and opportunities. This should be linked to the programme governance arrangements (see below). [Ongoing].
Recommendation: FCDO Somalia will need to maintain a level of policy engagement, preferably in coordination with other actors such as UNSOM, on issues such as the Justice Model, key legislation, allocation of resources within the Somali national budget and resource-sharing between the FGS and FMS in order to see progress on critical institutional issues. [Ongoing]
The S3i allegations have delayed the joint financing of the programme. For some partners, particularly those who were also engaged in SSJP Phase 1 throughout the previous ODA reprioritisation cuts, this has been a challenging time. Whilst the solid foundations laid in building a values-based team and approach have stood the programme in good stead, it is important to recognise that partners ability to withstand funding uncertainty is finite.
Recommendation: FCDO Somalia to maintain close contact with those leading in HQ on the UK-UNOPS relationship to ensure awareness of any potential delays in concluding the reviews and any changes to the position of other donors which would negatively impact on the programme. FCDO Somalia and Nabadgelinta leadership to maintain close contact with the EU and Dutch Embassy locally to keep them appraised of progress. [Ongoing]
Considerable effort has been made to develop a one-programme approach across the partners from the very outset and to establish how this interacts with the existing governance structures and processes of the partners. There are still some details to be finalised.
Recommendation: Finalising the governance structures should be a critical focus for FCDO and UNOPS in the next quarter. [Q3]
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

SSJP II Theory of Change (as set out in the Business Case): / If we support more inclusive negotiation on political, legal and financial frameworks and enable and incentivise security and justice institutions to be increasingly inclusive, capable and accountable and to work together to respond locally identified needs and priorities / And if we understand and strengthen positive social norms that reinforce inclusive approaches to the rule of law / All while continually applying structured learning, research and evidence to inform programme adaptation and to influence wider stakeholders – Somali and international – to increasingly collaborate / Then Somalis will benefit from improved security and access to justice through inclusive approaches that enjoy broad based understanding, support, and both elite and public confidence / And ultimately there will be improved rule of law in Somalia, which contributes to strengthened social contract between the State and Society and to establishing the foundations of sustainable political settlement.

The inception phase of Nabadgelinta has conducted a context analysis and a Gendered Political, Social and Economic Analysis of the security and justice landscape, as well as a detailed review of the programme’s own Theory of Change. These processes have:
1. Affirmed the importance of inclusivity of approach, including inclusivity of customary and traditional beliefs, actors and institutions.
2. Affirmed the criticality of security and justice issues to the overall political settlement and political processes in Somalia, and that security and justice actors are not currently viewed as neutral, inclusive or accountable.
3. Challenged our thinking around the importance of and the potential evolution of a social contract directly between citizens and the state, and highlighted the competition between different layers of government, as well as between formal and informal institutions and systems.
4. Confirmed the limitations of stand-alone top-down or bottom-up approaches and the importance of being able to form diverse interest-based coalitions to effect lasting change.
5. Confirmed the importance of social norms – observing that instrumentalising gender norms and relations is closely linked to contestation for political and ideological power; and
6. Proposed exploring security programming rooted in peacebuilding approaches.
Reviewing the Nabadgelinta Theory of Change was a major priority during inception. UNOPS developed an initial ToC for the programme document, prior to signature, based on in-depth primary and secondary research carried out during SSJP Phase 1. The review process enabled co-creation of a revised ToC with the implementing partners, thereby increasing their ownership and commitment to the programme and allowed the assumptions to be interrogated from a Somali perspective, which had been limited prior to the contracting of downstream partners. The evolution of the ToC has been set out in detail in the inception outputs. This process included some deep reflection on how change happens without external intervention in Somali society and politics. This exercise enabled Nabadgelinta partners to identify and better understand the essential phases through which successful change in Somalia will likely need to pass. It also suggested ways that external support might be brought to bear – in a limited and targeted manner – to help ensure change is successful, legitimate and sustainable. This work reaffirms the programme’s chosen approach, focused on inclusivity and problem-solving, suggesting that this could improve the degree of Somali-ownership, greater acceptance of the ‘solutions’ identified, and greater endurance and resilience of the actions taken.
[note] See Annex 1

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The progress made in the inception period has set up the programme well to move towards implementation on track. The deep interrogation of the Theory of Change provides a strong degree of confidence in the overall design of the programme. The proposed formative research and approach to community engagement will provide opportunities to fill gaps in understanding and direct action towards community priorities and enable a range of stakeholders to engage in problem-solving.

Progress has been made to address outstanding issues identified in the Due Diligence Assessment and to respond to FCDO’s desire for greater scrutiny following the S3i allegations (all logged in the Delivery Plan). This, together with the establishment of key programme management policies and tools set out in the inception deliverables provides a high degree of confidence that the programme management arrangements are strong and well-suited to the complex and adaptive programme approach as envisaged in the Business Case.

As stated above, the funding outlook for Nabadgelinta is uncertain. The two other donors, the Dutch and EU, are unable to progress to signing commitments until the reviews triggered by the S3i allegations have been concluded. They are continuing to prepare for this, which is positive, but their participation cannot be guaranteed. To date, UNOPS has been able to meet the shortfall from the reserve, but if the uncertainty persists into the new calendar year, FCDO and UNOPS will need to consider the viability of the current programme model and level of ambition. The nature of contracts and the volume of staff in the programme mean that pausing activities will not necessarily save significant resources and the programme stands to lose key staff members if resources do not continue to flow to downstream partners.

If the programme receives funding from other donors and can progress, FCDO will commission an independent mid-term review of Nabadgelinta to report by the end of FY 23/24. This will be required to inform a business case addendum to secure funding for the outer years of the programme. It is recommended that the independent Mid-Term Review is commissioned no later than October 2023 and carried out January – March 2024.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Somalia has seen important progress in recent years, but these gains are extremely fragile. Achieving the shared HMG objective of a more secure, resilient and stable Somalia, requires a broadening and deepening of the political settlement and social contract, improved security and an acceleration of Somalia’s economic recovery. This requires that the process of strengthening the rule of law be approached not as a technocratic exercise, but as a political process through which the expectations and obligations of state and society are negotiated, reinforced and institutionalised. In practical terms, this requires that (a) resources and capacity are directed to meet the expectations of the public; (b) acceptable and affordable security and justice institutions are capable of delivering against those expectations; and (c) collective social expectations of the legitimate extent of state power and of citizen’s obligations support strengthening of the rule of law.

Enhanced security is key priority in Somalia to address the threat posed by Al Shabab, including to UK interests in the region, and to enable a transition away from a reliance on ATMIS to Somali led security. Improving security is critical enabler for progress on wider development and in seeking to reduce the significant humanitarian needs in Somalia.

Although it is early days, the President has set out an ambitious strategy to address many of these issues and the newly appointed Cabinet are demonstrating a high degree of coherence around these priorities. The UK is at the forefront of the international community in supporting these efforts. It has been instrumental in establishing a Core Group of Security Partners (CSPG) to channel support and is the penholder in the UNSC on Somalia. The UK is also a recognised global leader on supporting security and justice reform.

In a more conducive policy environment, this programme is well-placed to develop evidence of what works at the local level and use these examples to influence policy making at a critical moment. The programme has the ability to work at local, FMS and FGS levels and to convene stakeholders from across the different levels of government. Early engagement with the authorities has been welcomed.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Coherent, contextualised programme design completed by the end of Inception (July 2022)
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Programme design completed based on a baseline situational analysis of the context and formative research on key security and justice challenges	By end of inception (July 2022), an initial programme design has been finalised drawing clearly on the baseline analysis and formative research	Completed. The Nabadgelinta programme completed a situation analysis in June 2022 (including a literature review and actor mapping) and a baseline gender-sensitive political economy analysis. Programme design is largely finalised and the delivery teams have started the initial implementation activities. / A proposal for formative research has been developed, based on the Theory of Change/Theories of Action, gaps identified in the literature review. The research findings will build on data collated during inception period and during SSJP phase I. / See Annex 2: list of inception deliverables
Districts in Jubaland and South West State selected for implementation against clear criteria	By end of inception (July 2022), implementation districts have been identified against clear criteria	Complete. Following a two-phase assessment, the programme team have selected four districts: Kismayo and Garbaharey in Jubaland and Baidoa and Hudur in South West.

Briefly describe the output’s activities and provide supporting narrative for the score. [max ½ page]

The programme conducted a thorough Situational Analysis and a Gendered Political and Social Economy Analysis (GPSEA) to inform the development of the Programme Theory of Change and the nested Theories of Action. The key findings are analysed in a detailed report provided to FCDO at the end of inception. The findings strongly reinforce the evidence which was produced for the SSJP II Business Case, the initial ToC and programme design. The analysis includes mapping of what is known to ‘work’ for the key thematic issues the programme aims to address and an overview of other actors engaged on these issues.

A two-step district assessment process was carried out, based on the following criteria:

Phase 1 (Inception)
- Governance, Security and Justice: Presence and capacity/functionality of existing (formal and informal) governance, security and justice structures whose engagement will be critical to the success of the programme.
- Accessibility: Degree to which identified districts offer the necessary likely physical access, safety and communications connectivity required by programme partners to take forward their interventions and staff to the districts.
- Receptivity: Presence, capacity and likely receptivity and appetite of existing informal institutions and organisations to cooperate with for the Nabadgelinta programme.
- Issues: Prevalence, impact and dynamics surrounding the three security and justice problems around which the programme anticipates focusing its initial interventions. These include: Land disputes, Accountability, and SGBV.
- Partnerships: Opportunities for Nabadgelinta to complement and build on the efforts of existing development programmes in the district, as well as assessing whether the district has experienced ‘over programming’, which might make it resistant to change.

Phase 2 (July-September 2022)
- Impact: There are current high-profile cases or from the past in the district related to either land disputes, SGBV crimes or accountability and there is evidence of willingness to address it.
- Improvability: Community organisations, elders and businesses within the district have openly expressed dissatisfaction with the status quo and raised their concerns publicly.
- Inclusiveness: There is history within the district of communication and meaningful engagement between state institutions and district elders, religious leaders, community leaders and residents.
- Legitimacy: The communities, businesses, and elders within the district accept the security and justice institutions as legitimate representatives of the state but are unable to accomplish their mandate from the district population’s perspective.

The conclusion of the district assessments is that Nabadgelinta will initially start work in Kismayo and Garbaharey in Jubaland and Baidoa and Hudur in South West. The decision to select two districts in each FMS initially sets the ambition realistically (aspiration was 2-3 districts). Given the uncertainties over donor funding and the strong likelihood of important learning emerging from the community entry phase of the programming, a staggered start is prudent.

The Initial design paper sets out how the programme will adopt a phased approach to co-creating activities with communities and other stakeholders, incorporate some of the key learning arising from the situational analysis and the Gendered Political, Social and Economic Analysis (GPSEA) which are set out below in the lessons section. It provides indicative design for work under both outcomes.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

N/A. Nabadgelinta will develop a results framework for the implementation phase which reflects programme planning, based on the outcome of the inception period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Key findings from the Situational Analysis and GPSEA:
[note] Full analysis available at Annex 3

-External factors (such as economic growth, lack of available resources, and broader social cohesion) have a significant impact on inclusive security and justice outcomes.

-Working with existing indigenous structures (i.e., local clan elders) may run the risk of disrupting the existing power dynamics governing the clan system Nabadgelinta should proceed carefully and maintain a detailed understanding of the risks related to disrupting these dynamics as it can never be clear that no harm will come of this disruption. Instead, Nabadgelinta should look for alternative ways to encourage inclusion at every step of the way and enable voices less often heard to come to the fore.

-The programme needs to be connected to decision makers at the FGS level in order to ensure
that it supports coordination between FGS and FMS, especially during this crucial post-election period. Local actors and security and justice service providers are often linked up to state level and federal level powerbrokers (with the reverse being equally true).

-The interaction between Shari’ah, Xeer and the statutory legal system: although Shari’ah is recognised as the basis of all law in all three major constitutions and is thus highly formalised in law, in juridical practice it largely plays an informal role, running parallel to customary Xeer and the statutory judiciary and acting as a sometimes alternative, sometimes complementary dispute resolution mechanism. The programme needs to develop a nuanced and comprehensive understanding of the local relationship between Shari’ah, Xeer, and the statutory legal system to mitigate any unintended consequences for justice outcomes and broader stability.

-Coalition building will likely be a key element of Nabadgelinta programming, based on an initial analysis of how change happens ‘organically’ in the Somali context. Nabadgelinta will need to understand the incentives, constraints, and obligations of a range of different actors, including what will motivate them to compromise and join a broader coalition for a common good.

-Prescribing, policing and instrumentalising gender norms and relations is at the very heart of how the contest for political and ideological power is being played out in Somalia today. The socially constructed meanings associated with being identified, or identifying, as ‘female’ or ‘male’, is serving the interests of, and to varying extents being used as a tool by, both those men with the monopoly of power acquired through clan-based ideology and those men leading efforts to overthrow or replace them on the basis of an alternative ideology, in particular, Al Shabaab.

-Security and insecurity in Somalia are gendered in multiple ways, including: how the forms of insecurity and violence take vary for females and males; as does exposure to and protection from risk of violence; who perpetrates most of the violence; who make up the vast majority of the uniformed security forces as well as non-uniformed; and, how violence against a person is dealt with differently in judicial terms.

- Looking at women’s security issues in isolation from those affecting their male relatives is unlikely to result in effective and sustainable security interventions When a woman or girl is assaulted and calls on her male family members to avenge her, it triggers male normative responses i.e. men want to take up arms and attack the clansmen of the perpetrator. These actions can ignite clan conflict – which if allowed to happen (i.e. elders do not intervene in time) then almost inevitably leads to male deaths.

-There is a need to understand how Al Shabaab uses political and social engineering, in part through re-configured gender norms, to exert its control and de-activate and replace ‘clan’ as the local central organising force. When Al Shabaab takes control of an area it quickly imposes changes to gender norms, ending the freedoms that enable women to act collectively and to mobilise and support their clansmen, and severing people from their connection to clan as an organising force, in multiple ways.

Output Title	High-quality partnerships formed to enable coherent programme delivery
Output number:		2	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Partners onboarded and inducted in a timely and effective manner	Contracting process concluded by end of February 2022, partners onboarded by end of March 2022	Complete. Contracting was concluded by 04 March 2022 and UNOPS was able to formally onboard all implementing partners by the end of March and hold a programme-wide workshop in March 2022 to kick-start inception.
Technical and organisational capacity assessments completed for all downstream partners and UNOPS	By end of inception technical and organisational capacity assessments have been completed for all downstream partners and UNOPS	Partially deferred by prior agreement with FCDO. / In April, UNOPS recommended deferring the / development and implementation of a wider / Technical Capacity Self-Assessment tool until the / early part of Implementation Phase 1, i.e. end of Q3. Recognising the commitment of UNOPS to stick to the original end of inception despite the procurement and contracting delays, FCDO accepted this delay. The team will follow-up on progress during the quarterly meetings. / A MERL Technical Capacity Self-Assessment Tool / was developed and implemented with programme / partners and a MERL Capacity Assessment Report has been completed, which will guide the programme’s capacity building activities and ensure that all programme partners are supported to grow their technical knowledge and skills in key MERL / approaches and capacity development strategy fully completed.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

UNOPS designed and delivered a thorough process of on-boarding partners which also provided opportunities to shape the inception phase outcomes. Kick-off meetings were held with each of the programme partners in February and March 2022 to introduce core team members from both organisations to one another, to discuss safeguarding and agree a process for harmonising workplans. UNOPS provided a Welcome Pack to programme partners, including an introduction to the programme identity and purpose, an overview of the foundational research that informed the programme's design and guidance on core issues and approaches relevant to the programme. UNOPS also convened two workshops in early March, which brought together senior leadership from across the programme to agree an initial set of shared values and behaviours to guide the programme, build relationships between the leaders of the partner organisations and begin discussions about how the programme wanted to work. These were followed by programme-wide retreats in March and May. These meetings have been fundamental to enabling joint delivery of the inception phase outputs.

The March induction retreat for all implementing partners served as the official launch of the programme. The retreat enabled partners to develop a shared understanding of adaptive programming and learning, including the values and behaviours that underpin that; to gain a deeper understanding of each organisation’s unique strengths and offerings; and to agree shared values and behaviours (that uphold and undermine them). It additionally provided an opportunity to begin co-creating and validating a programme-wide draft ToC, in particular those assumptions that need clearer articulation.

A second programme-wide retreat was held in late May and again brought together a broad cross-section of individuals from across the programme, including several who travelled from Baidoa and Kismayo. This retreat built on the weeks that had preceded it to produce an initial set of nested theory of action (ToAs), as well as a broad workplan for the first year of Implementation. The programme’s senior leadership also met to begin unpacking a programme-level governance structure to take the programme forward.
[note] [From the Nabadgelinta Programme ToC paper:] ‘A Theory of Action describes how a programme’s planned activity is expected to translate into a defined change within the confines of the programme’s assumptions and knowledge. A ToC is a theory about what happens in the wider world; a ToA describes what a programme will do to effect that change.

In April, UNOPS recommended deferring the development and implementation of a wider Technical Capacity Self-Assessment tool until the early part of Implementation Phase 1, i.e. end of Q3. Recognising the commitment of UNOPS to stick to the original end of inception despite the procurement and contracting delays, FCDO accepted this pragmatic delay. The full Technical Capacity Assessments will be completed in the coming quarter (by end Dec 2022) and will provide essential foundation for the targeted capacity development support envisaged in the programme design, particularly for Somali partners to strengthen potential for replication and sustainment of outcomes beyond the programme.

The MERL capacity assessment provides an overview of the programme-wide expertise, capabilities and gaps in capacity. The assessment has been done alongside the development of a MERL strategy and the two have informed and fed from one another. This will ensure that the final MERL strategy meets expectations of donors and implementers alike, and that the programme has the capabilities necessary to deliver it. The capacity-building plan includes the deployment of local MERL expertise alongside programme delivery teams in both States, the provision of a virtual helpdesk function, technical facilitation of some complex elements of the MERL strategy such as storytelling and learning across the consortium.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes have been made to the structure of the downstream partnerships, resulting from the outcomes of the procurement process. Nabadgelinta was initially designed to be delivered under three components, as follows:

Component 1: Implementation	Responsible for co-designing and delivering integrated solutions to address concrete security and justice problems identified in each target location, and for implementing, testing and adapting diffusion and advocacy approaches to ensure area-based engagement informs and influences wider strategic direction and decisions. / The Implementation Component was to be delivered through three / professional service contracts (PSCs) covering the following areas of expertise: (a) Participatory Public Policy and Institutional Strengthening; (b) Social / and Behaviour Change; and (c) Public Safety and Access to Justice.
Component 2: Technical Assistance and Partnership (TAP) Facility	Responsible for providing a flexible package of demand-driven support, expertise and guidance to Nabadgelinta programme teams and for developing and amplifying programme evidence to influence wider global discussions on security and justice reform programming. The TAP Facility was to be delivered through a single PSC.
Component 3: Monitoring Evaluation Research and Learning (MERL)	Accountable for designing and delivering an overall MERL strategy and approach, which tests and informs the programme’s understanding of the pathways to change, facilitates continual adaptation of the programme’s approach, and contributes to building the evidence base for what works in security and justice programming. The MERL Component was to be delivered through a single PSC.

Following a competitive procurement process conducted under UNOPS tendering processes, UNOPS signed three professional services contracts (PSCs) with suppliers as set out below:

Component:	Lead partner	Consortium partners:	Date contract issued:
Component 3: Monitoring Evaluation Research and Learning (MERL)	Itad and Altai	Tusmo and Hiraal Institute	15/02/2022
Component 1: Implementation Participatory Public Policy and Institutional Strengthening	Asal and Saferworld		24/02/2022
Component 1: Implementation Social / and Behaviour Change	Equal Access / International	BBC Media Action, Somalia Women Study Centre, Somalia Community Action, Perspective Media	04/03/2022

Full rationale for these changes is available at Annex 4 and in the Inception Phase Report.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This output particularly responds to lessons from the previous SSJP Phase 1:

SSJP PCR Lessons:	SSJP PCR Recommendations:	Nabadgelinta actions:
Poor partner collaboration hindered programme effectiveness: Partners can often allow competition to undermine collaboration, whilst quarterly reviews brought partners together to consult and review progress, many of the partners delivered their work without full utilisation of the potential for synergies across the programme.	Recommendation: The structure of the follow-on programme ensures that all partners are unified as much as possible to deliver the overall programme under the direction of UNOPS fund manager, with political and strategic support from FCDO. This can potentially usefully include co-location of partners, and the use of an integrated and joint programme-wide results framework, which is agreed and owned by all partners and risk management system, to drive collaborative thinking and delivery.	Action taken: from early-market engagement onwards, UNOPS have driven a clear message about the importance of a one-programme approach and integrated delivery. These messages were re-affirmed at the programme kick-off workshops (which FCDO participated in) and are reflected in the deep engagement of all partners in the revisiting of the ToC and ToA. Time has been dedicated to exploring and setting core values for the partnership, agreeing programme governance and more operational ‘ways of working’ have also been set out in writing. A one programme approach to safeguarding has been developed to ensure a consistent and cohesive approach to safeguarding across all implementing partners. And UNOPS have used a ‘What Does Done Look Like?’ methodology to positive effect, ensuring clarity on roles and responsibilities during collaborative tasks.

Output Title	Key programme management tools are established to guide the effective delivery of the programme.
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Programme has a detailed Risk Management Framework and risk matrix, separate Safeguarding approach, and a detailed Value for Money Framework	By end of inception, there is an agreed Risk Management Framework, Safeguarding approach and VFM framework	Complete. The programme partners have jointly developed a Risk Management Framework and a Risk Matrix which conforms to FCDO risk categories and ratings. A safeguarding approach has also been developed as has a VFM framework. FCDO has provided feedback and the final versions of these important programme management tools needs to be formally agreed by partners.
Programme has a detailed Monitoring, Evaluation, Research and Learning strategy	By end of inception a MERL strategy has been completed	Complete. A MERL strategy has been completed. It proposes a developmental evaluation approach as being most suited to the programme design and ways of working, with a strong emphasis on narrative story-telling focused on change. It will remain a live document, updated regularly.
A revised Programme Theory of Change has been agreed amongst the partners and nested, thematic or geographic theories of change have been developed to guide work in the short-to-medium term	By end of inception, there is an agreed Programme-wide ToC and nested ToC	Complete. A Programme-wide ToC and nested Theories of Action (ToA) have been developed for the thematic security and justice areas in which the programme intends to work, namely: / -There is a lack of mutual accountability between security and justice actors and communities. / -The administration of land ownership is highly politicised and a key driver of inter-communal and political conflict. / -Women in general and SGBV survivors in particular have little to no agency in their choice of justice providers and face potential threats.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Reviewing the Nabadgelinta Theory of Change was a major priority during inception. UNOPS developed an initial ToC for the programme document, prior to signature, based on in-depth primary and secondary research carried out during SSJP Phase 1. The review process enabled co-creation of a revised ToC with the implementing partners, thereby increasing their ownership and commitment to the programme and allowed the assumptions to be interrogated from a Somali perspective, which had been limited prior to the contracting of downstream partners. The evolution of the ToC has been set out in detail in the inception outputs. This process included some deep reflection on how change happens without external intervention in Somali society and politics. This exercise enabled Nabadgelinta partners to identify and better understand the essential phases through which successful change in Somalia will likely need to pass. It also suggested ways that external support might be brought to bear – in a limited and targeted manner – to help ensure change is successful, legitimate, and sustainable.

The MERL strategy proposes a developmental evaluation approach as being most suited to the programme design and ways of working, with a strong emphasis on narrative storytelling focused on change. Encouragingly, the strategy has embraced the challenge of adaptive programming and makes some pragmatic proposals about how data generated by the programme can be harvested and analysed to populate an overall Results Framework. The initial programme design work has enabled a preliminary set of outcomes mapped with an examples of what ‘high-ambition’, ‘medium-ambition’ and ‘expected’ outcomes might be.
[note] See Annex 5

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The review and ‘unpacking’ of the Programme ToC has identified three cross-cutting approaches which Nabagelinta will need to incorporate into design and approach to be successful:

1)	Islamic Based Programming: Nabadgelinta’s design and approach must be rooted in Islamic principles and informed by meaningful partnerships with Somali religious leaders. This will be critical to the programme’s ability to engage deeply on questions of social norms and expectations, and essential to the programme’s successful co-creation and engagement with communities and key stakeholders.

2)	Social Behaviour Change/Communication (SBCC): A social behaviour change approach entails a systematic use of tools, approaches, and ways of engaging that promote critical reflection, knowledge acquisition, self-efficacy, and seeing things from a new perspective, alongside efforts to develop the motivations and skills required to enable change. SBCC approaches work across the whole ecosystem that surrounds and influences communities. As a result, they have the potential to support positive behavioural changes that are driven by real needs and are sustainable over the long-term.

3)	Hybrid Approach: By supporting negotiated agreements between Somalia’s statutory, religious and customary institutions and strengthening synergies between Somalia’s institutions in order to establish a more harmonised and accountable legal system Nabadgelinta will contribute to more consistent dispensation of justice, irrespective of social identity or influence. This approach also recognizes the important role of working with Somalia’s legal pluralism in the search for equal justice and fair resolution.

As the programme moves into implementation, there is an urgent need to agree a new Results Framework which will be developed based on the programme design, ToC and MERL work accomplished during the inception phase. This should be available by the end of November 2022.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress under this output addresses several of the recommendations from the previous programme, the Somalia Security and Justice Programme (SSJP I)

SSJP PCR Lessons:	SSJP PCR Recommendations:	Nabadgelinta actions:
Insufficient investment in programme management: This review and previous annual reviews indicate that the original design under-estimated the management burden of such a complex programme in a challenging conflict context. This was adjusted in 2018 with the appointment of UNOPS as fund manager. Unfortunately, UNOPS did not adequately resource the fund management team, and this has only recently been remedied following very active engagement by FCDO.	Recommendation: The follow-on programme invests substantially in the management resources of UNOPS to lead and manage the programme.	Action taken: UNOPS have expanded the management team to include Technical Lead, Programme Delivery Lead and a MERL Adviser, a Knowledge Management and Communications Officer, as well as budgeting for two Area Delivery Leads (one per FMS). The final extension of SSJP I enabled UNOPS to retain a high performing Political Economy analyst from the previous programme.
Poor partner collaboration hindered programme effectiveness: Partners can often allow competition to undermine collaboration, whilst quarterly reviews brought partners together to consult and review progress, many of the partners delivered their work without full utilisation of the potential for synergies across the programme.	Recommendation: The structure of the follow-on programme ensures that all partners are unified as much as possible to deliver the overall programme under the direction of UNOPS fund manager, with political and strategic support from FCDO. This can potentially usefully include co-location of partners, and the use of an integrated and joint programme-wide results framework, which is agreed and owned by all partners and risk management system, to drive collaborative thinking and delivery.	Action taken: from early-market engagement onwards, UNOPS have driven a clear message about the importance of a one-programme approach and integrated delivery. These messages were re-affirmed at the programme kick-off workshops (which FCDO participated in) and are reflected in the deep engagement of all partners in the revisiting of the ToC and ToA. Time has been dedicated to exploring and setting core values for the partnership, agreeing programme governance and more operational ‘ways of working’ have also been set out in writing. A one programme approach to safeguarding has been developed to ensure a consistent and cohesive approach to safeguarding across all implementing partners. And UNOPS have used a ‘What Does Done Look Like?’ methodology to positive effect, ensuring clarity on roles and responsibilities during collaborative tasks.
Limited analysis of value for money to drive programme decision-making: The original design highlighted potential value for money metrics but the structured system to measure value for money was not developed and therefore whilst decisions did reflect cost-effectiveness considerations this was not done based on a strong evidence basis, nor was due consideration given to the other metrics.	Recommendation: The follow-on programme develops a robust framework for the collection of evidence on appropriate value for money metrics and uses this in a structured way to proactively manage the value for money of the programme.	Action taken: Detailed proposition on VFM developed in the inception phase. Some adjustment needed and a first ‘live’ version will be agreed by end of October 2022 to drive decision-making and enable effective monitoring.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

During inception, the major cost driver is personnel and expertise. The balance of expenditure, with higher spend on enabling and support lines such as procurement and contract advice within UNOPS and on SAFE training, compared with lower expenditure on travel and operational costs reflect the early stage of the programme. Salaries will remain the major cost driver throughout the life of the programme. This is driven by the programme approach which is heavily reliant on people’s engagement to coalesce around issues and build consensus on solutions. This approach seeks to increase citizen ownership and leadership legitimacy, thereby increasing sustainability and lasting impact.

In the MOU negotiations with UNOPS, the UNOPS fee calculator has been used to agree a fee of 6%. In line with UNOPS standard practice, the FCDO contribution is subject to an additional 1% levy until the programme becomes jointly financed by other donors. The Executive Board reviews are going to explicitly examine the UNOPS cost structure and it is reasonable to assume that the approach to fees will be revised in 2023 and we stand ready to amend the MOU and budget accordingly.

VfM performance compared to the original VfM proposition in the business case

During inception, the programme has developed a detailed and ambitious draft Value for Money proposition to enable an annual assessment of economy, efficiency, effectiveness and equity. It proposes 16 indicators (including monetary, quantitative and qualitative) and proposes a mixture of benchmarking, comparisons and stand-alone measurements. FCDO has provided detailed feedback on the indicators proposed (including challenging some on feasibility of data collection), and requested that Nabadgelinta (i) provide weighting for the indicators and (ii) attempt to develop targets and milestones for the indicators which would allow for VFM to be assessed at key points throughout implementation as part of normal MEL reporting/review of the RF.

The framework will endeavor to track indicators in a bid to answer the following questions :

Proposed VFM Framework	Observations to date:
Equity – How fairly are the benefits derived from the interventions being distributed, / in particular among marginalised groups? I.e., is the programme meaningfully supporting women, / girls and those from marginalised groups above and beyond including them in activities? Does the / programme have a plausible theory of change, being tested in a robust way, about how to reach / marginalised groups?	Clear commitment to considering inclusion and particularly gender in analysis and preparatory design. The programme now has a robust ToC which sets out plausible means to reach marginalised groups.

Effectiveness – How well are the outputs interventions having the intended / effect? I.e., Is the programme achieving the right outcomes and benefits in relation to the amount / invested. Does the programme have a plausible theory of change that is being tested in a robust way, / and signs of a good initial return on investment?	Too early to assess the effects of the programme but there is a robust Theory of Change which increases confidence of a good return on investment.

Efficiency – How well does the programme convert inputs into outputs? I.e., is the programme / testing which combination of outputs is likely to contribute to outcome-level change, with appropriate / rigour and pace, and adapting accordingly?	Inception outputs have been delivered to high standard against a demanding timeline. The quality of the process of unpacking the ToC and developing ToAs, as well as the MERL strategy’s emphasis on adaptation and learning give a high degree of confidence that the programme will successfully convert inputs into outputs in the implementation phase.

Economy – Is the programme buying inputs of the appropriate quality at the right price? I.e., is the programme managing its main cost drivers and investing resources of the right quantity and quality to support learning?

Cost-effectiveness – What is Nabadgelinta’s ultimate impact on donor foreign policy objectives? / I.e., does the programme’s achievement of its outcomes offer wider strategic benefit to the donors in relation to the scale of investment.	Too early to assess

See detailed proposed indicators in Annex 6

Assessment of whether the programme continues to represent value for money

The programme has just completed the inception phase, based on the strong delivery of inception outputs, there is sufficient evidence the programme is on track, has established the right partnerships, systems and processes to facilitate high-quality implementation and will capture lessons which will support wider policy and institutional influencing goals. There remains a risk that if other donors do not join the programme as planned, it will need to be reshaped and scaled back, but this decision point will not come until the end of the current FY.

The programme design strongly responds to identified needs, with the intention of generating tangible improvements in citizens’ experience of security and justice. To be successful it will be important to pro-actively cultivate and foster practical collaboration across the Security, Stability and Justice portfolio, between partners of different programmes (i.e. with SSF 3, CSSF and PREMIS 2), as well as with other new programmes coming on-stream, such as the EU’s Security Sector Governance capacity-building programme and new iterations of the Joint Justice and Joint Police Programmes.

The programme contributes substantially to UK’s upstream threat goal - reduce threats to UK interests from Al Shabaab (AS) and other extremist groups, strengthen long-term stability and build a state that works for its citizens and Open societies goal - Strengthen state-building, contributing support towards agreeing an effective federal model; take forward reconciliation; improve respect for human rights, women, minorities and media freedom; and increase cooperation between the FGS and FMS.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

SSJP risk appetite has remained ‘eager’ (severe risk rating). This programme has one of the highest risk appetites in the overall FCDO Somalia portfolio, but this is deemed acceptable given the overall balance within the portfolio, the centrality of the programme to the Country Plan and the active monitoring of risks. During the inception period, generally, the programme has been able to operate within the agreed risk appetite and the programme team have developed a detailed risk management framework (including processes for review, monitoring and escalation) and a risk matrix which has been reviewed and agreed amongst all delivery partners. Key risk management tools have been developed by the partner consortium and are in the process of being agreed via the programme governance structures, including the risk management approach and safeguarding policy and code of conduct. These conform to (and in some parts exceed) FCDO guidelines and recognised good practice. In the interim, each partner organisation has been operating within their own policies and procedures (and these were reviewed by UNOPS during the bid assessment and contract award stage. The FCDO Somalia TPM agent will provide an additional layer of assurance with the capability to conduct verifications of delivery and horizon scanning to promote timely mitigation in this high-risk environment,

FCDO undertook a Due Diligence Assessment of UNOPS prior to signing the MOU. Overall, the findings were positive, but a limited number of outstanding actions have been incorporated into the Programme Delivery Plan to increase assurance (see action table in the programme management section below). These are being actively monitored and actioned. FCDO are in the process of seeking additional information from UNOPS about the due diligence it has done on the downstream partners as part of the framework of enhanced scrutiny agreed between FCDO Somalia and UNOPS Somalia following the S3i allegations. These actions and progress are summarised at the end of the programme management section of this report.

Strategy and context:

Security context: major rating - During inception, risks relating to security and access have materialised (as expected) as insecurity around the final stages of the Presidential elections disrupting access to carry out district assessments. Access and security conditions have been an important factor in district selection (discussed in more detail in Section C, output 1).
Mitigation: the risk is beyond programme control, the team paused travel where access risks substantially increased and instead utilised technology where possible. The programme team will continue to actively monitor and take necessary action if need arises. From the design phase, this programme has been established as a flexible and adaptive programme. FCDO Somalia has provided clear direction that the programme needs to anticipate instability and ensure that it has some activity in lower-risk areas which could continue in such circumstances, as well as setting an ambition to work in some higher risk locations and acknowledge that geography of risk is very dynamic.

Sector context: During the inception phase, there has been a noticeable shift in the approaches of some other donors away from state-building approaches in the security and justice sector, in favour of greater emphasis on service delivery and supporting capacity development at the sub-national level. Coupled with budget reductions for several like-minded donors, it seems likely that there will be less investment in the UN Joint Rule of Law programmes for example, which Nabadgelinta planned to use as a key channel for lessons learned and wider influencing.
Mitigation: The programme team has reviewed assumptions around engagement at the FGS level and will build more of this into the programme design and planning. FCDO will continue to engage with other donors in the security and justice coordination groups and advocate for a pragmatic division of labour.

Policy and Programme Delivery:

UNOPS HQ S3i fraud allegation: severe rating - Both FCDO and UNOPS have had to devote considerable time and resources to managing the risks to financing arising from the S3i fraud allegations, and this will continue to dog the programme for the coming months.
Mitigation: FCDO Somalia agreed a framework for enhanced scrutiny with UNOPS Somalia to provide added assurances over UK funds over the next 12 months. Some good progress has been made in enacting this (captured in the delivery plan) although not yet complete.
ODA pressures and the requirement to reduce financial year budgets meant the programme had to reduce planned activities for example the initial planned target districts were six but was reduced to two due to financial constrain. ODA pause also impacted on delivery. This is a Major risk because it is impacting on expected programme results.
Mitigation: closely monitoring programme delivery and escalating for consideration to avoid extreme impact on delivery.
Famine Conditions in South West appear to give greatest cause for concern and this is one of the programme’s focus states.
Mitigation During inception, FCDO, UNOPS and in some cases, implementing partners have engaged a wide range of stakeholders and sought to manage expectations – particularly around the type of assistance which will be provided (technical over material, and not always targeting formal institutions).

Reputational:

Other donors fail to confirm their contributions to Nabadgelinta in light of the UNOPS HQ S3i allegations: Both the EU and Dutch governments have signalled their continued interest in supporting the programme but are unable to move forwards until the outcomes of the review process which has been established by the UNOPS Executive Board are clear. This now seems unlikely to happen before February 2023. This uncertainty presents a major and increasing risk to the programme, given that further UK ODA reductions are anticipated in the current FY.
Mitigation: FCDO and UNOPS are proactively engaging with the other donors to keep them appraised of progress (for example, the EU attended the End-of-Inception presentations). The FCDO programme team will continually review the feasibility of the programme as currently designed and promptly identify any signs of this risk increasing to LSLT, together with recommendations on the best way forward.

Financial and Fiduciary:

Fraud: An attempted fraud by downstream 3rd tier partner was promptly identified and addressed by one of the 2nd tier partners. This was immediately reported to UNOPS, who immediately made FCDO aware. The case has been registered in the FCDO system and allocated to the Programme Team for follow up. The UNOPS Internal Audit and Investigation Group (IAIG) team praised the Tier 2 partner for their vigilance, which prevented programme funds from being misused, as well as their high-quality investigation. A joint decision was made to terminate the contract of the 3rd tier partner.
Mitigation: Strong financial oversight procedures at the level of the second-tier partner ensured that this fraud was prevented. UNOPS and the tier 2 partner took prompt action to review whether this was a systemic risk and acted accordingly. Work is now ongoing to consider the delivery impact of the decision to terminate the third-tier partner.

As the programme moves to implementation, managing the risks around the buy-in of key FGS and FMS stakeholders, security context and access, and the potential challenges posed by the severe drought conditions and famine-like conditions will be actively monitored.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

During the reporting period, UNOPS performed well, they undertook multiple procurement processes which resulted to the team successfully bringing on board three consortiums. By the end of inception UNOPS and all downstream partners delivered the agreed deliverables as indicated in the scoring section.

FCDO has regularly and closely engaged with UNOPS throughout inception. The SRO participated in the technical review of bids for the TAP facility and the policy and institutions strand and was consulted on the final decision to revise the contracts awarded (as set out in detail in Section C, Output 2). The FCDO SRO attended the kick-off meetings and programme-wide retreat in March 2022, which was an opportunity to meet all the key individuals from across the consortia. The FCDO SRO and PRO aim to have a weekly informal catch up with the UNOPS Programme Director (and the Fund Manager as required) on a weekly basis which ensure awareness of issues affecting progress.

UNOPS undertook a rigorous procurement process, three consortiums were procured to deliver different aspects of the programme as highlighted in the output scoring section. The three consortia include:
1. ASAL and Safer World – Public Policy and Institutional Building
2. Equal Access, BBC Media Action, Somalia Women Study Centre, Somalia Community Action, Perspective Media – Social Norms
3. Itad, Altai, Tusmo and Hiraal Institute
Narrative reporting for Q1 and Q2 (i.e., the inception period) has been provided in the detailed Inception Phase Report. Going forward, UNOPS will provide a quarterly narrative and financial report to FCDO. The first of these is due on 30 October 2022 (and 30 days after the end of each quarter thereafter) and the respective programme management teams will continue with quarterly progress and compliance meetings.

The programme spent £3.3m during the reporting period. The spend is between two components. Component 101 focusing on support to Somalia and component 102 focusing support to Somaliland.

Component	Component Description	Year	Committed	Spend	Balance
300860-101	Support to Development of Police and Access to Justice in Somalia	2021	0	1,500,000.00	0
300860-101	Support to Development of Police and Access to Justice in Somalia	2022	1,973,305.00	1,526,695.00	0
	Sub total		1,973,305.00	3,026,695.00	0.00
300860-102	Support to policing and access to Justice in Somaliland	2021	0	174,536.34	0
300860-102	Support to policing and access to Justice in Somaliland	2022	458,466.02	117,561.64	25,911.00
	Sub total		458,466.02	292,097.98	25,911.00

Overall, financial forecasting and reporting has been timely and reasonably accurate, supported by use of milestone payments in the contracting of downstream partners. FCDO have requested a revised budget for the remainder of the financial year, given that we no longer expect significant contributions from other donors until Q4, when the reviews triggered by the S3i fraud allegations are scheduled to be completed. Given ongoing ODA pressure for the UK and the current challenges of co-financing, the programme team have advised UNOPS to adjust planning to suit the available resources.

Two formal reviews have also taken place. (i) A quarterly review of progress and compliance, conducted at UNOPS office in Nairobi in May 2022 and (ii) An end of inception workshop at British High Commission in Nairobi in June 2022, at which inception deliverables were presented. The findings of these reviews have informed this annual review.

Since the S3i allegations emerged, FCDO Somalia has put in place a framework of enhanced scrutiny to provide an additional layer of assurance. The table below provides an update of actions taken under this enhanced framework of scrutiny, as well as actions taken in follow-up to the Due Diligence Assessment. These actions are tracked and updated via the Programme Delivery Plan.

Enhanced risk management	UPDATE Q1
1. FCDO Somalia to provide key UNOPS Somalia staff with knowledge and understanding of FCDO policies and approaches to fraud and safeguarding (by 30 July 2022).	FCDO Somalia REACH to deliver/facilitate the information sharing on 26th September 2022 to key UNOPS Somalia staff identified by the Deputy Country Director (Programmes).
2. UNOPS Somalia to provide FCDO Somalia with a quarterly update on the management response to the recent audit of the UNOPS Somalia Country Office and status of remedial actions (on 30 June, 30 September and 30 December 2022).	Latest update on the UNOPS Somalia audit is with FCDO Somalia REACH for review. / The PRO and REACH have already reviewed and provided feedback on downstream partners audit reports shared by UNOPS. None of these presented any cause for concern.
3. UNOPS provide FCDO Somalia with a summary of the key elements of the commercial process used to identify and contract the downstream partners of Nabadgelinta, detailing the names and roles of those involved at each stage, the key considerations and the decisions (by 15 July 2022)	FCDO Somalia programme team reviewed and did not identify major concerns (but see 4. below).
4. UNOPS Somalia to share with FCDO Somalia the due diligence assessments they have carried out on the downstream partners for Nabadgelinta and the partners’ latest audit reports (by 30 June 2022)	PRO and Commercial manager reviewed the documentation. The documents shared are background check and do not meet FCDO standards for due diligence. Further feedback will be sought to clarify how UNOPS checks their IPs governance, financial, PM and safeguarding capabilities.
5. UNOPS Somalia to hold and update a dashboard of follow up actions for downstream partners in relation to due diligence and audit and to share this with FCDO Somalia as part of the Nabadgelinta quarterly review (first iteration by 31 August 2022).	Fund Manager to look at the action and propose ways of actioning it before the next quarterly review (Oct 2022)
6. UNOPS Somalia and FCDO Somalia jointly commission an independent programme-wide audit on Nabadgelinta to be undertaken no later than June 2023 (bringing forward the audit planned for FY 24/25).	Future action. Agreed with UNOPS on the understanding that the UN single audit principle to be upheld.
Actions arising from the Due Diligence Assessment
No inhouse M&E capability: UNOPS and the MERL partner will present a MERL Framework for Nabadgalinta as one of the outputs of inception	Complete
Currency and reporting: FCDO Somalia is consulting with HQ about how this could be accommodated whilst mitigating the risk of currency fluctuations	Complete – agreed to common donor reporting in USD if exchange rate is tracked at the time of conversion.
UNOPS to actively monitor and manage the exchange rate risk	Ongoing
FCDO to monitor adherence to UK resource accounting principle – request for funds which can be utilised within a quarter & accurately prepaid on monthly basis.	Ongoing
Agreement reached in MOU that any interest earned must be reinvested into the programme.	Complete
UNOPS is required to maintain a consolidated register for assets procured using UK funds and in case of contribution to a joint programme ensure they also maintain a consolidated asset register. FCDO to follow up regularly on the adherence to asset policies and spot-checking results	Complete
Decentralised partner procurement - Proactively share partner info with HMG who may have experience in Somalia for further check/ triangulation.	Ongoing to positive effect – collaboration with several CSSF programmes is underway and risk information shared with USAID-funded programme.
UNOPS Somalia will produce a Safeguarding Framework and a Risk Management Framework for the programme during Inception	Complete

Date of last narrative financial report	30/06/2022	Date of last audited annual statement	28 December 2021