## Annual Review Template

Title: Somalia Security and Justice Programme II
Programme Value £ (full life): £28.5m over 5 years rising to a total of £54m over 8 years (subject to further approvals)		Review date: June 2024
Programme Code: 300860	AMP start date: 08/10/2021	AMP end date: 31/03/2029

Summary of Programme Performance
Year	2022	2023	2024
Overall Output Score	A	A	B
Risk Rating	Severe	Severe	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005061.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005057.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The Somalia Security and Justice Programme Phase (SSJP) II forms part of a wider Embassy portfolio of stability, security and justice investments designed to deliver on the UK’s priorities. It seeks to support the cross-government objective of a more secure, resilient and stable Somalia, with a broadening and deepening of the political settlement and social contract, improved security and an acceleration of Somalia’s economic recovery. It seeks to strengthen the social contract and increase individual security though a political process, ensuring the expectations and obligations of state and society are negotiated, reinforced and institutionalised. In practical terms, this requires that (a) resources and capacity are directed to meet the expectations of the population served; (b) acceptable and affordable security and justice institutions can deliver against those expectations; and (c) collective social expectations of the legitimate extent of state power and of citizens’ obligations support strengthening of the rule of law.

SSJP II aims to deliver tangible improvements to the accessibility, efficiency, quality and predictability of security and justice outcomes for ordinary people. The programme will work with both formal and informal institutions. In the period covered by this annual review, SSJP II comprised two components:

1. Nabadaynta Soomaaliya (Towards a Safer Somalia), managed by the International Organisation for Migration (IOM) and implemented by two consortia. This component is active in South-West State and Jubaland state. They identify the most pressing security and justice concerns of local citizens and deliver improved responses through a variety of formal and informal channels; and
2. Rapid Stabilisation Support to Somalia (RSS), implemented by IOM as a rapid response to Somali government operations against Al Shabaab during 2022-23. This pilot project fell under SSJP II as it provided a programme structure that allowed swift implementation. Its successor will be implemented under the Integrated Security Fund, allowing FCDO to combine RDEL and CDEL investment.

Following the conclusion of the RSS pilot project, and should it be agreed to manage a further contribution under the Integrated Security Fund, future SSJP II Annual Reviews will not review RSS performance separately.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Nabadaynta
Nabadaynta uses adaptive programming principles, seeking to bring about lasting change via a range of innovative programme elements. Terms used that are specific to Nabadaynta include:
- Co-creation: An inclusive approach seeking to bring together a wide range of stakeholders, including government officials, marginalised groups, faith leaders, and implementing partners to be involved in the design of project outputs.
- Blending: aims to adopt innovative approaches to supporting security and justice by combining security and justice expertise (including institutional and public policy development, reform and community safety, access to justice) with social norms and behaviour change approaches. This requires substantial joint working by downstream partners.

Description	Score	Weighting
Output 1: Inclusive context: Continuous contextual understanding of dynamics of security and justice in specific locations in Somalia (inc. from gendered, social and political economy perspectives)	A	14%
Output 2: Common concerns: Support for convening people/groups with divergent interests and/or identities to coalesce around common concerns	B	35%
Output 3: Somali-led strategies: Support for Somali-led development and implementation of strategies for achieving changes in safety and/or fairness on common concerns	C	7%
Output 4: Learning & adaptation: Evidence of i) programme’s strategic decision-making driven by learning; and ii) use of learning to influence strategic decision-making of other actors (Somali and international)	C	14%

Last year’s annual review noted that SSJP II, and the Nabadaynta component, would need far greater stability, in terms of predictable funding and settled partnerships, over the 2023-24 year to allow it to focus on delivery. While there is evidence of progress, the project has continued to face significant challenges that have limited its ability to deliver in its current form. The pace of delivery continues to be impacted by relationship challenges between IOM and its downstream implementing partners. These challenges have significantly degraded the ability of the programme to adapt, co-create or blend in designing and implementing its interventions.

Methodological differences were noted which impacted the intended blending approach. For example, the two consortia embraced different ways of identifying the issues. One partner conducted town halls meetings to identify all potential issues hence generating a long menu of issues with a view that this was an accountability forum with government expected to take responsibility. The other embraced an approach focused at identifying targeted issues and possible solutions with an aim to jointly work on some of the issues identified. Attempts to reconcile the two proved challenging because the framing was fundamentally different. Other challenges included operational and contractual issues which persisted following the transfer of the project from UNOPS to IOM (see last annual review for details). This led to the project being in large part unable to deliver the full scope of its ambitions. The situation has clearly caused personal and institutional stress to those involved.

IOM, as the Fund Manager since late 2023, has attempted to agree a modified and more realistic delivery profile for partners but this was rejected. Given the continued delays to project timelines, growing stakeholder frustration with the pace of delivery, and the continued challenging relationship between partners, it is difficult to see the prospect of meaningful improvements in the functioning of the programme should the project remain unreformed.

Despite these challenges, there has been evidence of delivery at the output level. The project has delivered the required number of research and analysis products (Output 1.1), identified Area-Based Problems (Output 2.1), developed locally led initiatives (Output 3.1), and undertaken learning activities required under Output 4. However, the transformative potential of the programme at the outcome level requires additional joint work, and the prospect of the programme delivering a successful blended approach in light of its fractured institutional relationships seems remote.
Rapid Stabilisation Support

Description	Score	Weighting
Output 5 - Vertical integration and trust: Communities’ trust in local institutions is strengthened and processes of government coordination and accountability lay the foundations for institution building	A	15%
Output 6 - Horizontal integration and trust: Social cohesion and civic engagement are promoted at the community level through proactive interaction, dispute resolution capacity, natural resource management mechanisms, and the restoration of economic value chains	A	15%

The RSS component pilot was implemented at pace over nine months by IOM, with a focus on Middle Shabelle, Hiraan, Galgaduud and Mudug. External evaluation commissioned by IOM suggests it achieved its output targets. There is some evidence of sustainability of the interventions, including through an increased sense of community ownership by use of a grant matching process.
[note] Final Evaluation of the ‘Rapid Support to Somalia’ (RSS) Project, GIST for IOM

The Theory of Change relies on improvements in horizontal and vertical trust, conceptualised as trust between local communities and each other, and then vertically with local leadership and the state. It focused on rapidly deliverable stabilisation activities including governance, infrastructure and in some cases social/sporting facilities. While seeking to be highly responsive to the needs of local communities and government priorities. There was no strong evidence of a coordinated approach across the Federal Member States involved. Despite attempts to improve information management processes there remained evidence of a disconnect between Federal Government and state/local level governance structures.
[note] ibid

It met the required level of outputs, raised trust between communities, individuals and the Federal Government of Somalia by at least the required level.

Major lessons and recommendations for the year ahead [1/2 page]

Nabadaynta
Nabadaynta is a complex project with a range of innovative elements. Since its initial design it has been impacted by various changes: At donor level, the change in the original budget, and a reduction in the breadth of HMG’s security and justice programming in Somalia impacted the scope of the programme. At delivery level the implementation period was marked by the need to novate the project’s fund management from UNOPS to IOM, programme management challenges, the pandemic and staffing uncertainties. Efforts to manage these have led to an uneasy set of circumstances: Nabadaynta is now no longer part of a far wider set of security and justice interventions, and it does not appear to have bedded down fully or been given the attention it required in the IOM structure to which it was moved. IOM agreed to retain the staff novated to it for one year, the date of which is approaching. It is not clear that key staff will remain in the agency at the end of this time, risking a loss of expertise.
[note] The business case envisaged complementary investments in justice and policing.

Since the conclusion of these major structural changes, a new range of serious challenges have become apparent relating to the functioning of project elements, particularly co-creation and blending. During this review period, it was clear the implementation approach was still contested with varying views. While one partner was confident that they were delivering the agreed workplan, the fund manager, other implementing partners and donors acknowledged the co-creation and blending had not taken root across the programme as anticipated. This has impacted delivery and not led to the period of stability called for in last year’s annual review.

Recommendations: Nabadaynta

Lesson	Recommendation
NS takes a very innovative approach and methodology which is complex. IOM and IP1’s relationship has deteriorated over the course of the year which led to a heavy management cost. Combined, it is difficult to identify if the project is struggling because of design issues, or weak delivery. Funders need to clarify whether if the management and delivery challenges in the project can be overcome, whether the programme is likely to be successful.	IOM should examine urgently all options with regard to its implementing partners, and report on steps it is taking to manage delivery. This should be combined with recommendations below to determine how the programme can improve its design as well as implementation. / Target: End October 2024
Blending: There was evidence of joint work on the ground, largely mediated by IOM’s programme co-ordinators, which involved sharing workplans and attending activities together. There was less evidence of a wholly blended approach in the Federal Member States, and at the management/Head Office level there have been significant challenges with this approach between the consortia involved.	FCDO should ask IOM to adapt the project’s operating model to capture lessons learned so far about how change works in Somalia and move towards a more simplified structure focused on delivery building upon already successful interventions. / Target: End October 2024
Co-creation has been extremely slow, and perceived as bureaucratic by those involved, including at the state government level.	FCDO should work with IOM to simplify the operating model to allow a focus on delivery. This should include a more directive stance by IOM where appropriate. There will be need for the project to develop a structure to support government security and justice actors to organically move to deliver actions to address concerns raised. This potentially could be the background upon which an institutionalised social contact will be built. / Target: End October 2024
The monitoring, evaluation, research and learning (MERL) framework is highly complex, leaving implementers confused by delivery requirements. Stories of Change lack evidence of consistency or of applicability beyond individuals.	The MERL partner should simplify the MERL framework as required, to ensure clear expectations at all levels of the project, and that all partners are able to reflect their specific contributions to the outcomes. / Target: End November 2024
The Fund Manager's commitment and efforts to reach a consensus among partners on the definition and application of the One Programme Approach have proved time-consuming and inefficient.	Continued challenges with this approach suggest that a significant restructure should be considered. / Target: End of October 2024
Ensuring gains made from participatory processes: Area Based Problem, Town Halls etc., results in tangible solutions through service delivery	FCDO and Fund Manager will need to strengthen the approach for how S&J issues are prioritised and acted upon, as a building block upon which security and justice actors will begin to institutionalise solutions-based service delivery. / Target: Ongoing
[note] See definition above: The project aims to adopt innovative approaches to supporting security and justice by ‘blending’ technical S&J expertise, including both institutional and public policy development and reform and community safety and access to justice, with social norms and behaviour change approaches. This requires substantial joint working by downstream partners.
[note] The One Programme Approach aims to agree shared values and ways of working that incentivise and enable collaboration amongst the programme IPs and prevent siloed working. This approach includes developing the governance arrangements and establishing the systems, and capabilities required to deliver a single, coherent and adaptive programme.

Rapid Stabilisation Support
Prior to the Annual Review, the ISF Somalia programme had decided to consolidate their investment in stabilisation in a larger programme with IOM, drawing together the ISF Early Recovery Initiative (ERI) with the Rapid Stabilisation Support component of SSJP II. FCDO will also continue to contribute a portion of CDEL to this successor programme. From July 2024, subject to Development Director approval for this new, larger programme will be managed by the ISF team, using ISF project management tools and modalities. The successor programme should benefit from having had a longer design period. It should take the major lessons identified by GIST’s Final Evaluation Report in the successor programme.

Recommendations: Rapid Stabilisation Support

Lesson	Recommendation
Information management and co-ordination between federal government military objectives and FMS political incentives.	IOM to develop and implement a strategy for greater co-ordination with/between key FGS and FMS actors in the successor programme. / Target: End November 2024
Broad range of activities over a wide and poorly connected area risks limiting overall impact.	FCDO should ensure that the successor programme is guided by a strategic planning document to facilitate strategic coherence and articulation of common goals which are critical to achievement of core outcomes and outputs. / Target: End November 2024
Need to align Results Framework more closely with the Theory of Change.	FCDO should re-examine the Theory of Change and Results Framework in the successor programme to ensure full alignment. / Target: End October 2024
Need for additional conflict sensitivity and GESI analyses for activities.	Ensure every intervention in the successor programme contains conflict sensitivity and GESI analyses and has a clear action plan for the inclusion of women in rural areas. / Target: Ongoing
Environmental/climate/nature-based solutions should be mainstreamed into the programme, and progress reflected in the results framework.	The results framework and review process for the successor programme should include specific targets on environmental peacebuilding issues. / Target: Ongoing
Ensure robust risk management and mitigations for every Activity Proposal under the programme.	IOM should ensure standard risk management processes and mitigation strategies are present for every activity undertaken by the successor programme. / Target: Ongoing
Lack of a comprehensive approach to sustainability.	Ensure the project has a clear exit strategy, to ensure long-term sustainability and community ownership. / Target: Ongoing

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
The RSS component was included as part of SSJP II two years after the Business Case was approved. Support to RSS was approved against a stand-alone proposal and Theory of Change. Given the rapid start up required to meet growing demand from the Federal Government, work to unify the theories of change was not finalised by the time internal decisions were made to increase the scope of RSS and combine a future FCDO CDEL contribution with ISF RDEL. The increasing scale and scope of the follow-on programme justifies FCDO Somalia’s decision to manage this holistically, rather than as two separate streams of funding.

The original SSJP II (Nabadaynta) Theory of Change posits that:

If we support more inclusive negotiation on political, legal and financial frameworks and enable and incentivise security and justice institutions to be increasingly inclusive, capable and accountable and to work together to respond to locally identified needs and priorities.
And if we understand and strengthen positive social norms that reinforce inclusive approaches to the rule of law.
All while continually applying structured learning, research and evidence to inform programme adaptation and to influence wider stakeholders – Somali and international – to increasingly collaborate.
Then Somalis will benefit from improved security and access to justice through inclusive approaches that enjoy broad based understanding, support, and both elite and public confidence.
And ultimately there will be improved rule of law in Somalia, which contributes to a strengthened social contract between the State and Society and to establishing the foundations of sustainable political settlement.

The theory has been bolstered by research undertaken as part of the project outputs (has met expectations, see below). The project’s MERL partner has undertaken a lengthy analysis of change in Somalia which sets out a stronger theoretical basis for the activities undertaken by Nabadaynta in particular. The past year has seen the MERL partner face some significant challenges with outcome harvesting from one of the implementing partners, which has resulted in a reduced ability to demonstrate the efficacy of the project. There have been similar challenges in producing joint findings to inform project activities.

The RSS Theory of Change states:

IF integrated stabilisation packages are delivered in liberated and fragile areas of Somalia;
THEN the social contract between Somali citizens and state institutions will be reconstituted;
BECAUSE conditions are created that restore trust horizontally, between communities, and vertically, between communities and local leadership.

External analysis by GIST for IOM found that this Theory of Change was clear and concise but relied on some implicit assumptions and did not fully articulate all components of the project objective. The movement of this project under the Integrated Security Fund will provide an opportunity to review and refine this Theory of Change, aligning with the wider ISF portfolio.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
Nabadaynta continues to suffer from significant delays in delivery. These are partially due to the remnants of the external challenges the project has faced (novation from UNOPS to IOM as fund manager, funding challenges and post-COVID issues) and partially due to significant current challenges in the relationships between partners.

The continuing tensions with one of the implementing partners reduce the likelihood of the project being able to deliver transformational change as articulated in the programme documents. At the time of writing, IOM has taken some action to address this through contractual mechanisms. These remains a significant risk, in absence of substantial structural change, the tensions will further impact project delivery in the current year.

This is apparent in the output-level scoring. For example, in Output 1 the project met the requirement for research and analysis, and for the number of findings. It did not meet the requirement for the findings to be joint (i.e. demonstrating blending and a collaborative approach between implementing partners). In Output 2, the project vastly exceeded the number of area-based problems (ABPs) it was designed to identify, reaching 17 when the target was three. However, it did not reach the requirement for joint working and building consensus around the issues identified. Output 3 also exceeded the quantity of Somali-led strategies required, but with a lack of compelling evidence that lasting change has resulted from these initiatives. Output 4 met its requirements for learning and adaptation using evidence generated by project activities, but the lack of observational change means the project has slightly underachieved on these outputs.

The challenge is that even where the project reaches the required level of activity, it is unable to deliver the innovative aspects that would make it truly transformational. There has been some improvement in co-ordination on the ground, driven largely by the recruitment of IOM co-ordinators, and the joint teams in the Federal Member States seem relatively cohesive. However, lessons from last year’s annual review relating to Fund Manager management of the implementing partners have not led to significant change.

RSS has concluded in its current format and whilst resources (CDEL) will be committed to the next phase, these will be managed jointly with the ISF (RDEL) funds to ensure a streamlined approach to programme management. Therefore, the RSS will not be part of the SSJP II programme monitoring and Annual Review in future. Results stemming from the RSS contribution will be assessed jointly as party of the ISF Somalia Annual Review.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
The ability to deliver outputs on the ground and the good working relationship of the field teams despite all the challenges highlighted, demonstrates the programme’s potential to deliver. However, to justify continuation, IOM must swiftly address the challenges flagged to unlock the potential and focus on delivery. The team should address:
1. The approach/ methodology - given the project’s complexity, IOM should simplify the co-creation processes to facilitate smooth implementation. The conclusions of the existing MEL processes indicate that a flatter structure could deliver swifter impact and greater value for money, while delivering against the Theory of Change.
2. Delivery partners - review the effectiveness of each of its implementing partners
3. The need for agility to allow the programme to quickly adapt to operating context.

The RSS component has demonstrated the capacity to deliver change on the ground in Somalia and has met its objectives for the year. Its presence in SSJP II supported its ability to deliver swiftly and support the Federal Government in realising the benefits of removing Al Shabaab from liberated areas. The project should implement the lessons of this pilot phase as it progresses to a new project under the Integrated Security Fund.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	(NS) Inclusive context: Continuous contextual understanding of dynamics of security and justice in specific locations in Somalia (inc. from gendered, social and political economy perspectives)
Output number:		1	Output Score:	A
Impact weighting (%):		14%	Weighting revised since last AR?	YES reduced – was 40%

Indicator(s)	Milestone(s) for this review	Progress
1.1: # and description of research and/or analysis products completed (disaggregated by category)	3 (1 x IP1; 1x IP2, 1x MERL)	Met expectation / Three research and analyses products were produced and used in various ways to inform interventions. / IP1: Think Session Analysis- focussed on integrating and applying Islamic principles in security and justice issues and produced through collaborative discussions with a wide range of stakeholders: religious leaders, community representatives, legal experts and policy makers. / IP2: Social and Behaviour Change (SBC) Strategy Paper: produced from other Nabadaynta research work on gendered political economy, it provides a roadmap for designing and implementing social, behavioural and norms change interventions to increase security and equitable access to justice in Somalia / MERL: Research Synthesis Report- produced from desk-based and primary research produced by the programme in the previous year to identify knowledge gaps and inform learning.
1.2: # and description of key findings from research and/or analysis relevant to co-creation, design and delivery process (disaggregated by types of finding)	4 Jointly produced Findings	Did not meet expectations / Four findings were produced, through reflections on research generated by Nabadaynta, but these were not joint and did not inform subsequent processes of co-creation, design and implementation of interventions.
[note] Nabadaynta has a learning system provided by MERL (Monitoring Evaluation Research and Learning) partner- through an agreed action plan, that involves coming together for reflection workshops.

This Output was designed to provide the project with contextual understanding of fostering community and government participatory processes. This aimed at enabling/influencing delivery of security and justice solutions in a way that puts community expressed concerns at the centre, particularly regarding the three priority themes - sexual and gender-based violence, land disputes and mutual accountability.

Indicator 1.1. For the year under review, three pieces of research and analysis were completed, therefore meeting expectations for this indicator. These research products have been useful in strengthening the evidence base, including informing strategic decisions about the development of intervention methodologies. For instance, the Social and Behaviour Change (SBC) Strategy Paper provided an evidence-based approach on transforming power dynamics, challenging social and gender norms that drive inequitable access to security and justice amongst communities. While the Think Session Analysis contributed actionable steps for operationalising Islamic principles in security and justice reform.

Indicator 1.2 was important to demonstrate a collaborative working approach between the two consortia - IP1 and IP2, using and triangulating findings from the various analyses to inform co-creation processes and the overall implementation of the project. Findings are categorized as (i) NUANCE: the findings that indicate the need for subtle refinements to a particular approach; (ii) RETHINK: Those that require a fundamental rethink about a proposed approach (iii) GIVE IT TIME: Those which appear important, but where it is not yet clear how the finding can be applied; and (iv) STOP NOW!: A finding that strongly suggests a proposed course of action should be abandoned. Although the project achieved four findings, these were individual reflections of partners, and not the joined up collaborative approach necessary under this indicator.
For instance,
1. There were different perspectives on what would be required to build trust and engagement between communities and authorities. The partners needed to GIVE TIME and RETHINK the approach to community engagement and trust building by revisiting the research findings and reflecting on new findings. On this finding, IP1 held the opinion that there existed sufficient trust between authorities and communities for them to self-organise and initiate action if provided with space to do so. Whereas IP2’s analysis underscored the need to invest time in building the confidence of traditionally marginalised and wider community to be able to raise issues openly with authorities.
2. While there were clear divergent views on approach to building trust, there was NUANCE on the willingness of communities and formal actors to meaningfully engage on security and justice issues, with the goal of finding solutions to issues identified. However, each developed this position through different approaches; IP1- through Public Participatory Processes and Town Hall meetings while IP2’s position was grounded in the process of inclusive Area Based Problems sessions whereby they identified common issues, after sufficient trust building and trauma healing sessions had been done.

These differences in perspectives and approach to trust building between communities and authorities, undermined the requirement to foster a joined-up approach. Each one ended up building a process that eventually brought together diverse communities and government stakeholders, albeit in different ways, to discuss pertinent issues around security and justice that required solutions. Despite the divergent perspectives, both IPs in their different approaches to inclusive dialogue, demonstrated the willingness of formal actors to engage with communities on common issues and solutions.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph
The only change to this output within the year was a reduction of the weighting from 40% (in 2022/23) to 20% in 2023/24). This was planned to reflect the project shifting from research and scoping to delivery. The weighting has been further revised on the incorporation of the RSS component from 20% to 14%. Considering there was lack of ‘joint’ findings, the project needs to review this requirement and adapt to a more simplified approach to sense making from the wide-ranging research and analyses produced to inform adaptation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
One of the recommendations relevant to this output from last year’s AR was to design an implementation approach that would contribute to coalition building, including considerations to gender norms and gendered experiences of security/insecurity and justice. The Social and Behaviour Change Strategy was important to inform an inclusive process that ensure an understanding of gendered relationships that undermined inclusive participation in engagement.

In the period under review, the importance of flexibility and adaptability in responding to diverse perspectives and contextual nuances was an important learning. While research and analysis provided valuable insights, the success of collaborative and participatory processes depended on effective communication, collaboration, and trust-building efforts.

Output Title	(NS) Common concerns: Support for convening people/groups with divergent interests and/or identities to coalesce around common concerns
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	YES – increased (was 30%)

Indicator(s)	Milestone(s) for this review	Progress
2.1: # and descriptions of AREA Based Problems (ABPs) around which there is potential for different groups of people (disaggregated by category) to coalesce	3	Met Expectation / 17 ABPs identified: 8 from Kismayo and 9 from Baidoa
2.2: # and types of support provided / to enable coalitions to form and progress (inc extent of ‘blended’ / characteristics)	4 support functions / 3 systems functions -At least 2 interventions blended at the level C of the spectrum	Moderately did not Meet Expectation / 7 Support Functions and 3 Systems Functions individually delivered by the IPS

This output was about bringing together stakeholders from community groups and formal institutions of security and justice, in a safe and inclusive way. The aim was for the stakeholders to interact and identify localised security and justice priorities, referred to in the project documentation as Area Based Problems. In delivering on this output, the project demonstrated how communities can be enabled to articulate and prioritise key issues of concern and influence responses from government. All of this was to be done through consensus building and meaningful dialogue between communities and government actors. Further, the approach required both IPs to foster and co-design joint approaches to consensus building so that the stakeholders could agree on common issues or concerns with the solutions eventually strengthening the social contract.

For Indicator 2.1, the achievement significantly surpassed the milestone, with 17 area-based problems (eight from Kismayo and nine from Baidoa). For Kismayo, the priorities ranged from a need to respond to land conflicts, responding to SGBV through better policing, enhancing collaboration between communities and institutions, and involving communities in policy development processes. In Baidoa, the stakeholders identified operational gaps between the justice and security institutions as well as the inadequacies of the Xeer system. They noted the need for capacity building for security and justice actors on how to engage with communities. See table below with a complete list of ABPs identified. More information reflecting on what next process provided below.
[note] Somali traditional system

Baidoa- Final list of Area Based Problems	Kismayo- Final List of Area based Problems
Elders’ involvement (interfering) in cases already at court (xeer jajab).	Judges and prosecutors lack the skills and independence needed to provide fair and just services.
Operational gap between police and courts.	Absence of a coordination and collaboration mechanism between the police, other security and justice actors and the public.
Absence of a coordination and collaboration mechanism between the police, security and justice actors and the public.	Gaps in government policies related to the needs of Somali communities
Lack of engagement opportunities between community and government.	Land disputes and conflict as a result of those disputes
Elevating the role of religious leaders on security and justice issues.	Marginalisation faced by vulnerable groups including Internally Displaced Persons (IDPs) and Traditionally Marginalised Groups.
Undue Influence over police and courts operations.	Women who experience crime and sexual and gender-based violence (SGBV) do not have enough support from police and face stigma and discrimination from the justice system.
Judges and prosecutors lack the skills and independence needed to provide fair and just services.	Limited human resource and capacity by S&J institutions to deliver services
Lack of children's rights after divorce.	Illiteracy, unemployment resulting in recruitment of child soldiers.
Drug abuse and addiction by youth and men

The indicator target number was informed by the amount of time and effort required to carefully navigate trauma, assure safe space for communities to openly express themselves. The implementing partner was also required to consider the power dynamics, and potentially conflicting views expected in consensus building. While the over achievement could be explained by the gravity and number of issues emerging in the discussions, focusing on identifying challenges reduced the time available to steer the process towards prioritising issues and to begin the process for generating responses from the formal institutions. As a result, the milestone was only met, but did not comprehensively achieve the level of collaboration required to inform the next step.

Furthermore, some government stakeholders who participated in the ABP process and interviewed for this Annual Review held the view that ABP process were unnecessarily long and repetitive, limiting time and effort needed to move the process to next steps. The project should develop a way for government- security and justice actors to organically move to actions to address concerns raised. This potentially could be the background upon which an institutionalised social contact will be built.

For Indicator 2.2, the target was not met. The indicator targeted at least two interventions co-designed to help the communities and the government to start working together. While IP1 generated seven areas and IP2 three (also known as support functions or system functions), these were individually undertaken which once again means no intervention was co-designed and delivered.
[note] Support Functions: functions that the programme identified as strategies that can help shift behaviours and systems towards greater safety and fairness.
[note] Systems Functions: These are functions that were seen as having the best opportunity to support the delivery of our chosen support functions and spoke to the Nabadaynta partnership’s core practice areas

Support Functions: functions that the programme identified as strategies that can help shift behaviours and systems towards greater safety and fairness.

1. Generating knowledge and liberating learning: Through Think Sessions, IP1 brought stakeholders together to discuss how Islamic principles could inform access to security and justice. This support function was meant to broaden the understanding of Islamic principles and teachings that support inclusion and respect for all genders in the programme interventions, while also addressing clan ideologies that propagate exclusion. On this support function, IP2 held training and learning sessions on norms diagnostics and behavioural drivers’ analysis for the Nabadaynta team and the broader security and justice communities of practice in Somalia. The learning was important to promote greater trust and coalition building between diverse actors, build consensus around key issues as a starting point for sustainable and transformative change.
2. Engaging and influencing: IP1 successfully negotiated with the Minister of Security, the Minister of Justice and the Baidoa District Commissioner to establish an independent planning committee (ITPC), aimed at mitigating the risk of ‘elite capture’. This approach enabled diverse community members to engage government authorities in a consultative process to agree on matters of concern and seek solutions. It was in one of these Town Hall engagements that a solution to street lighting through the engagement of private sector was identified and lauded as a direct result of the inclusive dialogue. Through the same support function, IP2 maintained government engagement in the ABP process, helping to build the legitimacy of trauma healing, challenging exclusionary norms in the action planning phase and building commitment to the identified solution.

Systems Functions: These are functions that were seen as having the best opportunity to support the delivery of the chosen support functions and spoke to the Nabadaynta partnership’s core practice areas

1. Strategies, structures and systems: IP1 supported security and justice ministries and the Baidoa district commission to establish the independent planning committee in Baidoa, composed of community members and local S&J influencers as a precursor to organising inclusive and participatory Town Halls. This was necessary to build trust and inclusive engagement in the Town Hall processes. Another example of a support function by IP1 was the establishment, and training of an ad hoc committee composed of community members, civil society organisations (CSOs), Police Advisory Committee (PAC) members, and parliamentarians to promote the Civilian Oversight Model (COM) endorsed by the regional security council of the respective states. The ad hoc committee is expected to continue engagement with the community and disseminate the process of implementing the civilian oversight model over the police. They will also gather public feedback, support and participate in the establishment of an Independent Oversight Police Board (IOPB). This will in turn contribute to building a coalition of stakeholders interested in establishing oversight mechanisms.
2. Service Delivery- IP1, provided support through Town Halls, contributed to two instances of government being more responsive to complaints: notably by the decision of Baidoa authorities to install streetlights and to curb the unnecessary discharge of firearms by the police.

These support functions were delivered independently by each consortium partner, therefore undermining the effort to deliver a blended intervention. Nevertheless, the focus on delivering tangible support to enable coalition formation and progress reflects a commitment to translating research and analysis into actionable strategies to support strengthening of social contract, albeit in their early stages.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph
The absence of blending triggered a review of project delivery arrangements and a decision to significantly amend these to align support functions with diverse stakeholder needs and priorities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The key recommendation from last year’s annual review relevant to this Output was to support the blending of security and justice expertise with social norms and behaviour change in project delivery. While efforts were made to support co-creation, this recommendation was not addressed, leading to lack of joint co-design and delivery of activities. However, the success of the inclusive process both IPs undertook has demonstrated the importance of participatory approaches and trust-building among diverse stakeholders.

In Somalia, it is not easy to find opportunities where communities interact, in an inclusive way, to discuss priorities and possibly find cooperation from formal institutions and policy makers. This project offered that unique opportunity, bringing together representatives from women, youth, the marginalised as well as those representing institutions such as judges, members of the federal member state parliament and other senior government figures. Considering the level of government involvement, this unique approach merits the investment of time, effort and resources.

Output Title	(NS) Somali-led strategies: Support for Somali-led development and implementation of strategies for achieving changes in safety and/or fairness on common concerns
Output number:		3	Output Score:	C
Impact weighting (%):		7%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1: # and description of Somali-led strategies developed for achieving changes in safety and/or fairness for people	2	Exceeded: 6 Strategies developed with implementation involving local expertise leading engagement
3.2: Evidence and analysis of the extent of implementation of Somali-led strategies	Identification of progress markers for implementation	Substantially Not Met: Some, but insufficient, Progress Markers tested informally with stakeholders

This Output is about the development of locally led initiatives for achieving change in safety and security as well as justice, through a process that embraced the inclusion of both marginalised people and political elites. Further it looks at evidence if these initiatives progressed to implementation.

Indicator 3.1, developing locally led initiatives was surpassed with 6 different processes. The processes focused on supporting diverse Somalis to co-create initiatives for achieving change on how Somalis experience security and justice. The Town Halls, for example, helped bridge the engagement gap around public participation and expanded civic dialogue on the provision of security and justice. The ABP initiative involved a participatory process amongst community members and government actors on issues of concern, eventually agreeing on tangible solutions. Inclusion of trauma healing and trust building sessions provided a sense of safety, as well as empowered community members – some of them marginalised persons – to engage government actors confidently on solutions for these concerns.

The project support has successfully led to emergence of ‘locally led initiatives’ such as the Community Oversight Model. However, it is uncertain, whether participatory processes implemented so far can organically emerge and sustain themselves as locally led, without being programme supported. Considering these are new initiatives in a context where the government holds the monopoly of engagement, there is a need for sustained dialogue and community engagement with policy actors, while carefully assessing change. Most of the initiatives, while successfully emerging, may potentially upset the status quo of power dynamics between government and communities. Unless these are continuously addressed, they may wash away the gains made in the participatory dialogues. During conversations to inform this annual review, some government representatives interviewed felt that the ABP process needed to be government led as ‘government actors knew best what concerns of communities are’, a pointer to the need for the initiatives to be nurtured and supported more to sustain change.

For Indicator 3.2 evidence of locally led strategies achieving tangible changes on the established engagement of government actors and communities is substantially not met. There was not any indication that the issues raised informed policy on aspects of security and justice. There were limited indication of sustained inclusion of women and marginalised people in participatory public policy dialogues, including no evidence of a willingness to continue with this participatory approach on common issues and solutions. From the menu of Markers developed to measure this indicator, very few have an indication of behaviour change, and where it is evident, it is mainly at the level of individuals. A reflection on some Progress Markers here below

1. Issues raised by communities are put at the centre of policy development. On this marker, there were reports of marginalised clan members being very appreciative of the opportunity to engage high level government actors over issues pertinent to them. There were individual senior government authorities indicating learning from the processes at a personal level and promising to drive change in the way services are delivered to communities. No indication of action or policy to address the issues were evident yet.
2. Inclusive community process at all stages and communities having forums to discuss issues at the local level. Some level of success on this marker considering the ABPs and Town Halls dialogues provided space for communities to discuss what mattered to them including identifying issues that programme would consider supporting.
3. Formal structures can participate in public forums and are willing to have two-way track communications with the wider public. It was noted that, in as much as open discussions between government authorities and communities are starting to emerge, the sustained willingness to have meaningful and open two-way communications with the wider public remains to be seen. There will need to be sustained support for the participatory processes to embed as part of government functions.
4. Increased platforms that bring together diverse Islamic leaders and authorities around concrete policy issues with Islamic-based advocacies on justice and inclusion. On this marker, the ‘Think Session’ on operationalising Islamic principles provided a one-off forum for bringing together Islamic leaders and authorities in a bid to understand and infuse the learning in driving some project strategies. It remains to be seen how this is maintained in the future, and how authorities respond in the long-term on implementation of justice and security solutions.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph
There were no changes made to this output during the past year. Project leadership should reflect on how it can make faster progress on the milestones, considering the need to measure a sense of change in the delivery and experience of security and justice amongst the key stakeholders in this project (formal actors in delivery and community as participatory recipients). While significant efforts have been undertaken by the Fund Manager and both IPs, without common goals identified and agreed by the project stakeholders there is a risk of delivery not contributing to core outcomes and outputs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
For the year under review, delivering this output has demonstrated examples of early success in some of the Somali-led strategies, highlighting the importance of community engagement and partnership in addressing complex societal issues. The strategies’ approach to building trust and inclusivity, lays the groundwork for sustainable change, hence underscoring the need for continuous communication and collaboration between stakeholders, to navigate challenges and adapt the strategies for even more successful outcomes.

To build on this momentum, it will be crucial to further amplify the voices of marginalised groups and ensure their meaningful participation in the development and implementation of these (and new) strategies. In addition, there is a need to build on early engagement with Somali stakeholders to clarify objectives, refine progress markers, and ensure accountability in the implementation of strategies. This can be achieved through regular feedback loops, participatory monitoring, and evaluative processes that empower local communities to drive change effectively.

Output Title	(NS) Learning & adaptation: Evidence of i) programme’s strategic decision-making driven by learning; and ii) use of learning to influence strategic decision-making of other actors (Somali and international)
Output number:		4	Output Score:	C
Impact weighting (%):		14%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1: # and description of cases where the programme’s strategic adaptation has been driven by learning	10 cumulative from previous year	Met expectation / Five types of learning done that fed into various aspects of programme implementation
4.2: # and description of cases where learning is used as part of political access and influence with other actors / (Somali and international)	3 events at which the programme shares learning with other actors (Somali and international)	Moderately Not Met: / While 5 events were held to share learning, no evidence of ‘use to influence’
4.3: Extent of ‘best fit’ approaches / that help programme progress on / adapted GESI continuum	3 interventions evidenced as GESI responsive, and 2 interventions evidenced as GESI transformative	Moderately Not Met / 5 GESI responsive examples evident.

This output focuses on how evidence generated by the programmes informed adaptive programming which is a central aspect of the design and implementation of Nabadaynta, including uptake and use of the evidence generated by external stakeholders. To keep this ambition strong, the project identified three pillars to guide the learning agenda:

1. The Adaptive Learning pillar focuses on deep contextual learning that involves interrogating and iterating the project theory of change and theories of action. It also includes reflecting on what is working and not working in the design and delivery of project activities and feeding these reflections into appropriate adaptations.
2. The Process Learning pillar focuses on project’s internal processes, including new and innovative ways of designing and delivering adaptive security and justice programming in complex environments. For instance, working through a one programme approach, co-creating with communities and institutions, and embedding values-based programming.
3. The Knowledge and Capacity Strengthening pillar focuses on building knowledge and capacity in key areas deemed important to the design and delivery of project activities and interventions.

Indicator 4.1 was about encouraging the project to understand and track the extent that learning was feeding into ongoing course correction and strategic adaptation. The cumulative target was achieved for this annual review. For instance, the findings from the formative research on co-creation informed adaptation of the ABP facilitators. This meant selecting members of ‘own group’ (e.g., female facilitators for women groups, IDP facilitators for IDP groups, etc.) therefore maximising the likelihood of trauma healing as a result of ‘safe spaces’ created for open dialogue. While some of the learning elements achieved may not be construed as sufficiently strategic, they enabled significant elements of adaptation that were important to delivery of the project.

Indicator 4.2 encourages the uptake of learning by other stakeholders in the security and justice space in Somalia, and beyond. With five events delivered within the year under review, the target of three planned events was exceeded, however there was no evidence of uptake of the learning as intended by the indicator. For instance, the event on ‘How Change Happens in Somalia’, showcased how a programme’s Theory of Change (ToC) can be successfully applied and operate differently from the traditional ‘top down’ way of delivering security and justice solutions. Instead, it supports inclusive participatory negotiations that strengthen positive social norms and enhance experience of security, justice and fairness. This offered an example of a collaborative approach that can potentially result in the gradual change of norms that fuel exclusion, inequality, and mistrust of authority.

Indicator 4.3 This indicator tracked how the programme developed its approach to gender equality and social inclusion (GESI). Evidently there was significant effort to understand the contextual realities in Somalia, clarifying both blockers and enablers of equality and inclusion, as well as applying international standards that inform approaches to GESI programming. The process of engagement and delivery of ABPs, Town Hall dialogues and the Civilian Oversight Model embraced inclusion and participatory approaches that demonstrated a community centric demand for accountability on Security and justice. This included enabling women and internally displaced people to express their concerns in a way that meant the government listened and acknowledged the concerns.

This review considers the indicator to have underachieved, as there has not been any observable result to confirm transformation as per the GESI Assessment and Mapping Tool developed to measure this progress. Rather, the delivery of interventions instead scored a ‘GESI responsive’ approach by enabling diverse participation. ‘Transformation’ would have to contain features of redress (setting right) gender and social inequalities and removing structural barriers/blockers to participation of disadvantaged populations. Considering the challenges inherent in tackling decades of inequality driven by dominant male and clan power capture that disfavours women and other marginalised people in the population, a transformative target was rather ambitious. Encouragingly, there are indications of early transformation in the confines of the delivery process, which if sustained may result to transformation in some ways.
[note] A a GESI Assessment and Mapping Tool was developed by the GESI experts from all Nabadaynta partners to inform implementation of GESI programming. The tool identified a continuum comprising five ‘conditions’: 1) GESI discriminatory: which favours either gender, or a particular social group, leading to deepening of gender and social inequalities 2) GESI Blind: which ignores gender and social inequalities in programme design and perpetuates status quo or potentially worsens inequalities, 3) GESI sensitive: -which acknowledges but does not robustly address gender and social inequalities, 4) GESI responsive: which identifies and address different needs of girls and boys, women and men, promoting equal outcomes for all, and 5) GESI transformative: which explicitly seeks to redress gender and social inequalities, remove structural barriers, and partner with disadvantaged populations

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph
There were no changes made to this Output in the past year. As a result of the review, it will be necessary for the programme to refine Indicator 4.3 based on a re-evaluation of GESI achievement against the ambition set on the assessment and mapping tool. The ongoing learning agenda in this programme needs to factor in a reflection of GESI realities in Somalia. This will help set a realistic level of ambition around what the Nabadaynta project could achieve in transforming how security and justice is delivered to the diverse population of Somalia.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The recommendation from last year, relevant to this Output was the need for proactive engagement of the Fund manager and donors with the programme’s political stakeholders to help manage the risk of capture. This recommendation was addressed through recruitment of a Programme Manager in Mogadishu as well as two area coordinators based in Baidoa and Kismayo by the Fund Manager. Moving forward, Nabadaynta should fine-tune and rethink its learning events – and the way it shares learning – to foster increased engagement from partners and strengthen influencing. Notably, the project can do more to ensure that learning shared with partners leads to tangible changes in programming and thinking around security and justice issues for others. The project should also seek to learn more from others – both international and Somali subject matter experts, as well as communities and local stakeholders. The project also needs to operationalise its own learning agenda, currently being finalised, with the full buy-in of IPs and donors, to drive strategic adaptation.

Rapid Stabilisation Support (RSS)
Rapid Stabilisation Support was a one-year pilot project, for which the successor programme has moved under the Somalia Integrated Security Fund portfolio. Information gathering for this review was limited to a presentation and Q&A with IOM Somalia, interview with the project’s SRO, and information provided by IOM including the final report of its external evaluation partner, GIST. This review’s assessment of outputs 5 and 6 relies on the independent analysis contained in the GIST report. Given that both outputs relate to increased trust amongst communities, there is some commonality between findings on horizontal and vertical trust.

Output Title	(RSS) Vertical integration and trust Communities’ trust in local institutions is strengthened and processes of government coordination and accountability lay the foundations for institution building.
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
No. of integrated (x-govt) stabilisation projects designed and implemented which are aligned to GoS plans (disaggregated by geographic/physical location)	% perception of target population reporting on trust and confidence in local institutions / Baseline: 35.6% / Target: increase of 10% from baseline	Substantially met: 68% / The GIST report for IOM sets out that a total of 48 activities planned, 18 were completed, 18 ongoing, nine cancelled and one rejected. This meets the requirement.
% Perception of target population reporting on trust and confidence in their local institutions	+10% increase from Baseline / Achieved: 68%	Data indicates that each indicator reached above the 10% requirement.

IOM conducted an extensive baseline perception survey (household level) in ten target locations to understand recipient needs. A randomised sample methodology was used (which covered 3500 households) for baseline data collection (using the IOM’s COSI methodology). For the endline assessment, perception surveys were conducted in the same locations, in addition to KII’s (Key Informant Interviews) with households directly involved in the programme, those not affected directly and government representatives (to triangulate findings from the perception survey data).
[note] As part of the data collection undertaken to establish Baseline figures of the project, IOM commissioned an external evaluation firm (GIST) to support in the data collection, analysis and reporting of a large COSI exercise (conducted under this project) COSI is a community stabilisation statistical index tool to measure how stability is understood locally, the extent to which a location is perceived to be stable and the key factors that influence perceptions. COSI focuses on seven critical stabilization themes including community recovery; rule of law; reconciliation and social cohesion; local governance; resilience to climatic shocks; livelihoods; and population movement

GIST analysis showed substantial progress against RSS outputs, each exceeding the 10% target increase. The indicator related to trust and confidence in local institutions demonstrated the most progress, with positive perceptions increasing by 32%. Progress in assessments of stability represented an overall 11% increase. The project has therefore met the milestones for this output.

The project was aligned with the UK Approach to Stabilisation, which at the time of writing it was being refreshed. Key elements include extensive community engagement based on robust and early analysis of local dynamics following military operations. RSS has followed this model to identify community needs. RSS has also sought to align with other relevant stabilisation interventions. Support to IOM to deliver RSS has also improved coordination amongst UN agencies and partners on stabilisation.

However, Activity Proposals drawn up by IOM and local authorities did not provide evidence of political economy, conflict sensitivity or GESI analyses tailored to local intercommunal dynamics and tensions. Only, one Activity Proposal demonstrated consideration of specific risks to women and girls and how activities could help address them. There was also limited evidence of activity designs including comprehensive approaches to sustainability or risk management. Risk matrices were not tailored to specific activities or locations, identified only generic, high-level risks, and applied the same scores to them across all Activity Proposals. Mitigations and residual risk levels were not identified. These issues should be rectified in the successor programme.

Output Title	(RSS) Horizontal integration and trust. Social cohesion and civic engagement are promoted at the community level through proactive interaction, dispute resolution capacity, natural resource management mechanisms, and the restoration of economic value chains
Output number:		6	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2% of committee members reporting improved dialogue and interaction with communities with which they had been in conflict in the past	+10% increase from Baseline / Baseline: 36.5% / Target: increase of 10% from baseline / Achieved: 61%	Substantially met. / GIST reports a 25% increase in the number of respondents reporting a positive perception of communities they had previously been in conflict with. / Committee members reporting improved dialogue and interaction with communities with which they had been in conflict in the past increased from 36.5% to 61%.
# of local mediation and reconciliation processes scaled-up through the Action.	Not provided in the RF	Met. / Two of four achieved – 50%.

GIST found that the positive perception of improved dialogue and interaction with communities with which they had previously been in conflict was reported by 61% of respondents, reflecting a 25% increase. Respondents also identified the broader impact of activities in developing horizontal trust (trust between communities). In identifying these impacts beyond the activities themselves, respondents linked the activity to broader stabilisation and peacebuilding objectives. For example, respondents in Adan Yabal identified “the depth of connections formed among women from diverse backgrounds through the activity, which had “strengthened the social fabric and fostered a sense of community”. These encouraged them to actively engage with the administration to advocate for inclusion in local decision-making. Within the context of extreme ongoing fragility and the absence of basic services, respondents felt the activity had “initiated the first steps toward community reconciliation and collaboration”.

Respondents in Moqokori, Xarardheere, Mataban, Adale and Farlibah identified the beneficial impact of the activities, as the first of their kind undertaken to date, in reducing intercommunal tensions and strengthening intra-community collaboration and cohesion, despite many of the activities in these locations not being aimed at strengthening intercommunal relations.

Across both outputs, GIST found that almost all respondents reported that activities had met or exceeded their expectations, and most respondents expressed satisfaction with the activities in their area, with some identifying the symbolic importance of support received after 15 years of al Shabaab (AS) control.

The challenges identified above relating to political economy, conflict sensitivity, GESI analyses and risk management are common to outputs 5 and 6, and therefore output 6 has also scored an A.

D: VALUE FOR MONEY [1pages]

Key cost drivers and performance
During the year under review, the major cost drivers in Nabadaynta remained personnel and expertise.

VfM performance compared to the original VfM proposition in the business case
Effectiveness	How well are the outputs of SSJP II interventions having the intended / effect? I.e. Is the programme achieving the right outcomes and benefits in relation to the amount / invested. Does the programme have a plausible theory of change that is being tested in a robust way, / and signs of a good initial return on investment?
	Nabadaynta is underpinned by a robust Theory of Change and the design of the project is modelled on understanding of how transformational change has happened in the past in Somalia. However, there are question over the effectiveness of Nabadaynta delivery. Whilst the research and analysis produced by the project has some intrinsic value, progress towards outcomes is uncertain.
Equity	How fairly are the benefits derived from the Programme being distributed, in particular among marginalised groups? I.e. is the programme meaningfully supporting women, girls and those from marginalised groups above and beyond including them in activities? Does the programme have a plausible theory of change, being tested in a robust way, about how to reach marginalised groups?
	On equity, both Nabadaynta and RSS have a positive story to tell. Nabadaynta has invested significantly in bringing women and minorities into project activities, openly acknowledging power relationships and providing meaningful support to marginalised people to enable their participation. Creating space in the project for their participation has also required significant advocacy with powerholders.
Efficiency	How well does SSJP II convert inputs into outputs?
	The degree of investment in attempts to establish a common programme approach which delivers on the ToC has yet to be realised as per the programme design objectives on co-designing and/or co-creation.
Economy	Is SSJP II buying inputs of the appropriate quality at the right price? I.e. is the programme managing its main cost drivers and investing resources of the right quantity and quality to support learning?
	Although management and administrative costs have been kept close to 8-10% in Nabadaynta, the project’s challenges have diverted much of the strategic management and technical capability available in the IOM Fund management team away from strategic and technical delivery and into contract and partner management tasks. This has also been the case for delivery partners, and even for donors. IOM attempted to manage this in a timely manner, but some management challenges were still unaddressed at the time of this review.
Cost-effectiveness	What is Nabadaynta’s ultimate impact on donor foreign policy objectives? / I.e. does the programme’s achievement of its outcomes offer wider strategic benefit to the donors in / relation to the scale of investment.
	The UK investment in particular has been significant. In the face of numerous challenges, progress to date, and results are not commensurate with the level of investment. Nabadaynta is yet to deliver the strategic insights into what works to enable it to successfully influence wider investment in security and justice.

Assessment of whether the programme continues to represent value for money
Last year’s Annual Review recognised the need for Nabadaynta to re-establish itself after the difficult period of funding uncertainty and novation to IOM. However, the delivery model of the Nabadaynta has become heavily contested by those in the delivery chain. This has resulted in costly, open-ended renegotiations on the project’s approach, which have diverted the time and attention of key project leaders in a number of organisations. Delivery has been delayed and the Fund Manager has been unable to address donor concerns about progress whilst engaged in dispute resolution. In its current form, the project offers poor value for money and adaptation is needed to address this.

Overview of risk management [1/2 page]
SSJP2 operates within allowable FCDO BEM risk appetite across all seven categories. Overall, across the two programme components, the risk management framework aligns to FCDO/BEM approach. IOM and downstream partners have actively participated in the FCDO-organized partner days to discuss cross-cutting challenges that affect delivery and share tried and tested mitigation measures. There is a valid due diligence report in use across all IOM programmes funded by FCDO. An update to the current Due Diligence Assessment is in progress. The programme has had the advantage of incorporating recommendations from other FCDO teams, including joint scrutiny which has worked well for the programme. Some of these include:
- Ensuring that IOM managed projects have a dedicated risk management officer at country office level rather than relying on staff at HQ level who provide support to multiple projects.
- Monitoring of the programme should be done periodically to assess progress. SSJP2 has linked IOM M&E team with the FCDO funded third party monitor to enhance regular monitoring.
- Compliance with FCDO quarterly reporting timelines. The programme team hold monthly meetings to ensure close monitoring of financial spend and timely quarterly reporting.

Each IP conducts an independent quarterly review of their respective risk register in accordance to changes in risk levels and share update with the IOM. Updates to the programme-wide risk register are discussed as a standing agenda item in the monthly Programme Management Team meeting where control and mitigation measures are agreed. IOM also undertakes after-action reviews in the aftermath of critical security incidents. Down-stream partners are routinely sensitised on FCDO reporting mechanisms and encouraged to log all issues to reportingconcerns@fcdo.gov.uk. We reassure partners and suppliers of the confidentiality and prompt action from our fraud and safeguarding team. Some of the risks the programme was exposed to during the reporting period are discussed below:

Contextual risks
The main contextual risks highlighted through the year were:
- Deterioration of the security situation following escalation of violence and/or conflict, impacting programme activities and placing programme staff at risk of harm
- The Federal Government of Somalia military campaign against Al-Shabaab is likely to have a huge impact on ongoing implementation work in Jubaland and South-West State, including accessibility to key locations.
The programme has responded by working with partners who have strong local networks and understanding of the local context.

Climate-related risks unique to the RSS component included logistical challenges and delays in construction works and implementation due to the El Niño rains during November 2023. Heavy rains and river flooding led to the displacement of population and closure of key access roads in Hirshabelle, Jubaland and South-West. The project also battled Environmental challenges by way of Saline intrusion which posed a significant environmental challenge during borehole drilling in Jirale. As seawater encroached into freshwater aquifers, IOM contractor had to continue to dig to deeper aquifers to reach freshwater located below the saline waters. This activity took significantly longer than planned, and more specialized digging materials had to be utilized which led to additional logistical complications. However, the vendor agreed to continue the additional drilling after programme closure to ensure higher levels of freshwater. Due to the good working relationship between IOM and long-term contractors on the ground these complications did not negatively impact on the budget.

Programmatic risks
Nabadaynta has been marred by relationship and governance related issues. The impact of this has been a slowdown in delivery and a significant toll on time and human resources. The relationship issue escalated to a point of intervention from co-donors. It deteriorated in recent months, with IOM unable to effectively exercise its functions as fund manager over one of the second-tier partners. The issues have led to additional challenges in assessing the project’s results, caused both by a lack of engagement between the implementing partner and the monitoring, evaluation and learning provider, and the challenges in IOM’s ability to deliver oversight and accountability for project performance. Donors engaged Third Party Monitoring (TPM) providers to verify activities have taken place as planned. These includes TetraTech under FCDO’s monitoring programme and an independent TPM service provider procured by the EU.

Other notable programmatic risks highlighted through the year include:
- low levels of programme buy-in from government authorities, especially in the area-based problems (ABP) identification process
- high expectations and demands from government officials on how they will benefit from the project in areas beyond its mandate. This often related to requests for activities, physical facilities, personnel, supplies and other logistical support needs that the programme not within programme mandate.
The programme has responded by ensuring continued engagement with key stakeholders especially senior federal member states representatives. In South-West State the list of ABPs have been signed off at ministerial level while the sign-off process is in progress in Jubaland. The MoUs established between the programme and Ministries of Justice and Security in Jubaland and South-West State, the Programme Advisory Boards held in Baidoa and Kismayo, and several visits to the federal states have further improved the relationship between authorities and the programme.

Fiduciary and safeguarding risks
Despite there being no reported cases on corruption, fraud and bribery during this period, we continue to hold conversations around reporting mechanisms and relentlessly encourage the fund management team as well as the IPs to report any Suspicions. We also ensure that we balance our messaging on FCDO’s zero tolerance to fraud and safeguarding with the reassurance around the importance of flagging such issues. There have been in-depth discussions around this during the bi-annual X-portfolio partner days as well as the Security & Justice Team partner days. In the operating context, it is inevitable that there will be cases of malpractice, and we will continue to work closely with the third-party monitoring team to get sufficient reassurance.

The programme team is currently managing a case that was escalated by one of the IPs and categorised as programme governance in nature.

Both components benefit from IOM’s robust financial system with several control mechanisms, checks and balances which detect and prevent external and internal corruption. IOM continues to ensure compliance with IOM global resource management standards including procurement, financial management and ensure transparency and accountability among its programme partners. IOM has standardised internal processes to investigate and resolve suspected cases of partner misconduct including fraud, bribery and corruption. These processes begin with an investigation involving all concerned (partners, IOM resource management and legal departments) and require that donors be notified at the earliest instance.

Overall, the programme has been able to deliver within its risk appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Programme Management
IOM has been consistent in providing quarterly delivery narratives and risk register and updates for both Nabadaynta and RSS project. Reporting is sometimes delivered outside the timelines set out in the MOU, particularly financial reporting owing to the multiple supplier layers and the turnaround delays that emanate from quality assurance processes in place. Nabadaynta provided annual progress reports that describe progress towards outcome and detailed performance against output indicators as contained in the theory of change and results framework including the associated resource forecast, funds receipt and utilisation of the resources used to deliver.

Nabadaynta has an established asset monitoring and tracking tool for the project. An updated asset register is shared quarterly with FCDO for review and record. As indicated in section ‘E’ above, Nabadaynta proactively discuss risks as part of its monthly programme management meeting with implementation partners and MERL service provider and share updated risk tracker with FCDO.

In the period under review, IOM convened the Joint Donor Committee meeting in October but from December, regular JDC meetings have been overtaken by frequent, ad hoc meetings focused on reforming the programme delivery structure and more recently, managing the further deterioration in working relationships triggered by this. Moving forward, IOM should recommit to organising regular JDC meetings.

IOM engaged the services of GIST to provide an external evaluation of the RSS project which has provided independent assessment of delivery and a wealth of reflections and recommendations for further development of the approach.

Financial performance:
Nabadaynta
In the reporting period Nabadaynta has received a total of £5,074,332 from the three programme donors i.e. FCDO, EU Delegation in Somalia and the Netherlands, as shown in the below table.

Table: Nabadaynta Soomaaliya funds received from donors in the reporting period 2023/2024.
	Donor	Donor contract currency	Amount received in donor currency	Amount Funds Received in USD
1	FCDO	GBP	£2,500,000.00	£2,500,000
2	EU	USD	$1,961,228.00	£1,532,196
3	The Netherlands	USD	$1,500,000.00	£1,171,865
	TOTAL			£5,204,061.00

As at June 2024, the actual expenditure stood at £4.9m translating to 97% of the total funds disbursed in the reporting period. Payments to downstream partners is milestone-based and is released on condition that agreed milestones are delivered to required standards. This method is effective in not only incentivizing IPs but also providing an added layer of quality assurance.

The programme forecast from the date of novation 01 July 2023 to 31 March 2024 was £5,936,540 ($ 7,794,370.) The actual expenditure disbursement as compared to the forecast is 80.5%. At the point of drafting this report, only 33.3% of the withheld milestone payment was still under review.

Despite a slight delay in signing the EU and Netherlands agreements and subsequently a delay in their disbursements, the forecast was not affected as FCDO funding was fully absorbed in the interim. Overall forecasts have fallen within the 5% allowable variance.

RSS project
The financial performance of RSS project has been positive in commercial and financial aspects. The £5M was disbursed towards the 10-month project duration. By the end of the MOU period the entire amount had been fully absorbed and committed in full. IOM have demonstrated strong financial management and adherence to their own procurement and financial procedures adhering to VfM values on procurements and ensuring efficient use of resources. They have maintained compliance with all relevant regulations.

Commercial
Following a challenging and protracted novation process, Nabadaynta retained core staff thereby providing for a smoother continuation of programming post-MOU signing. Where IOM had to recruit additional staff (for example, the Monitoring and Evaluation lead), the timelines were significantly longer than anticipated, so the transfer of the key fund management staff was critical in avoiding further delays. This also effectively created a continuation of stakeholder relationships formed during the inception phase under UNOPS. However, strained relationship with IP1 were already evident prior to novation and has since deteriorated.

Stakeholder Management
Shortly after novation, IOM senior managers made efforts to revitalise Nabadaynta’s profile and relationships with government stakeholders. Importantly, this resulted in the agreement of MOUs with FMS authorities which helped clarify how the project would work with State Ministries and which Ministry would take lead responsibility for government engagement with the project. Initial suggestions about how to draw Federal government representatives into project governance in each FMS could not be agreed upon

In early design, SSJP II considered that Federal Government policy and institutions might ultimately be influenced by evidence developed by the project on what works, and that this could enable replication and further evolution the project’s problem-solving approaches on a larger scale. After successive challenges which have slowed delivery, the project is not yet at a stage where it can provide government decision makers with compelling evidence, but this should remain the target for outer years of the project.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The team invested effort and time updating the results framework, with the fund management unit engaging closely with FCDO’s monitoring programme team to ensure a robust framework and outcome map is in place going forward. This was achieved by holding:
- Bilateral consultations and deliberation between FCDO programme staff and MEL lead, the MERL partner and the fund management team
- Bilateral consultations and deliberation between the MERL Partner and the IPs
- In-depth discussions on RF outcome and impact indicators

One of the key findings out of these processes is the unharnessed opportunity to strengthen ownership of the RF and Outcome Map. An action point that has been earmarked for immediate action. Secondly, the IPs raised concerns about their ability to meet outcome indicator 2.1 and 2.2 targets. Both IP1 and IP2 voiced their concerns related to the outcome map. The MERL partner and IOM agreed that a light-touch revision of the outcome map before the end of the year is a necessary step in the process. This will be actioned as part of the recommendation on simplifying results framework.

Learning:
To remain responsive and relevant to the evolving context and shifting dynamics, the programme has prioritised Adaptive Learning and placed it at the centre of the programme delivery. Focus has been on developing the Programme-wide Learning Strategy in collaboration with the Fund Manager and the Implementing Partners, Altai. Altai proactively involved all key stakeholders in a stocktaking process aimed at generating an initial version or a foundational framework for the learning strategy. A notable challenge in this reporting period has been that learning is occurring without a comprehensive Learning Strategy to steer the process. As a result, the team has been working in parallel and placing greater emphasis on coordination.

In the coming year, the MERL Service Provider will continue to be the penholder on the development of the Learning Strategy and engage the Implementing Partners more on working toward a collectively owned Learning Strategy

Date of last narrative financial report	May 2024	Date of last audited annual statement	May 2024