## Annual Review

Title: Girls’ Education South Sudan Programme Phase 2 (GESS2)
Programme Value: £70m		Review date: The review will cover the period from 1st August 2019 until 31st March 2020
Programme Code: 300449	AMP start date: / 29 March 2018	AMP end date: / 31 March 2024

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	C	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300449/documents
DevTracker Link to logframe	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300449/documents

A. SUMMARY AND OVERVIEW

The Girls’ Education South Sudan programme (GESS2) is reducing barriers to education and improving attainment levels for children, particularly girls. In the last year, it supported:

- 4,300 primary and nearly 200 secondary schools with grants to improve the learning environment (such as providing toilets, educational materials such as textbooks or equipment including desks);
- Modest cash transfers to more than 374,000 girls to supplement their household income and encourage them to attend school;
- Activities to change community attitudes towards education, including educational radio programmes targeted at two million people;
- Support for improving the quality of education, including Learning Groups and skills training, as well as teacher training, and mentoring schemes, and;
- Support for data collection to improve evidence on what works, including the Schools’ Attendance Monitoring System (SAMS), which reports on teacher and pupil attendance.

During this review period, the programme also secured funding from the Government of Canada. This reflects the significant role GESS is playing in improving girls’ education and demonstrates how UK aid and development leadership maximises impact by attracting additional resources.

This is the second phase of the programme. Despite successes, South Sudan continues to have some of the lowest educational indicators in the world. There are significant gender disparities for enrolment and attainment, increasing the risks of sexual and gender-based violence (SGBV) and hampering female participation in stabilisation efforts, basic service provision and economic growth. The challenging context within which this programme is being delivered, including ongoing instability, has been exacerbated by the onset of COVID19, which led to school closures on 20th March. The majority of the period under review was not affected by the pandemic, but sufficient space in the report will be given to outlining where COVID19 has had an impact on performance and to providing recommendations for how the programme might adequately respond to the secondary impacts of the crisis.
[note] According to the National Baseline Household Study, National Bureau of Statistics, 2009 the literacy rate for males remains at 40% compared to 16% for females. By mid-2019, at the start of GESS2, enrolment reached 1.8 million learners – 45% of whom were girls. However, it is estimated at least 2.2m children across the country are still out of school, and a significant number of girls continue to drop out as they progress through the system (UNESCO Global Initiative on Out of School Children, Country Study, May 2018 ).

Delivering education support in this context and manner aligns with UK objectives under the 2015 Aid Strategy:
1. To strengthen global peace, security and governance: Poor education outcomes for girls is proven to undermine female participation in stabilisation efforts and hinder growth and basic service provision, fundamental to a long-term poverty reduction.
2. Strengthening resilience and responding to crisis: tackling the secondary impacts of COVID19 including on child protection and education outcomes.
3. Tackling extreme poverty and helping the world’s most vulnerable: GESS2 will support all children in South Sudan, one of the poorest countries on earth, to have equitable access to a quality education. In doing so GESS2 is also aligned with the 2019 UK Conservative manifesto commitment to ‘stand up for the right of every girl in the world to have 12 years of quality education.’
Delivery
The programme is overseen by staff from the UK’s Foreign, Commonwealth and Development Office (FCDO). Regular meetings are held with the implementing consortium lead Mott MacDonald and downstream partners (referred to as State Anchors, or SAs). As co-chairs of the Education Donor Group (EDoG), the UK also delivers influencing objectives central to the successful implementation of GESS2.

GESS2 is managed and delivered by a consortium led by Mott MacDonald/Cambridge Education (MM/CE), and supported by BBC Media Action (BBC MA), Leonard Cheshire (LC), Montrose and Windle Trust International (WTI). MM/CE have overall responsibility for managing and ensuring effective delivery of the consortium partners (CPs) and sub-contractors (including 7 SAs across 10 States) delivering the programme.

The Ministry of General Education and Instruction (MoGEI) are regularly engaged both formally, through quarterly steering committee meetings, and informally to shape and support implementation of GESS2.

GESS2 Timeframe:
Month	Activity
March 2018	Business case approved by Ministers
June 2018	Tender for Managing Agent launched to market
November 2018 – January 2019	Original tender for Managing Agent cancelled and relaunched to market
May 2019	Contract award for Managing Agent
May 2019	Inception phase begins
July-September 2019	Programme launch + implementation of CTs and CGs begins (AR period begins August 2019)
October 2019	Inception phase ends and remainder of implementation phase starts
20th March 2020	COVID declared Global Pandemic and school closed
31st March 2020	End of year 1 reporting period and review period ends

Methodology
Due to COVID19 restrictions, this light-touch desk-based annual review has been conducted by the UK team overseeing implementation of GESS2 and has been informed by remote interviews with MoGEI, Consortium Partners and SAs. It is recommended that the next annual review is carried out in-country by an independent evaluator external to FCDO South Sudan.

Summary supporting narrative for the overall score in this review
The programme has scored an A (met expectations) against the areas of assessment outlined below. Major successes over this review period include the programme reaching the highest unique number of girls with CTs in a single year throughout GESS1 and 2; piloting varied CT amount and a multi-tranche approaches to distribution; exceeding all targets for school capitations grants, despite challenges with disbursal and reach, and; enabling the Government of South Sudan (GoSS) to invest £4.8m in capitation grants – the highest payment ever made by the Government. Foundations were also laid for achieving future milestones on both behavioural change and quality components, both of which are likely to boost the two out of three impact targets which were narrowly missed. There remain concerns about the quality of research, the ability of the programme to ensure equitable access, especially in hard to reach areas and the impact of COVID19 on programming. However, it is clear that achievements at output level are translating into outcome and impact level results, demonstrating the continued validity of the theory of change and giving confidence that the programme can adapt to the changing context. From a programmatic perspective, GESS is on track to spend as planned and is demonstrating strong awareness and prioritisation of key cross-cutting themes including value for money; gender equality and safeguarding.

Major lessons and recommendations for the year ahead
- Theory of change assumptions, programme targets and activities should be reviewed in light of COVID19 and additional Canadian funding.
- The primary risk to the programme remains limited investment in the education sector by the Government of South Sudan, which will hinder progress against GESS programme impact goals. FCDO engagement at senior level is essential to influence prioritisation of education spending.
- Engagement of both men and women in behaviour change activities is essential to secure genuine and sustained change.
- An official monitoring tool to track female drop-outs from eligible classes and development of a process for supporting re-enrolment. This should look at access to CTs and links with mentoring and behaviour change communication. This is particularly relevant in light of recent school closures which are expected to result in large scale dropouts.
- Capitation grants currently face two big challenges: i) non-release of funds by State Ministries of Finance ii) equity issues around access to finance for new schools or those recovering from previous closures. Discussions with MoGEI should explore streamlining the CG distribution process and focus should be given to supporting schools to meet the minimum approval standard.
- For a more complete equity picture, data on enrolment by grade and progression should be collected and inclusivity of all children, especially those with disability, should be mainstreamed across all outputs to ensure that no child is left behind.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The original theory of change (ToC) (see Annex 1) is still valid as evidenced by progress towards both outcome and impact level indicators. Programme activities are expected to contribute to reduced barriers and equitable access to education for all children; accelerated gains in girls’ enrolment (particularly secondary) and accelerated educational attainment for girls and boys. At the impact level, GESS2 will provide a source of stability and continue the work to transform the life chances of South Sudanese children, particularly girls, through education.

It is recommended that:
1. The ToC and logframe targets are reviewed in the context of COVID19. Temporary ‘COVID19’ logframe targets should be considered to reflect the additional ‘response’ activities once data on school re-enrolment is available.
2. At the mid-point of the programme, the ToC assumptions are tested to ensure that they are still relevant in the context of COVID19, considering long-term school closures and the global economic contraction. The following assumptions in-particular should be reviewed internally by MM and FCDO to instruct future activities under GESS2:
1. Direct financial support to girls to attend school increases enrolment.
2. EU Impact project continues to pay salary top-ups to primary school teachers.
3. Government continues to pay teachers (even in an ad hoc manner)
4. Government continues to support primary school CGs
Analysis to understand the contribution of girls’ education to growth and stability is conducted by FCDO.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

All outcome indicators (see Annex 2 for list of impact and outcome indicators) measured at the point of review have been exceeded. This demonstrated that the programme has the correct blend of behaviour change, direct financing, quality and research components to drive improved attainment and enrolment at both primary and secondary school level. Progress towards outcome targets should be catalysed further as both behaviour change and quality components mature from implementation into delivery phase.

Of the impact level targets, two out of three were narrowly missed, both focused on gender parity. This indicates that while enrolment is increasing (a major achievement for the programme), barriers to girls’ enrolment compared with their male counterparts still persist. It is important to consider that components one, behaviour change, and four, quality, are yet to move into delivery phase and are directly targeted at improving girls’ access to and retention in education. Therefore, future years impact targets should not be revisited purely on this years’ results. However, the programme will want to consider revising logframe targets based on the impact of COVID19 and the introduction of an additional £8.8m funding from Canada.

It is also important to consider factors beyond the control of the programme impacting gender parity. As outlined above, it is recommended that the assumptions in the ToC are reviewed and recommendations are made about what additional activities, beyond the scope of the programme, are needed to enable success at impact level. This should include British Embassy Juba (BEJ) influencing activities, for example to leverage Government of South Sudan investment in education services and coordination with the EDoG to ensure complementary programming amongst donors.

At the end of the reporting year, GESS2 was still on track to achieve the expected impact and value for money (VfM). However, COVID19 will likely impact on VfM (although this impact is currently unknown) as implementation of some outputs have been paused and activities delayed because of restrictions. All of which mean the programme will have to quickly implement within the current programme timeline and budget allocation when schools reopen. An extensive re-design of the workplan will be required in order to deliver against planned activities while balancing VfM considerations.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
In line with programme and country objectives, UK Aid Strategy and manifesto commitments, GESS2 is successfully contributing to long-term growth and stability in South Sudan by increasing the enrolment and attainment rates of girls at both primary and senior level. The onset of COVID19 has made UK investment in education services in South Sudan even more important in order to mitigate protection risks while schools are closed and support re-enrolment when schools reopen.

## C. DETAILED OUTPUT SCORING

Output Title	Communication to girls, boys, women and men to shift attitudes and behaviour related to the education of girls and children with disabilities.
Output number:	1	Output Score:	A
Impact weighting (%):	10% (Recommend this is increased to have equal weighting with CTs and CGs at the next AR when quantitative targets are also assessed.)	Weighting revised since last AR?	Not reviewed in last AR as logframe had not been finalised.

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and children with a disability (non-cumulative)	N/A	Sub-output 1.1 will be measured at midline in 2021 and at endline in 2023.
1.2: Number of school communities reached with community mobilisation	N/A	Sub-output 1.2 milestone for March 2020 is N/A as community mobilisation activities will only start in 2020 when new SAs have been contracted and trained.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output one builds on behaviour change activities undertaken during GESS1 which aimed to shift perceptions about the benefits of girls’ education and break down behavioural barriers to enrolment. GESS 2 will continue community mobilisation and behaviour change activities, seeking to expand into hard-to-reach communities and adapt messaging to support enrolment of marginalised groups such as children with disabilities.

Quantitative data was not collected on output one in this reporting period as activities were focused on laying the foundations for future years. Therefore, for the purpose of this review, this component will be assessed against the following objectives which signal potential to achieve results in future years and were agreed in the GESS1 Programme Closure Review (PCR) and/or 2019/2020 workplan:
1. Rebuilding listenership of the ‘Our School’ radio programme previously broadcast under GESS 1.
2. Onboarding of State Anchors (SAs) for community mobilisation (CM) activities.
3. Expanding the reach of community mobilisation and behaviour change activities to hard-to-reach areas.
4. Adapting messaging to include advocacy on education of marginalised groups with a focus on children with disabilities.
GESS2 performed well against these objectives:
1. ‘Our School’: Previous episodes of ‘Our School’ were re-aired and messaging was reinforced by presenter-led discussions designed to secure interactive engagement with the subject matter. Discussions were shaped by updated guidelines and training materials. An analysis of caller feedback found that the episodes and discussions were seen as relevant and engaging. However, it is important to note that the majority of callers and participants in discussions were male.
2. Community mobilisation onboarding: All SAs were selected and onboarded and six out of ten community mobilisation focal persons have been recruited.
3. Expanding to ‘hard to reach areas’:
1. Three new partners were recruited, expanding reach of ‘Our School’ further in Northern Bahr Ghazal, Eastern Equatoria and Central Equatoria. A total of 31 stations are now broadcasting ‘Our School.’
2. A community mobilisation (CM) strategy, incorporating mapping of hard-to-reach areas, has been developed. The strategy adapts the approach from GESS1 to focus on training community volunteers to run CM activities in their own communities instead of recruiting external community mobilisers. This is expected to have a better chance of engaging hard-to-reach communities and marginalised groups due to improved local knowledge and pre-established relationships.
Increasing participation of children with disabilities:
‘Our School’ presenters have received training on inclusion sensitive moderation and have delivered inclusive messaging but are unable to facilitate in-depth discussions on disability inclusion without detailed training. This has been on hold due to COVID19 travel restrictions but will now be undertaken remotely.
Relationship with MoGEI: Improved collaboration with MoGEI on output 1 exemplified by i) endorsement of ‘Behaviour Change Communication Strategy’ and ii) identification of the Director General of the Directorate of Gender Equity and Inclusive Education as the focal point iii) GESS Steering Committee meeting with MoGEI on 11th December 2019.
Challenges/performance issues (pre-COVID)
- Delays to output one stem from delayed SA procurement and CM focal persons recruitment. The delay is attributed to a failed tender process in three States followed by contract negotiation challenges. All seven SAs are now on board and six out of ten CMs recruited. This will be completed once COVID19 restrictions ease and should not impact on the programme’s ability to meet midline targets.
- Only 58% of the population (approx.) have access to radios making it hard to ensure equitable access to behaviour change messaging. This is particularly relevant in hard-to-reach areas and during COVID19 when CMs are less able to engage face-to-face. GESS2 will benefit from radio distributions by other major programmes such as the Global Partnership for Education (GPE) in response to COVID19 and therefore should influence the design of these programmes to ensure that they are reaching areas in need. CM efforts should be also be targeted towards areas not reached by radio.
  [note] GESS1 output one end line impact survey
COVID19 challenges and response:
Output one has been adapted to respond to COVID19. Staff and beneficiary safety to prevent the transmission of COVID19 has been prioritised by suspending all in-person training and CM activities. This has delayed disbursement of disability inclusion messaging under the ‘Our school’ initiative and training of CMs and Community Mobiliser Volunteers (CMVs), but webinars are now ongoing to help achieve midline targets. As restrictions ease, plans are in place to double the number of CM volunteers to deliver activities at a family level, mitigating the risk of spreading COVID19 amongst large groups. Output one has also been adapted to respond directly to COVID19, through creation of awareness raising public service announcements which disseminated COVID19 safe messaging; protection messaging; and promoted distanced learning in line with MoGEI initiatives.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
As this component will be fully implemented from year two, there is no data on which to assess VfM, however baseline data on spend broken down by State has been collected to inform future analysis.
Over the coming year it will be important to monitor the impact of COVID19, with costs associated with adapting public service announcements and producing webinars already exhausting parts of the output 1 budget. It will also be important to monitor the expansion of BCC and CM activities to children with disabilities, hard-to-reach areas (including considering language of instruction) and expand the role of women in the behaviour change dialogue to ensure effectiveness and equity.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Consideration of the long-term impact of the implementation challenges associated with COVID19 was analysed in a ‘medium-long term response strategy.’ It was agreed that no changes to logframe targets for Output 1 year 2 (March 2021) were required but that recognition should be given for additional COVID19 related activities.
Progress on recommendations from the previous AR
As outlined above, the programme has acted on recommendations from both the GESS1 PCR and the previous AR to extend influencing work on behaviour change to hard-to-reach communities and prioritise marginalised groups, in particular children with disabilities.

Lessons learned this year and recommendations for the year ahead:
- Equal access across genders: Access to BCC and CM for women is challenging as men predominantly control access to radios in the household and women are not always guaranteed a voice in community and family level discussions. While men are an important target audience for BCC, it is essential that women are enabled to be part of the debate in order to secure genuine and sustained change. To address this, GESS2, with influencing support from British Embassy Juba, should look to support radio stations to employ female presenters and ensure equal representation on GESS programmes. Similarly, GESS2 CMs and CMVs should have a good mix of males and females. Where possible, CMs should facilitate female only listening groups to ensure that women are given a voice in the behaviour change discourse.
- Mentoring/role models: Research has shown that mentors and role models who show girls the variety of life-options open to them can help reduce instances of teenage pregnancy and early forced marriage. GESS2 should look to develop a mentoring/role model communication strategy and align this with MoGEI’s new ‘girl’s education ambassadors’ initiative.
- Referral pathways: Based on evidence from similar crises, e.g. Ebola, there is a high likelihood that long-term school closures will lead to a spike in teenage pregnancy rates. FCDO should support linkage between GESS2 and the UK led Health Pooled Fund to support creation of effective referral pathways for girls to access sexual and reproductive health services.

Output Title	Cash transfers to girls to improve enrolment, retention, transition and completion rates.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Not set at last AR

Indicator(s)	Milestone(s) for this review	Progress
2.1 Cumulative number of (unique, individual) girls receiving cash transfers	315,000	Achieved: 374,127
2.2 Cumulative number of cash transfers received	315,000	Achieved: 398,499 (some learners were given cash transfers over two tranches)

Briefly describe the output’s activities and provide supporting narrative for the score.
GESS2 provides direct financial support to girls from Primary 5 (P5) – Senior 4 (S4) in the form of cash transfers (CTs). This intervention is designed to support enrolment, retention and completion of education by removing economic barriers which can force girls and their families to deprioritise education in favour of income generating activities. There is a cross-cutting benefit of this activity to both enrolment rates and as a mitigation against protection risks such as child marriage, teenage pregnancy and forced labour.

In 2019, GESS2-supported girls were provided an average of £11.24GBP per girl, conditional on a threshold level of attendance in school. Attendance was monitored daily at school level and uploaded onto the Schools’ Attendance Monitoring System (SAMS). This data was then verified by SAs ahead of disbursal. Funds were distributed by payment agents under monitoring from SAs and MoGEI officials. Building on lessons learned from GESS1, GESS2:
1. Allocated differentiated CT amounts to target classes with high drop-out rates, particularly from transition to secondary school (P8) and exam, or ‘candidate’, classes (P8 and S4). This aims to provide additional incentives for girls to sit exams and transition from primary school to secondary.
2. Piloted two tranche payments (August and November) for candidate classes to ensure that they receive scholastic materials at the beginning of the year but are incentivised to remain in school until they sit exams. Girls who were unable to receive their payments in tranche one due to insecurity or inaccessibility were also paid during the tranche 2 distribution.
As well as piloting these new approaches, output two exceeded year one targets for both the cumulative number of unique girls reached (119% against targets) and cumulative number of cash transfers received (127% against targets). This is the highest unique number of girls ever paid in a single year throughout GESS1 and 2.

This achievement can be attributed, in-part, to reaching new schools and returnees. However, the main driving factor was the corrective decision made by FCDO and MM to pay an additional class in 2019, accounting for an additional 96,305 girls, to make up for the missed payments in 2018, which occurred due to delayed procurement and subsequent delayed signing of the new contract for GESS2. It is recognised that, to achieve this, implementing partners carried out validation and payment of girls above the logframe target. However, it was agreed that for this decision to be cost neutral, P5 and P6 classes would be paid 50% of the full CT value. Therefore, we cannot attribute the same impact value to reaching the additional girls and, for this reason, this output has been scored an A rather than an A+.

Challenges/performance issues pre-COVID
1. Legacy of instability: Despite the high overall reach of CTs, States significantly affected by 2016 instability (primarily in the Greater Equatoria region) are still facing challenges with reopening schools, thus limiting GESS’ ability to disburse CTs to girls in this region. FCDO interventions both programmatically through GESS and influencing should focus on these areas.
2. Access: Payment agents continued to face issues with flooding and insecurity, limiting access to hard-to-reach areas. While CT payments are already planned to avoid expected seasonal disruption, recent changes to the length and severity of the rainy season should be considered. The multi-tranche payment approach which increases the chance of girls who missed out on tranche one receiving their CT should continue.
3. Value amount: The average value amount was reduced from a planned £16GBP average to £11.24GBP due to the decision to pay the additional class missed during the programme break in 2018, resulting in P5 and P6 classes only receiving 50% of the full CT amount. Most classes therefore received the equivalent of £16GBP, except for P5 and P6 who received the equivalent of £8GBP. In future, GESS should carry out a CT value amount assessment ahead of each distribution to determine the ideal value to achieve VfM.
4. Safeguarding: Safeguarding training for staff ahead of CT distribution and to ensure incidents are reported is continually being strengthened. GESS should continue to seek improvements and engage with both the Ministry of Finance and MoGEI on payment of teacher salaries to mitigate the risks of teacher-led extortion.

COVID19 challenges
Apart from disruptions to payment of 2019 Round 2 CTs to girls in Western Equatoria, COVID19 did not have a major impact on year one CT achievements. These girls had originally been missed because of the transition to a new SA. The plan was to pay them in tranche 1 2020 but schools closed shortly after the start of the 2020 academic year. These girls will now be paid during the 2020 CT distributions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Economy and efficiency: GESS2 demonstrated significant improvements across the board compared with GESS1 (baseline for comparison purposes). Achievements include: improving the value amount received by beneficiaries from 67% to 82% (3.5% below the five-year target); reducing administration costs from 33% of the total CT amount to 18% (4.5% above the five-year target), it is also important to note that more girls than ever before were reached with these administrative costs; and the proportion of costs not disbursed reduced from 33% to 18% (4.5% above the five-year target). Major cost savings were realised during the CT tender process which forced major price competition and resulted in savings on CT execution charges and leveraged preferential foreign exchange rates. Compared to the Bank of South Sudan’s indicative exchange rate, the programme made savings worth more than £1.3m in total. These savings were used to enhance the CT value amount girls were paid. Locking in these rates also transferred foreign exchange volatility risk to the Cooperative bank, who were the banking agent procured for 2019 payments. The missed targets can, in part, be explained by GESS not paying all eligible girls in 2019 (due to access issues) despite substantial investment of time and resource in completing the data checks prior to payment.

Effectiveness: As outlined previously, achievements at output level are translating into results at outcome level, demonstrating the effectiveness of CTs as a driver of enrolment. However, as the highest spending component of GESS, there is still a need to test the method for delivering CTs through a mid-line evaluation to ensure maximum effectiveness, in particular the effectiveness of CTs in supporting retention.

Equity: The non-discriminatory nature of cash transfers (as long as a girls are in school and regularly attending they will be eligible) is in line with the UK’s agenda to leave no-one behind. However, future reporting should be disaggregated by the number of children with disabilities accessing CTs to inform whether extra measures are needed to ensure equitable access.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The onset of COVID19 has been the major change to this output which will impact future year’s activities and targets. As a result of school closures, girls have become exposed to increased protection risks as household financial pressures push children into marriage which threaten their safety and re-enrolment when schools reopen. GESS2 will look at adapting the conditionality and value amount of CTs to respond to the crisis. This will have an impact on 2020/21 programme spend.

Previous Annual Review (AR) recommendations:
GESS2 has made mixed progress against previous AR recommendations. Good progress has been made on ‘strengthening SA capacity to communicate CT timings and the amount in a timely way to drive transparency and accountability.’ This has been done through CT orientation sessions with SAs and regular technical and management meetings with consortium partners to discuss implementation challenges. FCDO should monitor the following recommendations as they continue to cause issues which effect implementation:
1. Monitor the assumptions made about pupil dropout rates and consider consequences for the budget.
2. Rainy season to be considered where possible when deciding payment cycles.
Lessons learned and recommendations for the year ahead
Light-touch testing of CT value amounts ahead of each distribution allows the programme to respond to changes in beneficiary purchasing power driven by economic instability.
1. Following research on the scale and nature of disability in South Sudan, GESS2 should consider the viability of including boys with disabilities in CTs.
2. As the largest spending component under GESS2, a mid-line evaluation of CTs should take place to assess efficiency of delivery and effectiveness of CTs as a tool to increase enrolment.
3. GESS2 CT response to dropouts needs to be formalised. At present, SAs are encouraging girls who have dropped out midway through the year (e.g. due to teenage pregnancy) to re-enrol. The decision on whether to pay the girl is made by School Management Committees (SMCs) based on perceived commitment to return to school and commitment of the family to support the girls’ re-entry into education. A formal monitoring tool to track dropouts and a process for supporting re-enrolment should be developed.
4. The roll-out of a bio-metrics pilot should be prioritised as soon as possible to further improve accuracy of pupil validation and cash distribution.
Output Title	Capitation Grants to schools to improve learning environment for all learners.
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Not reviewed in last AR as logframe had not been finalised.

Indicator(s)	Milestone(s) for this review	Progress
3.1 Cumulative Number of Primary Schools that are approved for capitation grant payment by MoGEI/GOSS.	4,200	Achieved: 4,312
3.2 Cumulative Number of Primary Schools supported by GESS to receive Capitation Grants, value amounts paid by MoGEI/GOSS.	3,800	Achieved: 3,899
3.3 Cumulative Number of Secondary Schools that have received Capitation Grants by GESS (Schools that received Capitation Grants in GESS 1)	185	Achieved: 191
3.4 Cumulative Number of Secondary Schools that have received Capitation Grants by GESS for the first time/unique under GESS 2	45	Achieved: 48

Briefly describe the output’s activities and provide supporting narrative for the score.

GESS2 provides direct funding to schools in the form of capitation grants (CGs) to supplement resources and enable them to provide a conducive learning environment which is accessible to all.

CGs for primary schools are funded by the Government of South Sudan and GESS2 funds are used for secondary schools. All CGs are delivered and monitored using GESS systems. Grant size is based on the number of pupils per school calculated using attendance data from the SAMS system. 2019 CGs were disbursed in two tranches, the first tranche (70%) was disbursed subject to completion of a due diligence (approval) process which ensured schools were still operational, collecting accurate enrolment data and had established budgeting/spending procedures and management structures aligned to a school improvement plan. The second tranche (30%) was disbursed based on schools accounting for at least 80% of the first tranche. To ensure maximum accountability to the affected population, School Management Committees (SMCs), which include teachers, parents and community members, are responsible for deciding how CGs are spent and, with technical support from SAs, ensuring transparency over accounting.

All milestones for output 3 were exceeded. In total, during 2019 Tranche 1, 4,312 primary schools with enrolment in South Sudan were approved for CGs (around 95% of total schools in South Sudan and 1.2% above target) with 3,899 of those approved (90.4%) receiving payment. 1,355 primary schools were approved for tranche 2 CGs with 1,290 (95.2%) receiving payment. Schools which were initially approved but found to be non-operational during further due diligence were not paid, accounting for the mismatch in approved vs paid figures.

It is important to note that GESS is not in complete control of Primary School CG payments. GESS’ contribution to sub output 3.2 therefore should be recognised as influencing the Government to adequately budget for and disburse Primary Schools CGs and helping schools to qualify, utilise and account for CGs.

GESS both funds and facilitates CGs to secondary schools (sub-outputs 3.3 and 3.4). 288 secondary schools were approved for tranche 1 of which 239 (83%) were paid. Of the 239, 191 were paid previously in GESS1 exceeding the target by 6. This is still far below the baseline figure of 317, highlighting that a significant percentage of schools that were reached under GESS 1 are now not operational as they were affected by conflict from 2016 onwards. Where possible, the programme should continue to focus resources to assist these schools to reopen. 48 secondary schools were paid for the first time in GESS2, exceeding the target by 3 schools. Of the 239 secondary schools paid, 208 have accounted for at least 80% of the 2019 Tranche 1 funds they received.

Challenges/performance issues not related to COVID19:
1. Secondary school tranche 2: Despite exceeding the logframe targets for secondary schools, it is important to note that tranche 2 (remaining 30%) was not paid to any secondary schools. This was attributed to transitional challenges from GESS1 to GESS2 meaning that the programme did not start until the second half of the year hindering the ability to carry out two due diligence processes.
2. Withholding funds: Some State-level Ministries continue to withhold funds from Primary Schools who previously were unable to account for spend, sometimes for reasons beyond their control. While funds are still being held, schools are unable to receive future payments as the same channel will be used for future tranches. At present, approx. South Sudanese Pounds (SSP) 32m (approx. £200,000) is still being held and changes in configuration of States has reduced the possibility of seeing these funds released. This is a twofold challenge: firstly, as costs have already been incurred by GESS2 in approving schools for CGs and transporting the money; secondly, these primary schools are missing out on much needed funding. It may be necessary for GESS to engage with MoGEI to re-consider conditions of accountability of funds that were held under previous administrations in order not to undermine future distributions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Economy and efficiency: The proportion of unit cost which is dedicated to administration and therefore not disbursed improved since GESS1 (the GESS2 baseline) from 27% to 14.5%. Government payment of CGs to primary schools is a key driver for both economy and efficiency of this programme and it is a major success that, despite disbursement and budgetary challenges, the £4.8m in CGs disbursed in 2019 is the highest payment ever made by the Government in any year. In the coming year it will be important to monitor costs associated with transporting money. These costs are likely to increase as GESS2 aims to reach more remote schools and inflation continues to rise as a result of COVID19.

Effectiveness: Output level achievements are translating into results at outcome level indicating the effectiveness of CGs as a driver of enrolment and attainment. The Education Transfer Monitoring Committee (ETMC) have increased the primary school CG value amounts for academic year 2020 to 43,000 SSP (£260) per school and 500 SSP (£3) per learner in response to inflation and to therefore maintain effectiveness. GESS2 should consider whether a similar approach is needed for senior school CGs.
Development of a School Budget Plan (SBP) tool has supported improvements in tracking and managing budgets increasing both the efficiency and effectiveness of due diligence processes.

Equity: All schools which meet the qualification criteria are eligible to receive CGs. In order to prevent risk of tensions arising around CGs, it is important to ensure clear communication on how decisions are made about eligibility, how funds are spent and to ensure the SMCs are responsible and transparent in how they spend the funds. The primary equity issue is that schools often most in need of CGs, e.g. those in poor, unstable or hard to reach areas, struggle to meet the eligibility criteria for receiving CGs as a result of their situation. This increases the equity divide for marginalised children. SAs should be supported to build the capacity of schools to meet the criteria and consideration should be given to adapting minimum standards for new schools or schools recovering from a period of closure due to instability to support their reopening. In addition, schools receiving CGs should be supported to carry out infrastructure assessments on accessibility to children with disability and utilise funding to make necessary improvements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Though not directly impacting logframe figures for this review period, COVID19 will have a major impact on 2020 CG distributions. Due to school closures, tranche 1 approval targets will not be met, delaying distribution once schools reopen. There is also uncertainty around the Government’s ability to meet the demand given pressures on the budget as a result of COVID19.Given the essential role that CGs will play supporting schools to meet COVID19 safe regulations and therefore reopen, both FCDO and GESS should consider allocating additional resources to support SAs to fast track the approvals and distributions process and continue to lobby the Government on the prioritisation of education spend and cash transfer disbursal.

Progress on recommendations from the previous AR,
Progress has been good. GESS has exceeded targets on CGs to new schools not reached under GESS1; additional due diligence has taken place between CG approvals and payments which has served to remove closed schools from eligibility lists; and SAs have received training to oversee accurate and timely school accounting for CGs which can meet due diligence requirements.

Lessons learned this year and recommendations for the year ahead
1. GESS and MoGEI should develop a strategy to support schools, especially new schools or those recovering from previous closures, to reach the minimum standard, either through mentoring or graduated financing.
2. Consideration should be given to adapting the mechanism for distributing of CGs to primary schools as GESS is investing significant funds in transferring CGs to State Ministry of Finance Offices which is then not disbursed to schools. FCDO and GESS, in collaboration with MoGEI, should consider streamlining this process by facilitating direct payment from the Ministry of Finance to schools.
3. Schools should be supported to undertake an infrastructural assessment to consider needs of children with disability and to use CG funds to make infrastructure improvements which are gender sensitive and integrate universal design principles to ensure that no child is left behind. CG reporting should then also include data on schools making disability focused improvements.

Output Title	Learning Groups, Quality Education and Resilience
Output number		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Cumulative number of teachers who participated in training, including training on gender-responsive and inclusive teaching methods.	N/A	Sub-output 4.1 will be measured at midline in 2021.
4.2 Number of learners in primary Accelerated Learning Programme (ALP).	N/A	Sub-output 4.2 will be measured at midline in 2021.
4.3 Number of learners in Accelerated Secondary Education.	N/A	Sub-output 4.3 will be measured at midline in 2021.
4.4 Number of learners participating in mentoring programme.	N/A	Sub-output 4.4 will be measured at midline in 2021.
4.5 Number of school management committees (SMCs) trained.	N/A	Sub-output 4.5 will be measured at midline in 2021.
4.6 Cumulative number of education management staff trained.	N/A	Sub-output 4.6 will be measured at midline in 2021.
4.7 Cumulative number of Payam Education Supervisors (PES) trained on supportive supervision	N/A	Sub-output 4.7 will be measured at midline in 2021.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 seeks to improve the quality of teaching in South Sudan to boost attainment and retention rates, especially amongst girls. The approach, developed in close coordination with MoGEI, seeks to overcome challenges undermining quality such as overcrowding, limited teaching materials, a lack of official qualifications amongst teachers and limited in-service teacher professional development opportunities. These challenges result in little interaction between learners and teachers. Output 4 seeks to overcome these challenges by:

1. Scaling up the teacher professional development training programme (piloted under GESS 1) with the aim of improving pedagogical skills by training more primary school teachers through blended learning approaches, peer-support and continuous self-learning.
2. Supporting Alternative Education System through provision of capitation grants, cash transfers and schemes of work to the ALP programmes, and establishment of Accelerated Secondary Education Programme (ASEP) for teachers, operationalising 50 Accelerated Secondary Education Centres and implementing intensive English course for teachers registered in ASEP. This will support a higher quality in primary teaching; increase the number of teachers meeting the minimum requirements for teacher qualification courses; and a larger number of teachers who qualify for payroll enrolment.
3. Implementation of Mentoring Programme, establishing mentoring clubs in both primary and secondary schools, with the aim of inspiring and empowering learners, especially girls, to continue their education successfully transit to secondary education, fulfil their potential and contribute to the development of their communities.
4. Training of SMCs and Boards of Governors (BoGs) to lead school development processes, qualify and account for the Capitation Grants and leads schools towards meeting the minimum standards.
5. Training of Education Managers and Payam (district) Education Supervisors to equip them with the practical skills to support schools to meet the minimum standards, become more inclusive and transparently use school funds (including CGs).
Quantitative data was not collected on output four in this reporting period as activities were focused on laying the foundations for future years. For the purpose of this review, this output will be assessed against the following objectives which are in line with recommendations in the GESS 1 Programme Completion Review, were agreed under the 2019/2020 work plan and signal a readiness to deliver results in future years.

1. Design of expanded Teacher Professional Development (TPD) strategy, including training teachers to work with children with disabilities.
2. Collaborating with MoGEI on prioritisation of accelerated learning as part of the national curriculum.
3. Contribute to the design of the revised in-service and pre-service teacher training course aligned with the new curriculum
4. Train secondary school teachers to act as tutors/facilitators of Accelerated Secondary Education for primary school teachers.
5. Design and implement mentor guides at both primary and secondary levels.
6. Design and implement training for SMC/BoG and train Payam Education supervisors on supportive supervision.
GESS 2 performed well against objectives aside from minor delays linked to COVID19:

1. Mott MacDonald (MM) and the UK agreed on expansion of TPD to more schools using Canadian funding and the TPD strategy from GESS1 was revised in order to achieve better value for money by focusing on school-based in-service training delivered at SA level.
2. Following engagement between MoGEI and MM, the revised primary Accelerated Learning Programme (ALP) is aligned with the new South Sudan Curriculum. In response to COVID19, the revised Alternative Education Programme was quality assured and is now being used to run the distance learning programme supported by Ministry of General Education and Instruction (MoGEI)
3. Pre- COVID19, GESS, in collaboration with State Ministries of Education trained 10 Master Trainers to teach in 20 ALP centres and registered 655 teachers (400 male/255 female) for Alternative Secondary Education.
4. GESS2 mentoring programme was developed, the work plan finalised, and targets discussed and agreed with SA Management for implementation once schools re-open.
5. Review of materials for training effective school governance completed and shared with MoGEI and partners implementing training for SMCs and BoGs. Monitoring and reporting format for Payam supervisors on distribution and retrieval of school financial reports and school registers was designed, explained to the SAs and introduced for implementation.
Challenges/ performance issues (Pre-covid)
- Lengthy discussions between FCDO and MM on the use of Canadian funding for GESS2 on school-based TPD led to delays in implementation. A final proposal which scales up TPD and will drive learning outcomes results at impact level has now been agreed.
- Limited distribution of new textbooks and unavailability of the new curriculum has hindered improvement of teaching standards. FCDO are engaging with the Global Partnership for Education on textbook distribution and will lobby MoGEI on publication of the new curriculum online.
- The formation of the MoGEI Technical Working Group on School Governance is still outstanding. Continuous follow up meetings with MoGEI are needed to re-establish the TWG.
Challenges related to COVID19
School closures resulting from COVID19 will necessitate a review of the TPD Implementation Plan, Mentoring Strategy and Effective School Governance strategy to ensure they are fit for purpose and allow to achieve results despite COVID-19 school closure.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
As this component will be fully implemented from year two, there is no data on which to assess VfM. However, it is already becoming clear that quality assurance and training teachers to support children with disabilities will be essential VfM criteria. It is recommended that criteria are agreed early in year 2.

Progress on recommendation from the previous Annual Review
The last Annual Review didn’t cover the quality component as no activities were underway.

Lessons learned this year and recommendations for the year ahead:
- To ensure sustainability of this output and avoid duplication, synergies should be built between GESS and MoGEI on all activities related to teacher professional development.
- TPD Implementation Plan, Mentoring Strategy and School Governance Strategy should be reviewed in light of COVID-19.
- GESS should prioritise recruitment of the Gender and Mentoring Advisor.
- GESS should ensure that inclusivity, especially of children with disabilities, is mainstreamed across all training delivered to both teachers and school governance groups.
Output Title	Knowledge, Evidence, Research and Learning (KERL) to build a knowledge base for support to girls education
Output number		5	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for the review	Progress
5.1 Number of research and evaluation studies conducted for GESS2.	2	Achieved: 0 / Two research studies were undertaken by March 2020 but failed to meet the required standard to draw conclusions and inform future decision making.
5.2 % of schools reporting regular attendance through SAMS.	35%	Achieved: 55% of schools reported regular attendance five or more times in 2019, exceeding target.
5.3 Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG).	8	Partially met. A total of 7 KERL TWG meetings were held in year one missing March 31, 2020 by a very small margin. One meeting not held due to COVID-19 restrictions.

Briefly describe the output’s activities and provide supporting narrative for the score
Output five is a blend of two activities which have cross cutting benefits for the broader programme:
Research: GESS 2 will generate evidence to inform programme structure and decision-making over the life of the programme. 17 research studies over five-years will cover a range of topics relevant to all outputs with the findings being discussed with MoGEI during technical working group meetings in order to inform broader education sector development.

Attendance monitoring: Schools report attendance through the School Attendance Monitoring System (SAMS). Data from this system is used to inform other activities under GESS such as CT and CG distribution and informs outcome and impact level results. GESS provides schools with training in the use of the SAMS system.

The following progress was identified during the reporting period across the sub-outputs:

5.1: Two research studies were completed and submitted by March 2020.The first research study examined the minimum monetary value threshold for a CTs, efficiency of double tranche payments and the feasibility of applying a biometric approach to the accountability. The second research study, implemented by Leonard Cheshire (LC), with support from the Knowledge Evidence Research and Learning (KERL) team, was a scoping study on disability inclusion in the GESS2 programme. The CT study had severe methodological limitations which undermined the representativeness of sampling data while the disability study did not provide sufficient information from which to draw conclusions on key areas such as opportunities for influencing policy making, adaptations to the programme and interlinkages with other programmes operating in this space. GESS could, therefore, not use these studies as an evidence base on which to make any decisions. The CT research will be repeated with a longer lead in time and with greater communication between FCDO, MM and Montrose. The disability and inclusion study will be developed further. MM and Montrose have also bolstered staffing capacity on the research component.

5.2: The year one target for attendance monitoring was exceeded and a successful handover of the South Sudan Attendance Monitoring System to MoGEI is on track with technical support from the MM team.

5.3: The target was partially met as seven out of the eight target KERL TWG meetings were held in year one. This constitutes 88% of the target. The final meeting was unable to take place due to COVID19 restrictions and was outside the programme’s control.

Challenges, including COVID19
- Delays in contracting SA reduced capacity to support with research fieldwork, reducing data collection and contributing to under performance on sub output 5.1. This challenge was exacerbated by flooding and inter-communal fighting in some areas, affecting SA ability to collect representative data.
- Despite the majority of TWGs taking place, their limited efficacy contributed to a communication gap which delayed approvals of research designs and tightened the timeframes under which research was undertaken. The eighth meeting was not conducted as scheduled due to COVID19 restrictions.
- Three states (Lakes, Eastern Equatoria and Western Equatoria) didn’t meet the attendance reporting target (35% for year 1). The underperformance was due to insecurity caused by communal conflicts which made access to the communities difficult.
Assess the VFM of this output compared to the preposition in the Business Case, based on performance over the past years.
No VfM indicators were set for research studies. However, given the ongoing challenges, especially effectiveness and ensuring equitable participation in research studies, it is recommended that FCDO, MM and LC agree indicators for assessment in future years. The below is a VfM assessment on output 5.2:

Economy: The overall cost-per-school reporting attendance has fallen from £968.77 in GESS-1 to £258.15 in 2019. However, given that this compares the average programme period under GESS1 against GESS2 year one achievement, it is helpful to mention that in 2014 (GESS1 year 1) this stood at £2,082. This shows that the programming is on the right trajectory to achieve value for money.

Efficiency: The achievement of 55% of schools reporting attendance at a cost per school of £258.15 represents good efficiency (£4.70 per % point). This can be compared to £968.77 with 85% of schools reporting in the final year of GESS-1 (£11.40 per % point). The reason for the decrease in schools reporting can be attributed to deterioration of mobile network in South Sudan rather than a decrease in investment from GESS. This was reflected in the 35% target for year 1.

Effectiveness: The effectiveness of SAMS is twofold. Firstly, it is a necessary tool for the effective management of cash transfers and capitation grants, both of which have been rolled out at national scale for the two rounds of payment in 2019/2020. Secondly, the system is increasingly becoming the major data source in the education sector, shaping sector management and reform beyond GESS.

Equity: Support to schools in the use of SAMS is being rolled out nationwide irrespective of location. County-by-county analysis demonstrating the equal distribution of SAMs can be viewed on https://sssams.org/sbrt/equitytable.php?year=2019 .

Progress since the last Annual Review
There were no recommendations made during the last AR as this component was not yet underway.

Lessons identified this year and recommendations for year 2.
- To ensure quality research i) a research agenda, based on donor and MoGEI priorities, programme needs and learning gaps, should be agreed at the start of each reporting period ii) sufficient time and staffing should be dedicated to research data collection, analysis and reporting iii) regular coordination meetings between FCDO, MM and Montrose should be implemented to streamline approval and review processes and provide necessary oversight on methodology.
- Quality as well as quantity of TWGs are essential to ensure their effectiveness as a coordination mechanism. MM and Montrose should establish criteria for joining TWGs and keep the membership at the minimum level for effective collaboration. Research findings shared with the TWG should also be disseminated amongst education donors via to the EDoG to avoid duplication activities.
- MM should explore remote learning options to support SAMS participation in areas of instability, especially as updates to the system are rolled out.
D: RISK

The overall risk rating for the GESS programme is Major, which is largely due to the challenging context in which it operates and the implications this has on effective programme delivery. Risk mitigation measures are captured below.

Context: With increased instability and inter-communal violence, GESS continually monitors the security situation and has enhanced procedures in place around potential flashpoints (e.g. around key dates related to the formation of the transitional government).

Delivery: FCDO continues to engage with other donors and advocate at the highest levels of Government for increased resources for education. In the absence of a reliable Government salary, continued support to teachers (currently provided through the EU’s Impact programme) is vital to avoid strikes and school closures. As the Impact programme nears its end, FCDO is working with other donors and the Government to ensure a responsible exit plan is in place. GESS will continue to adapt to the consequences of COVID through distanced learning (DL) and maintaining student engagement whilst schools are shut. Drawing lessons learned from DL efforts during current school closures will be essential for this. In response to hyperinflation and fluctuating exchange rates, GESS also continue to engage with the banking agents to drive VfM in the rates they secure and maximise the value of the CTs received by the girls.

Fiduciary: GESS has tight control procedures in place at SA level and GESS HQ, to ensure robust oversight over finances. There is regular engagement between FCDO, GESS and MoGEI on the importance of protecting girls who receive CTs and that theft of CT amounts will not be tolerated.

Safeguarding: Safeguarding for all children receiving GESS2 support is a priority. Mitigations and progress on safeguards within the programme are explored further in the next section.

Risk Management
Mott MacDonald has a risk management plan in place which aligns with the conflict sensitivity approach. Risk monitoring is embedded throughout the programme to capture both the risk the context presents to programme delivery and the risks the programme can create in the context, if not managed effectively. Key tools used include a centrally held MM risk register which is shared with FCDO on a monthly basis, heat mapping to identify conflict risk areas across the country, a delivery chain risk map which is updated and shared with FCDO quarterly and an incident tracker capturing any issues identified throughout the reporting period. Risk management and oversight will be further strengthened by the introduction of third party monitoring this year.

COVID19 Implications
It is our assessment that COVID19 will exacerbate almost all risks to the programme, most crucially the risk that school closures as a result of COVID19 will negatively affect educational outcomes for children in the absence of a decent alternative through distance learning and; prolonged school closure could lead to children not returning to education because of long breaks in the formal system. The disruption to education will also significantly increase the protection risk considerations for the programme, as it will expose children to risk of child labour, increased teenage pregnancies, early marriage, sexual exploitation and abuse when the safe space of the school is closed. FCDO is heavily engaged with the Government to support school re-opening plans. Programme monitoring has been maintained and issues and cases continue to be quickly reported and investigated.

Recommendations:
1. FCDO continue to prioritise engagement with the MoGEI regarding teacher salary payment, and ensure the programme remains alert and adaptive to the risk of teacher strikes.
2. FCDO to review the programme risk register with GESS considering COVID19 to ensure alignment on key risks and mitigations.
Update on Partnership Principles
As with other DFID South Sudan programmes, there are no specific conditionality requirements linked to this programme, as it does not channel funds directly to or through the partner government.

The GESS2 programme does however seek to work with and support the Government in a number of ways in order to build capacity of both the national and state ministries and encourage sustainability of the interventions. These include, but are not limited, to:
- The establishment of the Steering Committee meeting at national level which is co-chaired by the MoGEI and FCDO. GESS2 also plans to support the Government with co-ordination at State level through the State Education Transfer Monitoring Committees (ETMC). These platforms look to promote transparency and accountability within the education sector as well as to encourage Government involvement and oversight over the GESS2 programme.
- Supporting technical assistance and supervisory visits by National and State Ministries (funds are only to cover travel expenses and are not channelled through Government).
- Providing capacity building and training of local Education Officials, School Management Committees (SMC’s) and Boards of Governors (BoGs).

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Cross Cutting Programme Delivery Components

Safeguarding
Setting standards and expectations among GESS partners in terms of behaviour and procedures around safeguarding has been a key priority for the first year of the programme, with intensive engagement with SAs to raise awareness around identification, reporting, monitoring and escalation of safeguarding incidents.

Progress has been made in year one to mainstream safeguarding considerations through all programme outputs. Key achievements include:
1. Adaptations made to CT messaging and practices following a risk assessment to strengthen safeguards. This included changes to the way in which communication was rolled out and adaptation to the procedures for all stakeholders involved in the payment process.
2. Safeguarding training for all GESS consortium partner (CP) and SA staff.
3. GESS have also raised the profile of safeguarding issues with MoGEI, who have been supportive in reinforcing programme messages on the importance of beneficiary safety.
There have been significant improvements to reporting practices over the year, indicating a solid understanding on the ground by SA staff and the positive results from early training and capacity building efforts. Activity in year two will seek to build upon progress made so far and further systematise reporting and identification of issues, continue to roll out training for all programme stakeholders (including the integration of safeguarding to teacher training) and will also to seek to address the wider protection risk to girls and the impact that violence and trauma can have on girls and their educational outcomes.

Recommendations:
1. When schools reopen, ensure that safeguarding systems, such as reporting mechanisms, are operational within the school system.
2. Seek opportunities to co-ordinate with donors and other partners on safeguarding training for teachers through the gender TWG and protection cluster. Consider opportunities for linking up with the UK centrally led, multi donor Safe to Learn programme (aimed at tackling violence against children) to maximise resources.
3. Improve co-ordination with MoGEI on safeguarding policy through the implementation of a joint safeguarding strategy.

Conflict Sensitivity
The focus for GESS in year one has been embedding a conflict sensitive approach in all interventions and setting up systems to monitor this. In the reporting period, GESS has developed a strategy for integration of conflict sensitivity into risk management across all components, has rolled out essential training for the new SAs and developed a heat map to monitor contextual changes which could present risks to programme delivery. The dedicated CS adviser works across all interventions advising on design and delivery to ensure a conflict sensitive approach is maintained and to identify potential risk areas requiring management.

Year 2 will be focussed on enhancing the training for the SAs to better embed an understanding across the programme in managing equity challenges. This will include a focus on training teachers and head teachers on their role in supporting peace and stability in communities, as well as SMCs in their role in promoting transparency and integrity.

Recommendation: To develop the use of the heat map to more effectively monitor displaced populations and those affected by shocks in context (eg. flooding) which have resulted in wide-scale dropouts. Explore ways the SAs can be more responsive to these populations through existing community mobilisation activity and to support to girls when they re-enrol in new schools to be eligible for CTs.

Gender Sensitivity
Gender considerations are mainstreamed throughout the programme outputs as the focus of GESS2 is to improve educational outcomes for girls and address the gender disparity in the education system in South Sudan. As an example, prior to COVID-19, 67% of primary school aged girls in South Sudan were out of school, compared with 58% of boys. The programme aims to address and tackle challenges which disproportionally effect girls in South Sudan, including both cultural and financial barriers to sending girls to school. A lower value is generally placed on educating girls, resulting in early marriage, teenage pregnancies and child labour practices which prevent girls from enrolling and regularly attending. These risks are exacerbated significantly by COVID19 implications and so the programme needs to remain responsive to tackling emerging or escalating risks to girls and address new problems as they arise.
[note] UNESCO, 2020 https://tellmaps.com/uis/oosc/#!/profile/WORLD/SSD

Despite the programme focus on girls, boys also benefit from the programme through the CGs which improve the learning environment for all children; and through the quality component which will increase the quality of teaching in schools, once activities have started. However, the programme’s focus (especially around the CTs) can create tension between boys and girls and the wider community, which the programme works to mitigate through education and effective communication through the behaviour change communication component. It is also important that GESS, alongside MoGEI, maintains and develops strong programme level communication reiterating the scope of the programme (highlighting that boys do benefit) but to also effectively communicate the greater need for support of girls in South Sudan.

Recommendation to explore entry points for addressing sexual and reproductive health in the programme through either output 1 (community outreach) or 4 (mentoring clubs) to support girls and boys to make more informed decisions about when to have children and increase their chances of completing secondary education.

Disability Inclusion
The lead consortium partner for disability inclusion (Leonard Cheshire - LC) have focussed this year on developing a mainstreamed approach to disability inclusion throughout the programme. They have co-ordinated across the outputs to ensure systems are in place ready for full implementation. They have rolled out a number of trainings and workshops to introduce the strategy for inclusive education and disability rights and participated in the training of the new SAs in January 2020. A focal persons network has been established with SA representatives from all states.

Areas of focus for year one have been providing technical advice to ensure communications are accessible for those with disabilities/hearing impaired; improving data collection on those with disabilities to inform programming (including improved identification of those with a disability); adapting existing infrastructure assessment tools on school accessibility to incorporate universal design principles, and; engaging on integrating inclusive education modules into teacher training. The focus for year 2 will be to start the actual implementation of activities agreed during these initial conversations. However, this will need to be supported and evidenced by further research into disability inclusion issues in South Sudan to better understand which interventions are possible, contextually appropriate and impactful. LC and all GESS partners will also step up engagement with MoGEI in order to support the drafting and approval of an inclusive education policy at national level.

Accountability
Achievements in this area which provide a good foundation for ensuring improved citizen participation, transparency and accountability include:
1. Strong communications plans, including State Anchor appearances on local radio and partnerships with State Ministries of Education.
2. Beginning to operationalise and support various governance mechanisms including School Management Committees, Payam Education Supervisors and Education Transfer Monitoring Committees (ETMC) which provide a good foundation for accountability and transparency with which to operate and build capacity.

Recommendations:
GESS 2 is well positioned to use existing entry points to improve transparency and accountability of the programme and the education sector more widely, specifically, under outputs 1.1, 1.2, 4.5 and 4.6:
1. GESS should seek to ensure that programme stakeholders (e.g. beneficiaries, parents and teachers)have a clear understanding of their rights as participants in the programme and are more able to constructively engage with service providers (donors, implementers, MoGEI) through effective feedback loops put in place. This will help empower them to participate effectively, challenge any wrongdoing and hold those in charge of service provision (donors, implementers, MoGEI) to account.
2. GESS together with FCDO should identify how to improve Government capacity, accountability and transparency in service delivery and promote a culture of willingness to listen and respond to beneficiary feedback, particularly at state level through capacity building activities.

The performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Procurement
The GESS1 SAs were contracted to deliver the inception phase of the GESS2 programme to bridge the period before GESS2 could contract new SAs. New SAs were due to take over from 1st November 2019, however this process was delayed by two months in order to provide the programme with stability amid political uncertainty related to the planned formation of the new Transitional Government of National Unity whilst paying the second tranche of CTs. The procurement of new SAs was conducted twice because three states were not successful the first time. Following a second procurement round, the new SAs took over in January 2020 and all but one had all signed their contracts as of March 2020.

In States where there was a changeover of SAs, the process was well managed to ensure a smooth transition with State Ministries of Education with no issues reported. However due to the initial delay in running the tender process and then having to re-tender three states, implementation has been delayed, particularly affecting outputs 1 and 4. To make up for delays, SA cost savings have been used to recruit more staff to recover lost time, e.g. CMVs have been added to output 1 and certain targets have been moved to year two.

Contract Management
The GESS2 contract was awarded to Mott in May 2019. Following an inception period, the implementation phase began in August 2019. Contractually, Mott provides DFID with timely monthly, quarterly and annual narrative reports. In rare instances where a report is delayed, Mott notifies the FCDO. On receipt of these reports, FCDO provides comments to Mott before the report is finalised. The Fund Manager met all year-one contractual milestone deliverables satisfactorily including on-boarding of all the three Consortium and seven State Anchor partners through various planning activities; recruiting of key positions; contract/agreement signing; year-one work planning; induction and orientation of all State Anchors in January 2020; SAMS handover to MoGEI; and commencement of other programme activities.
It is recommended that consideration is given to the volume of reporting required and FCDO feedback issued in order manage the demand on MM’s time. In turn, MM should seek to continuously improve the quality and accuracy of reporting.

Commercial
Since the announcement of the additional £8.8m of funding from Canada, the UK and MM have been heavily engaged in negotiations on the best use of the funds. Now the use of these funds has been agreed, negotiations are currently ongoing to agree how the contract will be amended to incorporate the additional money whilst still maintaining VfM on programme delivery versus the original contract.
In addition to the incorporation of these funds, additional changes to be included in the amendment are:
1. Changes to key personnel listed in the contract.
2. Cost neutral changes to fund manager costs to reflect changes during inception.
3. Movement of some funds from grant monies to the fund manager element of the contract following discussions with DFID commercial department.

Financial performance
Funding methodology: Payment to Mott for cash transfers is made ‘just in time’ for onward submission to the payment agent, while the remainder of programme activities is made in arrears based on a monthly forecast. Mott is required to account for the disbursed funds as part of their quarterly reporting.

Assessment: During the period under review, the programme expenditure for all the outputs was lower than the initially approved forecast by £369,048 a variance of 5%. This was attributed to a) slow opening of schools which affected the beginning of data entry as data clerk costs are the main driver under output 5; b) the delayed recruitment of SAs and c) CG tranche 2 payment was not paid. Despite the above challenges, the UK has spent a total of £6,921,359 this year and since the start of the programme has spent 13.6% (£9,565,885) of the total £70m which is in line with expectations. Mott is still on track to fully spend the budget by March 2024.

Audit
Mott are currently finalising their audit report for the period covering May 2019 – March 2020. The audit which is based on the UK’s financial year will be shared with FCDO in September 2020.

Value for Money
The business case did not set VfM metrics. However, VfM indicators were developed as part of the inception phase deliverables and these have been explained in detailed under each of the outputs in section C above. Overall, the programme continues to demonstrate value for money. Programme costs are within budget and major savings were realised in areas such as CTs, giving the programme flexibility to respond to changes in operating context and level of need. The programme has met targets on time across the majority of impact, outcome and output indicators, demonstrating effectiveness and efficiency of UK spend in driving up attainment and enrolment rates amongst girls. The programme continues to drive equity as a core principle, however a deeper understanding of access issues for children with disabilities is needed in order to ensure that no child is left behind. Activities in this area are planned for year two.

Recommendations:
1. For a more complete equity picture, data on enrolment by grade and progression should be collected. Analysis on children who drop out from school to identify barriers to their continued education would inform decision making on the distribution of programme resources address these barriers and ensure no-one is left behind.
2. The current GESS VfM strategy and framework should be reviewed to set out VfM indicators for the next year.

Monitoring
In addition to those mechanisms outlined under output 5, GESS has been successful in setting up monitoring mechanisms in partnership with MoGEI during the first year of implementation, including the re-establishment of the quarterly meeting of the GESS Steering Committee (co-chaired by MoGEI and FCDO) as an important forum for engaging MoGEI on key issues. GESS and MoGEI visited 690 primary and 107 secondary schools to assess the adherence of COVID-19 protocols, safeguarding and verification of individual girls in the 2020 tranche 1 payment. Joint monitoring field visits were also carried out with FCDO and used to verify that GESS activities are progressing in line with the workplan and get beneficiary feedback on the implementation of the programme.

FCDO has earmarked budget for third-party monitoring to enhance scrutiny of the programme across all ten States. The contract should be in place by mid-autumn 2020. An evaluation of the effectiveness of CTs on increased enrolment is also in the pipeline. This will be assessed in the next annual review.

Learning
Two research studies aimed at i) exploring the minimum monetary value threshold for a CT, efficacy of double tranche payments of CTs and the feasibility of applying a biometric approach to the accountability of CTs in South Sudan and ii) scoping disability inclusion in GESS, were finalised in the reporting period. However, due to the limited methodology used in these researches, FCDO will not use this research studies for the intervention areas. Next steps on research and learning have been outlined under Output 5.

Progress on recommendations from previous review
See Annex 3 for a full list of progress against recommendations on both output delivery and programme management from GESS 1 PCR and GESS2 AR 2019.

Asset Management
The fund manager has maintained the asset register that was rolled over from GESS1 and was last updated in July 2020. 450 assets from the closed GESS1 programme were transferred to GESS2.

DFID undertook a physical verification of assets in October 2019 (in one of the ten states) and further verification will take place once the COVID19 travel restrictions have been lifted. The spot check for GESS assets (vehicles, generators, motor bikes, computers) in Wau were successful. The vehicles used by the SA were well maintained. The vehicles had tracking systems installed, logbooks for monitoring movements, valid insurance and were well branded, in line with FCDO branding guidelines.

Compliance
Delivery against contract KPIs, and Terms and Conditions: Contractual KPIs were not formally assessed in year 1 as negotiations took place between the UK and Mott to agree assessment criteria. Formal assessment started from April FY 20/21 with assessment taking place on a monthly basis as an interim measure.

Compliance with the Supply Partner Code, drawing on advice from PCD: Mott are 100% compliant with the code and have moved all their corporate assessment documentation onto the InSPIRE platform.

Compliance with the new cost and transparency requirements, highlighting any profit variance and challenge and use of Open Book Accounting: Mott have reported against all new cost and transparency requirements including against financial accounting, tax compliance, IATI, conflicts of interest, appointment rules and all areas of the Code) They have also submitted their profit declarations.

Performance of Partners, including summary of the SRM scorecard assessment for each delivery partner: The last SRM scorecard was completed for Mott relates to the period of 1 July 2018 – 31 Dec 2018.  The scorecard process resumed in February 2020 but this was paused prior to Mott having the opportunity to participate.

Date of last narrative financial report	Final version of the Annual report submitted on 7/8/20	Date of last audited annual statement	N/A – first audited annual statement due to be submitted in September 2020

Annex 1. GESS Theory of Change

Accelerated educational attainment for girls’ and boys’.
Accelerated gains in girls’ enrolment (particularly secondary).
Reduced barriers and equitable access to education for all children
£70m
Input
Provide a source of stability and continue the work to transform the life chances of South Sudanese children, particularly girls, through education

Annex 2: Impact and Outcome Indicators
IMPACT INDICATORS
Impact Indicator 1		Baseline 2018 (March 2019)	Milestone (March 2020)
Gender Parity Index (GPI) for primary schools (%boys>girls (1:1) (Per Year)	Planned	0.87	0.84
	Achieved		0.83
Impact Indicator 2		Baseline 2018 (March 2019)	Milestone (March 2020)
Gender Parity Index (GPI) for secondary schools (%boys>girls (1:1)) (Per Year)	Planned	0.65	0.64
	Achieved		0.63
Impact Indicator 3		Baseline 2018 (March 2019)	Milestone (March 2020)
Total Number of children enrolled in schools (Annually - Academic Year)	Planned	1,784,664	2,088,057
	Achieved		2,186,024
OUTCOME INDICATORS
Outcome Indicator 1		Baseline 2018 PLE	Milestone (March 2020)
% of girls passing Primary Leaving Examination (PLE)	Planned	76.27%	77.50%
	Achieved		84.90%
Outcome Indicator 2		Baseline 2018 SSCSE	Milestone (March 2020)
% of girls passing South Sudan Certificate of Secondary Education (SSCSE)	Planned	76.3%	73.40%
	Achieved		93.20%
Outcome Indicator 3		Baseline 2018 (March 2019)	Milestone (December 2019)
Number of girls enrolled in upper primary (P5-P8)	Planned	298,220	330,087
	Achieved		344,635
Outcome Indicator 4		Baseline 2018 (March 2019)	Milestone (December 2019)
Number of girls enrolled in secondary schools (S1-S4)	Planned	36,555	39,202
	Achieved		44,544
Outcome Indicator 5		Baseline 2018 (March 2019)	Milestone (March 2020)
% of teachers demonstrating inclusive practices during lessons	Planned	218 head teachers and 1918 teachers in 218 schools.	N/A
	Achieved		N/A

Annex 3: Progress on recommendations from GESS 1 PCR and GESS2 AR 2019
DFID Programme Completion Review 2018/Annual Review 2019
Implemented the recommendation as Proposed			3
Implementation of this recommendation ongoing			3
Implementation of this recommendation is yet to take place			10
	High Priority Recommendations	STATUS SUMMARY
1	DFID South Sudan to work with appointed GESS2 Lead Supplier/Consortium in the Inception Phase to assess the optimal timing for payment of CTs, to deliver the best outcomes in terms of registration, retention, and contribute to educational outcomes.	Available evidence from phase one is that CTs are required early in the academic year (AY) when girls need the resources to buy essential items. However, considering the rate of dropout it was agreed to have multi-tranche payments to ensure early payment in the AY, at the same time incentivise retention as girls wait for the second tranche. For this to be feasible, GESS is ready to pilot and roll out biometric solution as soon as schools reopen. Furthermore, research study concluded in year one recommended 1st tranche payment at the beginning of the AY.
2	Develop clearer metrics for a VfM Strategy in the Inception Phase with clear indicators for measuring progress over the course of the programme.	Completed
3	GESS2 to develop a Conflict Sensitivity strategy during the Inception Phase and provide periodic advice and political economy analysis during implementation, liaising closely with Better Aid in Conflict programme.	The Conflict Sensitivity (CS) strategy was developed and put in place which included an analysis of the political economy and the context through document reviews, including media reports and interviews. 3 meetings held, and a number of correspondences occurred between GESS and BAC CSRF. Additionally, this relationship was formalised in March 2020 in the form of a MoU, which outlines ways for continued and consistent collaboration. / Some adjustments were made, and activities moved to Year 2 given delays in part due to COVID19.
4	To mitigate exchange rate fluctuation risks, GESS2 to design a mechanism for managing exchange rate fluctuations.	Exchange rate fluctuation plan developed at Inception phase. / The procurement of the banking agent has been made an annual process in order to better manage and mitigate against exchange rate fluctuations. Analysis by Mott informed the TORs and assessment criteria during the procurement of this year’s banking agent to best protect the programme funds from fluctuations.
5	GESS2 to assess the feasibility of paying differentiated amounts to girls enrolled in higher grades and children with disabilities to meet their education needs.	Paid candidate classes a higher amount in 2019. Data is being collected on children with disabilities. / Study on the needs of children with disabilities to determine the value amount to be paid to meet those needs in year two of the Programme.
6	GESS2 to develop a system strengthening and sustainability plan during Inception Phase, building on the existing GESS1 ‘Lasting Change’ document.	It was agreed with DFID during the inception that for sustainability plan to be effective, it needs to be grounded in context and experience in the field. It was therefore agreed that this will start to be developed once IPs are fully on board, review/assess sustainability plan of GESS1 and start to develop sustainability plan informed by this in year two. / Year two; submit with annual report 2.
7	GESS2 to prioritise schools that did not receive CGs from GESS and schools in areas affected by conflict.	This remains GESS2 priority issue. As of the 31st of March 2020, over 643 primary schools and 48 secondary schools have been paid for the first time ever.
8	GESS2 Lead Supplier to work with Regional Anchors and local disability organisations to train school governance bodies on disability inclusion in the 1st year of implementation.	The disability inclusion content to be added to the following School Governance Materials: - Guide for SMC/BoG (Q2 2020). - Manual for SMC/BoG trainers (Q2, 2020). - Workplan (Q1, 2020) / Training of the SMC/BoG did not start in AY 2020 due to COVID19.
9	GESS2 to explore the option of issuing biometric IDs or unique pupil ID cards. This will strengthen assurance and enable the tracking of pupils and deliver data on girls’ retention and drop-out rates.	Pilot and possibly rollout Biometric solution when it is safe to do so after schools reopen.
10	Gender and inclusion training targeting teachers and School Management Committees /Board of Governors (SMC/BoGs), community leaders, MoGEI staff and mentors and seek ways to strengthen strong female representation in the SMC/BoGs.	Ensure that the composition of the SMC/BoG requires inclusion of women. (Q4, 2019, Q1, 2020). Ensure that M&E tools monitor inclusion of women in the SMC & BoG. (Q2, 2020). Add inclusion content to the teacher training materials. (Q2,2020). / Training for teachers on gender and disability inclusion will be added as part of the teacher training content.
11	GESS2 to work with MoGEI policy and existing curricula to prioritise Accelerated Learning Programmes (ALP)[1]. Emphasis will be on literacy and numeracy as well as life skills, including gender, sexual and gender-based violence, peace education and health, hygiene and protection. Develop strong links with existing humanitarian interventions (e.g. learners from agricultural training) in the 2nd year of implementation.	The launch was planned for April 2020 in WES and to roll it out nationally. This was however curtailed by COVID-19
12	GESS2 to contribute to the design of the revised in-service and pre-service teacher training courses aligned with the new curriculum.	Agreement on the use of Canadian funding to be reached as it has a potential to give GESS 2 the urgency to support MoGEI to initiate the work on revised curriculum framework and courses included in the framework.
13	DFID South Sudan to ensure the Education Donors Group (EDoG) proactively engages in discussions to ensure cohesion and clarity in the development of a Common Donor Framework, and a broader, coherent education sector strategy that is conflict sensitive, considers different scenarios ranging from conflict to a more developmental approach if conditions permit.
14	GESS2 to sustain and intensify the social and behaviour change communication component, expanding content to respond to a context of increased vulnerability and working through other languages.	Refresher training of state presenters to adapt inclusive programming. Working together with government & SAs to map out new languages for new content in year 3 is planned in Aug 2020. A desk research & formative research focusing on hard to reach areas, such as pastoral communities to explore social norms around girls & chn with disabilities, to inform new BCC programmes in year 3, has been planned for Aug 2020. Selection of new languages for new content in year 3 will be guided by recommendations from SAs, MoGEI as well as looking at SAMS data to guide the selection. Process is planned for July 2020. The content will be fully addressed in eyar 3 when production of new programmes begins.
15	Develop simpler, common-sense validation and accountability tools for capitation grants, that more clearly attribute specifically for DFID funds.	The training and roll-out of the tool will commence in earnest as soon as it is safe to do so.
16	Explore ways to support the needs of boys, particularly at the upper primary and secondary level (e.g. school-based sports and arts activities, and access to mentoring programmes). Ensure that mentoring programmes for both boys and girls include life skills and resilience building.	Mentoring programme to include explicit focus on specific need of girls and boys. Mentoring strategy (Q2, 2020)