## Annual Review 2023

Title: UK Support to Financing of Recovery from Economic Emergency in Ukraine (FREE Ukraine)
Programme Value £ (full life): / Grant: / £74m RDEL grant / Guarantees: / First World Bank guarantee ($450m) / Second World Bank guarantee ($500m) / Third World Bank guarantee ($500m)		Review date: April 2023
Programme Code: 301512	AMP start date: March 2022	AMP end date: 15 October 2051

Summary of Programme Performance
Year	2022/23
Overall Output Score	A+
Risk Rating	Major

DevTracker Link to Business Case:	Teams are in the process of uploading after a pause.
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

The UK Support to Financing of Recovery from Economic Emergency in Ukraine (FREE Ukraine) programme (2022-2051) has provided fiscal support to Ukraine to help the Government of Ukraine (‘GoU’) sustain essential public service delivery to the Ukrainian people, including wages for hospital workers, pensions for the elderly, and social programmes for the vulnerable. The UK began this programme in February 2022, after Russia’s military build-up and full-scale invasion of Ukraine led to a significant and worsening financing gap, with Ukraine unable to source affordable finance from domestic or international capital markets and revenue sources drying up. In response, financing from donors, Multilateral Development Banks (MDBs) and International Financial Institutions (IFIs) began plugging the fiscal gap.

The UK has channelled grants and guarantees via the World Bank’s International Bank for Reconstruction and Development (‘the IBRD’). The World Bank’s Multi-Donor Trust Fund for co-financing of the Ukraine Second Economic Recovery Development Policy Program (‘the MDTF’) absorbed £74 million in UK grant funding across March and April 2022. The UK subsequently provided USD 1.45 billion in guarantees to the World Bank’s Public Expenditures for Administrative Capacity Endurance (‘PEACE’) Project. These guarantees are designed to stretch the IBRD offer beyond what the IBRD would otherwise be able to lend to Ukraine on its own balance sheet. A further guarantee is planned for 2023, taking overall UK guarantees for Ukraine via IBRD to USD 1.95 billion. Details on the size of respective tranches and their timings may be found in Annex A.

Purpose: From the outset, the programme has recognised that welfare of the poorest and most vulnerable Ukrainians is acutely at risk from the war. UK support therefore aims to empower the Ukrainian government to continue paying salaries and welfare payments, thereby preventing vulnerable groups from falling below the poverty line due to missed payments. This social safety net has been critical for vulnerable groups in wartime. For instance, 44% of internally displaced households - one of the most vulnerable groups in Ukraine - cite pensions or government allowances as their primary source of income, compared to just 30% who still primarily rely on their salary.

Indirectly, the project aims to help Ukraine win the war by mitigating the risk of economic collapse, which would severely constrain the country’s ability to defend itself, to provide basic services to its population and to sustain national unity in the face of external and internal pressures. Finally, UK fiscal support has a symbolic importance: it is designed to demonstrate, to Ukraine and the world, that the UK is alive to the range of acute needs Ukraine is experiencing, from military to humanitarian to fiscal. Our support to the World Bank is a gesture of unity: we are one of 14 countries that have rallied around the World Bank’s emergency financing instruments, demonstrating that we stand ready to work in concert with other donors to help support the Ukraine government in maintaining public services.

Management: day-to-day operational management of both the MDTF and PEACE, and mitigation of associated fiduciary risks, has fallen principally to the World Bank Group, though the FCDO team has maintained a dialogue throughout with operational leads and via our Delegation in Washington, DC. The HMG team responsible for engaging with IBRD on guarantees to support Ukraine was the International Financial Institutions Department (‘IFID’) in Spring/Summer 2022, with this responsibility handed over in Autumn 2022 to the Ukraine Economic Support Team, supported by the programmes team at British Embassy Kyiv. While the UK has worked closely with IBRD during the MDTF and PEACE’s mobilisation and monitoring phases, the central outcomes and outputs described in this report have been ultimately decided by the IBRD, with the UK playing an auxiliary role as guarantor of a minority of PEACE funds.

Summary supporting narrative for the overall score in this review

This review has considered how this programme has performed in its first year, from March 2022 to March 2023. This will be a light-touch annual review given the tightly restricted parameters of the support provided. The review is based on the following:

- Conversations with staff at the World Bank Group
- Conversation with staff at the Ukrainian Ministry of Finance
- Analysis of World Bank reporting documents
- Internal analysis of the Ukrainian fiscal situation, performed by HMG economists and policy professionals
Overview. It is the overall judgement of the review team that against a backdrop of intense uncertainty, the World Bank has made impressive progress in stretching its own systems to mobilise a reliable channel for emergency assistance, to which the UK lent early and agile support. This instrument has been impactful – the PEACE project has become the World Bank’s flagship financing instrument to Ukraine, enabling donors to unite their efforts to provide fast, targeted and predictable support. The UK is responsible for some of that impact, having guaranteed USD 1.45 billion of PEACE’s total disbursed funding of USD 14 billion (as of March 2023), or 10%.
[note] Bank staff advised that USD 14 billion of support has been disbursed via PEACE as of 13 March 2023. The total value of pledges at that point was higher, standing at USD 20.6 billion. Source: “Supporting Ukraine through the War”, World Bank, 24 February 2023.

Caveats. However, the PEACE project does not include the EU’s macrofinancial support to Ukraine, which has been substantial, and the vast majority of PEACE support has been enabled by US grant funding. The UK should be realistic therefore about the extent to which our fiscal support can be said to have had a decisive impact in reducing Ukraine’s large and ever-widening fiscal gap, particularly in comparison with other donors (notably US and EU). Indeed, the UK’s fiscal package is dwarfed by Ukraine’s monthly fiscal gap, which has averaged USD 5 billion per month since the full-scale invasion, with USD 1 billion of these needs not met on average each month.

Detail on outputs: The PEACE project has reportedly met or exceeded its targets for Output 1, “maintaining core state functions”, gaining an A+. For example, PEACE has reimbursed administration staff in non-security sectors, paying more than the target of 85% of staff. The project has helped more than its target percentage of schools (90%) to remain operational. On Output 2, “volume of finance mobilised”, it is true that the UK’s grants and guarantees have acted to increase the volume of affordable finance available to Ukraine when access to domestic and international borrowing was severely curtailed, and UK as one of many donors has helped create a cascade of grants and guarantees via PEACE. This has been confirmed in conversations with both World Bank and GoU.

Overall assessment of outputs. As a result, the programme can be scored as “A+: Outputs exceeded expectation”, since this programme has, as expected, served to: signal UK support; leverage additional IBRD support; and contribute to GoU’s ability to fulfil its core functions. While UK support cannot be said to singlehandedly have had a stabilising effect on the Ukrainian economy, it is true that we have contributed to a strong cross-donor response, without which Ukraine’s economy would likely have found itself in a graver position.

Attribution. The UK guarantees have been used to reimburse a range of expenditures including salaries of education and government employees (first guarantee under PEACE), pensions and social assistance payments (second guarantee) and salaries of public university employees and family and child benefits (third guarantee). However, only a minority of UK funding can be attributed to a specific category of payments – the August 2022 pension bill is the clearest example of a single tranche of payments being reimbursed by funding mobilised almost exclusively by UK guarantees (namely, the UK’s first World Bank guarantee). Therefore, it is possible to attribute certain results to UK support, but only in limited instances.

Major lessons and recommendations for the year ahead

- Revise the Theory of Change and logical framework of results for this programme to match latest developments, in close partnership with World Bank. These revised frameworks ought to better reflect latest reported results and the latest developments in Ukraine’s fiscal position, as well as demonstrating UK impact. In future, and if time allows, it would be beneficial to work more closely with the Bank in deciding results frameworks from the outset, so that UK priorities can be reported against consistently over the lifetime of a fiscal programme.
- Plan and advocate for a longer-term approach to financing Ukraine’s fiscal gap. It is imperative that the UK work closely with the international community and at the international financial institutions and multilateral development banks in which we hold shares to develop a cross-partner approach to Ukraine’s fiscal position. For the UK, this would look like ensuring our multilateral contributions are being maximised at the fiscal and real economy levels. Drawing on a mix of instruments, the UK should be able to mobilise development finance and stretch our existing equities. In order to maximise benefit and enable GoU to plan effectively, new tranches of support should be communicated early and provided in a predictable manner, so that GoU can factor it into their plans.
- The UK and donors need to continue tracking closely the risks to Ukraine’s economic overall stability. War intensity will be a key factor in determining the size of Ukraine’s residual financing gap in 2023. If further international support is insufficient in filling a growing gap, then the GoU may be forced to adopt destabilising measures such as monetary financing, expenditure cuts and increasing arrears.
- In line with the above, the UK will need to keep tracking risks internally. Given the loan guarantees cover risk of payment default until 2051, the UK will continue to periodically update its assessment of default risk during this period.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The intended impact of the programme is to support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion.

Outcomes are a reduced financing gap for the Ukrainian Government, the maintenance of essential state expenditure (e.g. pensions and state salaries) and services, and reduced instances of economic instability. Guaranteeing World Bank lending continues to be a highly cost-effective way of providing economic support to Ukraine.

The Theory of Change is based on the translation of key inputs (UK grants and guarantees) into the key outputs of additional IBRD financing, alongside the reimbursement of salaries and welfare payments made by GoU. The theory is that this process, from inputs to outputs, will lead in turn to the identified outcomes of:

- a reduced financing gap for the Ukrainian Government,
- maintenance of essential payments (e.g. pensions and state salaries) and services,
- more broadly, signalling international support with a view to alleviating market concerns regarding Ukraine’s ability to meet its financing obligations.
Broadly, the Theory of Change as provided in the original Business Case remains valid, even though the war has continued longer than hoped. There is evidence in Section C that the inputs chosen have yielded the anticipated outputs and good reason to believe that this will lead to the overall impact identified, i.e. the Ukrainian economy is somewhat stabilised. However, the Theory of Change could be updated and aligned with World Bank’s reporting framework to ensure that UK priorities are integrated into overall reporting plans for this support: this constitutes one of this review’s key recommendations.

In addition, it must be recognised that UK support is a form of emergency financing, and contribution to any longer-term impacts will be very hard to ascertain. Ukrainian macroeconomic stability will be overwhelmingly influenced by the length and extent of the war. The UK package of support was provided on a no-regrets basis given the scale and urgency of the need, and was never expected to be a panacea for Ukraine’s economic challenges.

In order to maximise the impact of UK funding, the intention at the time of mobilisation was that, along with commitments from other donors, the UK guarantee and grant would act as a strong signal of support for the Ukrainian economy, limiting further negative assessments from credit ratings agencies and capital outflows. As hoped, the UK contribution was followed by a range of other donors, the majority of which have followed through on their existing commitments and likely signal the potential for further support.

The World Bank assesses that UK guarantees have been catalytic. In the case of Ukraine, the UK remains the largest guarantor of IBRD financing to approved and ongoing World Bank-supported projects in Ukraine (as of March 2023), and the UK’s role has made a material difference to the amount of financing that the Bank has been able to provide. In addition, given the UK’s leadership, other donors were willing to enter into guarantee arrangements that mimicked those concluded by the UK. World Bank assess therefore that the UK’s decision to guarantee funding via PEACE meant support from other donors was deployed faster than would have been the case without UK leadership.

GoU assesses similarly that UK support has strengthened the case of PEACE, demonstrating to other donors that PEACE is a functional and transparent channel for fiscal support. From the Ukrainian perspective, the UK has been a key supporter to PEACE, acting as the second-largest donor to the programme with our USD 1.45 billion in guarantees.

In discussions with Ukraine and the Bank, a commonly-held view emerged that the UK’s trust in the PEACE channel, and its decision to act quickly to channel support via this instrument, had built confidence in PEACE among other donors considering PEACE as a funding instrument. While difficult to prove definitively, this may amount to an unexpected benefit of the UK’s decision to support the programme.

In a similar vein, GoU reported that strong information flows built by PEACE between Ukraine and donors had opened Ukraine’s fiscal systems up to scrutiny. This habitual, transparent communication was seen to have built trust between Ukraine and donors. In gaining access to detailed information on spending and accounting processes, donors were able to see the impact of their support and build confidence in Ukraine’s processes of public management: this may be seen as another unexpected benefit of the decision by the UK and other donors to channel support via PEACE.

Supporting narrative: international fiscal support has helped the Ukrainian government to continue to function from February 2022 to March 2023

Per HMG internal analysis, fiscal support provided to Ukraine by the UK and other donors has contributed to:

- Maintaining high levels of foreign exchange reserves in the Central Bank: the current level of reserves is $28.9bn, $1.5bn higher than on the morning of the invasion. These reserves are needed for critical imports and to preserve exchange rate stability. Consistently high reserves, especially from the second half of 2022 onwards, have allowed the Central Bank to avoid a further currency devaluation that would have accelerated inflation and squeezed living standards.
- Reducing Central Bank financing of the deficit, which would have created large inflationary pressures and impacted greatly on consumer purchasing power and public morale more broadly. The Central Bank effectively printed money to fill $12bn of the 2022 financing gap not covered by international or domestic support. However, owing to higher levels of international support, January and February 2023 were the first post-invasion months in which the budget was financed without recourse to this destabilising policy.
- Helping create the space for Ukraine to fund its war effort, by freeing up Ukrainian resources for military expenditure, which has increased tenfold since the invasion and now accounts for over half of all government spending.
- Helping GoU support businesses; keep schools and hospitals open; keep utilities running, and keep emergency services running
Taken together, these factors have helped underpin Ukraine’s economic stability. Of course, UK support alone cannot be said to have achieved all of the above, but it is fair to say that the UK’s contribution has been part of a strong team effort, without which Ukraine’s economy would be in a worse place by March/April 2023, the end of the period covered in this review.

Taking into account the above, we recommend that the UK and donors closely track Ukraine’s economic stability, as shocks and deterioration pose clear risks to our intended outcomes. Donors, including the UK, must not become complacent on Ukraine’s financing. This will mean actively monitoring the situation and keeping further support measures, beyond those covered in this review, under consideration.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Conversations with World Bank staff have indicated that UK guarantees have leveraged additional IBRD funding (beyond what would have been available otherwise), on a one-to-one basis. As the precise figures underpinning this claim relate to sovereign risk ceilings, they are not public. The increasing of IBRD lending capacity on a one-to-one basis is the programme’s central output from the UK perspective. In this regard, the UK’s programme has so far managed to deliver on its central output, and this is likely to also apply for future guarantees via PEACE.

Per Bank staff, the overall effectiveness of PEACE is best demonstrated by the number of individuals paid as a result of the Project, detailed in Section C. The Bank has hit its targets for these indicators (number of pensioners and public servants paid; number of schools operational), demonstrating that the programme is largely on-track.

Another of the intended outcomes of the programme is to broadly help to address market concerns regarding Ukraine’s ability to meet its financing obligations in the wake of the invasion. All credit rating agencies have substantially downgraded Ukraine since February 2022 and all believe further restructuring of eurobond debt is very likely. At the time of drafting the Business Case, market concerns around financing obligations were valid because GoU was still servicing all debt. Since then though, a debt deferral agreement has been reached with official and eurobond creditors that means GoU is no longer financing a lot of its obligations.

As a result, it is unlikely that UK fiscal support will alleviate concerns about debt repayment, as GoU is no longer servicing this debt. Nevertheless, while it is not currently applicable, reinstating market access for Ukraine remains a broader UK objective. Therefore, though this outcome not being met at the current moment, we recommend retaining it within the results framework.

These encouraging results at the output level appear sufficient to deliver – at least partially – on the programme’s intended outcomes and impact. The FREE programme’s intended impact is to support the macroeconomic stability of Ukraine, support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion. The UK has likely partly contributed to these impacts (though the scale of Ukraine’s financing gap is far greater than the UK’s contribution); the PEACE project as a whole, which had disbursed USD 14 million by March 2023, seems to have contributed more significantly to filling GoU’s financing gap since the full-scale invasion. However, the key point here is that the PEACE project (and therefore the UK’s contribution to it) may not achieve the desired outcome of stabilising the Ukrainian economy if the military situation deteriorates significantly in the coming months.

This is because war intensity will be a key factor in determining the size of Ukraine’s residual financing gap in 2023. If further international support is insufficient in filling a growing gap, then the GoU will be forced to revert to destabilising measures such as monetary financing, expenditure cuts and increasing arrears. In this way, the UK’s FREE project and PEACE overall may deliver on outputs but fail to deliver on outcomes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Almost all of the funding unlocked by this programme has already been transferred to Ukraine as of April 2023. The fiscal grant provided via the MDTF has been transferred to Ukraine. The three UK guarantees on World Bank lending (USD 1.45bn) have been largely disbursed (USD 1.375bn out of USD 1.45bn), and they will remain extant until 2051 as Ukraine makes repayments. As such, the FCDO does not have an option to discontinue this programme; instead, the focus of FCDO teams is on managing the outstanding guarantees and evaluating whether further grant/guarantee support to Ukraine is required and is well-placed to deliver VfM.
On its own merit, there is a strong justification for the UK to make provisions for further fiscal support to Ukraine for as long as the war is ongoing and likely beyond. When considered as part of the wider portfolio, fiscal support is crucial: much of the UK’s support to Ukraine, particularly military, governance and energy support, rests on the assumption that Ukraine’s government remains functional. A hyperinflationary spiral would prevent the Ukrainian state from waging the war effectively, at least temporarily, and helping Ukraine win the war has stood as the UK’s foremost political priority since February 2022.

## C. DETAILED OUTPUT SCORING

Output Title	Support for core government functions (targets and statistics provided by the World Bank)
Output number:		1	Output Score:	A+
Impact weighting (%):		75%	Weighting revised since last AR?	No

Output 1: Support for Core Government Functions.

Results

Currently, PEACE reimburses expenditures incurred by the GoU to pay government, school and healthcare employees' wages; first responders' wages; pensions and social assistance payments. As of March 2023, the UK has guaranteed almost £1.3bn (USD $1.45bn) under PEACE. The PEACE project as a whole has disbursed USD 14 billion in financial support between February 2022 and March 2023. PEACE has achieved the below results per reporting by the World Bank, against which the UK has provided a score assessing how far the World Bank has met its own targets.

These outputs are set by the World Bank as they are implementing and monitoring the programme. As guarantor, the UK has not been closely involved in the design of the outputs, and has elected to use World Bank reporting as the basis of our reporting for this output. Going forward, we recommend working closely on results frameworks with the Bank as we mobilise future support, to ensure reporting reflects UK priorities: this recommendation is reflected at the bottom of this section and in this report’s summary.

Indicator 1.1	Extent to which government continues to exercise core functions (online filing taxes, issuing birth certificates, processing online requests for housing and utility subsidies)				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A outputs met expectation
Value	5.00	5.00	5.00	4.00
Date	07 April 2022	13 June 2022	23 June 2022	30 June 2023

Indicator 1.2	Number of public administration staff paid in non-security sectors				Was World Bank target met? UK score

	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderately exceeded expectation
Number of staff paid on time	160,000	160,000	148,793	At least 85% of staff paid in the baseline month
Number of female staff paid on time	110,000	110,000	110,000	At least 85% of staff paid in the baseline month
Date	07 April 2022	13 June 2022	30 September 2022	30 June 2023

Indicator 1.3	The number of school employees paid on time. / Comment: The reduction in the target is mainly related to some staff who fled the country and decided to resign, staff who joined military, and other potential losses. No wage arrears, beyond shorter delays in newly liberated territories				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderately exceeded expectation
School employees paid on time	160,000	160,000	148,793	At least 85% of staff paid in the baseline month
Female school employees paid on time	300,000	300,000	300,000	At least 85% of staff paid in the baseline month
Date	07 April 2022	13 June 2022	30 September 2022	30 June 2023

Indicator 1.4	Number of schools that remain operational (whether remote, in-person or blended)				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderately exceeded expectation
Value	13,966	13,866	12,822	10,000
Date	15 April 2022	13 June 2022	30 Sep 2022	30 June 2023

Indicator 1.5	Share of pensions paid on time				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A++ outputs substantially exceeded expectation
Share of pensions paid on time to all pensioners	100.00	100.00	99.43	90.00
Date	01 Feb 2022	01 Feb 2022	30 Sep 2022	June 2023

Assessment: Based on the above, the PEACE project has reportedly met or exceeded all its targets for this output, ranging from an A to an A++ on the five indicators. As a result, FCDO teams award it an A+ for this output. PEACE has continued to reimburse public administration staff in non-security sectors, paying above and beyond the target of 85% of staff paid in 2022. The project has helped over 90% of schools to remain operational.

Attribution: The UK guarantees have been used to reimburse a range of expenditures including salaries of education and government employees (first guarantee under PEACE), pensions and social assistance payments (second guarantee) and salaries of public university employees and family and child benefits (third guarantee). The most detailed reporting on the UK contribution to PEACE relates to the UK’s first IBRD guarantee, which the World Bank reports was responsible for covering the majority of the state pension bill in August 2022 – detail below, in Output 1.4. Since this is the most clearly attributable subtranche of UK support, pensions are foregrounded in this section, since effects of the UK contribution can be most clearly distinguished.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.1 (core state functions): PEACE has continued to reimburse social assistance, including to 460,000 people with disabilities. The Guaranteed Minimum Income support supports 256,000 people. The Housing and Utility subsidy supported 1.8 million beneficiaries in October. This social safety net has been critical for vulnerable groups in wartime. For instance, 44% of internally displaced households - one of the most vulnerable groups in Ukraine - cite pensions or government allowances as their primary source of income, compared to just 30% who still primarily rely on their salary. The payment of the housing and utility subsidy has also helped Ukrainians to heat their homes during a difficult winter of attacks on energy infrastructure.

Output 1.2 (payment of public administration staff in non-security sectors): The target was exceeded, as the total proportion of staff paid in September was around 92%, which is over and above the target of 85%. However, there was a drop in the absolute number of staff paid: was due to a reduction in total number of personnel, rather than non-payment of some staff: the Bank states that no wage arrears had been reported as of 30 September 2022.

Output 1.3 (number of school employees paid on time): PEACE has supported the reimbursement of payments made to 450,000 school teachers, meaning over 85% of school employees are paid on time under PEACE (above target). Like the public administration staff mentioned in the above output, the number of school employees also fell over the lifetime of the programme: Bank staff report that this reduction is mainly related to some staff fleeing the country, resigning, or joining the military. No wage arrears, beyond short delays in newly liberated territories, have been reported.

Output 1.4 (pensions): Since the full-scale invasion, the GoU has reportedly continued to fully ensure the fulfilment of social obligations to the population, particularly pension payments. In August 2022, the expenditures on pension payments to the citizens, except for pensions of the military personnel, totalled UAH 43,9 billion, or 98% of the accrued (planned) amount of the pension payments. The World Bank reported to the FCDO on 9 December 2022 that the majority of these August payments are attributable to the UK’s first guarantee of USD 500 million. The number of people receiving pension during that period stood at 9.86 million, of which 81% received old-age pension; 14% - disability pension; and 5% - pension to survivors of the Chernobyl disaster.

Case study: August 2022 pension bill
World Bank staff published a report detailing the use in August 2022 of the UK’s first USD 500 million guarantee to reimburse approximately 88% of the GoU’s pension bill for that month. This allowed the Ukrainian population collecting pensions – a group which represents approximately a quarter of the population and over-represents elderly people and people with disabilities – to continue receiving a monthly payment for subsistence.
The number of people receiving a pension during that period stood at 9.86 million, of which 81% received old age pension, 14% received a disability pension, and 5% a survivorship pension (principally for survivors of the Chornobyl disaster). Eligible expenditures for pensions under PEACE for pensions amounted to UAH 21.8 billion (~USD 590m) in August 2022, or 102% of the state budget’s August pension plan (part of the August amount was used to cover July payments, which were only paid to 97.6%). The reimbursement of the August pension bill under PEACE can be partly, though not wholly, attributed to UK financing, since our first guarantee was equal to approximately 88% of the bill.
That funding was aimed, in particular, at subsistence minimum top-ups; long-service related supplements; top-ups to disability pensions, pensioners with dependent children, persons with disabilities, war veterans, families of deceased war veterans; compensating the unreceived amount of the single social contribution due to the use of the simplified tax system; pensions and compensations to those who suffered from the Chernobyl disaster, as well as spending on social insurance for employees of certain professions in the extractive industries and agriculture.

The continued payment of pensions by the GoU is extremely significant for society, in that it confers legitimacy on the government and delivers the message that no Ukrainian will be left behind. The payment of pensions is particularly important because the individuals who have chosen to stay in Ukraine despite the war are frequently older (and less mobile) than those who have left, and so the population who have stayed are disproportionately reliant on the types of welfare payment that PEACE (underwritten by the UK’s August guarantee) can reimburse.

Challenges

In the context of this output, GoU has reported challenges when trying to add new categories for reimbursement to PEACE’s remit. Following high volumes of donor support, the Ministry of Finance suggested adding categories of eligible expenditure with each new donor pledge.
Adding new categories sometimes brought new challenges, for example by developing new reporting standards for healthcare salaries, as the process for paying salaries in the healthcare sector differs substantially from that of the educational sector. While onerous, GoU has reported that these changes will be useful in future as they will allow GoU to better calibrate budgets with payments from the centre.
Recommendations / lessons learned

- Recommendation: In future, and if time allows, it would be beneficial to work with the Bank in deciding results frameworks from the outset. This would ensure that UK priorities can be reported against consistently over the lifetime of a fiscal programme.
- Recommendation: Revise the Theory of Change and logical framework of results for this programme to match latest developments, in close partnership with World Bank. These revised frameworks ought to better reflect latest reported results and the latest developments in Ukraine’s fiscal position, as well as demonstrating UK impact.
Output Title	Additionality of IBRD lending
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress over reporting period.
2.1: Percentage of IBRD funding mobilised by UK guarantees which is additional to what the IBRD would have been able to lend without UK support	100%	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score.

- At the time of the mobilisation of this programme, the World Bank was understandably taking an incremental approach to using up its own exposure limit for Ukraine. In providing guarantees to Ukraine, the UK’s intention was to only issue a guarantee to the World Bank if our guarantees were able to support financing that was additional to the Bank’s own lending plans. The primary output related to the programme was therefore that the UK guarantees should enable an equivalent volume of additional IBRD lending to Ukraine, over and above what could have been committed otherwise, in support of macroeconomic stability.
- The UK guarantees were therefore intended to be in support of planned IBRD financing to Ukraine. We know that 100% of the UK support provided via our £74m fiscal grant would have been additional to and separate from IBRD lending, in as much as it took the form of a grant via a Multi-Donor Trust Fund.
- FCDO received written confirmation from World Bank staff in March 2023 that UK guarantees have mobilised additional lending beyond what was possible on the IBRD balance sheet.
- During conversations in February 2023, Bank staff reiterated that IBRD was at its lending limit and they required donor grants and guarantees to keep disbursing via PEACE. Bank staff judged that the hypothetical limit on further PEACE lending supported by others’ guarantees was around US$10bn. As a result, it is likely that the UK’s fourth guarantee will be additional to IBRD lending.
- Disbursement. The World Bank has confirmed to us that financing supported by the UK was disbursed on the dates provided in the table at Annex A.

How UK support will impact future needs. As at March 2023, the IMF projects in its central scenario that all of Ukraine’s fiscal needs for 2023 will be met by current pledges. Despite this, the outlook remains uncertain: the latest IMF central scenario projects a $41.7bn financing gap, but this is likely to be revised up significantly to reflect the current underreporting of military expenditures. The G7 has already pledged $39bn for 2023, with initial disbursements allowing monetary financing to be avoided so far in 2023. As a result, the UK’s planned future support will certainly play a role in meeting Ukraine’s future needs, though this role. The UK’s pledge should also help to provide certainty for the Ministry of Finance when planning for future needs.
Challenges
Bank staff have highlighted the need for donor contributions to keep pace with GoU plans and to remain regular in order to have a stabilising effect. GoU plans its disbursements to manage liquidity, but February had a lower influx of donor support compared to January, so any reduction in the flow of donor support can be destabilising for Ukraine. This is compounded by the fact that verification of requests can take time. These two factors combine to mean that even if the fiscal gap of USD ~38bn is met over the year, delays within individual months can still mean Ukraine is required to resort to monetary financing to cover the irregularity, because Ukraine’s liquidity management happens on a monthly basis and because donor pledges and disbursements do not translate to the support immediately hitting Ukraine’s balance sheet, as the verification process takes time. The Bank provided MoF with two experts that support the coordination and verification process as part of enhanced implementation arrangements.
Lessons learned

The PEACE project, and UK support to it, has been effective in meeting part of Ukraine’s financing gap. The Bank provided MoF with two experts that support the coordination and verification process as part of enhanced implementation arrangements: this could be repeated as part of future fiscal support efforts.

Recommendations

- Recommendation: In order to be maximise benefit and enable the GoU to plan effectively, new tranches of UK support should be communicated early and provided in a predictable manner, so that GoU can factor it into their plans.
- Recommendation: Plan and advocate for a longer-term approach to financing Ukraine’s fiscal gap. It is imperative that the UK work closely with the international community and at the international financial institutions and multilateral development banks in which we hold shares to develop a cross-partner approach to Ukraine’s fiscal position. For the UK, this would look like ensuring our multilateral contributions are being maximised at the fiscal and real economy levels. Drawing on a mix of instruments, the UK should be able to mobilise development finance and stretch our existing equities. In order to be maximise benefit and enable the GoU to plan effectively, new tranches of support should be communicated early and provided in a predictable manner, so that GoU can factor it into their plans.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

- Economy: collectively, the FREE programme has mobilised significant volume of additional finance to Ukraine at a relatively small up-front cost to the UK. There is a cost to channelling grants through a World Bank MDTF but it has broader effectiveness benefits.
- Efficiency: As identified in the Business Case, the Ukraine guarantee will carry greater risk than other UK guarantees to support MDB lending for macroeconomic stability, but this reflects the context in Ukraine and is a risk HMG took on knowingly at the time of approval.
- Effectiveness: Direct support for the government budget has enabled the GoU to maintain funding for essential services. It has also reduced the administrative burden for GoU as they are only required to liaise with the World Bank, rather than each individual donor.
- Equity: There is a strong need for additional finance in Ukraine to support the core functioning of the state and continue providing some form of continued social safety net. This remains as true, if not more true, as when the Programme was approved. Per World Bank reporting, PEACE reimbursed the payment of salaries of 100% of the female public administration staff in non-security sectors (total: 110,000) and of the female school employees within scope of the project (total: 300,0000). UK guarantees were used to maintain the reimbursement of payments of pensions, notably in August 2022, which demonstrates PEACE’s value in supporting vulnerable groups.

E: RISK [½ to 1 page]
Overview
Financial risk. MDB loan guarantees are typically considered low-risk, with relatively minimal exposure to FCDO (essentially using FCDO’s balance sheet to secure much larger World Bank financing, with low risk that the guarantee will be called). In the case of Ukraine, there is a greater risk that the GoU will default on the loan and the Bank will call in the guarantee than in the case of other parts of the UK guarantee portfolio. The UK would make a payment on the guarantee if scheduled payments (from the GoU to the World Bank) under the guaranteed financing are late by more than 180 days. Assessment of this risk is detailed in the Annual Statement of Progress. This risk is judged to have increased in the programme’s first year as the war has gone on, though the outlook for donor support appears strong.

Exchange rate risk for UK liability: The Business Case identified that the potential impact on FCDO’s balance sheet and cash flows – should the guaranteed loan(s) default – will be subject to movements in the conversion value of USD to GBP. The value of the principal guaranteed by FCDO will be fixed in the currency of the loan agreement in line with previous UK guarantees to the World Bank. Under FREE, UK guarantees have supported lending in both EUR and USD. Should FCDO decide to pursue recoveries, there would be a risk to the net CDEL budget position in that the loan recoveries repaid to FCDO would not necessarily equal the GBP amount paid to the World Bank on trigger of the guarantee. Staff continue to monitor this risk closely so that contingency planning can consider any growth or reduction in the liability.

Exchange rate risk for PEACE absorptive capacity: Bank staff identified the devaluation of the hryvnia as a challenge. UAH devaluation means less USD of PEACE funding is needed to match reimbursements.  As PEACE disburses in USD, the value of reimbursable expenditures declines, meaning the ability of PEACE to absorb donor funds declines too.  Pensions are inflation indexed, which offsets to some extent the impact of a currency devaluation because while a devaluation reduces the US$ value of PEACE reimbursables, the UAH value of pensions is rising which acts in the opposite direction.

Default risk. Bank staff thought this was unlikely given Ukraine’s extremely dedicated approach to making repayments to date. The key default risk identified by the Bank was whether Ukraine would be able to use short-term support to return to growth, in the absence of FDI and private sector investment. If growth is lower than, say, the 4.5% interest charged by the Bank in the medium term, default could become an issue.

Reputational Risk: Reputational risks could arise in case of financial mismanagement of these funds on the part of either GoU or the World Bank. Perceptions of corruption in Ukraine remain high, and any future reports of corruption could reduce public and donor appetite for providing fiscal support to Ukraine. Since PEACE began, the Bank has taken steps to improve the internal verification process at GoU, both to speed up payments and to build donor confidence in the transparency of the payment verification process.
Fraud and Fiduciary Risk: FCDO is content that the IBRD’s financial accountability policies and practices are robust and the reimbursement approach of PEACE goes some way to mitigate risks. The IBRD has strong internal audit procedures and a well-established fraud detection system. The World Bank will disburse funding into designated bank accounts related to the specified purposes of the financing agreement.
When approving the first guarantee, GoU provided assurances that it could retain control of bank accounts even in scenarios where some Ukrainian territory is not under government control. As time has gone on, the prospect of this risk materialising appears to have diminished, as fighting has become restricted to the East and South, far from the seat of government, and initial attempts to destabilise via false flag operations and disinformation appear to have failed.
Political Risk: The Business Case identified the potential for funding to fall under Russian control as a risk. However, there is a risk that UK support is disbursed slowly or considered too modest, leading to criticism from the public or from other donors. Since the war began, GoU and media outlets have resorted to public criticism when they have perceived support as taking too long to materialise. This risk applies to UK support, if it is viewed as either too slow to disburse or too small in scale.
Delivery Risk: There is a risk that the conflict escalates further and is further protracted, with the economic situation worsening as a result. International commitments are insufficient to support macroeconomic stability. A year into the programme, this remains a major delivery risk as it would make it unlikely that the programme would have the desired outcome or impact. As such, one of the key recommendations of this Review is that the UK and partners continue to closely monitor pledges and inflows of donor funds into Ukraine, to make sure the residual financing gap does not become too large for Ukraine to bear.
Recommendation: The UK and donors need to continue tracking closely the risks to Ukraine’s economic overall stability. War intensity will be a key factor in determining the size of Ukraine’s residual financing gap in 2023. If further international support is insufficient in filling a growing gap, then the GoU will be forced to revert to destabilising measures such as monetary financing, expenditure cuts and increasing arrears.
Recommendation: In line with the above, the UK will need to keep tracking risks internally. Given the loan guarantees cover risk of payment default until 2051 and potentially 2052, the UK will continue to periodically update its assessment of default risk during this period.
Update on partnership principles
The UK does not have a partnership principles agreements with the GoU, though the process for developing one is underway.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Most financial and commercial considerations are not directly applicable to this programme, which is governed by an MoU. All funds disbursed under PEACE and MDTF were channelled via the World Bank, and were managed according to their procedures.
In 2023, the Bank plans to carry out Agreed Upon Procedure reviews by an audit company with the following objectives:

- Determine whether monthly reports on Eligible Government Expenditures were correctly compiled and consolidated on the basis of reports received from lower-level units, and financial data included in such reports reconciles with Treasury data or other applicable data sources.
- Determine whether Government has functioning controls over preparation and compilation of such monthly Eligible Government Expenditure reports, including exclusion of items that are financed by the government but not eligible to be financed by the Project; Determine whether Government has functioning controls over accrual, payment and subsequent recording of those Eligible Government Expenditures.
- Determine for a sample of Eligible Government Expenditures included in each such monthly report, that those eligible expenditures are fairly stated, and eligible, and such expenditures have been made in accordance with the Project documents.

BE Kyiv continues to engage regularly with the Bank, meeting at least quarterly, and receives regular readouts from UKDel. This channel of communication has provided an important foundation for understanding PEACE, its risks and its outlook.
The UK and World Bank have operated in partnership on PEACE. The initial design of the programme was undertaken by the World Bank, with the UK determining to offer a guarantee towards the end of the World Bank’s design stage. During implementation, the UK has co-ordinated directly with the World Bank. Delivery has benefitted from the World Bank’s in-house technical expertise.

Annex A: Detail on fiscal support provided by UK via IBRD

To date, the UK’s fiscal support to the Government of Ukraine (‘GoU’) has been channelled via IBRD in the form of the following components.

- a £74m UK ODA grant (RDEL) to the IBRD’s Multi-Donor Trust Fund for Co-financing of the Ukraine Second Economic Recovery Development Policy Program (“the fiscal grant”)
- EUR 425.7m (approx. $450m) UK guarantee of IBRD lending to Ukraine via PEACE (“the first guarantee”)
- $500m UK guarantee of IBRD lending to Ukraine via PEACE (“the second guarantee”)
- $500m UK guarantee of IBRD lending to Ukraine via PEACE (“the third guarantee”)

Details of disbursement and signing may be found in the table below:

	Fiscal grant	1st WB guarantee	2nd WB guarantee	3rd WB guarantee
Value	£74,000,0000	€ 425,700,000.00	$500,000,000.00	$500,000,000.00
Signed	N/A	1 June 2022	11 October 2022	20 December 2022
Disbursed	Approved 7 March. £50m in 21/22 and £24m in 22/23 / (TF073792)	22 June 2022 / IBRD94030	21 October 2022 IBRD94470	USD 295 million disbursed 9 February 2023. Rest disbursed in February/March 2023
Final planned repayment	N/A	2040	2041	2051