Author’s note: Some sensitive text and figures have been redacted ahead of publication.

Business Case - March 2022

Summary Sheet

Department CDD/Portfolio/ Business Plan Summary: N/A – this programme is an emergency fiscal support programme developed to respond to the fiscal shock caused by Russia’s full-scale invasion of Ukraine. This was not foreseen or included in previous business planning. The Ukraine Country Plan is currently being redrafted.

Title: UK Support to Financing of Recovery from Economic Emergency in Ukraine (FREE Ukraine)
Programme summary: / The UK will provide fiscal support to the Government of Ukraine through a £74m grant to a World Bank Multi-Donor Trust Fund and up to $450m in guarantees of World Bank lending to Ukraine. The guarantees will enable the IBRD to lend more than it would otherwise do so to Ukraine. Collectively, this will provide important financial support to Ukraine at a time of great need as well as an important signal to markets regarding the international commitments to support Ukraine’s economy. / The guarantee will carry no upfront costs. Future costs would arise if Ukraine were to default on its borrowing from the World Bank. / The grant represents an additional allocation of ODA to Ukraine and will be disbursed as early as possible in FY22/23.
What is the rationale for UK aid spending? / On 24 February 2022, Russia launched a large-scale invasion of Ukraine. Ukraine’s financing gap is large and growing, and the Government has been unable to access international capital markets reliably and affordably. Ukraine urgently needs financial assistance to support its economy and the provision of essential services. There is a significant political imperative to support Ukraine, both domestically and internationally. Aligning support to World Bank financing can provide rapid and coordinated financial assistance in a single package, limiting administrative burdens for the Government of Ukraine.
Programme Value: / Up to $450m guarantee; £74m fiscal grant		Country/ Region or Sector: / Region: Ukraine / Sector: Multi-sectoral
Department/Country Office confirmation / Contact name:		(BC SRO); / (Programme SRO)
Threshold for Approval of Business Case:		Foreign Secretary / HMT
Date of Approval of Concept Note:	N/A	Name of Approver / N/A
Date of Approval of Business Case	28/03/22	Name of Approver / HMT
Programme Code: / .	Start Date: / March 22	End Date: / Oct 2051
Overall programme risk rating: / Further details in “Risk” section	Major
Vault Number:	N/A

## Intervention summary

What support will the UK provide?
The UK will offer a guarantee of up to $450m to allow the World Bank to increase the size of its upcoming financing operations to the Government of Ukraine and provide a £74m grant contribution to a World Bank Multi-Donor Trust Fund to disburse as part of the March 2022 Supplementary Development Policy Loan financing package. The funding will provide direct support for the Government of Ukraine’s budget.
Why is the support required?

Ukraine urgently needs fiscal support to enable the Government to pay salaries, pensions, maintain safety nets and keep key state functions and essential services operating. The poorest and most vulnerable Ukrainians are most acutely at risk from the war. The Russian invasion of Ukraine has led to a large and growing financing gap There is a significant political imperative – both domestic and international – to support Ukraine.

What are the expected results?

The intended impact of the programme is to support the macroeconomic stability of Ukraine, support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion. Outcomes will reflect a reduced financing gap for the Ukrainian Government, the maintenance of essential payments (e.g. pensions and state salaries) and services .

What are the key risks to success?

There are considerable and varied risks associated with the programme. The most significant risks are:
- Delivery risk: The conflict escalates further and/or is protracted, with the economic crisis worsening as a result. International commitments are insufficient to support macroeconomic stability.
- Financial: The Government of Ukraine defaults on its loan obligations to the World Bank and the UK guarantee is called. .
- Reputational / fiduciary: .
- Political: .

The risks associated with the programme are assessed as major. However the context in Ukraine is extraordinary and the economic and political consequences of not acting rapidly significantly outweigh these risks. UK support should be considered on a no regrets basis.

## Strategic Case

Context

On 24 February 2022, Russia launched a large-scale invasion of Ukraine which is ongoing. There was immediate international condemnation and, in response, the G7 agreed to collectively protect the economic and financial stability of Ukraine and enforce increasingly severe sanctions that target Russia’s economy and leading Russian individuals.

The immediate economic impacts on the Ukrainian economy are unprecedented. Demand for Ukrainian sovereign debt fell sharply, with investors seeking a significant premium to hold it – the ‘yield to maturity’ on Ukrainian sovereign debt has almost tripled to 37% in the space of a week. Credit default swap markets priced in an 83 per cent probability of Ukraine defaulting on its commercial sovereign debt in the next 5 years. The Ukrainian currency fell to a 7-year low; it has stabilised at this level in the wake of Central Bank intervention but reserves are limited and Ukrainian USD sales in the first 6 weeks of 2022 exceeded those in the entirety of 2021. Ukraine was downgraded by both S&P (to junk status) and Fitch on the 25th of February and put on review for downgrade by Moody’s.
[note] https://cbonds.com/indexes/Cbonds-Ukraine-Sovereign-Eurobond-YTM-Index/
[note] https://www.ft.com/content/63054434-0904-4ec1-9004-dc6942413628; note on CDS

The Government of Ukraine’s financing gap is large and growing. Prior to the invasion, financing needs for 2022 were around $19bn and Ukraine intended to cover this primarily through domestic borrowing; this is no longer possible. The GoU has a $1bn sovereign bond due in September and made a $300m coupon payment due on 1st March. The Government raised ~$270m from a sale of ‘war bonds’ on March 1st, with a 1-year maturity and 11% yield.

On March 9, the IMF approved a disbursement of $1.4bn to Ukraine under the Rapid Financing Instrument (RFI) which will provide unconditional financial support. This followed a request from the Government of Ukraine. The RFI will help meet urgent balance of payment needs. Ukraine’s $5bn Stand-By Arrangement (SBA) with the IMF has been paused to enable the RFI disbursement.

Ukraine can borrow from two multilateral development banks (MDBs) in which the UK is a shareholder: the World Bank and the European Bank for Reconstruction and Development (EBRD). The EBRD provides financing primarily to support the private sector and does not have an instrument to provide sovereign budget support. EBRD will bring forwards a package of additional financing measures for Ukraine in the coming weeks .

The World Bank’s non-concessional sovereign financing arm for middle-income countries – the International Bank for Reconstruction and Development (IBRD) The IBRD has a budget support instrument, Development Policy Loans (DPLs) and it has DPL operations planned for March, June and September, focussed on energy and social support / pensions. The World Bank has rapidly established a multi-donor trust fund (MDTF) to enable grant donor finance to be channelled through the Bank alongside the March DPL.

1. Since 2014, the G7 and international financial institutions (IFIs) have provided more than 48 billion in combined bilateral and multilateral support to Ukraine. Since the invasion in February 2022, international partners, led by the G7, have committed additional economic support to Ukraine through grants, loans and guarantees. Some of this support is conditional and/or linked to IFI support, and the majority is still to be disbursed or operationalised :
  1. EU: EUR1.2bn of loans and EUR120m of bilateral grants for budget support.
  2. France: EUR200m of loans and up to EUR1bn of guarantees through French banks and conditional on using French suppliers and contracts.
  3. US: US$1bn of sovereign guarantees restricted by sector and linked to IMF conditionality. Up to $3bn of export credit facilitate the procurement of US goods and services via the Import Export Bank of the United States.
  4. Canada: US$489m in macro-financial loans linked to IMF conditionality.
  5. Germany: EUR300m in loan guarantees.
  6. Japan: US$100m loan for conditional budget support.
  7. Netherlands: EUR79.75m in IBRD loan guarantees.
  8. Sweden: US$50m in IBRD loan guarantees.

On 23 February 2022, as part of this coordinated international effort, the UK announced it stood ready to guarantee up to $500m of Multilateral Development Bank (MDB) commitments to Ukraine, subject to agreeing the exact support mechanism and going through the established approval processes. This guarantee will enable the MDB(s) to increase the overall size of their financing to Ukraine, reducing the fiscal financial gap. This will help safeguard Ukraine’s ability to maintain delivery of essential services and the operation of key state functions. On 7 March 2022, the UK announced a £74m grant contribution to a World Bank Multi-Donor Trust Fund (MDTF) in support of an IBRD DPL for Ukraine. This Business Case considers the delivery of MDB guarantees through the IBRD as well as the grant financing to be provided to the MDTF.
[note] https://www.gov.uk/government/news/uk-sets-out-new-multi-million-dollar-economic-package-of-support-for-ukraine

Including this business case, the UK will have committed a total of £394m in bilateral grants to Ukraine over the 21/22 – 24-25 period. This includes £220m in humanitarian support following the invasion, as well as £100m for energy security and reform committed prior to the invasion. The UK is retaining UK Export Finance (UKEF) cover to ensure that commercial trade and credit flows continue between the UK and Ukraine.

Need and Rationale

Ukraine urgently needs additional fiscal support to enable the Government to pay salaries, pensions, maintain safety nets and keep key state functions and essential services operating. The World Bank estimate that 2022 financing needs have risen by at least $2bn in the past week and that the financing gap faced by Government stands at $11bn - $12bn but is growing daily. IFI and donor support is critical to support closing this gap . This is additional to significant humanitarian needs that are not considered in this Business Case.

IBRD DPLs are a particularly valuable source of affordable external finance for Ukraine. They provide direct support to the budget of the Government of Ukraine and can provide greater volumes of finance than individual bilateral donors, often much more rapidly and without additional bilateral conditions from some other donors which can limit the effectiveness of their bilateral budget support.

The amount MDBs can lend to Ukraine is restricted by the Banks’ country exposure limits. The MDBs set an ‘exposure limit’ for each country based on the creditworthiness of that country, and therefore the level of risk they attach to lending to it. Lending headroom at both the IBRD and EBRD will have declined following the downgrades. The World Bank’s proposal to provide $3bn of financing this calendar year is likely to require additional shareholder guarantees to increase their exposure limit to Ukraine.

The invasion of Ukraine has led to refugee flows of more than 2 million people in just 13 days. Significantly greater numbers of people are internally displaced. There has been large-scale destruction of key infrastructure, including schools and hospitals, and there is intense pressure on services and infrastructure that remains. The poorest and most vulnerable Ukrainians are most acutely at risk from the war. The Government of Ukraine requires assistance to support these populations.

There is a significant political imperative to support Ukraine, both domestically and among the international community. The commitments from the UK and others are clear evidence of this. Aligning support to IBRD financing is a clear opportunity to provide rapid and coordinated financial assistance in a single package, limiting administrative burdens for the Government of Ukraine. The UK support to this broader financing effort provides a strong statement of support in line with UK leadership in establishing the International Ukraine Support Group.

Expected Results

At impact level, the UK’s contribution to IBRD financing for Ukraine will – as far as possible in the current circumstances – contribute to relative macroeconomic stability, support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion. Outcomes will reflect a reduced financing gap for the Ukrainian Government, the maintenance of essential payments and services, . The principal output is the volume of additional IBRD finance to Ukraine, over and above what could have been committed otherwise.

Wider assurances

As a shareholder in the World Bank, and one that has used guarantees in the past, the UK regularly engages with the World Bank about governance standards and assurances, risk appetite and risk mitigation and the quality and inclusiveness of programmes. During the IBRD approval processes the World Bank will seek to secure the necessary assurances while disbursing finance as rapidly as possible and managing the heightened risk. The World Bank has safeguards policies for DPLs, including an exclusion list for what can be financed (e.g. military expenditures). Operational Policy 2.30 sets out the World Bank’s policies and principles to supporting countries in conflict.

## Appraisal Case

Introduction to Appraisal Case

In comparison to G7 counterparts, the UK has a more limited set of instruments available to provide direct financial support to countries. The UK has neither an agreed framework to provide sovereign guarantees nor a direct sovereign lending capability for this purpose. In 2015, UK Ministers announced that DFID would no longer directly provide bilateral budget support, but we have continued to support the provision of budget support through International Financial Institutions, where we know there are trusted intermediary check and balances in place. The overarching objectives of UK fiscal support to Ukraine is to support macroeconomic stability and the continued provision of essential services as far as possible.

Options Appraisal

A do-nothing option has been dismissed. There would be substantial negative political implications to not acting in support of Ukraine’s economy, especially given others’ commitments.

1. There are 3 options for how the UK could provide fiscal support to Ukraine:
  1. Guarantee additional MDB commitments to Ukraine: This transfers risk from the MDB balance sheet to the UK and enables the MDBs to lend more than they otherwise would be able to for Ukraine (either through direct lending or through other approaches such as credit enhancement guarantees). A $500m guarantee (or series of smaller guarantees up to $500m) can support $500m in additional MDB commitments to Ukraine on a 1 to 1 basis.
    [note] Credit enhancement guarantees can improve the terms of a country’s access to international capital markets. The World Bank provided such a guarantee to Ukraine in 2018 and 2019.
  2. Guarantee a Eurobond issuance: The UK would guarantee $500m of a Eurobond issued by the Government of Ukraine. The FCDO would need to negotiate the terms of the guarantee with the Government of Ukraine. Such a guarantee would be similar to the Eurobond guarantees provided by the US Treasury (UST). Like UST guarantees, any payments made to the bondholder following the guarantee being triggered would not score as ODA. The FCDO does not currently have a framework in place to provide such guarantees.
  3. Grant finance: The UK would provide £74m (c. $100m) grant into a new World Bank multi-donor trust fund (MDTF) to co-finance planned World Bank lending to Ukraine. The £74m figure would position the UK as the largest contributor to the MDTF.
    [note] Japan have committed $100m in loans to the MDTF.

1. The options are appraised against 6 critical success criteria. These criteria are intended to ensure that the UK can provide timely fiscal support to Ukraine that aligns with the scale of need, while balancing this against the cost and key risks to the UK. Options are scored out of 10 against each criterion. These criteria are:
  1. Volume of fiscal support provided: Ukraine’s financial needs are significant. The volume of fiscal support provided should reflect this need.
  2. Financial risk: What is the financial risk (e.g. contingent liabilities) associated with the option?
  3. Financial & programming trade-offs: What is the likely scale of trade-offs across the wider FCDO portfolio in implementing each option?
  4. Speed: How quickly could the option be implemented?
  5. Terms of finance: How favourable are the terms of finance provided by each of the options?
  6. Fiduciary risks: What is the assessment of the residual fiduciary risks associated with each of the options?

Table 1: Scoring of options
	Guarantee MDB commitments	Guarantee Eurobond issuance	Grant finance
Volume of fiscal support	8	10	2
Financial risk	5	2	10
Financial & programming trade-offs	8	5	2
Speed	6	2	9
Terms of finance	8	5	10
Fiduciary risks	5	3	5
Total score	40	27	38

Volume of fiscal support: The guarantees score considerably higher under this criterion, as they can support a much larger volume of additional finance to Ukraine than grants alone. The Eurobond issuance guarantee scores slightly higher than the MDB guarantee because an equivalent size of guarantee would likely support a larger overall financing package (i.e. a $500m guarantee might be in support of a ~$700m Eurobond issuance).

Financial risk: Grant finance scores the highest as it carries no further financial risk after the grant is disbursed. The Eurobond guarantee carries a significant financial risk especially in the context of Ukraine and scores lower than the MDB guarantee. Interest exposure on a given principal Eurobond guarantee is likely to be higher and the UK does not implicitly benefit from the MDBs’ preferred creditor status (PCS) which increases the risk of default. The MDB guarantee involves a manageable level of risk over a long (c. 20 year) period.
[note] The lending associated with a guaranteed Eurobond issuance is likely to have higher interest rates than MDB lending. See paragraph 28.
[note] This reflects that MDBs are generally given priority for repayment of debt in the event of a sovereign borrower experiencing financial stress.

Financial & programming trade-offs: There are significant trade-offs to grant financing of fiscal support to Ukraine, especially in the context of increasing humanitarian need which will also require assistance. Grant financing to a World Bank MDTF will score as RDEL and would require savings from other bilateral portfolios . The guarantee options only require spend if called, and as such score better, but face different potential trade-offs. Both guarantees would count against the FCDO’s guarantee risk limit for contingent liabilities which could create trade-offs with other planned guarantees .
[note] .

Speed: The World Bank has rapidly established a new MDTF to channel partner grant contributions in support of planned lending operations to Ukraine and will make its first disbursements alongside the March Supplementary-DPL (S-DPL). An MDB guarantee could also be operationalised relatively quickly although not as fast as a grant. Guaranteeing a Eurobond issuance would take significantly longer to operationalise – the UK does not have an existing framework in place for providing this kind of support to countries and agreement with HMT would be required over how any non-ODA costs would be covered.
[note] A Supplementary DPL (S-DPL) is essentially an add-on to a previous DPL, requiring no further prior actions be completed before the disbursement of funds.

Terms of finance: Grant finance does not need to be repaid by the recipient country and so scores highest. Guaranteeing MDB commitments also scores well because reference interest rates (particularly when borrowing in EUR) are negative, and so effective interest rates on MDB lending can be as low as 0.1%. Guaranteeing a Eurobond issuance would result in less favourable terms than MDB lending.
[note] The AAA-rated IDB guaranteed 75% of a sovereign bond issuance by Ecuador in 2020. This resulted in an estimated 225 basis point improvement on the terms it would have been able to secure otherwise (estimated at 9.5%). A UK guarantee may not secure such a pricing benefit as the UK’s sovereign credit rating is below AAA.

Fiduciary risks: Guaranteeing MDB commitments and grant finance through a WB MDTF are both assessed as having equivalent fiduciary risk as they are essentially the same (MDB) channel for financing, with equivalent monitoring and reporting. Fiscal support from MDBs generally flows to designated government bank accounts which are used for specific purposes (i.e. pensions, salaries etc). . Guaranteeing a Eurobond issuance is assessed as higher fiduciary risk as there would be no MDB monitoring and reporting processes in place.

MDB guarantees and grants are both high-scoring options. The guarantee can support a greater volume of financing than the grant and avoids up-front financing costs and associated programming trade-offs, but the grant can be disbursed quicker and offers more favourable terms for the Government of Ukraine. The context in Ukraine is shifting rapidly and the speed as well as volume of financing is of increasingly critical economic and political importance. The recommendation is to take forward both the MDB guarantee and MDTF grant financing options with a view that the grant financing can be disbursed as soon as possible in FY22/23 ahead of the guarantee which may not be utilised until June 2022.

Guaranteeing MDB operations
There are two key choices in implementing a UK guarantee of MDB commitments to Ukraine: which MDB(s) to support with guarantees, and which MDB commitments to guarantee. The latter is discussed in more detail in the commercial case.

EBRD and IBRD are the two MDBs that can provide sovereign financing to Ukraine. This business case does not consider guarantees for EBRD. The UK shareholding in EBRD is led by HMT and an EBRD guarantee would require sign-off through HMT processes. HMT are exploring this option in parallel and have requested that $50m of the announced guarantees be retained for potential support to EBRD; this would leave $450m of the total announced volume of guarantees that could be allocated to IBRD. IBRD is likely to be a more viable and effective option for using guarantees to support additional fiscal support, given the UK’s previous experience in providing guarantees to support additional IBRD lending to Egypt, India, Iraq and Jordan and the IBRD’s development policy loan (DPL) instrument which can provide direct support to the Government of Ukraine’s budget. The EBRD primarily finances the private sector, and its sovereign support does not have an equivalent budget support instrument.

.

Future operations and any associated prior actions are being kept under review based on developments in Ukraine. .

Mitigating the programming trade-offs of grant financing
The appraisal case identifies the financial & programming trade-offs as a major disadvantage to providing grant finance. The business case and programme team considered funding part of the grant contribution by reallocating existing energy security commitments to Ukraine to reduce trade-offs with other bilateral allocations in 22/23 and to make the funding committed to energy security available sooner. The Foreign and Development Secretary provided a clear steer to proceed with a fiscal grant and protect existing energy security commitments to maximise the impact of the UK’s economic support package for Ukraine. .

Recommendation: Approve up to $450m in guarantees for IBRD financing operations to Ukraine, and £74m in additional grant finance to the World Bank’s MDTF in support of the March S-DPL, disbursing as soon as possible in FY 22/23. The decision on which IBRD operations to guarantee will be taken by the SRO in consultation with International Financial Institutions Department (IFID), UKDEL and FCDO Finance. Guarantees will only be issued if they support financing that is additional to the World Bank’s own lending plans.

The full approvals process for the details of the guarantee are set out in the management case; final guarantee agreements will only be signed once the details are agreed between the World Bank, FCDO and HMT. Business case approval is being sought now to enable the UK to respond rapidly and flexibly to the IBRD’s need for guarantees to extend lending to Ukraine.

Theory of Change for Preferred Option

The Government of Ukraine is in critical need of fiscal support following the Russian invasion. The combination of guarantees and grants to support broader World Bank financing to Ukraine is intended to deliver a package of support that is both timely and recognises the scale of need.

The key inputs in the intervention are World Bank financing operations and accompanying guarantee(s) and grant financing from the UK to expand the size of those operation(s). The UK guarantee should enable an equivalent volume of additional IBRD lending to Ukraine, over and above what could have been committed otherwise, in support of macroeconomic stability. This is the primary output related to the programme.

The World Bank is understandably taking an incremental approach to using up its own exposure limit for Ukraine. The UK will only issue a guarantee to the World Bank that if it supports financing that is additional to the Bank’s own lending plans. The UK guarantee will be in support of planned IBRD financing to Ukraine; this will enable additional direct support to the budget of the Government of Ukraine and has the advantage of being quick to operationalise given that they are already in the pipeline .

The intention is that the guarantee and grant will contribute to reducing the size of the Ukrainian government’s financing gap, maintain essential services and payments, and more broadly help to address market concerns regarding Ukraine’s ability to meet its financing obligations in the wake of the conflict. The guarantee and grant can make a direct contribution to the size of the financing gap by enabling up to $550m of additional affordable financing for Ukraine but is clearly insufficient to address it alone. The intention is that along with commitments from other donors, the UK guarantee and grant will act as a strong signal of support for the Ukrainian economy, . This requires other donors to follow through on their existing commitments and likely signal the potential for further support.

These outcomes will be assessed by monitoring key economic indicators set out in the results framework. Any attribution to UK support should be seen as one part of a wider package made up of contributions and commitments from a group of like-minded international donors. The UK announcements of both guarantee and grant financing may act (or already have done so) as a pull factor for contributions from others. Further escalations in the conflict will diminish the ability of the guarantee to support market confidence as financing needs are likely to grow rapidly.

The overall intended impact of UK support is to support macroeconomic stability in Ukraine, support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion. This would in turn help to limit increases in the poverty rate and in the long-term potentially support a quicker economic recovery from the conflict. In practice, it must be recognised that UK support is a form of emergency financing, and contribution to any longer-term impacts will be very hard to ascertain. . The UK package of support should be considered on a no-regrets basis given the scale and urgency of the need.

VfM Measures

The following VfM assessment has been made drawing on the ‘four Es’ framework, and within the overarching objective of supporting macroeconomic stability in Ukraine by providing timely fiscal support that aligns with the scale of need:
- Economy: collectively, the guarantee and grant support a significant volume of additional finance to Ukraine at a relatively small up-front cost to the UK. The UK’s exposure to the guarantee reflects the terms of IBRD financing to Ukraine: the highly favourable terms (compared to international capital markets) offered (long maturities and low interest rates) limit in-year exposure for the UK. There is a cost to channelling grants through a World Bank MDTF but it has broader effectiveness benefits.
- Efficiency: the average risk-adjusted in-year exposure of the guarantee is currently estimated at around £5m, and in-year exposure will be minimal for the grace period (see Financial Case). The Ukraine guarantee will carry greater risk than other UK guarantees to support MDB lending for macroeconomic stability, but this reflects the context in Ukraine. In supporting additional finance to Ukraine, a UK guarantee of IBRD lending is likely a much more efficient use of risk on the
  [note] The average is calculated across the lifetime of FCDO’s guarantee portfolio and not the maturity of individual guarantees. See Table 2.
  [note] The Egypt, Iraq and Jordan guarantees have average yearly expected losses of £1.2m, £3.2m and £1.1m, respectively.
- UK’s balance sheet than guaranteeing a Eurobond issuance, given the less favourable terms associated with a UK-guaranteed Eurobond and the implied higher risk of default because of a lack of preferred creditor status (PCS).
- Effectiveness: Direct support for the government budget enabled the Government of Ukraine to maintain funding for essential services . Supporting IBRD financing increases the speed with which financing can be disbursed to the Government of Ukraine, with all funding operating within the World Bank’s processes. It is also reduces the administrative burden for the Government of Ukraine as they only have to deal with the World Bank and not various individual donors. The World Bank will disburse funds directly into designated bank accounts for specific purposes related to the financing agreement.
- Equity: There is a strong need for additional finance in Ukraine to support the core functioning of the state and continue providing some form of continued social safety net.

Summary VfM Statement for Preferred Option

A UK guarantee to support additional MDB lending to Ukraine represents good value for money given the broader context and political imperative to provide fiscal support to Ukraine. The guarantee has no up-front cost and therefore does not present immediate trade-offs with other spending programmes. It is an efficient use of risk on the UK’s balance sheet in comparison with other options, and the IBRD’s favourable lending terms and PCS limit the UK’s total in-year exposure. Guaranteeing planned World Bank financing enables UK support to be clearly aligned with a larger overall financial package that can be disbursed rapidly to the Ukrainian government and support core functioning of the state and a continued social safety net. This business case is also clear that the guarantee carries significant risks – both financial and fiduciary – but that these are mitigated by safeguards put in place by the World Bank (see Table 3) and more broadly that this is an extraordinary scenario in which the costs of not acting significantly outweigh these risks.

## Commercial Case

Guarantee: Contractual details and type of agreement

As recently as the week of 14 February, we understood the World Bank had sufficient headroom to cover planned lending to Ukraine for 2022. However, Ukraine was downgraded by two ratings agencies on the 25th of February, increasing the World Bank’s assessment of the credit risk of lending to Ukraine and reducing its country exposure limit. The World Bank expedited plans for the March S-DPL in the wake of the invasion of Ukraine.

FCDO will stand ready to provide a financial guarantee to the World Bank to cover risks of default up to a maximum of $450m (or EUR-equivalent, approximately EUR400m) in principal. This would be paid out on an unconditional basis if scheduled payments under any of the guaranteed loans are missed and move into non-accrual status (more than 180 days late on payments). FCDO guarantees will only be issued if they support financing that is additional to the Bank’s own lending plans. Approval for the Business Case is being sought now to ensure the UK can be flexible and responsive to the needs of Ukraine in providing a guarantee. Further details on the likely structure of guarantees under this Business Case are provided in the Financial Case.
[note] Ukraine has recently chosen to borrow in EUR from the World Bank.

In principle the FCDO could charge the World Bank for the provision of a guarantee to reflect the risk that is being transferred. This fee would likely be passed on to the Government of Ukraine as the borrower in some form. The FCDO has not charged a fee for any of its previous guarantee agreements with the World Bank, and there would be reputational risks to introducing a fee for a guarantee to Ukraine in the current context. In line with previous guarantees to the World Bank, the recommended course of action is for the UK not to charge a fee.

Grant finance

The UK’s grant contribution will be made to a recipient executed World Bank MDTF. The World Bank charges a sliding scale of fees based on cumulative commitments to the Trust Fund; This covers all costs related to the administration of funds, staff costs for managing the trust funds, treasury functions of execution and is a centrally agreed fee in line with the reforms introduced as part of the 2021 Trust Fund policy.
[note] 5% on first $50m committed, 4% on the next $450m committed and 3% on next $500m committed and 2% thereafter.

An option was also considered to provide the grant directly to the Government of Ukraine. This would likely have lower associated costs than the MDTF but would carry increased financial and reputational risks to the UK. The UK has not provided direct bilateral budget support since 2015. It would also require greater administrative effort for both the UK and the Government of Ukraine and take longer to disburse; the Ukrainian Ministry of Finance has explicitly emphasised a preference for fiscal grants to be coordinated through the World Bank. Given all these considerations, this option was rejected.

Risks

Foreign exchange: FCDO will provide a guarantee to the World Bank denominated in the same currency as the loan(s) to Ukraine (i.e. USD or EUR). A GBP-denominated guarantee could expose the World Bank to a currency mismatch at the point the guarantee was triggered .

Denominating the guarantee in the currency of the loan enables the World Bank to release significantly more lending for Ukraine than would otherwise be the case. However, this would expose the UK to exchange rate risk: should the guarantee be triggered at a time when GBP is weaker against the USD or EUR than its current level, UK payments to the World Bank would cost more than the initial estimate. Conversely, should the guarantee be triggered at a time when the Pound is stronger than its current level, the UK payments would be cheaper. The exchange rate risk will be monitored regularly as part of the management of the guarantee.

It is complex to assess the value for money of providing the guarantee in USD or EUR using a benefit/cost framework. . In practice, the UK obligations (and any resulting payments) under both options would be the same, and the UK would continue to face additional exposure to interest payments. In line with the approach taken in previous guarantees to the World Bank, the recommended option is to issue a guarantee denominated in the currency of the loan and accept and monitor the exchange rate risk. If the UK has influence over the currency of the loan guaranteed, it is recommended that the UK guarantees a EUR-denominated loan; this is expected to reduce the overall and in-year exposure of the guarantee (see Table 2 – Financial case).
[note] Previous guarantee business cases have used the ‘grant equivalent’ of additional lending enabled by the guarantee to estimate the benefit. The IMF/WB grant equivalent is assessed against a fixed 5% discount rate and will decline if the interest rate increases. In practice, the alternative commercial terms for additional Ukrainian sovereign borrowing would likely increase by at least as much as any increase in the variable reference rates used by the World Bank. The grant equivalent is therefore not particularly useful when comparing MDB terms to those on commercial capital markets.

The grant commitment (and payment to the World Bank) will be made in GBP. This ensures there is no exchange rate risk to the value of the UK’s grant commitment. The World Bank will immediately convert the GBP received into the currency it will disburse funding to Ukraine, so it does not experience exchange rate risks.

Interest rate: The guaranteed World Bank lending to Ukraine will have a variable interest rate. The UK will consequently face an interest-rate risk related to the value of its guarantee. If interest rates (and/or the IBRD’s spread) increases, the UK’s exposure to the guarantee will also increase. At the end of January 2022, major banks were pricing in US interest rates rising to 1.5% to 2% by year end; estimating exposure based on current IBRD interest rates is highly likely to understate the maximum exposure the UK could face.
[note] Compared to current Federal Funds rate of 0.25% and 6M Term SOFR reference rates of 0.65% (March 3rd, 2022).

1. The UK has three options to manage this risk:
  1. Accept and monitor the risk;
  2. Fix the UK’s total nominal exposure; or
  3. Hedge the risk.

Option II would result in a haircut on the size of the principal that could be lent to Ukraine. The size of the haircut would depend on the context, the terms of the guarantee and the nominal exposure cap but is likely to be significant. Option III would involve purchasing a hedging instrument to remove the risk from the SOFR or EURIBOR component of the interest rate, but risk would remain on IBRD’s variable spread which cannot be hedged. The cost of such an instrument was estimated for the Egypt guarantee and was significant. It would also contravene HMT’s Managing Public Money guidance that central government organisations should not purchase insurance. The financial risk associated with increases in interest rates is estimated to be small in comparison to the scenario in which interest rates stay at their current rates (see Financial Case). The preferred option is therefore to accept and monitor the risk, as with previous UK guarantees to support World Bank lending.
[note] At the time the Egypt Business Case was written, the total principal ($150m) and interest ($70.5m) exposure at prevailing interest rates was estimated at $220.5m. Applying a nominal exposure cap of $220.5m to total UK exposure would have resulted in a 31% ($47m) haircut in the value of additional lending that could be supported.
[note] At the time of the Egypt Business Case, the cost of the hedging instrument would have been 19% of the amount of principal guaranteed.

The exchange rate and interest rate risks interact with each other as well as with the terms of lending guaranteed and the risk of default. The financial case outlines how these risks and considerations can jointly affect UK exposure.

Commercial considerations affecting Value for Money

Providing fiscal support to Ukraine through a combination of a guarantee(s) and grant finance via the World Bank represents good value for money for FCDO for the following reasons:
- The combination of grant and guarantee strikes a good balance between making some assistance available as soon as possible while ensuring that a larger volume of finance can follow.
- The guarantee can unlock an equivalent volume of lending from IBRD without HMG having to release additional funds up front.
- It increases the volume of affordable finance available to Ukraine when its access to domestic and international borrowing is severely curtailed.
- Providing support through the World Bank ensures that World Bank monitoring and reporting processes are followed. It also reduces the associated administrative burden for both the UK and Ukraine.

Recovery process

If the Government of Ukraine defaults on a loan repayment, and the UK makes the covering payment to the World Bank the UK will decide at that point on the treatment of any recoveries of unpaid funds from Ukraine. There would be three potential options:
1. The UK assumes ownership of the rights to the guaranteed portion of the missed repayment, with the right to pursue recoveries bilaterally. In such a case, the UK guarantee payment would be viewed as purchasing a loan asset from the World Bank and would require FCDO to incur a non-ODA charge to make the payment. The size of the non-ODA charge would be equivalent to the size of the payment, minus the grant equivalent element (which would score as ODA). Given that the expectation would be for the GoU to repay as quickly as possible, the grant equivalent would be zero and the entire payment would be non-ODA. FCDO does not have a non-ODA budget for this purpose.
2. The UK assumes ownership of the rights to the guaranteed portion of the missed repayment, but immediately agrees not to pursue recoveries, in effect granting debt relief to Ukraine. Unilateral debt relief is not ODA eligible and so unless this was coordinated with wider agreement to provide debt relief to Ukraine, the entire payment would be non-ODA. More broadly, this unilateral approach would not be consistent with UK policy on debt relief.
3. The UK forgoes the right to any recoveries, and the right remains with the World Bank. In this case, the payment to the World Bank would be classed as 100% ODA. The World Bank would decide whether to pursue recoveries or not, and in the case that it did and obtained recoveries, would consult with FCDO on their appropriate use.

What assurances have been obtained on the organisation’s capability and capacity to deliver

Core competences of organisation to deliver in-country
The World Bank will act as administrator for the guarantee arrangement and grant financing flowing through the MDTF and will monitor and manage the risks on our behalf, in accordance with their own policies and procedures, including procurement, financial management, disbursement and safeguards (environmental and social) policies, prevention of fraud, corruption and the use of resources to finance terrorist activity.

1. The World Bank are a trusted partner to the Ukrainian Government with a track record of successful delivery. The UK has an established partnership with the World Bank through contributions to a regional Trust Fund.
2. The World Bank will disburse funding into designated bank accounts related to the specified purposes of the financing. .

Procurement Capability
As the DPL provides unearmarked and on-budget financing to the Government of Ukraine, they will be responsible for the use of the money and all procurement that results.

## Financial Case

Budgetary implications for FCDO

Guarantee
This agreement will enable the UK to guarantee up to $450m (approximately £335m) of loan principal repayments from the Government of Ukraine to the World Bank, plus interest repayments. The interest rate on the loan(s) will be variable, and so UK exposure to interest repayments is uncertain. Under the terms of lending agreed for the March 2022 S-DPL to Ukraine, the interest repayment exposure to a $450m (or EUR-equivalent, approximately EUR400m) guarantee at current interest rates would be $82m or EUR11m depending on the currency of lending. If Ukraine sought to borrow at longer maturities, the total exposure would increase. Both principal and interest exposure are subject to exchange rate risk. This is discussed further in Table 2 (Affordability). It is expected that Ukraine will seek to borrow in EUR and therefore the UK’s guarantee would be EUR-denominated. The assessment of USD-denominated guarantees is primarily for sensitivity analysis.
[note] Fixed spread terms are currently suspended for new IBRD borrowing.
[note] The March 2022 DPL has a 5 year grace period and 18 year maturity, resulting in an 11.75 year average maturity.
[note] IBRD lending terms here, using 6M Term SOFR or 6M Euribor. EUR interest exposure is small because EURIBOR rates are currently negative.
[note] Under a 5-year grace period and 34-year maturity, the maximum interest exposure at current rates would be $177m or EUR53m. This reflects both higher IBRD spreads on longer maturities and the principal being paid off over a longer period.

The guarantee(s) will have no immediate budgetary impact in DEL. They will be disclosed as a financial guarantee (contingent liability) in FCDO’s Annual Report and Accounts and Annual Estimates when the agreement(s) is/are signed. In line with the UK Government Financial Reporting Manual, an initial provision will be recognised using non-cash Resource Annually Managed Expenditure (RAME) budget, to reflect the fair value of the guarantee. This will be the equivalent of the lifetime expected credit loss of the guarantee. The guarantee will only have a DEL impact at the point at which the guarantee is triggered, and a payment request is made by the World Bank. Then the cash impact and ODA impact will be at time of payment (usually 30 days after payment request is made).

FCDO will retain the flexibility to issue one or more guarantees to the World Bank up to the $450m exposure limit on principal loan repayments. The process for agreeing the final details of the guarantee agreements is outlined in the Management Case.

Grant
The fiscal grant will score as RDEL and will be disbursed as soon as possible in the 22/23 financial year. It represents an additional ODA allocation to Ukraine for FY 22/23.

Default

Repayments on the guaranteed loan(s) will be due twice yearly. If the GoU misses a scheduled repayment and remains in arrears on the payment for a period of 180 days, the World Bank will issue a payment request to FCDO for the value of the share of the due repayment to the World Bank covered by the guarantee (calculated pro-rata) with payment terms of 30 days.
[note] For example, if the UK provided a $100m guarantee to increase the size of a loan from $100m to $200m, the World Bank would issue a payment request to the UK for $100m / $200m = 50% of the value of the missed loan repayment.

The accounting treatment would be as follows:

  1. If an outflow of resources from FCDO becomes probable – i.e. there becomes a greater than 50% likelihood of GoU defaulting on a loan repayment(s) and therefore triggering the guarantee – FCDO will increase the provision to the likely amount of the default in its Non-Cash Resource Annual Managed Expenditure budget (RAME). FCDO will make an assessment whether to fully provide for the remainder of the guarantee in RAME.
  2. The payment would be recognised as an accrual in DEL once it is certain that the guarantee will be called (and the RAME provision would be released). The World Bank terms usually include a 180-day period for the country to repay the defaulted amount before the guarantee is called. The charges incurred by FCDO will depend on the value of the guarantee(s) and terms of the underlying loan(s). Assuming a single $450m guarantee for simplicity and using the terms of the March S-DPL, the missed principal charge would be approximately £12.9m, plus an interest charge initially starting at £2.6m (£0.6m if EUR-denominated loan). Both charges would be CDEL. With the assumed structure that there are two scheduled repayments for each calendar year, the maximum financial risk to FCDO is likely to fall in FY28/29. Under baseline assumptions, the current estimate of the maximum in-year exposure is £31m if USD-denominated or £26m if EUR-denominated and both are subject to further exchange rate and interest rate risks.
    [note] For example, if the UK issued two $225m guarantees associated with different loans then if Ukraine defaults on one it will almost certainly also default on the other. So assuming a single $450m guarantee just a simplification of this.
    [note] June and December.
  3. Any payments will be made from the fiscal Capital DEL (CDEL) budget.

At the point of a default, should the UK choose to pursue recoveries (‘option I’ in paragraph 58), any subsequent repayments from Ukraine would be surrendered to HMT’s consolidated fund.

The World Bank has a standard contracting condition that retains the right to ‘accelerate the loan’ at the point when the guarantees are triggered; this would place the entirety of the loan into immediate default. As with previous World Bank guarantees, FCDO will secure agreement that the UK’s guarantee obligations are limited to scheduled repayments, and so in the event of default the UK loan guarantee would not be accelerated. In this case loan guarantee payments would continue to fall as per the originally agreed repayment schedule of the loan.

If three payments are missed sequentially, then the full value of the outstanding contingent liability will be immediately provisioned for in RAME (RAME expense). As future defaults occur, the RAME provision will be gradually wound down (RAME income) as CDEL payments are made. The profile of CDEL payments will follow the profile of the original repayment schedule agreed between the IBRD and GoU, even if the IBRD decides to write off the loan, so there is no risk of a larger than expected CDEL impact in any one year.

Affordability

Guarantee
RAME: FCDO’s RAME budget is reviewed twice annually as part of the Main and Supplementary estimates processes. FCDO does not have a fixed annual allocation and as such is usually able to adapt to changing circumstances by increasing or reducing its bid to HMT accordingly. However, the latest opportunity to do this in each financial year is December and so it is essential that there is good monitoring of the risk of a call on the guarantee to ensure that enough RAME cover is sought. RAME is a control total, and a breach would result in FCDO’s annual report and accounts being qualified, which would lead to a Public Accounts Committee hearing

CDEL: Annual charges in the event of a default would need to be met from FCDO’s existing CDEL allocation through reprioritisation of planned spend in-year. The maximum annual payment associated with a default in a baseline scenario is currently estimated at £31m at prevailing interest and exchange rates; this would represent less than 2% of FCDO’s fiscal CDEL budget for FY21/22.

1. We consider 5 scenarios for each of the USD and EUR denominated guarantees to assess their affordability under various stress scenarios. These scenarios are:
  1. Baseline: Current interest and exchange rates; 5-year grace period and 18-year maturity as per March 2022
  2. Long maturity: Current interest and exchange rates; 5-year grace period and 34-year maturity.
  3. Exchange rate risk: Current interest rates, GBP immediately depreciates 15% against the USD/EUR and remains there for duration of guarantee; 5-year grace period and 18-year maturity.
    [note] A 15% depreciation against the USD would mean GBP sitting at an annual average considerably lower than at any point in the last 50 years.
  4. Interest rate risk: SOFR and EURIBOR rates immediately rise to reflect 20-year US Treasury (USD) / German Bund (EUR) rates and remain there for the duration of the guarantee, current exchange rates; 5-year grace period and 18-year maturity.
    [note] This is a proxy for a significant interest rate rise over the period of the guarantee. This scenario is likely to overstate the exposure risk in the short term even in an interest rate stress scenario as any increase in interest rates will almost certainly be gradual.
  5. Stress scenario: A combination of the interest rate and exchange rate scenarios. The long maturity scenario is not included because while it increases total exposure, maximum and average in-year exposure is reduced.

Table 2: UK exposure under different scenarios
	Total exposure (USD / EUR)	Maximum in-year exposure (USD / EUR)	Average in-year exposure / (USD / EUR)	Average risk-adjusted in-year exposure, 40-year lifetime (USD / EUR)	Average risk-adjusted in-year exposure, loan lifetime / (USD / EUR)	Risk-adjusted lifetime exposure (USD/EUR)
Baseline	£397m / £342m	£30.8m / £26.4m	£20.9m / £18.0m	£5.1m / / £4.6m	£10.8m / £9.6m	£205m / £182m
Long maturity	£469m / £378m	£18.1m / £13.7m	£13.4m / £10.8m	£6.8m / / £5.7m	£7.8m / / £6.5m	£273m / £227m
Exchange rate risk	£457m / £394m	£35.4m / £30.3m	£24.1m / £20.7m	£5.9m / / £5.2m	£12.4m / £11.0m	£236m / £209m
Interest rate risk	£462m / £367m	£35.9m / £28.3m	£24.3m / £19.3m	£5.8m / / £4.8m	£12.2m / £10.1m	£231m / £192m
Stress	£531m / £422m	£41.3m / £32.6m	£27.9m / £22.2m	£6.7m / / £5.5m	£14.0m / £11.6m	£266m / £221m
[note] We include two measures for risk-adjusted in-year exposure. The FCDO guarantee portfolio has a 40-year lifetime, which is the basis for assessing in-year exposure risks against FCDO’s agreed limit. The ‘loan lifetime’ average risk-adjusted in-year exposure is included to highlight the impacts of different loan maturities.

Compared to baseline assumptions, the stress scenario increases total exposure, maximum in-year exposure and average in-year exposure by approximately 34% for USD-denominated guarantees and 23% for EUR-denominated guarantees. The USD-denominated guarantee experiences a larger increase in exposure under stress because it involves a larger increase in interest rates. The total risk adjusted exposure under the EUR-baseline scenario is £182m, rising to £221m under the EUR-stress scenario. This compares favourably to the full cost (~£335m) of an equivalent grant financing contribution.

Figures 1 and 2 present estimated in-year exposure and risk-adjusted in-year exposure over the lifetime of the guarantee under the EUR baseline and stress scenarios. The focus on the EUR-denominated guarantee reflects that Ukraine has recently chosen to borrow in EUR from the IBRD. In-year exposure peaks in the first year for which two principal payments are due (FY28/29). In-year exposure declines from this point as principal payments are made and consequently the interest charge declines.

In contrast, risk-adjusted in-year exposure is at its maximum in FY39/40. This reflects that the risk-adjustment accounts for the likelihood that Ukraine has defaulted on a single payment at a given point in the loan’s lifetime; this likelihood increases over time. The approach to estimating the cumulative likelihood of a single missed payment is discussed in paragraph 83, but it should be noted that the baseline approach presented here is a conservative one that reflects the uncertainty around the context in Ukraine.

Figure 1: UK in-year exposure, £m

Figure 2: UK risk-adjusted in-year exposure, £m

.

Grant
.

Monitoring risk of default

As the CDEL charge would materialise after a delay of 180 days in the World Bank receiving payment from the Government of Ukraine, FCDO will maintain regular channels of communication with key World Bank stakeholders, including a formal process for flagging milestones in escalating risk to ensure HMG receives early warning of any heightened default risk, thereby allowing a provision to be made in AME and contingency plans to be put in actions to deliver the required DEL resource in that financial year.

Details on the process for monitoring default risk are set out in the Management Case.

ODA eligibility

The ODA eligibility of any triggered guarantee payments would depend on which option was chosen for the treatment of recoveries (paragraph 58). Options I (UK pursues recoveries bilaterally) and II (UK grants debt relief) would likely require at least part of the payment to be classed as non-ODA. The DAC Secretariat has indicated that under Option III (UK forgoes rights to recoveries), payments resulting from the guarantee being triggered would score 100% as ODA under the current rules. Given the non-ODA implications, the programme team and SRO would discuss with FCPD and HMT before deciding whether to seek recoveries or not, in the event of default

Financial risks

Context: FCDO’s maximum exposure will be the GBP equivalent of $450m of principal plus interest. The maximum interest exposure is currently estimated at the GBP equivalent of $82m or EUR11m depending on the currency denomination of the loan, but the guaranteed loan(s) will carry a variable interest rate, so this amount could increase or decrease with global interest rates. The maximum exposure will reduce annually if the Government of Ukraine meets its repayment schedule with the World Bank.
[note] As discussed in paragraph 62.

Default risk: Default risk is best proxied by Ukraine’s sovereign credit rating. Ukraine was downgraded by both S&P (B to B-) Fitch (B to CCC) and put on review for downgrade by Moody’s (from B3) on 25th February. .

Fraud and Fiduciary Risk: HMG funding will not be provided directly to the Government of Ukraine at the time of the guarantee being called. FCDO is content that the IBRD’s financial accountability policies and practices are robust. The IBRD has strong internal audit procedures and a well-established fraud detection system. The World Bank will disburse funding into designated bank accounts related to the specified purposes of the financing agreement. .

Exchange rate risks: The value of the principal guaranteed by FCDO will be fixed in the currency of the loan agreement in line with previous UK guarantees to the World Bank (paragraphs 49 - 52). The potential impact on FCDO’s balance sheet and cash flows – should the guaranteed loan(s) default – will be subject to movements in the conversion value of USD to GBP. Should FCDO decide to pursue recoveries, there would be a risk to the net CDEL budget position in that the loan recoveries repaid to FCDO would not necessarily equal the GBP amount paid to the World Bank on trigger of the guarantee. This would need to be monitored closely so that contingency planning could consider any growth or reduction in the liability. The FCDO Finance Director will confirm that they are content for FCDO to take the currency risk.

Risk mitigation: HMT’s Managing Public Money guidance states that “central government organisations should not normally buy commercial insurance to protect against risk. Since the government can pool and spread its own risks, there is little need to pay the private sector to provide this service. In general, it is cheaper for the government to cover its own risks”. Self-insuring is therefore preferable to paying the World Bank to remove exchange and interest rate risks.

## Management Case

Management arrangements

1. The fiscal support package will be managed in FCDO by a Programme Manager to be recruited into the Ukraine programme team. The SRO will be the BE Kyiv Development Director / Head of Programmes
2. The SRO will lead on monitoring the risk of default regularly and through a formal annual process involving carrying out a Default Risk Assessment (DRA) at the end of the financial year, in line with central requirements. The content of the annual DRA would draw from that of the Iraq and Egypt guarantee DRAs, with additional context-specific indicators for Ukraine. This involves monitoring key macroeconomic risks; it will also assess developments in the conflict. The assessment will be carried out with input from the IMF and World Bank. The SRO will report the findings to FCDO’s Finance Directorate, as well as monitoring progress against the World Bank Development Policy Loan reforms.
3. The Financial Transactions Steering Board will provide oversight of the guarantee, in line with the recent update on the governance of guarantees. The guarantee will be disclosed in FCDO’s annual report and accounts.
4. The team will draw on other FCDO colleagues in BE Kyiv, International Financial Institutions Department (IFID), and wider Eastern Europe and Central Asia Directorate (EECAD) shared advisors to provide expertise not already covered in the team, the UK’s WB Delegation, and the WB regional team with responsibility for the World Bank financing. The SRO will also manage the relationship with HM Treasury around the guarantee.
5. There is explicit statutory authority under the 2002 International Development Act for the issue of Guarantees.

Approval process

FCDO
1. This business case seeks approval for the issuance of up to $450m in guarantees to support additional IBRD financing to Ukraine and £74m in additional grant finance to the World Bank’s MDTF in support of the March S-DPL. The structure of the guarantee(s) is not yet decided because, as argued in appraisal and commercial cases, retaining flexibility is critical to maximise the impact.
2. The full approvals process for issuing the guarantee is outlined below. Ministerial approval is being sought before the final details of the guarantee have been agreed to ensure the UK is able to move quickly to negotiate with the World Bank and maximise the impact of the guarantee. Further assurances following Ministerial approval will ensure that a guarantee still delivers VfM for the UK. The Business Case SRO will ensure the approval process is followed.
Approval of the Business Case
  1. Financial Transactions Steering Board (FTSB) approval of BC via email. The FTSB oversees FCDO’s contingent liabilities and ensures the risks associated with them are manageable and within agreed limits.
  2. Investment Committee approval
  3. FCDO Ministerial approval of BC
  4. HMT approval of BC by the Chancellor, following clearance by FCDO spending and contingent liabilities teams
Following Business Case approval, the FCDO team managing the guarantee will negotiate the structure and details of the guarantee with the World Bank, ensuring close engagement with HMT.
  1. Parliamentary Approval – requiring a Departmental Minute to sit in Parliament for 14 sitting days (alongside Written Ministerial Statement). If there is a need to report an urgent contingent liability with less than the required 14 days’ notice, then FCDO would need to explain the need for urgency, agreeing this with HMT, and write to the chairs of the Public Accounts Committee (PAC). This would usually be the final step but Parliamentary approval will be sought early to enable the UK to move quickly to issue a guarantee once the details are agreed.
  2. The SRO for the guarantee, in consultation with IFID and UKDEL, will decide which World Bank loans to guarantee.
  3. Approval of the guarantee details, structure, and risk assessment by HMA Ukraine, FCDO IFD Director, HMT Director.
  4. FCDO Finance Director approval of finalised guarantee structure and updated risk assessment.
  5. FCDO PUS as Accounting Officer formally approves provision of a guarantee.

World Bank
1. Following FCDO, HMT and Parliamentary Approval, FCDO will sign the loan guarantee agreement with the IBRD to enable the World Bank to finalise preparation of the project proposal(s) and subsequently disburse the loan(s).
2. The proposed guarantee is within the World Bank’s headroom for bilateral guarantees and does not require separate approval. Loans covered by the guarantee will be approved by the World Bank Board as per the normal procedure, with the Board approval and loan agreements referring to the use of the UK guarantee.

Risks

The risks around the programme are assessed to be major. A summary of the key risks and associated mitigating actions is set out in Table 3. It should be noted that the mitigating actions can only have a limited impact on the residual probability and impact of the key risks given the context of the situation in Ukraine.

Table 3: Summary of key risks and mitigations
Risk	Probability	Impact	Mitigation	Post-mitigation probability	Post-mitigation impact
Delivery
Pre-disbursement: Guaranteed financing not disbursed	Medium - High current probability (with considerable uncertainty)	High impact on recognised Government of Ukraine / Low impact on UK finances	The UK and other international donors are providing significant broader support .	Medium-High current probability (with considerable uncertainty given intention to guarantee June DPL)	High impact on recognised Government of Ukraine / Low impact on UK finances
Post first disbursement: Financing not fully disbursed	Low current probability	High impact on recognised Government of Ukraine / Low impact on UK finances	The financing is likely to be disbursed in a single tranche	Very low current probability	High impact on recognised Government of Ukraine / Low impact on UK finances
Protracted conflict increases financing gap faster than fiscal support can be committed/disbursed	Medium	High impact on recognised Government of Ukraine / Low impact on UK finances	.	Medium	High impact on recognised Government of Ukraine / Low impact on UK finances
Political
.	.	.	.	.	.
.	.	.	.	.	.
Reputational
.	.	.	.	.	.
World Bank financing does not meet UK high standards on sanctions	Low	High	Financing will disburse directly to designated Government of Ukraine bank accounts for specific purposes. Financing related to the UK grant or guarantee is highly unlikely to be in breach of UK sanctions.	Very low	High
Financial
The USD:GBP exchange rate depreciates significantly, increasing the GBP value of any USD payments	Low	Low-medium	Accept exchange rate risk as offering better VFM options for reducing risk. Monitor exchange rate and ensure FCPD are sighted on the cost implications if a default becomes more likely.	Low	Low-medium
Interest rates rise significantly, increasing the maximum liability for the UK	Medium	Low-medium	Accept interest rate risk as offering better VFM than options for reducing risk. Monitor interest rate risk and ensure FCPD are sighted on the cost implications if a default becomes more likely.	Medium	Low-medium
The Government of Ukraine defaults on its obligations to the IBRD	Low-Medium	High	The UK and other international donors have committed considerable macro-financial assistance to Ukraine. The UK will continue to engage other donors on the implementation of their commitments to Ukraine.	Low	High
Financial monitoring insufficient to afford timely provision to meet triggered guarantee payment	Low	High	Financial reporting requirements will be agreed between the World Bank and the UK in advance of signing the guarantee agreement. This will include WB immediately notifying FCDO following the GoU missing a payment, to enable 180 days for FCDO to consider making a provision, which will minimise the risk of insufficient funds being available. FCDO will ensure the guarantee has an SRO throughout its life, to carry out required annual default risk assessments and regular monitoring of the likelihood of the guarantee being triggered.	Very low	High
Estimated risk-adjusted in year exposure related to the guarantee increases, crowding out FCDO ability to provide other guarantees	Medium	Medium-High	Prior to confirmation of the guarantee the financial risk associated with the guarantee will be kept under review and total exposure can be reviewed ex-ante if the trade-offs are assessed as too major	Medium	Medium-High
The guarantee has similar economic risks as existing FCDO guarantees resulting in increased concentration risk in the portfolio and a possibility of multiple guarantee calls simultaneously.	Low-medium: there is no geographical overlap with existing FCDO guarantees however there may be a correlation to guarantees where economies are dependent on oil (e.g. Iraq or Nigeria (within Room 2 Run guarantee)	Low-medium	Finance Directorate review Default Risk Assessments from all guarantees in the FCDO portfolio to identify any overlapping risks	Low-medium	Low-medium

Monitoring and evaluation

Prior to issuance of guarantee / disbursement of financing
The Business Case and programme team will keep the risks under regular review, aligning with updated assessments of likely conflict and political scenarios. The guarantee will only be issued if it remains good value for money in delivering the desired outcomes. Any guarantee will be structured so that it remains within the FCDO’s risk appetite.

Post-issuance / disbursement
The FCDO PRO will draft a monitoring plan following approval of this Business Case. This will specify who monitors which activities, when this will occur (at baseline, specific milestones, and at programme completion), and how the activity will be measured. Where possible, monitoring will rely on the WB’s own monitoring processes.

The SRO/PRO will work with a nominated person in International Finance Directorate who will track the performance, impact and risk issues on this guarantee (and other guarantees in FCDO’s portfolio) and report regularly to Finance colleagues and the FTSB.

The SRO will update Finance Directorate and the FTSB on the likelihood on a six-monthly basis as part of the FTSB Management Information Review and through a Default Risk Assessment at the end of the financial year. If the likelihood of default is assessed at any point to be greater than 30%, the SRO will also inform HMT. For at least the first 18 months of the programme, the PRO, in consultation with the SRO, will carry out quarterly reviews based on monitoring by the WB. These reviews will assess the likelihood of default as well as the implementation and results of the loans. The frequency of these reviews will be re-assessed after 18 months based on the broader context in Ukraine. Members of the FCDO Project team will hold six-monthly review meetings with the World Bank on the status and progress of the overall guarantee. They may also participate in World Bank review missions or meetings for individual loans.

The Project team will draw up an Evaluation Plan following approval of the Business Case and agree this with the World Bank. This will establish appropriate Indicators (quantitative and qualitative where appropriate) to measure progress against the Outputs and Outcomes set out in the Theory of Change, milestones/targets at annual review points and at the conclusion of programme, and the sources of evidence and reporting systems through which data will be collected (these are likely to rely primarily on World Bank systems). It will draw on the evaluations carried out by World Bank staff, and assessments carried out by HMG staff.

ANNEX A: .