Author’s note: Some sensitive text and figures have been redacted ahead of publication.

## Annual Review - FREE

Title: UK Support to Financing of Recovery from Economic Emergency in Ukraine (FREE) Ukraine
Programme Value £ (full life): / Grant to the World Bank FREE DPO: / £74m RDEL grant – Original business case / Guarantees facilitating lending under the World Bank’s PEACE IPF: / First World Bank guarantee ($450m) – Original business case / Second World Bank guarantee ($500m) – Addendum 1 / Third World Bank guarantee ($500m) – Addendum 2 / Fourth World Bank guarantee ($500) – Addendum 3		Review date: June 2024
Programme Code: 301512	AMP start date: March 2022	AMP end date: 15 October 2051
[note] https://projects.worldbank.org/en/projects-operations/project-detail/P178794?_gl=1*epg97i*_gcl_au*MTM0MDE0NjkzOS4xNzIxMDY2Njk4
[note] https://projects.worldbank.org/en/projects-operations/project-detail/P178946

Summary of Programme Performance
Year	2022/23	2023/24
Overall Output Score	A+	A+
Risk Rating	Major	Major

DevTracker Link to Business Case:	D0005248.odt (live.com)
DevTracker Link to results framework:	See business case.

A. SUMMARY AND OVERVIEW

Description of programme

The UK began this programme in February 2022, after Russia’s military build-up and full-scale invasion of Ukraine led to a large and destabilising fiscal shock. Under the conditions of the invasion the GoU was unable to raise sufficient volumes of finance, both domestically and from international capital markets to manage the rapid rise in defence expenditure. In response, donors and International Financial Institutions (IFIs) have extended billions in emergency budgetary assistance to plug Ukraine’s fiscal gap. Following the invasion donors (including the IMF) provided $29.2 billion in fiscal assistance over 2022 followed by a further $39.9 billion in 2023, which in both cases is around a third of total government expenditure in 2022 and 2023.
[note] Calculations are based on the data presented in the IMF’s Staff Report for the Fourth Review of the Extended Arrangement under the Extended Fund Facility. Accessible here: https://www.imf.org/en/Publications/CR/Issues/2024/06/28/Ukraine-Fourth-Review-of-the-Extended-Arrangement-under-the-Extended-Fund-Facility-Request-551207.

The UK Support to Financing of Recovery from Economic Emergency in Ukraine (FREE Ukraine) programme (2022-2051) is a part of this donor response. It has provided fiscal support to help the Government of Ukraine (‘GoU’) sustain essential public service delivery to the Ukrainian people, including the wages of public sector workers, pensions, and social protection programmes, including for the vulnerable. The UK has channelled grants and guarantees via the World Bank’s International Bank for Reconstruction and Development (‘the IBRD’), a global development bank geared toward providing financial and advisory assistance to middle- and low-income countries. The World Bank’s Multi-Donor Trust Fund (‘the MDTF’) for co-financing of the Ukraine Second Economic Recovery Development Policy Program – an emergency financing package - absorbed £74 million ($97.5 million) in UK grant funding across March and April 2022. Since then, the UK has provided $1.95 billion in guarantees to the World Bank’s Public Expenditures for Administrative Capacity Endurance (‘PEACE’) Project. These guarantees are designed to extend the IBRD’s lending capacity beyond that which it otherwise would be able to. A summary of the tranches can be found in Annex A.
[note] The UK’s fiscal support programme initially took its name from the World Bank’s FREE Supplemental Development Policy Loan. This name has been retained and is used to refer to UK assistance despite UK guarantee support under the same programme being channelled at a later stage via the World Bank’s PEACE project.

Medium-term response – Ukraine Economic Stabilisation Programme (‘UESP’): up to March 2023, FREE had been the focal point of UK’s fiscal assistance but the operating environment has moved on significantly since its inception. Over 2022-23 as Ukraine’s needs grew the original business case was extended 3 times through addendums. However, with the onset of a longer war it became clear that Ukraine will remain dependent on external assistance over the medium-term and a sustainable solution was needed. As a result of the need for longer term macro-financial support the G7 is now structuring its assistance around Ukraine’s IMF programme, having committed ‘financing assurances’ to be delivered over the course of a 4-year Extended Fund Facility arrangement. With the transition to multi-year and predictable support, the SRO took the decision (March 2023) to supersede FREE with a new longer-term intervention called UESP; the Prime Minister announced this at 2023 Ukraine Recovery Conference, and the business case for UESP was approved in Jan 24. See further detail below in the scope section.
[note] To help the IMF overcome the high uncertainty of lending to country in an active war the G7 agreed to provide three assurances in March 2023. A commitment to help close Ukraine’s residual fiscal gap; an agreement to support debt sustainability by reducing Ukrainian bilateral official debt; and a commitment to stand behind Ukraine’s repayments to the IMF in the event of default.

Purpose: from the outset, FREE has aimed to safeguard public services by financing public sector salaries and social welfare payments, and in doing so protecting groups who are most vulnerable to the impact of the war. By helping to sustain the Ukrainian state and its stability, the programme also aims to play a role in mitigating the risk of economic collapse, thereby indirectly helping Ukraine to win the war. Finally, it is important to highlight that this programme is the UK’s contribution toward a collective burden sharing arrangement, which symbolises G7+ unity and our success in mounting a sustained multilateral effort at scale.

Scope: since the last annual review only a single tranche of UK guarantee assistance has been put in place. This guarantee was signed in 04/08/2023, with the underlying funding disbursed via PEACE between September to November 2023 in two stages (see Annex A). This review will focus primarily on this single tranche but also the performance of PEACE as a whole. Like before this review is relatively light-touch given the tightly restricted parameters of the support provided, with judgements based on the following:

- Conversations with staff at the World Bank Group,
- Conversation with staff at the Ukrainian Ministry of Finance,
- Analysis of World Bank reporting documents,
- And internal analysis of the Ukrainian fiscal situation, performed by HMG economists and policy professionals.

As set out above the operational context has been complicated by the pivot toward long term support, while loan guarantees also tend to be long term instruments mirroring the tenor of the loan; in this case Ukraine has often opted for terms greater than 20 years. Any delivery and associated development assistance is therefore front loaded as the point of disbursement, with the programme team anticipating a shift to financial risk management, potentially for several decades as loans are repaid. We have consulted the FCDO’s Centre for Deliver to agree a proportionate approach that balances resourcing with best practice. This includes querying whether annual reviews remain appropriate over the long term. See details below in the recommendation section and Section F.

Management: day-to-day operational management of both the MDTF and PEACE, and mitigation of associated fiduciary risks is unchanged. Principally this is managed by the World Bank Group, with the FCDO’s EECAD Ukraine Economic Support Team (EST) maintaining a close dialogue with operational leads (based in-country) and via the UK delegation in Washington, DC. The central outcomes and outputs described in this report have been ultimately determined by the World Bank, with the UK playing a role as guarantor. The EST works closely the International Financial Institutions Department (‘IFID’) and British Embassy Kyiv on the monitoring of risk and the broader policy and strategy underpinning the UK’s fiscal assistance.

Summary supporting narrative for the overall score in this review

Overview. UK loan guarantees provided to the World Bank have continued to perform strongly since the first reporting period. The World Bank’s PEACE project is one of a hand full of flagship financing instruments, alongside the EU’s Ukraine Facility, which are coordinated under the broader macro-financial framework of Ukraine’s IMF programme. Operationally the World Bank has flexibly absorbed a variety of donor contributions (from guarantees through to grants) to deliver predictable and timely monthly assistance, while also successfully navigating the risks posed by Ukraine’s war time context.

Caveats. Over the last reporting period fiscal support for Ukraine has become more sophisticated with the agreement of Ukraine’s IMF programme, which was unlocked by G7 financing assurances (as outlined above). War time uncertainty remains very high, but the scale and level of coordination has improved. The combined package committed by the providers of financing assurances and the IMF amounts to $122 billion, or the amount needed to meet Ukraine’s expected fiscal gap between March 2023 and March 2027. All UK guaranteed funding under FREE, totaling $1.95 billion, has now been put in place: of which $500 million was delivered in the reporting period. FREE has therefore played a relatively small but still significant role in the initial phase of the IMF programme until UESP was put in place. Further calculations contextualising the UK’s contribution are set out in Section B.

Assessment of outputs. Based on a strong performance against the targets for Output 1 and Output 2, the programme has been scored as “A+: Outputs exceeded expectation”. This programme has, as expected: contributed to GoU’s ability to fulfil its core functions; and leveraged additional IBRD support. That said, with the UK only committing a single $500 million tranche over the reporting period, the programme’s stabilising impact is modest. However it is still an important component of a strong multilateral response that has helped mitigate the risk to the resilience and stability of the Ukrainian state.

Attribution. Again, like the previous reporting period the UK’s share of assistance under PEACE is relatively small while only a minority of UK funding can be attributed to specific categories of payments. Therefore, it is possible to attribute certain results to UK support, but only in limited instances. The UK’s 4 tranches of loan guarantees under FREE have reimbursed a range of public expenditure, with the fourth reimbursing similar lines of government expenditure in this case $298.8m on state pensions and $200m on medical wages. In general terms UK guaranteed lending comprised around 28.3% of the total commitment under Additional Financing 5 ($1.77bn). This can be thought of as a rough proxy for the UK’s relative share of the outcomes set out in Section C, but the UK’s contribution is much smaller when measured on aggregate level across the reporting year.
[note] As documented in the last annual review (03/22-03-23) this has included the salaries of education and government employees (first guarantee under PEACE), pensions and social assistance payments (second guarantee) and salaries of public university employees and family and child benefits (third guarantee).

Major lessons and recommendations for the year ahead

Programme management

Programme management should be proportionate to the loan lifecycles. With Ukraine opting to select the most affordable loan tenor and a new programme being put in place, we recommend combining the programme management cycles of FREE and UESP. The programmes heavily overlap and are complementary. Future reviews should be combined and take place in April; and periodic risk monitoring should also be combined.
Policy
Fiscal assistance needs to be a continuing part of the UK’s strategy. The experience of delivering fiscal assistance under FREE has clarified the scale of Ukraine’s funding challenges if it is to avoid instability, fund military pressures and emerge from the war well placed to deliver on its Euro-Atlantic ambitions. This approach is already underway via FREE’s successor programme, UESP    .

Enhancing Ukraine’s self-sufficiency should be pursued alongside fiscal support. This review observes that high uncertainty, risks to Ukraine resilience and donors’ fiscal constraints mean that the UK should support the development of Ukraine’s domestic resilience.

Ensuring fiscal assistance can deliver wider development priorities. UK assistance under FREE has often been agreed quickly on an emergency basis and consequently with no conditionality. This was appropriate at the time. However, with relative stable emerging, and PEACE’s wide-ranging success and scale, there could be scope to integrate programme expertise or technical assistance to enhance their development impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The intended impact of the programme is to support the Ukrainian state to continue to function and alleviate suffering in the face of the invasion.

Outcomes are a reduced financing gap for the Ukrainian Government, the maintenance of essential state expenditure (e.g. pensions and state salaries) and services, and reduced instances of economic instability. Guaranteeing World Bank lending remains a highly cost-effective way of providing economic support to Ukraine.

The Theory of Change is based on the translation of key inputs (UK grants and guarantees) into the key outputs of additional IBRD financing, alongside the reimbursement of salaries and welfare payments made by GoU. The theory is that this process, from inputs to outputs, will lead in turn to the identified outcomes of:

a reduced financing gap for the Ukrainian Government,
maintenance of essential payments (e.g. pensions and state salaries) and core functions,
more broadly, signalling international support with a view to alleviating market concerns regarding Ukraine’s ability to meet its financing obligations.

As guarantor of World Bank lending the UK is reliant on its reporting and monitoring to measure progress toward outcomes. As recommended in the last annual review the theory of change has therefore been revised over the reporting period to tie outputs more closely to the World Bank’s Implementation Status and Results Reports (ISR). This is not a substantive change to the overall logic of the theory of change, rather improving its specificity. See detailed overview of outputs in Section C.

There are several factors beyond the UK’s control that complicate the assessment of UK guaranteed lending. This is because (a) its impact is closely linked to the success of the collective international response; and (b) because of the pooled nature of donor funding within PEACE. It is also important to highlight that the logic of the theory of change is anchored on the short term given the programme’s focus on emergency budgetary assistance that delivers immediate economic stabilisation.

Despite the longer war the theory of change of the original business case remains valid. As detailed in Section C there is significant evidence that the inputs chosen have continued to yield the anticipated outputs and significant evidence that desired impact is being achieved as described below.

The World Bank has confirmed that the UK’s fourth guarantee has led to additional financing on a 1:1 basis, and therefore closed Ukraine’s financing gap by the same amount. Though the UK’s contribution toward closing Ukraine’s financing gap is small, it is an important part of the overall G7 and IMF response that closed the gap over the reporting period. Overall, the UK is the second largest donor to PEACE (as of June 2024) which is a fundamental part of Ukraine’s macro-financial support. As a whole PEACE delivered $25.5 billion since its inception in 2022 (as of June 24), with a total UK share via FREE of 7.8% (based on $1.95 billion in loan guarantees). PEACE roughly met a third of Ukraine’s financing gap over the first year of the IMF programme (beginning March 23), of which the UK’s share was 1.2%. The single $500 million guarantee that falls within this reporting period facilitated approximately 28.3% of the funding used to deliver the outputs detailed in Section C under the World Bank’s Additional Finance 5.
[note] It is difficult to calculate the precise shares for two reasons. Firstly, Ukraine’s financing gap is calculated on a rolling 12-month basis at each quarterly review; and second donor assistance falls across multiple years and varies according to their respective accounting treatments. This calculation is based on the financing gap over the first year of the programme ($42.5 billion) and the total amount disbursed via PEACE over this time frame (c.$12-13 billion), of which $0.5 million is from the UK.

This has helped to enable the return of relative stability, which has in turn facilitated broader benefits not foreseen in the original business case. The combination of economic stability and donor assistance has ensured the space and success of broader policy making, with GDP growth of 5.3% in 2023 (IMF); inflation trending down to 3.2% in April (24) from a peak of >26% in Q1 2023 (National Bank of Ukraine, ‘NBU’); central bank reserves reached an all-time high of $43.8 billion in April 2024 (NBU); and a sustained withdrawal from monetary financing over 2023. The predictability and continuity of monthly donor disbursements in 2023 stands in contrast to the NBU needing to provide $12 billion in monetary financing in 2022 to cover Ukraine’s financing gap. The IMF has, via quarterly reviews and discussions with UK officials, repeatedly commended the Ukrainian authorities for their skilful policy making. Ukraine has made good progress toward implementing all the required programme conditions, which has improved the resilience and functioning of the state. As documented in the previous review, PEACE has firmly established itself as functional and transparent channel, which has built donor trust and also opened up GoU’s public financial management to scrutiny. These factors are clearly mutually reinforcing, particularly from a balance of payments perspective.

UK guaranteed funding has delivered the stated outcome of reimbursing public sector salaries and social payments. Discussions with the World Bank have confirmed that the relevant UK guaranteed loan paid for pensions and medical wages. Taken together with World Bank’s IRS and their ‘Listening to Ukrainian Citizens’ Report (‘LCU’), which show the timely disbursal and impact of PEACE over 2023, we can conclude that the outcome of maintaining essential payments and core services has been achieved. This is analysed in detailed in Section C.
[note] https://thedocs.worldbank.org/en/doc/2c2d81f33cb64ac4695818d3cf988fa2-0080012024/original/Listening-to-Ukraine-Poverty-Note.pdf

    .

Overall since the last review, there is increased evidence that the programme has, at an output and outcome level, helped deliver on the programme’s intended impact. FREE’s intended impact is to support the macroeconomic stability of Ukraine, help the Ukrainian state to continue to function and alleviate suffering in the face of the invasion. From the analysis of outcomes and outputs above we can be confident that UK assistance, particularly as a part of the collective donor response has played a role in supporting stability and the functioning of the state over the last 12 months.

In reimbursing pension payments and health services, we can also conclude that PEACE, and therefore UK assistance has supported the functioning of the state and helped to alleviate suffering. Balanced against this, poverty has increased since the invasion began, with 3 in 10 Ukrainians now living in poverty (See LCU Report, 2024). Discussions with GoU, consideration of the World Bank’s LCU Report and the Independent Commission on Aid’s (‘ICAI’) Review of UK aid to Ukraine sets out how external assistance (including PEACE) has helped to substantially mitigate the economic and welfare impacts of the war. Therefore, it is our judgement that without PEACE the situation it likely to have significantly worse. This is examined in more detail in Section C.
[note] https://icai.independent.gov.uk/review/uk-aid-to-ukraine/review/

    .

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

It is not possible for the UK to exit this programme early due to the legally binding nature of loan guarantees. With all assistance delivered the team’s focus will now shift to a monitoring and risk management posture.

More generally the judgement of this review is that there continues to be strong evidence that this programme’s narrow focus on using loan guarantees to facilitate fiscal support via PEACE has represented good value for money. Based on the merits outlined above, this review also endorses future consideration of PEACE or equivalent instruments to deliver fiscal support under FREE’s successor programme, UESP.

## C. DETAILED OUTPUT SCORING

Output Title	Support for core government functions (targets and statistics provided by the World bank as set out below)
Output number:		1	Output Score:	A+
Impact weighting (%):		75%	Weighting revised since last AR?	No

Output 1: Support for Core Government Functions

Overview: PEACE functions on the basis of providing fiscal assistance by reimbursing the expenditures incurred by the GoU to pay government, school and healthcare employees' wages; first responders' wages; pensions and social assistance payments. It has now disbursed $25.5 billion in assistance since its inception in 2022. The guarantee delivered during the review period facilitated two disbursements of $200 million and $298.8 million on 22/09/23 and 22/11/23 respectively. Of the $500 million total, $298.8 million was used for pension costs and $200 million went toward medical wages. In general terms UK guaranteed lending supported 28.3% of the funding under Additional Financing 5 which totalled $1.77 billion. Chart A provides a visual breakdown of Additional Financing 5 by use and the UK’s contribution. For reference purposes Table A provides a full breakdown of PEACE for 2023.

Approach: the outputs of this programme are set by the World Bank as they are implementing and monitoring the programme. As guarantor, the UK has not been closely involved in the design of the outputs and has elected to use World Bank reporting as the basis of our reporting. The summary below is based on the detailed scoring of indicators set out immediately below, which is drawn from the World Bank’s ISR reports. This is supplemented by the World Bank’s Intermediate Results Indicators and the findings of the LCU report.

Assessment: this assessment focuses primarily on the UK’s fourth guarantee but also PEACE as a whole. Based on the details below the PEACE project has reportedly met or exceeded all its targets for this output, ranging from an A to an A+, with three of the five indicators scoring A+. On balance the review team awarded an A+ to this output. This is a continuation of the strong performance in the previous year where FREE also scored A+. PEACE mostly exceeding all indicators with 93% of non-security staff paid on time; 99.4% of pensions paid on time; and nearly a third more schools remain operational than originally targeted.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.1 (core state functions): the World Bank has assessed PEACE to be performing above target in relation to the extent that the Government continues to be in a position to exercise core services, including filing taxes, delivery of income, housing and utility subsidies, and birth certificate issuance. The World Bank’s LCU analysis of poverty and the human impact of the invasion similarly concludes that despite huge challenges, remarkably most public services have continued in 2023 even in areas impacted by conflict. In the last quarter of 2023 satisfaction with healthcare services was high with 78% either satisfied or better, while across the year 85-92% of health clinics were operational each month. Additionally, 85% of social transfers were paid on time every month. The LCU Report credits sustained external support for enabling the GoU to mitigate the impact of the war and even help improve the overall welfare of households over 2023 despite the general rise in poverty since the invasion. From a UK perspective, the ICAI review reaches a similar conclusion, highlighting the strategic significance of UK loan guarantees in helping the GoU avoid arrears on public sector salaries and pensions, which would have worsened the economic and humanitarian crisis.

Output 1.2 (payment of public administration staff in non-security sectors): no wage arrears were reported over the period with GoU exceeding its target level of public administration staff being paid. This has been a key facet of ensuring public services are able to continue.

Output 1.3 (number of school employees paid on time): from April to December 2023, an average of 89% of teachers and health care workers received their salaries without disruption. As of December 2023, 477,796 teachers were paid as a result of PEACE, which is 27,796 more than the baseline target level.

Output 1.4 (number of schools that remain operational): in December 2023, 12,600 schools remain operational across Ukraine. Across each month of the year examined a minimum of 89% of children aged 6–18 were enrolled in school, though many (72%) were taught remotely in areas under active hostilities.

Output 1.5 (pensions): 97% of pensions were paid on time every month between April and December 2023. Household income derived from social transfers including pensions and other social assistance represented more than half of household incomes in 2023 compared to a fifth in 2021. With many household incomes collapsing and unemployment rising, households have becoming increasingly dependent on old age pensions and social assistance. For the poorest 30% of the population, old-age pensions and social assistance payments accounted for around 73% of household income (Source: LCU). This underscores the importance of PEACE’s timely disbursement to these groups and its role in helping to offset poverty.

Chart A: Breakdown of Additional Finance 5 by end use and UK contribution

Table A: Total disbursements via PEACE by end use for 2023

Government employees’ wages	$776,300,368.23
School employees’ wages	$1,740,071,407.10
University staff wages	$555,523,099.05
Pensions	$6,595,843,014.64
IDPs Payments	$613,151,720.20
GMI +HUS +Disabilities	$689,832,914.23
Family and child allowances	$507,248,036.47
Program of Medical Guarantees	$1,403,904,284.30
First responders’ wages	$598,192,497.99
TOTAL	$13,480,067,342.21

Indicator 1.1	Extent to which government continues to exercise core functions (online filing taxes, issuing birth certificates, processing online requests for housing and utility subsidies)				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A – met expectations
Value	5	5	5	4
Date	07/04/2022	07/09/2023	11/03/2024	30/06/2025

Indicator 1.2	Number of public administration staff paid in non-security sectors / Comment: The reduction in value of indicator is related to reduction of staff. No wage arrears have been reported as / of August 30, 2023.				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderated exceeded expectations.
Number of staff paid on time	160,000	134,941	131,823	At least 75% of staff paid in the baseline month.
Number of female staff paid on time	110,000	110,000	105,000	At least least 85% of staff paid in the baseline month.
Date	07/04/2022	07/09/2023	31/12/2023	30/06/2025

Indicator 1.3	The number of school employees paid on time.				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderately exceeded expectations
School employees paid on time	450,000	491,658	477,796	At least 85% of staff paid in the baseline month
Female school employees paid on time	300,000	300,000	300,000	At least 85% of staff paid in the baseline month.
Date	01/03/2022	07/09/2023	31/12/2023	30/06/2025

Indicator 1.4	Number of schools that remain operational (whether remote, in-person or blended)				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End target	A+ outputs moderately exceeded expectations
Value	13,866	12,900	12,600	10,000
Date	15/04/2022	01/09/2023	31/12/2023	30/06/2025

Indicator 1.5	Share of pensions paid on time				Was World Bank target met? UK score
	Baseline	Actual (previous)	Actual (current)	End Target	A outputs met expectations
Share of pensions paid on time	100	98.90	99.60	90.00
Share paid to female pensioners	65	61	61	85
Date	01/02/2022	30/06/2023	31/12/2023	30/06/2025

Output Title	Additionality of IBRD lending
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Output 2: Additionality of IBRD lending

Briefly describe the output’s activities and provide supporting narrative for the score.

The UK’s fourth guarantee unlocked additional lending on a 1:1 basis above and beyond the IBRD’s lending limits. This has been confirmed by the World Bank team and is reflected in overview of UK guaranteed disbursements summarised in Annex A. The programme has therefore delivered against this output as expected (score: A) for the year.

Indicator(s)	Milestone(s) for this review	Progress over reporting period.
2.1: Percentage of IBRD funding mobilised by UK guarantees which is additional to what the IBRD would have been able to lend without UK support	100%	Achieved

Progress on previous Review’s recommendations

All recommendations from last Annual Review have been implemented. A summary of the actions that have been take since are outlined below:

As proposed the theory of change has been tied more closely to the World Bank’s reporting framework.
- To adopt a longer-term approach, a new programme (UESP) has been put in place to target fiscal sustainability over a multiyear cycle and protracted war, which aligns with Ukraine’s IMF programme.
- The FCDO has continued to closely monitor its Ukraine risk exposure. To do so improvements have been made to internal procedures including enhanced scrutiny in key departmental fora; and regular dialogue with both the IMF and the World Bank on macro-economic and financial risks stemming from Ukraine.
Lessons learned

    .

PEACE has had remarkable success at helping to mitigate the impacts of war on households. The World Bank has proved it can be relied on to deliver macro-financial support at scale and pace while helping to protect households in a complex war time context. This underscores the versatility of loan guarantees across a range of contexts.
Recommendations for the year ahead

This review’s analysis combined with consideration of the UK’s policy aims for Ukraine has led to the following recommendations for the year ahead. These recommendations were formed in consultation with the EST and are also summarised in the long list of recommendations in Section A:

Fiscal assistance needs to be a continuing part of the UK’s strategy. The experience of delivering fiscal assistance under FREE has clarified the scale of Ukraine’s funding challenges if it is to avoid instability, fund military pressures and emerge from the war well placed to deliver on its Euro-Atlantic ambitions. This approach is already underway via the FREE’s successor programme, UESP    .

Enhancing Ukraine’s self-sufficiency should be pursued alongside fiscal support. This review observes that high uncertainty, risks to Ukraine resilience and donors’ fiscal constraints mean that the UK should support the development of Ukraine’s domestic resilience.

Ensuring fiscal assistance can deliver wider development priorities. UK assistance under FREE has often been agreed quickly on an emergency basis and consequently with no conditionality. This was appropriate at the time. However, with relative stable emerging, and PEACE’s wide-ranging success and scale, there could be scope to integrate programme expertise or technical assistance to enhance their development impact.
## D: VALUE FOR MONEY

Key cost drivers and performance

Guarantees do not incur an upfront cost to the FCDO, but instead carry a risk of potential costs in the event that a guarantee is called and the FCDO is required to pay out. In this instance the potential cost is driven by the likelihood that these guarantees are called as a result of Ukraine defaulting on any of the IBRD loans guaranteed by the UK. There has been no call on these exposures and therefore no payout cost to the UK thus far.

VfM performance compared to the original VfM proposition in the business case

The VfM performance remains broadly consistent with the original proposition as outlined below:

- Economy: collectively, the UK’s FREE programme has mobilised nearly $2 billion of additional finance to Ukraine at a very low up-front cost to the UK (via the World Bank’s PEACE project). Discussion with Ukrainian Ministry of Finance and Bank Staff have also confirmed that cost of IBRD finance is comparable if not cheaper than the funding Ukraine has access to via domestic markets and had access to pre-war via international capital markets.
- Efficiency: as identified in the Business Case, these guarantees will carry greater financial or default risk than other UK guarantees to support MDB lending. However, this reflects the context in Ukraine and it is a risk HMG took on knowingly at the time of approval. Despite this we judge these guarantees to be an efficient use of FCDO resource. As confirmed by the World Bank each UK guarantee enables additional lending on a 1:1 basis. The World Bank’s AAA credit rating also allows them to borrow relatively cheaply from capital markets and lend on at more affordable terms to Ukraine. IBRD loan guarantees are a more efficient use of risk on the UK’s balance sheet to facilitate lending on terms that are equivalent or more generous that Ukraine’s could access pre-war. The ICAI’s review of UK aid to Ukraine in April 2024 noted that guarantees provide much greater support than traditional aid funding would have achieved.
- Effectiveness: this annual review has shown how World Bank lending has enabled the GoU to maintain funding for essential services. The outputs examined in Sections B-C show a strong track record of delivering fast, flexible and targeting support guaranteed by the UK under challenging war time conditions. PEACE has also helped to reduce the administrative burden for GoU at a time when capacity is severely limited as they only need to liaise with the World Bank, rather than individual donors.
- Equity: PEACE’s value is demonstrated in safeguarding the core functions of the state, including pensions and social transfers that many vulnerable citizens rely on. As set out in Section C, PEACE has ensured nearly all pension and social transfers were paid on time (April-Dec 2023). Equity is also demonstrated by the World Bank’s lending policies, which include provisions on gender and social inclusion.

Assessment of whether the programme continues to represent value for money

Based on the assessment above, we judge that guaranteeing World Bank lending to Ukraine continues to be an economical and cost-effective way of providing economic support to Ukraine, in line with UK objectives of sustaining essential public service delivery to the Ukrainian people. The programme therefore continues to represent strong value for money and should continue.

E: RISK

Overview of risk management

FCDO’s overall programme risk appetite for Ukraine remains ‘eager’, which is unchanged from the previous reporting period despite adjustments being made in December 2023. Here two of the seven sub risks appetites – financial and reputational categories - were downgraded from receptive to cautious. This was done at the request of the Development Director to more closely track FCDO’s overall risk appetite. These were the only adjustments made over the reporting period. As it stands the FCDO has an eager risk appetite for strategy and context and policy and programme delivery; and a receptive appetite for people. The remaining risks have been categorised as cautious. This is summarised immediately below.

Risk Category	Appetite
Strategy and Context	Eager
Policy and Programme Delivery	Eager
Public Service Delivery and Operations	Cautious
People	Receptive
Safeguarding	Cautious
Financial and Fiduciary	Cautious
Reputational	Cautious

Generally, loan guarantees can be thought of as relatively low risk, but in this instance they are significantly higher as a result of the war and the operating environment in Ukraine. In addition to the pressures and instability caused by the war, several risks flow from financial and fiduciary based challenges. This is reflected in the downgrading of Ukraine’s credit rating following the invasion and the ongoing presence of corruption. Ministers knowingly accepted these risks at the point of agreeing to provide fiscal assistance to Ukraine.

The programme team works closely with the World Bank on their controls and management. As set out below the team’s general approach, including to risk management has been to engage closely with the World Bank and GoU, while tracking and analysing risks (particularly financial) internally. From this approach the team are content that the World Bank’s controls are robust, but we will sustain active monitoring of financial and fiduciary risks:

- The FCDO cannot fully mitigate against a scenario where Ukraine defaults on its international obligations. This would have financial implications for the FCDO should the World Bank call UK guarantees.
- Over the reporting period the ICAI published their Rapid Review on UK Aid to Ukraine. This acknowledged the significant controls in place across the portfolio, including for this programme but noting the fraud risk in Ukraine. The FCDO is looking at options to strengthen its mitigating measures at the portfolio level.

To address Ukraine’s reliance on donor assistance and to support risk management, the team continually advocates for wider Ukrainian self-sufficiency and resilience at the policy level. This helps promote a balance of effort from GoU in applying domestic measures to reduce dependence on external finance, whilst sustaining those levels from donors and IFIs.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

As a loan guarantee programme, most financial and commercial considerations are not directly applicable. As an instrument PEACE is closely controlled and restricted in terms of usage. For example, there are no procurement activities involved. All UK guaranteed funds that are disbursed under PEACE were channelled via the World Bank and therefore managed according to their procedures.

The UK and World Bank have operated in partnership on PEACE, from design through to implementation and monitoring. The programme team has uniquely strong working relations with the Bank, meeting at least quarterly and staying in monthly communication with the country team. This is supported by UK officials in Washington and their dialogue with staff at the World Bank’s headquarters. These relationships are crucial to the UK’s oversight of delivery.

As set above the FCDO has now delivered all loan guarantees under FREE. This will mean resourcing pressures should recede as the focus shifts to risk management and monitoring the performance of loans. This will entail adjustments to programme management.
[note] The EST is consulting the CfD on this approach. Programme management will need to strike a balance between long term resourcing and best practice issues.

The performance of PEACE

Based on consultation with deliver partners this review finds that the Bank has delivered quality and timely assistance, particularly in terms of outputs (see Section C) and risk management. Built into PEACE are several layers of protection to prevent against corruption and misuse of funds. Firstly, PEACE’s design, which is based on reimbursable expenditure, tightly controls the end use to only eligible expenditure lines. The World Bank uses a third party accounting firm to conduct audits of agreed expenditure controls (Agreed Upon Procedures, ‘AUP’), and a grievance redress mechanism is operated by the World Bank. Additionally, the UK benefits from the US’ additional checks and auditing procedures. This includes the tracing of funds between ministries and payment monitoring down to the individual level; sample checks on individuals in receipt of government payments; and US’ technical assistance to Ukraine’s supreme audit institution.

This finding is supported by the AUP review, which identified no major issues on a subset of expenditures reimbursed by PEACE between March and December 2023. This covered civil servant wages, school employees wages, IDP payments, family and child allowances, and university staff wages. The third party audit firm, PWC assessed whether expenditures were correctly compiled and consolidated, GoU controls over expenditure reports and whether expenditures were fairly stated and eligible. The AUP also conducted a follow up review into the issue of preventing ghost medical workers. Overall, no or only minor discrepancies were identified. These were related to manual or partially automated controls, resulting in rounding and human errors.
[note] This is the third AUP conducted by PWC. It can be accessed on the World Bank’s website: https://documents.worldbank.org/en/publication/documents-reports/documentdetail/099126102292422040/idu1731787a41182e1485f19d7d1006120eaecc4

Recommendations

Based on the details above this review recommends the following adjustments to improve and streamline programme management:

Programme management should be proportionate to the loan lifecycles. With Ukraine opting to maximise loan tenor for affordability, and a new programme being put in place, we recommend combining the programme management cycles of FREE and UESP. The programmes heavily overlap and complement one another and it is our view that future reviews should be combined and take place in April; and periodic risk monitoring should also be combined.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Over the past year the team has moved away from a reactive war time response to strategic and long-term assistance. This has underpinned the decision to move from FREE to UESP. To bring monitoring and evaluation in line with this approach the team has focused on deepening relationships with key delivery partners, particularly the World Bank and GoU. Consultation is regular and structured, supported by an enlarged FCDO team including an additional economist and programme accountant. The team’s efforts are informed by broader consultation with the G7, the EU and other donor institutions where there are often detailed and candid exchanges of views. Several visits to both Vienna and Kyiv have also been made to engage the World Bank and GoU directly, including to hold deep dive sessions.

There are several publicly available reports setting out PEACE’s performance, but through the channels above the team has privileged access to an array of supplementary financial and qualitative information regarding programme issues and Ukraine’s needs. The information drawn from these channels is sufficient for effective programme management.

Evidence

The evidence available on performance is drawn heavily from the World Bank’s PEACE programme and publicly available economic and financial data providers. There have been no major changes to the evidence base over the last year.

Learning

The primary lesson learnt over the last year is the broader potential development impact of loan guarantees. FREE’s focus on emergency budget support to help deliver stability and preserve public services has underscored the versatility and impact loan guarantees are having in Ukraine in an ODA constrained environment. This includes at the household level. With the development of a new longer-term programme, and the growth of FCDO’s Ukraine country portfolio there is scope to explore new innovations and linkages between priorities. For example, the integration of technical assistance.

Annex A: Overview of loan guarantee tranches under FREE

UK Support	Fiscal grant	1st guarantee	2nd guarantee	3rd guarantee	4th guarantee
Value	£74m	€ 425.7m	$500m	$500m	$500m
Signed	N/A	01/06/22	11/10/22	20/12/22	04/08/23
Disbursed	Approved 07/03. £50m in 21/22 and £24m in 22/23 / (TF073792)	22/06/22 / IBRD94030	21/10/22 / IBRD94470	$295m 09/02/23 / $203m 17/02/23 / £0.8m 20/05/23 / IBRD 9466-UA	$1.3m 04/09/23 (fee) / $100m 22/09/23 / $398.8m 22/11/23 / IBRD 9573-UA
Final planned repayment	N/A	2040	2041	2051	2042