## Annual Review Template

Title: SUPPORT TO INTERNATIONAL SECURITY SECTOR ADVISERY TEAM (ISSAT)
Programme Value £ (full life): £ 2,600,000		Review date: January 2021
Programme Code: 300614	AMP start date: 1/9/2019	AMP end date: 31/8/2024

Summary of Programme Performance
Year	2020
Overall Output Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	ISSAT BC
DevTracker Link to Results Framework:	Results Framework

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Together with like-minded donors, the UK established the International Security Advisory Team (ISSAT) in 2008. ISSAT is a semi-independent department of the Geneva Centre for Security Sector Governance (DCAF). It has 16 member states and 7 multilateral institutions who ‘mandate’ (commission) the organisation to assist in a wide range of ways. ISSAT is at the centre of donor co-ordination efforts in the Security and Justice (S&J) sector, and the UK is developing a central position in ISSAT as a founding member and through membership of the ISSAT Governing Board Core Group. ISSAT provides practical support to the international community in its efforts to improve security and justice internationally, primarily in conflict-affected and fragile states. It does this by working with a group of member states and institutions to develop and promote good security and justice reform practices and principles, and by helping its members to build their capacity to support national and regional security and justice reform processes.

ISSAT has two main approaches: to provide practical support to the international community in its efforts to improve security and justice, primarily in conflict-affected and fragile states, and a convening role to collectively develop and promote good security and justice reform practices and improved co-ordination of its members.

ISSAT operates through a pooled multi-donor fund that apportions funds equally between three funding streams: ‘pillars’ (i.e. 1/3rd each pillar). Pillar 1 is ring-fenced for individual donors’ priorities; Pillar 2 is dedicated to supporting the multilateral system (the multilaterals contribute via a cost-sharing arrangement), and Pillar 3 covers training and knowledge development.
DFID funded ISSAT until 2015 and then resumed funding in 2019 under the current programme. The current programme contains two components; a larger Component 1 for funding to ISSAT, and a separate Component 2 for small-scale research or analysis work that does not go through ISSAT. Through the UK’s funding to ISSAT under Component 1, the organisation delivers field advisory support, capacity building and knowledge services to HMG, bilateral and multilateral members and advocates for greater donor coherence and coordination at the policy level. Between October 2019 – March 2021), FCDO will have contributed £600k core funding to ISSAT. FY 20/21 Component 1 funding was reduced from £500k to £400k under a Covid re- prioritisation exercise. An amount of £181k available under Component 2 was reduced to £87k (the amount that had already been committed) under the same exercise.
[note] Oct ’19 – March ’20: £200K; April ‘20- Mar ’21: £400K.
[note] £100k pa as allocated under the Business Case, plus a roll-over of £81k from previous FY year. Strictly speaking, the Comp 1 (ISSAT was cut further, while funds available under Comp 2 were transferred to limit the reduction to ISSAT funds.

ISSAT responded quickly and effectively to Covid-19, independently producing useful analyses. Covid-19 stopped overseas travel. This had particular effect on provision: preventing the running of courses overseas physically (Pillar 3) and preventing country visits in support of Pillar 1 & 2 activities. Demands of re-prioritisation, the merger of DFID and FCO into FCDO, and strategic review processes created uncertainty which reduced HMG demand for support from ISSAT. However, although Covid has been disruptive to the quantity of activities undertaken by ISSAT under specific outputs, it has not been disruptive to the quality of the activities. ISSAT is assessed as having ‘met expectations’ and achieved an A (met expectations) which is a notable result in view of the disruption of the year under review. Although ISSAT exceeded its Output milestones and would normally have qualified for an A+ (exceeded expectations), it was felt that some of the datasets were not large enough to support such a conclusion.
[note] Security and Justice Reform Response to Covid-19 crisis: New Thematic in Practice page – April 2020; Rule of Law Reform and States of Emergency: New Thematic in Practice page and Advisory Note – May 2020; States of Emergency and Disaster Responses to Covid-19 in Practice: Emerging Trends for SSG/R: New Thematic in Practice page and Advisory Note – June 2020; Advisory Note on Post-COVID-19 Access to Justice and SSG/R – August 2020; Adapting methodologies for working in Covd-19 crisis type environments (session at November Governing Board meeting and paper to be distributed shortly)

Output 1.1 met/exceeded expectations in 100% of cases (milestone: 80%) but cancelled activities, a large number of ongoing activities, and challenges in securing feedback from members meant this milestone relied on 4 feedback forms only. Output 1.2.1 exceeded its milestone, achieving 85% post-training satisfaction (milestone: 70%). Output 1.2.2 was not counted due to insufficient data though the data available trended toward exceeding the milestone (60%) also. The number of joint activities (Output 1.3) exceeded the milestone (40%) at 60% of 38 tasks. Milestones for both Impact and Outcome Indicators were the establishment of data collection mechanisms. These were both achieved despite the disruption to activities.

The year 2020 was tumultuous for all but also strategically important for ISSAT. A single Operational Strategy and Results Framework has been agreed between ISSAT and its members (the UK Results Framework was revised to better fit ISSAT’s in Oct 2020). A methodology for measuring impact and a Compact to improve Governing Board Member (GBM) feedback are under development. A 10-year Evaluation carried out in February 2019 is still relevant and its recommendations should be kept under review. Bedding down these initiatives is a priority, as reflected in the recommendations.
[note] Evaluating our impact, methodological note
[note] Partnership for Gathering Results

Major lessons and recommendations for the year ahead
1. Shift AR due date forward one-month to 1st March in order to better capture ISSAT annual reporting (FCDO).
2. FCDO management of ISSAT would be improved with more regular, formal meetings with ISSAT than at present ISSAT should ensure that staff with oversight of the programme results framework, finances and risk management are routinely present (ISSAT/FCDO).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Theory of Change
Under the Theory of Change, FCDO are making a commitment to work with ISSAT, and to contribute specialist staffing and programme funding (Inputs). In return, FCDO will receive advisory support to S&J programming in developing country contexts, will benefit from improved knowledge and professional development, and will benefit from improved co-ordination and consensus between donors and with multilaterals (Outputs). This will mean that FCDO is better equipped to deliver more effective politically informed and gender-sensitive security and justice interventions (Outcomes). More effective interventions will mean in turn that FCDO activities help to build stability, the intended Impact of the programme.

This approach remains valid and necessary. Several security & justice programmes are in development within FCDO and have called on ISSAT capabilities, as have established programmes and regional directorates. A forthcoming ISSAT initiative on impact assessment (see below) should help to demonstrate the ways in which ISSAT support is helping members to build stability in fragile/conflict-affected countries. As ISSAT does not implement activities in developing countries directly, it’s mechanism for contributing to enhanced stability is to influence and build the capacities of its members. This will be challenging as doing so rests on many assumptions: that members such as the UK adopt and implement ISSAT’s recommendations and analysis, that the programming itself is well-calibrated toward the causes of instability and is conflict-sensitive, and that operating contexts allow for the ISSAT-informed programming to have a positive impact, for example. Security & justice is a notoriously difficult sector in which to demonstrate impact, and ISSAT will be seeking to demonstrate impact at one level removed. Further evidence on the effectiveness of ISSAT’s approach to these questions will be valuable given that the economy of the approach (shared costs) and its efficiency (quick and easy commissioning) are much clearer. ISSAT does not implement programmes directly, so relies on Member’s own decision-making to target marginalised groups but does disaggregate participation by gender (equity).

Progress towards outcomes
The desired Outcome is that FCDO and other GBMs are better equipped to deliver effective, politically informed and gender-sensitive security and justice interventions. This is indicated by the percentage of recommendations to all GBMs that are partially or fully accepted in mandate reports, accompanied by a narrative on how the mandates have influenced bilateral and multilateral GBM decision-making around interventions.

In 2020, ISSAT developed a Strategic Framework to ensure better coherence between GBM’s individual results and to reduce reporting requirements. FCDO revised its own Results Framework, in accordance with Smart Rules, to align with the ISSAT Strategic Framework and will encourage other GBM Core Group to do likewise.

The 2019 10-year evaluation was clear that ISSAT’s mandated work shouldn’t be at the expense of leadership and convening around key priorities. Separating substantive convening work from administrative/management meetings, better networks across GBMs to secure substantive policy lead participation (particularly in the case of geographies), and clear objectives would help, while recognising that in the best cases priorities emerge in the course of ISSAT’s ongoing work and benefit from flexible, iterative approaches. ISSAT needs to use its collective voice to shape and influence the wider SSR agenda, noting that it relies on GBM’s to guide this process including by identifying and communicating their own priorities. In many ways, ISSAT can only be as good as the level of substantive engagement of its members.

## C. DETAILED OUTPUT SCORING

Output Title	Advisory Field Support for Members' missions
Output number:		1.1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 Level of performance - percentage of members report that ISSAT’s contribution met or exceeded their expectations	80%	100%

Sixteen advisory field support activities have been recorded under this Output for the period under review (Oct ’19 – Dec ’20, see Annex 1 for complete list). Nine remain ongoing, one activity has been postponed due to Covid-19, and feedback has not been returned for two activities. The Output 1.1 milestone of 80% of activities met/exceeded expectations has been exceeded, albeit through feedback on four activities. Given that feedback has only been received on 25% of activities overall, the Output is scored as an ‘A’. The limited number of timely feedback returns illustrates the ongoing challenge for ISSAT of securing feedback – ISSAT should improve networking across GBMs to reduce reliance on a single point of contact. The Compact on data collection being established as an Outcome baseline will also help address this issue.

Covid-19 related impacts included initial delays to activities until travel was possible (and then replaced by adapted methodologies once the scale of the pandemic became clear) or deferring decisions on programmes, which had a knock-on effect on delaying requests to ISSAT, as GBM immediate priorities / focus shifted.

There is wide variation in the complexity of ISSAT tasks. Rapid, relatively light tasks such as a mapping count the same as extended engagement such as, for example, the UNAMID Lessons Identification work or the programme of support to the SSR Team of the OSESGY to strengthen their support to the Yemeni peace process and preparations for future SSR activities (this was moved to Pillar 2 for on-going support).

Work with the multilateral organisations under this Output also varies in strategic weight. With its work on UNAMID transitions, OSESGY, and OROLSI strategy in the Sahel, ISSAT should in time be able to demonstrate its influence (Outcome) and Impact. The same 2014 Annual Review flagged that “ISSAT needs to make sure that its support to the UN and EU is as strategic as possible to maximize its influence. This means that ISSAT need to ensure that their capacity to respond to UN and EU tasks are not taken up by mandates that do not have the potential to influence the wider organisation”. That recommendation still stands, ISSAT should not replace the need to build evaluation capability into programming.

A DFID 2014 Annual Review of ISSAT used the same indicator (whether individual activities met/exceeded expectations) as is used here. Then, ISSAT also 100% met expectations. An indicator used over a long period should not be lightly set aside but equally if it has been systematically met over years, it raises a question as to whether the indicator drives improvement (see also Output 1.2 later). Noting that ISSAT is currently bedding down data collection systems, we do not propose adjusting indicators but flag that the indicator could perhaps be augmented in the future

RECOMMENDATION: Review this indicator for stretch, recognising that any change would have to form part of the strategic approach agreed between all Governing Board Members

Output Title	Knowledge and professional development for member staff
Output number:		1.2	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Percentage of training participants who report that ISSAT's training met their expectations ("agree" / "strongly agree")	70%	85 %
1.2.2 Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance as a result of ISSAT training (longer-term, 6 months)	60%	-

This Output is designed to assess the effectiveness of ISSAT’s training, knowledge and professional development activities. Covid had an obvious substantial impact on in-person trainings taking place in 2020, with at least five cancelled or postponed to 2021. Nonetheless, seven trainings took place virtually. The team also increased its efforts on updating the training courses as well as translating these into virtual delivery formats that will provide an ISSAT with additional ways to reach S&J advisors deployed in the field that will remain valid post-Covid-19. Two trainings took place in Q4 of 2019. Types of trainings varied and in addition to the ISSAT trainings, individual ISSAT advisors reinforced trainings being delivered by GBMs. These do not have the same post-course evaluation mechanisms. Data on the usefulness of the support is captured through mandate feedback forms.

Under Indicator 1.2.1, a milestone of 70% immediate post-training satisfaction was achieved with an 85% ‘met expectations’ rating (in 2014 the milestone was 87% and the result was 94%). Adapting the trainings and obtaining this result was a notable achievement in challenging circumstances.

There are clear Value for Money benefits in being able to share the costs of developing trainings (economy). With a larger pool of participants to draw on, more trainings can be held (efficiency) and more specialised trainings can develop (effectiveness). Trainings targeted at geographies (Tunisia, Iraq) are a welcome development.

There is insufficient information at this stage to populate Indicator 1.2.2. which augments immediate post-completion feedback (see Indicator 1.2.1 above) with 6-monthly follow-ups. Only one training course took place outside the 6-month time gap to qualify for review. That the training courses of half the year under review fall outside the review period would seem to be an enduring issue that needs to be recognised and adapted to. The indicators could be de-linked, i.e. populated with different review periods and/or different courses.

A comment from a training in Sweden noted that real change requires commitment from within the organisations, suggesting that “all trainings need to be followed up with mentoring and other activities to reach beyond output level.” Options should continue to be explored. It may be that six-monthly follow up could be merged with a generic building a community of practice indicator (‘How many times accessed the ISSAT resource centre?’ for example).

Trainings developed and implemented by ISSAT have built-in shared costs under Pillar 3 making these economic in VfM terms. Working across GBM’s gives a wider pool of GBM staff to draw from, and more targeted specialised trainings can be developed which GBM’s individually would not resource. Pre-existing trainings can be adapted to fit GBM requirements which reduces the costs of developing separate courses.
RECOMMENDATION: Clarify the application of Indicator 1.2.2 and consider whether broadening (and loosening it) beyond purely training follow-up might be worth exploring.
Output Title	Improved co-ordination and consensus between donors, and with multilaterals
Output number:		1.3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.3.1: % of ISSAT mandates that bring together multiple bilateral and multilateral GBMs	40%	60%

This output is designed to assess how well ISSAT is facilitating co-operation between members and developing co-ordinated approaches. Out of 38 tasks/substantive external activities that took place over the reporting period, 23 were joint mandates, or ones directly supporting joint engagements representing a result of 60%, exceeding the milestone of 40%.Unilateral GBM activities are more closely linked to Governing Board Members’ programming activities. These have been more prone to cancellation during this period than joint GBM activities which tend to be of a more generic research or mapping type that us more amenable to a desk-based approach. This will have skewed the data toward joint activities, which explains why this Output scored an ‘A’ rather than an ‘A+’ as the results suggest. The VfM benefits of joint tasking is clear through shared costs. The UK benefitted from £481k worth of work at a cost of £152k, representing a saving of c.75%.
[note] Converted from CHF figures on 21/01/21 at https://www1.oanda.com/currency/converter/
Joint mandates to note include:
- The lesson learning mandate with UNAMID (United Nations – Africa Union Hybrid Mission in Darfur) which fed into, through the GBM’s the debates on the future of UNAMID at the UNSC.
- The Training Requirement Analysis for EU civilian CSDP missions and EU Member States which provided a common understanding of gaps and challenges and recommendations for greater complementarity in approaches.
- The Middle East and North Africa donor mappings which provided a common understanding across donors and multilaterals on opportunities for greater coordinated engagement across nine countries in the region.
- In 2020 ISSAT completed stage 2 of its development of a Security, Justice and Governance indicator framework, that offers up to 300 indicators on security, governance and justice to its Governing Board Members to integrate into SSG/R programming.
The impact of joint activities, usually co-funded research pieces, could be increased by using these as convening opportunities to discuss implications and/or recommendations. Examples of good convening already exist (e.g. UNAMID work). Similarly, joint mandates could provide opportunities for strategic approaches with multilateral members. Clearly, convening should not be, and is not, limited to convening around commissioned activities. ISSAT can be clearer and more confident in championing priorities, and developing work based on these, including drawing on Pillar 1 support if required.

RECOMMENDATION: Consider clarifying convening priorities and/or convening GBMs around completed mandates, where appropriate

D: RISK [½ to 1 page]

Overall risk rating: Minor
The fiduciary, safeguarding and reputational risks of working with ISSAT remain minor. However, delivery should be rated as medium risk, reflecting that ISSAT is still working on demonstrating impact through its work with Governing Board Members. Overall performance has been rated as ‘A’ this time around. This is primarily due to limited feedback on GBM satisfaction and outcomes following from activities tasks. Efforts will be made to improve data collection in this area and the risk rating will be reviewed regularly, an assumption being that if data remains patchy this could reflect delivery challenges and warrant increasing the risk level to ‘moderate”. The nature of working in the security & justice sector as often high-risk reflects on external context which should also be regarded as of moderate risk. Noting this, the programme remains Minor risk but will be kept under review. The risk register is reviewed every six months or when certain circumstances warrants an ad-hoc update. Since approval of the Business Case, the risk register has been updated to include the Covid-19 implications both from an internal and external perspective.

Risks due to Covid-19 (Internal)
Fiduciary/Operational/Reputational
Three monthly meetings with ISSAT to review the risk register did not take place consistently through the year: Programme Management capacity assigned to this programme was limited due to conflicting demands on the PM’s time. Where resource limitations affect programme management, this needs to be communicated to SRO or beyond if no action is taken.

The financial impacts of Covid obliged a prioritisation exercise that projected a reduction of funds across both Components, by £334k for this FY. This would have created a delivery risk. The risk was mitigated by movement of funds between components and between programmes, resulting in an overall spend reduction of £100k this year but compensated by an equivalent increase to next FY meaning there would be no reduction to the overall £ 2.6m budget approved under the Business Case. Impact on delivery and reputational risks as a result of these cuts was minimal.

Risks due to Covid-19 (External)
Delivery
This year’s reduction in the budget and restrictions caused by Covid-19 has had an effect on the work ISSAT had planned (Component 1) and on the amount and range of analysis products commissioned (Component 2). Some risks have therefore been partially realised and the risk register will be updated alongside the AR process. ISSAT re-prioritised their work in early 2020 to be more Covid-19 relevant while remaining within the scope of the programme results framework.

Key Mitigation actions
A Key Mitigation action taken under Component 1 was to work with ISSAT in targeting funds to priority activities which minimised the impact of July 2020 funding reductions.
Under Component 2 (research/analysis), Due Diligence Assessments were carried out before Accountable Grant Agreements were offered to the British Institute of International and Comparative Law and the Centre for Crime and Justice Services. As the value of these agreements were very low the assessments were done proportionately.
RECOMMENDATION: To review the Risk register at the quarterly meetings with ISSAT. Where resource limitations prevent this and other substantive engagement, this need to be flagged to SRO/superiors.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

The FCDO team managing the programme comprises of an SRO (20%), a Programme Manager (25%) and Programme Officer (30%, a later addition). The Programme Manager left her post in October and temporary cover has been provided by the Strategy, Programme and Corporate team and by the Programme Officer providing additional support. The SRO and Programme Manager have been developing their programme management knowledge and additional support has been provided through the CSMD programme hub network. Demands from other areas of policy and programme work plus reduced staff capability have resulted in some minor shortfalls in corporate requirements, such as later than planned publication of some documents, but given the constraints in available staff capacity, the programme was managed effectively.

ISSAT (Component 1)
The agreement between FCDO and ISSAT is a multilateral Memorandum of Understanding. The second annual payment to ISSAT was delayed and reduced due to the internal Covid-19-related ODA Review and re-prioritisation exercise. The process was managed well by both parties with careful consideration given to various possible scenarios. The budget at the start of the 2019/20 financial year was £500K and this was reduced to £400K following the re-prioritisation. Payment has been made. The 2019 Annual Audited Statement by an independent Auditor which found the accounts to be accurate and fair was received in May 2020. Communications with ISSAT are regular and useful, taking place around the six-monthly GBM meetings and ad hoc around the commissioning of mandates. However, having more regular meetings covering a more structured agenda (including risk) with minutes recording decisions and tasks would assist management of routine corporate tasks.

TECHNICAL ASSISTANCE (Component 2)
Two pieces of analysis work were agreed in March/April but due to Covid-19 challenges these were delayed to September-November. Details as follows;

Bingham Centre for the Rule of Law – Accountable Grant (£13,100), on:
Mutual Legal Assistance (MLA) in criminal matters in the UK and in developing countries:
This is due for publication in February 2021 and payment should be completed by AR conclusion.
The Centre for Crime and Justice Studies – Accountable Grant (£29,414), on:
Oversight & Accountability in UK jurisdictions.
This study has been delayed in part due to expanding scope that may require a further tranche of funding.

Thirdly, an external consultant (Deployable Civilian Expert) was hired in November 2019 to support the SRO in finalising a DFID Position Paper and Evidence Framework on Security & Justice Position Paper (£35,000).

Financial Management
We are forecasting a full spend this financial year on the reduced budget amount of £400k pa. Forecasting and accruals have been mostly accurate but have been made difficult due to Covid-19 delays and cuts. Any future short-term work under Component 2 would be better issued with a specific individual component number (i.e. one component number per piece of work commissioned) to make the Finance easier to manage.

FCDO’s internal ODA re-prioritisation review in July 2020 required a reduction of programme spend for F/Y year to 2021/22. This was compensated for by the transfer of unspent funds from another CHASE programme into the ISSAT component, the deferral of a further amount until 2021/22 (so those funds would not be spent in FY 20/21 but would instead be available as an additional amount in FY 2021/22) and a transfer between Components. The net result was the ISSAT Component 1 payment for 2020/21 was reduced from the £500K originally forecast to £400K. A re-prioritisation of funds that could have had substantial negative impact on ISSAT’s activities was largely cushioned through effective programme management.

Value for Money

The Programme remains good value for money as we continue to get the research and analyses we need to re-engage effectively and increase the impact of UK’s engagement in Security and Justice at a proportion greater than the cost of the investment.

The UK participated in 9 of the 21 joint activities, contributing £125k of total cost of £480k for all activities in which the UK participated. This represents a saving of c.75% on full cost. The UK’s three unilateral mandates totalled £22k. The cost-sharing allows the UK to support a much wider range of activities. Although the UK would not of itself initiate all of these mandates, accessing other workstreams has benefits in wider exposure across S&J workstreams. Other VfM benefits not quantified include the benefits in ISSAT’s light commissioning process (versus more onerous procurement within GBMs), the VfM benefits of more effective donor programming, and the VfM benefits for donor funding of improved effectiveness of multilaterals who often find accessing strategic advice and support a challenge.

RECOMMENDATIONS: Review the resources assigned to programme management is transparency returns and managing information (FCDO).

Date of last narrative financial report	13/5/2020	Date of last audited annual statement	13/5/2020

Annex: List of activities covered under Annual Review
List of UK requests	Complete /Ongoing	Output / 1.1/1.2	Joint Y/N / Output 1.3	Total / Cost CHF’000	UK / Share / CHF’000
Mapping of donor S&J breakdown	COMP.	1.1	N	-	2.4
North Africa Mapping	COMP.	1.2	Y	84	21.5
Backstopping support to OSESGY	COMP.	1.1	N	-	15.1
Middle East Mapping	COMP.	1.2	Y	43.7	22.6
Review of UN Police Advisory Cttee	ONG.	1.1	Y	16.8	4.4
Jordan Inclusive Community Security	ONG.	1.2	N	-	9.6
NATO Effective Advising development	ONG.	1.1	Y	59.9	11.5
UNAMID Lessons Identification	ONG.	1.1	Y	132.2	30
SSR & VE Training	ONG.	1.2	Y	92.9	23.2
Int. Police Advisory Masterclass	ONG.	1.2	Y	33.7	11.2
Regional Effective Advising Iraq	ONG.	1.2	Y	60	20
OROLSI strategy development support	ONG	1.1	Y	60	5

List of activities covered under Outputs
Output 1.1
2020
- Mapping of donor S&J breakdown
- Support to OSESGY – feedback received
- Evaluation for Sweden Police programme in Moldova – reminder sent for feedback
- UNDP evaluation in Palestine – on-going
- UNDP evaluation in DRC – on-going
- UNDP evaluation in CAR – on-going
- UNAMID Lessons Identification – on-going
- Support to OSCE assessment in BiH – on-going
- Development of NL Whole of Government approach to SSR/RoL – on-going
- Development of UN Police Advisory Committee concept – on-going
- Support to UNSOM-UNDP programme design in Somalia – on-going
- Support to development of OROLSI strategy for engaging in the Sahel – on-going
- North Africa Mapping (OAK) – feedback received
Q4 2019
- Middle East Mapping (OAK) – reminder sent for feedback
- Review of the NL Expert Pool (PDT) – reminder sent for feedback
- Phase 1 - Joint EU, UN and WB Prevention and Peacebuilding Assessment in Burkina Faso – phase 2 (due to take place in 2020) has been postponed due to Covid-19
Output 1.2
2020
- Effective Advising – Swedish mandate (delivered virtually)
- RBM for Development course run in partnership with GCSP and Small Arms Survey (delivered virtually)
- Pilot Course of virtual format of the updated Security & Justice Governance and Reform Course (on-going so no data available)
- Support to IGAD training on SSR in South Sudan (delivered virtually)
- German Staff College SSR Training in support of military planning processes & capacity building (delivered virtually)
- Support to IGAD training on SSR in Sudan
Q4 2019
- Effective Advising course run in partnership with Interpeace
- Support to IGAD training on SSR in Somalia