## Annual Review Template

Title: SUPPORT TO INTERNATIONAL SECURITY SECTOR ADVISERY TEAM (ISSAT)
Programme Value £ (full life): £ 2,600,000		Review date: 01/01/21-31/12/21
Programme Code: 300614	AMP start date: 1/9/2019	AMP end date: 31/8/2024

Summary of Programme Performance
Year	2020	2021	2022
Overall Output Score	A	A	A
Risk Rating	Minor	Minor	Minor

DevTracker Link to Business Case:	ISSAT BC
DevTracker Link to results framework:	ISSAT RF

A. SUMMARY AND OVERVIEW

Description of programme

Together with like-minded donors, the UK established the International Security Advisory Team (ISSAT) in 2008. ISSAT is a department of the Geneva Centre for Security Sector Governance (DCAF). It has 16 member states and seven multilateral institutions who ‘mandate’ (commission) it to assist in a wide range of ways. ISSAT is at the centre of international lessons learning, best practice leadership and co-ordination efforts in the Security and Justice (S&J) field. The UK has a central position in ISSAT as a founding member and through membership of the ISSAT Governing Board Core Group. As a core funder, the UK is part of a small group of other bilateral members (France has just re-joined the core group). ISSAT provides practical support to the international community in its efforts to improve security and justice internationally, primarily in conflict-affected and fragile states. It does this by working with a group of member states and institutions to develop and promote good security and justice reform practices and principles, and by helping its members to build their capacity to support national and regional security and justice reform processes.

ISSAT has two main approaches: to provide practical support to the international community in its efforts to improve security and justice, primarily in conflict-affected and fragile states, and a convening role to collectively develop and promote good security and justice reform practices and improved co-ordination of its members.

ISSAT operates through a pooled multi-donor fund that apportions funds equally between three funding streams: ‘pillars’ (i.e. 1/3rd each pillar). Pillar 1 is ring-fenced for individual donors’ priorities (which can include joint mandates/co-funded activity); Pillar 2 is dedicated to supporting the multilateral system (the multilaterals also contribute via a cost-sharing arrangement), and Pillar 3 covers training and knowledge development. The UK therefore has attribution across all activity under pillars 2 and 3, and those activities the UK mandates under pillar 1.
DFID funded ISSAT until 2015 and then resumed funding in 2019 under the current programme. The current programme contains two components; a larger Component 1 for funding to ISSAT itself, and a separate Component 2 for small-scale research or analysis work that does not go through ISSAT. Through the UK’s funding to ISSAT under Component 1, the organisation delivers field advisory support, capacity building and knowledge services to HMG, bilateral and multilateral members and advocates for and facilitates greater donor coherence and coordination at the policy/strategy, practice and lessons learning and sharing, levels. Between October 2019 and March 2021, the FCDO will have contributed £600k core funding to ISSAT.
[note] Oct 19-March 20: £200K; April 20-Mar 21: £400K.

Summary supporting narrative for the overall score in this review

This programme has scored an A as it has exceeded its output and outcome indicators. It remains a relatively minor risk programme, especially considering its thematic area, and retains strong value for money metrics particularly due to the cost-sharing nature of the funding. This is especially impressive when considering the organisation is still readjusting from Covid-19 and the subsequent changes to its budgets and work in challenging contexts.

For Output 1, ISSAT exceeded their target of 80%, and achieved 100% for the ‘percentage of members reports that ISSAT’s contribution met or exceeded their expectations’. ISSAT had 15 Advisory support mandates in 2021, including four starting in 2020, and eight closed in 2021. These programmes included for example a mid-term review of a strategic police reform project in Somalia supported by the UK, Germany and the EU, and Rule of Law assistance, which HMG is looking at as a useful model for ISSAT support as HMG develops its own integrated cross-government approach to SSR.

On Output 2, ISSAT scored 83% on a 75% milestone for ‘Percentage of training participants who report that ISSAT's training met their expectations’ and 70% on 65% milestone for ‘Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance as a result of ISSAT training’. Despite the impact of Covid-19 on in-person trainings, ISSAT delivered 15 trainings in the reporting period, including in Niger, Tunisia and Iraq, while ISSAT have redeveloped their training materials and courses for online trainings.

Output 3 was similarly strong, with 74% scored for a 40% milestone on ‘% of ISSAT mandates that bring together multiple bilateral and multilateral GBMs’. Here, 31/42 tasks were joint mandates or supported joint engagements which highlights how ISSAT have worked at facilitating cooperation between members. This included donor mappings for Iraq and Ukraine, Lebanon Security Sector Resiliency, and working with EU CSDP missions and the UN SSR Unit.

Major lessons and recommendations for the reporting year

Response to previous Major lessons and recommendations for the year ahead:
Shift AR due date forward one-month to 1st March in order to better capture ISSAT annual reporting (Action: FCDO).
The shift in date was appreciated, although this still falls in the period of accounts closure. As such, a financial report for 2021 will not be available until after the 1st March (with the DCAF audited statement only released around April). Recommend the reporting date is pushed back further to allow for this reporting.

FCDO management of ISSAT would be improved with more regular, formal meetings with ISSAT than at present. ISSAT should ensure that staff with oversight of the programme results framework, finances and risk management are routinely present (ISSAT/FCDO).
FCDO-ISSAT have regular formal and very frequent informal meetings and communication. ISSAT staff leads for the programme results framework and finances have participated in several ISSAT/FCDO meetings. Nonetheless, the mechanism for more regular, scheduled formal meetings between the respective leads including on the programme/financial and risk management side awaits full formalisation. FCDO has lacked a dedicated ISSAT Programme Manager for part of the year and this needs to be re-established as quickly as possible to properly resource the SRO, PRO and PM functions. A quarterly risk meeting is being established in line with the recommendations from the recent audit.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Theory of Change

Under the Theory of Change, FCDO is making a commitment to work with ISSAT, and to contribute specialist staffing and programme funding (Inputs). In return, FCDO will receive advisory support to S&J programming in developing country contexts, will benefit from improved knowledge and professional development, and will benefit from improved co-ordination and consensus between donors and with multilaterals (Outputs). This will mean that FCDO is better equipped to deliver more effective politically informed and gender-sensitive security and justice interventions (Outcomes). More effective interventions will mean in turn that FCDO activities help to build stability - the ultimate intended Impact of the programme.

This approach remains valid and necessary, with some new emphases to reflect the upcoming development of FCDO’s approach to SSR. Several security & justice programmes are in development within FCDO and have called on ISSAT capabilities, as have established programmes and regional directorates. A forthcoming ISSAT initiative on impact assessment (see below) should help to demonstrate the ways in which ISSAT support is helping members to build stability in fragile/conflict-affected countries. As ISSAT does not implement activities in developing countries directly, its mechanism for contributing to enhanced stability is to influence and build the capacities of its members. Evidencing this will be challenging as success rests on many assumptions: that members such as the UK adopt and implement ISSAT’s recommendations and analysis, that the programming itself is well-calibrated toward the causes of instability and is conflict-sensitive, and that operating contexts allow for the ISSAT-informed programming to have a positive impact, for example. Further evidence on the effectiveness of ISSAT’s approach to these questions will be valuable given that the economy of the approach (shared costs) and its efficiency (quick and easy commissioning) are much clearer. ISSAT does not implement programmes directly, so relies on Member’s own decision-making to target marginalised groups but does disaggregate participation by gender (equity).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact assessment conclusions

The pilot methodology for measuring ISSAT’s impact was finalised (with FCDO inputs), and a remote assessment carried out by an ISSAT-contracted consultant on ISSAT’s support to its Governing Board Members (GBMs) in Liberia over the past ten years. The purpose of the remote assessment was threefold: 1) to look at evidence that ISSAT’s support is resulting in better GBM S&J interventions, which contribute to a more positive real-world effect on people’s security and justice; 2) to look at what we are trying to measure; and 3) to make recommendations on the methodology we should use. The first draft of the report has just been submitted to ISSAT. The final draft will be shared with core GBMs by the end of February 2022 for discussion in the next core group meeting. Note that the UK has not conducted substantial S&J work in Liberia so ISSAT’s impact on UK activities will not be under review. The methodology will be later applied to UK priority contexts and where the UK has played a much greater role, however. The study raises up an important question in relation to the Impact statement. Whilst all interviewees expressed their appreciation for the work carried out, especially in terms of its quality, utility, collaboration, and professionalism, there was a consistent observation that ISSAT’s impact statement was outside of its mandate (and therefore unattainable) and should be changed.

The desired Outcome is that FCDO and other GBMs are better equipped to deliver effective, politically informed and gender-sensitive security and justice interventions. This is indicated by the percentage of recommendations to all GBMs that are partially or fully accepted in mandate reports, accompanied by a narrative on how the mandates have influenced bilateral and multilateral GBM decision-making around interventions.

Feedback received thus far for Advisory Field Service (AFS) mandates specifically offers a positive outlook, as 99.3 % of all recommendations provided were formally accepted by mandators (see table 1 below). ISSAT also received statements of intent to implement recommendations from several of the mandators. Performance indicators around quality and level of reception of recommendations were included into ISSAT’s feedback form to provide a bridge to higher-level analysis on outcome effects of the support provided. A dedicated recommendations tracker is in preparation to generate more granularity on the type of recommendations made by ISSAT and their take up by GBMs, including qualitative factors such as conflict sensitivity and gender. ISSAT takes seriously the challenge of evidencing its impact. Higher-level effect of mandates concluded in 2021 will be reviewed and reported on in the following year to allow mandators time for processing and acting on the support provided.

Table 1: Percentage of GBMs acceptance of recommendations provided
Title Mandate	Recommendations	% of acceptance
Support to OSCE assessment to develop/align S&J programme in Bosnia	Lessons/methodological advice incorporated by the OSCE team in the execution of the assessment – Qualitative feedback	N/A
2. UNDP GP RoL – DRC Evaluation	All 28 recommendations provided were fully accepted.	100%
3. UNDP GP RoL- CAR Evaluation	27 out of 28 recommendations provided were accepted.	96,4%
4.UNDP GP RoL- Palestine Mid-term review Evaluation	All 11 recommendations provided were fully accepted.	100%
5. OSESGY - Pay, Integration and Force Management	Indirect advisory, mapping and research support designed to produce options framework - Qualitative feedback	N/A
6. UN/AU Darfur Lesson Identification Dissemination 2021	Lessons identification exercise which produced a set of strategic and programmatic lessons, which were partially implemented - Qualitative feedback	N/A
7. NL Whole of Government (WoGA)	All 7 recommendations (4 short-term, 3 long-term) provided were accepted. The 4 short-term have been partially implemented so far.	100%
8. Mid Term Review (MTR) of the Joint Police Programme (JPP)	All 33 recommendations provided were accepted - 27 fully agreed and 5 partially agreed, 1 pending clarification.	100%
Total % of applicable entries		99,3%

## C. DETAILED OUTPUT SCORING

Output Title	Advisory Field Support for Members' missions
Output number:		1.1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	no

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 Level of performance - percentage of members report that ISSAT’s contribution met or exceeded their expectations	80%	100%

Fifteen Advisory Field Support mandates were facilitated by ISSAT in 2021 including four mandates which had been initiated in year(s) prior and came to conclusion in 2021, four mandates that were delivered from inception to close-out within the reporting period, and seven mandates which ISSAT initiated in 2021 and that remain on-going. However, only eight mandates gave formal feedback. In particular the Core Group donors, should improve feedback on completed mandates. The impact of Covid-19 was still felt concerning deferral of GBM decisions on programmes, with a proportional effect on delaying requests, finalising contracts and/or ToRs. This impacted the start of mandates, some of which have now transited to 2022 (for example support to UN Joint SSGP in Somalia, and the development of a framework for OROLSI’s engagement in the Sahel).

The four key mandates which started and concluded within the reporting period were of importance. A mid-term review of a strategic police reform project in Somalia supported by the UK, Germany and the EU, provided significant input towards redesign for a second phase in addition to more immediate improvements and long-term recommendations. During the same reporting period the current phase of evaluation A of the UNDP’s Global Programme on Rule of Law was concluded, which focussed on improvement of programme monitoring systems. ISSAT worked in support of the UN Office of the Special Envoy for the Secretary General for Yemen on the development of a policy planning framework on armed group management, including integration and payment schemes, with strong potential for usage by a broader audience following official release.

Mandator feedback was received for the eight relevant mandates completed in 2021 (100%). All mandates for which written feedback forms were received rated on or above expectations. Feedback received outside of the formal mandate process was also positive. (100% - see table 2 below). There is an inherent contradiction in soliciting feedback. Soonest after an event or piece completion gets higher response rates but it is not possible to take a longer-term view. Soliciting feedback six months to a year later gives a better perspective but, because of issues like staff turnover and the nature of ‘firefighting’ in challenging contexts, receive much lower responses.

In addition to AFS, some engagements under ISSAT’s Outreach and Knowledge feed into enabling GBM decision making. In 2021 this included two country mappings Iraq and Ukraine, (the latter of which is on-going).

Output Title	Knowledge and professional development for member staff
Output number:		1.2	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	no

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Percentage of training participants who report that ISSAT's training met their expectations ("agree" / "strongly agree")	75%	83%
1.2.2 Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance as a result of ISSAT training (longer-term, 6 months)	65%	70%

This output is designed to assess the effectiveness of ISSAT’s security sector reform and governance training, knowledge, and professional development activities.  The current indicators only capture elements related to training and professional development. Analysis related to ISSAT’s knowledge activities has been included as an additional section afterwards.

Covid continues to have a considerable impact on in-person trainings taking place in 2021, with several in-person events cancelled, postponed, or adapted to online delivery methodology. Despite this a total of 15 trainings were delivered in 2021. ISSAT’s development of trainings contextualised to specific geographies is generally a positive expansion with trainings delivered in Niger, Tunisia and Iraq (the latter virtually), but ISSAT and FCDO should continue to consider whether country/organisation-specific trainings are the most strategic and VFM use of resources. The Professional Development and Training (PDT) team also completed the update and validation of core and specialist SSG/R training courses, as well as translating several of these into a virtual delivery format. Online permanently available training offerings do not have the same post-course evaluation mechanisms, hence data on the usefulness of the support is not captured in the same manner as those offered via dedicated mandate requests with complete After-Action processes and mandator feedback forms.

Under Indicator 1.2.1, an average of 82.8 % participants rating the training as having ‘met expectations’. Whilst a shift back to in-person training and hybrid events will be more optimal, the way ISSAT adapted the trainings and obtaining this result was a notable achievement in challenging circumstances.

Indicator 1.2.1 remains challenging to report against in a meaningful way. Of the six training courses that were between six months and one year ago, quantitative data is available for just one: the first Effective Advising course in Iraq, where 65% of participants stated they were “using models and ideas [they] had learned about in [the]course in [their] day-to-day work”, and they were “applying techniques and tools [they] learned and practiced in the Effective Advising course in [their] professional life’. Three courses involved ISSAT embedding into the delivery of a training by a GBM, leaving ISSAT reliant on the evaluation mechanisms of that GBM. Qualitative feedback has been received from one in relation to the delivery, but this does not provide data to input into the indicator. This situation was compounded by the departure of ISSAT’s Head of Professional Development and Training in August 2021. The new incumbent will start in March 2022 and re-establishing a robust outcome-monitoring system for the trainings is a priority.

The VfM benefits remain extant from 2020. There are clear Value for Money benefits in being able to share the costs of developing trainings (economy). With a larger pool of participants to draw on, more trainings can be held (efficiency) and more specialised trainings can develop (effectiveness). Trainings developed and implemented by ISSAT also have built-in shared costs under Pillar 3 making these economic in VfM terms. Working across GBM’s gives a wider pool of GBM staff to draw from, and more targeted specialised trainings can be developed which GBM’s individually would not resource. Pre-existing trainings can be adapted to fit GBM requirements which reduces the costs of developing separate courses. FCDO plans to engage with ISSAT on better embedding the political approach and analysis into ISSAT trainings.

In terms of gender equality, the proportion of female participants in trainings was 36% and the proportion of female trainers was 58%.

Table 3: Professional Development and Training Courses

Course Title	Dates	Mandators / Partners	% of female participants	% of female trainers	% of training participants rating training as meeting their expectations	# of participants
German Staff College Security Sector Reform (SSR)Training (military planning processes)	22.03.2021-09.04.2021	Germany	43% (3 of 7)	100% (1 of 1)	Not Available	7
RBM and beyond 2021	05.07.2021-09.07.2021	DCAF, GCSP, SAS	81% (17 of 21)	50% (2 of 4)	89.4%	21
ESDC Austria core course on Security Sector Governance (SSG) April 2021	26.04.2021-30.04.2021	Austria / ESDC, Austrian MoD, ASPR	64% (18 of 28)	50% (1 of 2)	89%	28
Effective Advising Iraq 1	26.05.2021-30.06.2021	Germany, Netherlands, UK, EU (EUAM Iraq)	41% (7 of 24)	71% (5 of 7)	75%	24
Effective Advising Iraq 2	05.11.2021-03.12.2021	Germany, Netherlands, UK, EU (EUAM Iraq)	33% (7 of 21)	71% (5 of 7)	100%	21
Operationalising Gender Workshop for Danish Police Instructors	22.11.2021-25.11.2021	Denmark	31% (8 of 26)	33% (1 of 3)	Not Available	26
Intro to Security Sector Governance/Reform E-Learning English	Perpetual Offering		30%	50% (2 of 4)	93%	559
Intro to SSG/R E-Learning French	Perpetual Offering		14%	50% (2 of 4)	100%	114
Course on SSG/R Contribution to PVE in Niger	11-15.10.2021	Germany, Netherlands, Denmark, Switzerland	5% (1 of 21)	60% (3 of 5)	100%	21
SSR/PVE blended (virtual and in presence) course in Tunisia – phases 1 and 2 (virtual)	May, June, Sept 2021	Netherlands, Germany, Switzerland, UK	50%	66% (2 of 3)	90%	17
UNMAS Heads of Mine Action Conference (HOMAC)	June and October 2021	UNMAS, UNOPS		100% (1 of 1)		76
ESDC Austria core course on SSG/G October 2021	04.10.2021-08.10.2021	Austria / ESDC, Austrian MoD, ASPR	32% (7 of 22)	33% (1 of 3)		22
Security and Justice Governance and Reform - ESDC & FINCENT	15.09.2021-13.10.2021	Finland / ESDC	32% (6 of 19)	40% (2 of 5)	92%	19
Security and Justice Governance and Reform - UNTSI Ireland	29.11.2021-03.12.2021	Ireland	32% (9 of 28)	50% (2 of 4)	100%	28
Senior Strategic Leadership and Change Management for SSR in Iraq	24.10.2021-28.10.2021	EU (EUAM Iraq) in partnership with Germany	12.5% (2 of 16)	46% (6 of 13)	100%	16

ISSAT’s outreach and knowledge work aims to enhance GBMs’ thinking and deliberations around the future of their ODA and the earmarked funding towards SSG/R. Knowledge products and mandate reports include recommendations to help build the evidence base for policy makers to inform strategies and decision making, with topics based on ISSAT GBMs’ policies, and political and thematic priorities.

In addition to the learning processes (after action reviews, Community of Practice, newsletters, etc.), Oak Foundation carried out 12 mandates, worked on two specific SSG/R methodologies (lessons identification approaches and applying design thinking) and ran five learning events.

Linking into one of the UK’s priorities, the mandates included operationalising the Conflict Prevention agenda through the development of two guidance notes under an UN-World Bank project focusing on security and justice drivers of conflict and how to better integrate those in joint country assessments and public finance reviews by the World Bank. These policy notes will inform future UN guidance around conducting assessments and Public Expenditure Review (PERs), taking into consideration SSG/R imperatives, as well as strengthening the UN capacity to partner with the World Bank to support sustainable SSR initiatives.

All mandate feedback forms for 2021 activities acknowledge that ISSAT met or exceeded expectations in all instances. ISSAT has previously attempted to go further and measure their impact but struggled to get meaningful data. ISSAT is currently compiling a summary of overarching, thematic, and methodological recommendations championed over the past two years to compare against how its GBMs are engaging in their support, with the expectation that this analysis will help shape more meaningful data collection for results.

ISSAT’s work on the development of a Security, Justice and Governance indicator framework advanced, with a case study to test the feasibility and applicability of an SSR index. The on-going people-centred approach mandate is also enabling ISSAT to capture community level indicators. Developing an index that adds value is a challenging undertaking, especially in such a complex field. Hence sufficient time is being allocated to build up strong foundations. The index methodology will be ready by the end of 2022.

Output Title	Improved co-ordination and consensus between donors, and with multilaterals
Output number:		1.3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	no

Indicator(s)	Milestone(s) for this review	Progress
1.3.1: % of ISSAT mandates that bring together multiple bilateral and multilateral GBMs	40%	74%

This output is designed to assess how well ISSAT is facilitating co-operation between members and developing co-ordinated approaches. Out of 42 tasks/substantive external activities that took place over the reporting period, 31 were joint mandates, or ones directly supporting joint engagements (including trainings with participants from across multiple GBMs) representing a result of 74%, exceeding the milestone of 40%.

In addition, under the OAK portfolio, ISSAT was able to convene policy makers and practitioners around learning events that discuss emerging areas of interest for SSG/R. These thematic learning events included reintegration and SSG/R, UN-EU cooperation and climate security, identifying entry-points for creating change, securing progress and aiming to scale up SSG/R. These events allow from cross-organisation reflection on risks, lessons and alternatives, enabling ISSAT to extract learning and evidence for its work around building the future business case of SSG/R.

Joint mandates are useful indicators of shared priorities. However, ISSAT is capable of, and has shown signs of much more dynamic co-ordination. Events such as the informal closed-door meeting in June 2021 on Mali following the coup, meeting on The Promise of Donor Coordination and SSG/R presentation and exchange around the development of a key UN SG Report on SSR and associated independent review show how this could be done. ISSAT has acknowledged that there is a growing need for political analysis, as well unpacking the trend of international assistance and impact in targeted countries over a longer period. As such, ISSAT is currently reviewing its donor mapping methodology, transforming it into a “Security Sector/SSR Political Analysis and Donor Engagement Mapping and Analysis.” The ultimate goal of such engagements in the future will be to support GBMs to understand the political ownership, agendas, strategy and benchmarks to inform SSG/R engagement in a given country.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to the outputs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

ISSAT increased its focus on convening GBMs in 2021 and has plans to continue this trend in 2022. The idea of convening GBMs to follow up on completed mandates was explored around the Somalia Joint Police Programme (JPP) evaluation. This was frustrated by the departure of the Head of the Programme and a negative programme audit, which has resulted in significant donor/programme discussions in country. This is precisely the type of situation that ISSAT should engage in, but it does raise the question of how to manage the needs and perspectives of both country and capital levels. An alternative approach, which is being considered for 2022, is to frame discussions around clusters of mandates, including:

- Somalia (JPP evaluation, support to the UNDP-UNSOM joint Security Sector Governance programme, EU assessment for entry points for support, case studies developed for the people-centred security study and the risk management analysis)
- Mozambique (in part subject to a concrete mandate, but otherwise drawing on ISSAT’s on-going analysis and other DCAF engagements in-country around business and human rights)
- Sudan (based on the scoping mission carried out in partnership with DCAF’s Operations division, depending on context developments)
- Challenges of national political transitions following the transition/exit of peace support operations (drawing on Liberia post-UNMIL, Sudan post-UNAMID, Guinea Bissau post-UNIOGBIS, and potentially bringing in analysis related to MONUSCO transitions)
FCDO OCSM is engaging with ISSAT on strategic policy and country priorities to shape the agenda (including around the theme of politics), and is developing a dedicated ISSAT project under Pillar 1 to support OCSM in developing a new HMG integrated policy and practice approach to SSR, centred on the political approach, as well as related guidance and training. OCSM is also encouraging and supporting ISSAT to strengthen its own approach to put politics at the centre of its approach, including in its mandates and support to bilateral and multilateral actors, methodologies, the expertise its tea mand roster and in its trainings.
Recommendation: put particular focus in the next Annual Review on ISSAT’s performance in delivering to these new OCSM policy and country priorities.

D: RISK

Overview of risk management

ISSAT had a commitment in 2021 to develop its risk framework and risk register. ISSAT is a department within the parent organisation, DCAF, and falls under the overarching corporate risk framework. A process to develop this has been on-going over the last year, and just being concluded now. The process has mapped DCAF’s risk universe, identified key priority risks, secondary risks, mitigating measures, and a monitoring system. This will be finalised in the next weeks. In the interim, ISSAT continues to use its previous risk framework.

An internal audit within FCDO, on FCDO management of ISSAT noted the lack of routine management of the FCDO / ISSAT risk register and recommended the risk register be overhauled and updated, with regular quarterly meetings instated with ISSAT management. This is now being put in place.

The audit also identified the need to schedule regular reviews of the risk register, a recommendation that has been taken up, with regular meetings scheduled. Further work needs to be made to ensure that DCAF, the parent organisation of ISSAT, also meets FCDO risk management standards (fraud, safeguarding) due to the oversight relationship between them.

The fiduciary, safeguarding and reputational risks of working with ISSAT remain minor. However, delivery should be rated as medium risk, reflecting that ISSAT is still working on demonstrating impact through its work with Governing Board Members, and this coming year will be an important test of whether the programme can deliver in a VFM manner on new OCSM priorities including policy and country priorities. The nature of working in the security & justice sector as often high-risk reflects on external context which should also be regarded as of moderate risk. Noting this, the programme remains Minor risk but will be kept under review. The risk register should be reviewed every three months or when certain circumstances warrants an ad-hoc update, such as occurred when Covid impact compelled restructuring of financing.

Current level of fiduciary risk and direction of travel since last ASP	Minor, stable
Specific assessment of corruption risk and direction of travel since last ASP	Minor, stable
Is a full FRA update required?	No

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Programme management

An internal audit reviewed the programme management of ISSAT noting specifically the need to ensure that funds were absorbed before requesting further annual payments.

The due date for ISSAT’s Annual Review date was moved to 9 March, approved by Director, to fit in better with ISSAT’s own annual data collection and processing. ISSAT receives a single annual payment into a pooled fund, shared between donors, and as such behaves like a multi-donor trust fund. However, the FCDO programme team has taken up the recommendation to get confirmation that all funds from a previous year are assigned before making further requests. Previous years have received generic (in the Business Case) and specific approval for each payment to be made in advance of need.

The Covid re-financing and temporary reduction in FCDO ODA budget (from 0.7% to 0.5% GDP) complicated making payment to ISSAT this year. Payment was made in August, four months later, following on the previous year which was 5 months late. Noting also that, for ISSAT, our scheduled payment date of 1 April is anyway late by their financial year which begins 1 January.

Programme management has been hampered through the absence of a programme manager for the second half of the year.

ISSAT represents good Value for Money (VfM). Clearly, economies have been made in reduction of travel and accommodation during the Covid period but ISSAT has not allowed this to overly reduce its impact, by adapting to online training and desk-based reviews. In-field analysis and on-site training is usually the preferred model, however. Cost management protocols at ISSAT are strong in this area though future Annual Reviews may wish to drill down into this area in more detail.

Joint mandates clearly lead to cost-savings through cost-sharing. However, there are other benefits. FCDO gets exposure to the priorities and new ideas of partner governments. With cost-sharing the efficiencies allow more scope to tailor engagement. For example, training courses can target specific issues (violent extremism) or geographies (Iraq, Niger, Tunisia). ISSAT’s procurement procedures are light and efficient. They are often willing to begin work on rough steers that are later refined. This responsiveness is unusual across FCDO and appreciated by OCSM and Country Offices. ISSAT is working on demonstrating its effectiveness in changing behaviour within GBM. The work is challenging and innovative. ISSAT is most effective in its convening capability, in the creation of a space where like-minded donors and multilateral partners can discuss and co-operate on the often heavily politicised but critically important issues of SSR/G.

The ISSAT Help Desk facility offers the opportunity for FCDO to draw on expertise that is not always easily available. It is economical (with no specific costs assigned), efficient (turning requests around in 1 – 2 days) and effective (in accessing expertise that is not always easily available). It should be used more.

Date of last narrative financial report	27.04.21	Date of last audited annual statement	16.07.21

Attach Audited statement G:\ISSAT Restricted\Financial Management\01. Accounts\Accounts 2020\Audit\2020 DCAF - Audit Report.pdf