## Annual Review
Title: Support to the International Security Sector Advisory Team (ISSAT)
Programme Value £ (full life): £2,326,764.88		Review date: 09/03/2024
Programme Code: 300614	AMP start date: 01/10/2019	AMP end date: / 31/12/2024

Summary of Programme Performance
Year	2020	2021	2022	2023	2024
Overall Output Score	A	A	A	A	A
Risk Rating	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	ISSAT Business Case and Summary
DevTracker Link to results framework:	ISSAT Logical Framework

A. SUMMARY AND OVERVIEW
Description of programme

The FCDO is funding the International Security Sector Advisory Team (ISSAT), a foundation that supports the international community to improve security and justice (S&J), with up to £2.1m of funding over five years. An additional £100k p.a. has been allocated for supplementary research, monitoring and evaluation and technical assistance needs on security and justice related priorities, which providers other than ISSAT can best meet bringing the total business case value to £2.6m over 5 years.

The purpose of the programme is to deliver effective security and justice interventions through ISSAT by providing guidance to help bilateral donors and multilateral organisations to deliver effective and politically informed security and justice responses, based on lessons from the field.

The programme consists of two components:

Component 1 for funding to the International Security Sector Advisory Team

Component 2 intended to fund small-scale security and justice-related research or analysis work outside of ISSAT.

The ISSAT component operates through a pooled multi-donor fund that apportions pooled funders’ contributions across three pillars.
- Pillar 1 is ring-fenced for individual donors’ priorities (which can include joint mandates/co-funded activities supported by the Core Group members).
- Pillar 2 is dedicated to supporting the multilateral system (with the multilaterals also contributing via a cost-sharing arrangement), as well as supporting greater joint engagement by International Partner Group Meetings (IPGMs) around multilateral Security Sector Reform (SSR) support.
- Pillar 3 covers training, knowledge, and project development, including a helpdesk function.

As a founding member of ISSAT, the UK is a member of the ISSAT Core Group of bilateral partners who provide contributions to ISSAT’s pooled fund and is a member of ISSAT’s International Partners Group (IPG) that brings together a much wider grouping of bilateral and multilateral actors active in the SSR field.

ISSAT works with a group of member states and institutions to develop and promote good security and justice reform practices and principles, helping members to build their capacity to enhance the effectiveness and quality of security sector reform (SSR) engagement and programming, and to facilitate the coordination and coherence of international assistance to nationally driven SSR processes.

The nature of the programme means that the indicators used are quantitative and are assessed by the level of feedback received by International Partner Group members. This, and the necessity of Core Group countries then taking action as a result of ISSAT’s research, means it’s challenging to assess the direct change ISSAT’s interventions have led to and the level of success. Next steps to address these constraints have been highlighted in the major lessons section of this report.

The UK-ISSAT relationship and programme management is led by FCDO’s Office for Conflict, Stabilisation and Mediation (OCSM).

Key changes to the programme this year:
1. The business case was extended from 31 August 2024 to 31 December 2024 to allow added time to align with the ISSAT financial year and for ISSAT to fulfil the programme’s anticipated deliverables and further monitor activities to completion.
2. The budget allocation for Component 2 was reallocated to Component 1 during the financial year. This means that activities planned under Component 2 have not taken place within this reporting year and have not been reported against the log frame outputs.

Summary supporting narrative for the overall score in this review

This programme continues to be a unique source of expertise and analysis into SSR and plays a vital role in convening international players in the SSR field. The programme’s design allows for reach and scale in FCDO support and ability to flex, though there are some instances where this approach has been challenging to operationalise.

The programme has continued to perform well and has scored an A. It has met all its annual output milestone indicators as set out in the programmes log frame/results framework and is currently in line with the FCDO’s expectations of the programme.

Our FCDO funding to ISSAT has continued to achieve the outcomes of the programme as ISSAT’s proficiency has allowed the programme to flex to new geopolitical contexts as required and continues to give the FCDO access to expertise as these contexts develop.

For the output scoring, the review has drawn on the data and explanations that ISSAT have provided. The scoring reflects an assessment of both output-level and overall performance and reflects some of the weaknesses identified in the output results aspect of the current UK-ISSAT results framework. The review team experienced some challenges in obtaining core group members’ feedback for reporting purposes (which was outside of ISSAT’s control).

This programmes overall risk assessment continues to be minor and demonstrates value for money due to the cost-sharing function of the programme. Further details on value for money are explained in section D of this report.

Based on the current results assessed in this review, the FCDO is on track to realise the outcomes and impact statements.

Major lessons and recommendations for the year ahead

ISSAT to strengthen its results framework and the current format of the programme’s log frame to be adapted to be more quantitative.
ISSAT should update its results framework and develop a more robust way to collect feedback and monitor progress against the programme’s expected outcomes.

Currently ISSAT asks IPG members for feedback after training sessions and mandate completion, but there may be instances where members are unable to provide sufficient feedback. This could impact the overall results framework.

We recommend that the results framework be changed from asking for qualitative feedback from core group members to quantitative results that can be better measured and accessed. The log frame should be revised within one month of this review.

The adoption of an amended impact-level statement in the ISSAT pooled fund results framework continues to make it more appropriate and measurable. ISSAT continues to place greater emphasis on data collection at an outcome level. This includes for example efforts to start more systematically tracking the extent of influence and take-up of recommendations contained in ISSAT reports and to assess how ISSAT’s efforts have contributed to bilateral and multilateral decision-making around SSG/R (Security Sector Governance/Reform) approaches and interventions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Figure 1
[note] Figure 1: References to DFID (Department for International Development) should be replaced with FCDO as Theory of Change was established pre-merger.
The programme’s theory of change as illustrated above sets out that the FCDO will work with ISSAT to contribute specialist staffing and programme funding (inputs). In return, FCDO receives advisory support to Security & Justice programming in a range of country contexts; benefits from: improved knowledge, professional development, and improved coordination; and also, consensus between donors and multilaterals (outputs). The FCDO is better equipped to deliver more effective, politically informed and gender-sensitive security and justice interventions (outcomes)

This review therefore assesses that the theory of change remains valid, and no changes are required at the time of this review.

ISSAT has been responsive to supporting UK priorities, fostering collaboration, lessons learning and good practice across the international SSR community, and continues to perform well in line with the objectives of the programme and theory of change. ISSAT also continues to:
1. emphasise improved security and justice outcomes for people as the ultimate objective of SSR, particularly in conflict-affected and fragile states
2. commit to its data collection with an outcome-level focus and tracks feedback and recommendations from International Partner Group (IPG) members to assess how its efforts contribute to decision-making around SSG/R interventions

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This programme continues to meet expectations and is being assessed as being on track to meeting its expected outcome of the FCDO being better equipped to deliver effective security and justice interventions. The work towards their outcome performance level is timely.

ISSAT continues to monitor its programme delivery risks and clearly report this yearly on risk areas that could impact intended outcomes such as internal staff expert capacity and donor funding.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Security Sector Reform and Governance continues to be a key thematic priority within the FCDO/OCSM, with this programme serving the agenda of both the OCSM and priority geographic teams and other thematic departments (such as Open Societies).

OCSM’s policy agenda, which includes SSR, Stabilisation, peace processes, gender and conflict prevention, is being supported by the pieces of work that ISSAT focuses on and the programme continues to demonstrate that it can respond to UK priorities and provide a cross-cutting mechanism to engage with international partners. This is clearly valued by international partners, as demonstrated by their feedback.

The programme stands to deliver important contributions to SSR guidance and approaches and is the right approach to deliver the outcomes we are looking for on delivering effective security and justice interventions.

Based on this there is a strong argument for continuing the programme.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Advisory Field Support (AFS) for Members' missions
Output number:		1.1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 Level of performance - percentage of Members report that ISSAT’s contribution met or exceeded their expectations	80%	100%

Output 1.1 - Advisory Field Support for Members' (AFS) missions Output Indicator 1.1.1: Level of performance - percentage of Members report that ISSAT’s contribution met or exceeded their expectations.

This indicator is measured through reviewing the mandate feedback forms that are filled in by the International Partners’ Group Members (IPGMs) after the completion of each mandate. The following evidence has been provided by ISSAT.

Group members shared high appreciation for ISSAT support to their resulting evaluations. They stated how they received positive feedback from their project and programme board, and greatly appreciated the team’s expertise.

As shown in table 1 below, 17 AFS mandates were active and 10 were completed in 2023. For the completed mandates, performance is measured through the feedback forms that IPGMs fill in after completion, or through more informal written feedback received when the feedback forms are not yet available.

Of the ten completed mandates, the Assessment of Rural Courts in Sudan in support of UNITAMS (United Nations Integrated Transition Assistance Mission in Sudan) was cancelled because the UN Security Council decided to close UNITAMS. The backstopping to Switzerland started with an initial phase from September 2022 to March 2023 with the development of a Trends Analysis. The lessons identification on SSG/R in the ECOWAS (Economic Community of West African States) region (Ghana and Liberia) was completed. A formal presentation to ECOWAS was planned prior to formal feedback from the main mandator, GIZ.

For the AU (African Union) SSR 10-year anniversary, ISSAT contributed to shaping the agenda of the conference held in Addis Ababa in November 2023, also contributing to the substantive part of the session on Coordination of Security Sector Reform assistance. This focused on the different roles and responsibilities of various SSG/R implementing partners, identifying options to strengthen the interaction between actors, Member States, RECs, AU, and other national and international partners. The AU indicated its appreciation for ISSAT support, with new opportunities for long-term support on SSR to the AU now on the table.

For the final evaluation of the UNDP (United Nations Development Programme) Rule of Law Global Programme in the OPTs, all eight evaluation recommendations were fully accepted, and UNDP endorsed the recommendation. ISSAT’s review was instrumental in leading to the adjustments of the overall programme’s strategy.

Regarding the support to the Office of Rule of Law and Security Institutions (OROLSI) in the UN (United Nations) to establish the OROLSI Sahel Strategy, ISSAT received very positive feedback from the UN “sincerely appreciating the cooperation with ISSAT/DCAF in the context of the OROLSI Sahel Project”.

Regarding the Programme Design of the Community Policing in Albania, the mandator (Sweden) recently published the tender for the new phase of the community policing programme which is based on the design scope provided by ISSAT. The representative of the Swedish Embassy in Albania said that they “…greatly appreciate ISSAT team expertise and the participatory processes for the design of the 3rd phase. We feel confident of having a document of good quality that can pave the way to a successful programme in the five years to come.”

Regarding the strategic analysis carried out in the Eastern Neighbourhood nations of Georgia and Moldova, points of contact within international partners networks confirmed that recommendations from both reports were applied at local level. As part of the feedback, one international partner thanked ISSAT stating “We are really happy with the analysis and the result. Excellent work”.

The support to the UN Resident Coordinator has been a major undertaking that led to a comprehensive assessment of the Security and Justice Sector in Niger. This happened before the coup. The head of the office stated “The work of the team supported forward thinking on the role of the Resident Coordinator’s office (RCO) in Niger. Their knowledge of the justice and security context in the UN combined with a high level of professionalism led to critical recommendations for the RCO.”

ISSAT is placing increasing emphasis on data collection at an outcome level, including more systematically tracking the level of full or partial acceptance of recommendations over time. A particular focus is on how ISSAT’s efforts have contributed to inform bilateral and multilateral decision-making around SSG/R interventions, so the added-value and influence it is having on international SSR engagement. This will be reported in the annual ISSAT Pooled Funders’ Report.

Table 1: List of AFS Mandates(activities) active in 2023

Mandate Title
AU 10-Year SSR Framework Policy Anniversary – Conference Support / Assessment of the Security and Defence forces of Comoros / Assessment of International Support to SSG/R in Ukraine / Strategic Analysis of Maritime Security and Justice Challenges in the Gulf of Guinea / Lesson Identification on SSR/G in the ECOWAS region - Ghana & Liberia case study / AU / RECs outreach and reinforcement SSR portfolio / Seed funding for AU/REC's Austria project / UN OROLSI targeted support to priority areas of Rule of Law and Security Institutions in the Sahel / Programme Design of Community Policing Albania Phase III / Strategic Analysis of Moldova’s Security Sector Reform and International Assistance / Backstopping CH - UNSC 2022 - 2024 / Strategic Analysis of Georgia’s SSR and International Assistance / UNDP Somalia (project funding) - Support to the Development of the Next Generation (SSR) Programmes / Support to UN RCO Niger - S&J Assessment and RCO capacity assessment, and roadmap for improvement - phase 1 (project funding) / UNITAMS Assessment of Rural Courts in Sudan / Strengthening UNDP Iraq capacities on Stability / Fragility assessments and information system in Iraq / UNDP Rule of Law Programme in Palestine Final Evaluation

Table 2: List of AFS Mandates closed in 2023
Mandate Title
AU 10-Year SSR Framework Policy Anniversary – Conference Support / UN OROLSI targeted support to priority areas of Rule of Law and Security Institutions in the Sahel / Programme Design of Community Policing Albania Phase III / Strategic Analysis of Moldova’s Security Sector Reform and International Assistance / Backstopping CH - UNSC 2022 - 2024 / Strategic Analysis of Georgia’s SSR and International Assistance / UNDP Somalia (project funding) - Support to the Development of the Next Generation (SSR) Programmes / Support to UN RCO Niger - S&J Assessment and RCO capacity assessment, and roadmap for improvement - / phase 1 (project funding) / UNITAMS Assessment of Rural Courts in Sudan / UNDP Rule of Law Programme in Palestine Final Evaluation

Output Title	Knowledge and professional development for member staff
Output number:		1.2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Percentage of training participants who report that ISSAT's training met their expectations ("agree" / "strongly agree")	80%	100%
1.2.2 Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance, as a result of ISSAT training (longer-term).	70%	90%

This output is designed to assess the effectiveness of ISSAT’s training, knowledge, and professional development activities.  The current indicators only capture elements related to training and professional development. Analysis related to participant responsiveness to ISSAT training courses has been included below.

The course targets practitioners and professionals including civilian military and police personal as well as civil society representatives and professionals in the private sector who are working on the provision, management and oversight of security and justice governance in the area of policy or practice.

The training focuses on providing participants with the knowledge and practical tools on security sector governance, reform, and justice. It touches upon the holistic nature of SSG/R and covers dimensions related to human security, access to justice and good governance with a focus on people-centered and state-centered security and justice in various development contexts.

Output Indicator Level 1.2.1: Percentage of training participants who report that ISSAT's training met their expectations ("agree" / "strongly agree").

Courses	Respondents	% Agree	Breakdown*
Netherland Interdepartmental SSG/R Training III 4-6 April 23	84%	100%	88% gave the highest rating
Security and Justice Governance and Reform (SJGR) Course Finland 05-09 June 23	77%	100%	88% gave the highest rating
Results-Based Management (RBM) for Peacebuilding, Security and Development Training	17%	100%	67% gave the highest rating
Summer School on SSG/R in Central Asia for OSCE Academy Alumni Network (Bishkek OSCE) 17-22 July 23	87%	100%	62% gave the highest rating
Ireland SSG/R Training 2023 11-15 Sept 23	65%	93%	80% gave the highest rating
Netherland Interdepartmental SSG/R Training IV 6-8 Nov 23	79%	100%	93% gave the highest rating
Slovakia SSG/R Workshop 21-23 Nov 23	67%	88%	88% gave the highest rating
Introduction to SSG/R e-Learning	N/A	98%	64% gave the highest rating
Overall Average	68%	97%	79%

*highest rating = strongly agree
Output Indicator Level 1.2.2: Percentage of participants (out of responses obtained) who report the ISSAT training contributed to their work performance because of ISSAT training (longer-term)
Courses	Respondents	% Agree	Breakdown*
Netherland Interdepartmental SSG/R Training III 4-6 April 23	21%	66%	33% gave the highest rating
Security and Justice Governance and Reform (SJGR) Course Finland 05-09 June 23	45%	75%	25% gave the highest rating
Results-Based Management (RBM) for Peacebuilding, Security and Development Training	17%	100%	67% gave the highest rating
Summer School on SSG/R in Central Asia for OSCE Academy Alumni Network (Bishkek OSCE) 17-22 July 23	60%	78%	33% gave the highest rating
Ireland SSG/R Training 2023 11-15 Sept 23	26%	60%	20% gave the highest rating
Netherland Interdepartmental SSG/R Training IV 6-8 Nov 23	Results available in February 2024
Slovakia SSG/R Workshop 21-23 Nov 23	Results available in February 2024
Introduction to SSG/R e-Learning	N/A	98%	67% gave the highest rating
Overall Average	34%	80%	41%

*highest rating = strongly agree
Table 3: List of PDT mandates active in 2023
Mandate Title
International Police Advisors Masterclass 2023
ESDC Austria core course on SSG/R March and October 2023
Military TRA for SSR-DDR
Security and Justice Governance and Reform (SJGR) Course 2023 Finland
Contribution to the German inter-ministerial SSG/R training
German Staff College SSR Training in support of military planning processes & capacity building
DDR Workshops
Security Sector Governance and Reform Course - UNTSI Ireland
ESDC EAB Support
Building the business case for international police deployments
Dutch Interdepartmental SSG/R Training (3rd and 4th)
Finland TRA Rule of Law
SPTC Training (GCSP Stans)
Swiss SSR/G Workshop Bern
OIF PVE Training
OSCE academy summer school in Bishkek
SSR/G workshop - Slovakia
International Police Officers Course Slovakia
Course on SSG/R & DDR – Switzerland 2024

Output Title	Improved co-ordination and consensus between donors, and with multilaterals
Output number:		1.3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.3 % of ISSAT mandates that bring together multiple bilateral and multilateral GBMs. [Governing Board Members, since revised to ‘International Partner Group Members’].	50%	70%

A total of 50 mandates were undertaken in 2023 of which 33 or 66% were joint mandates. Joint mandates are: 1) Mandates funded by more than one partner, 2) Mandates funded by a mix of pooled fund and project sources and 3) Mandates funded under pillars 2 and 3.

By bringing colleagues together under joint mandates, ISSAT can continue to build capacities of SSG/R advisors. An example of this in 2023, was the course that was conducted in Ireland with partners UNTSI (United Nations Training School Ireland) by the financial support of the UK and Ireland. The course was aimed at 30 practitioners and professionals working on the planning, design, provision, management and oversight of security and justice governance.

A full list is provided below.

Table 4: List of joint mandates
AU 10-Year SSR Framework Policy Anniversary – Conference Support
Assessment of the Security and Defence forces of Comoros
Assessment of International Support to SSG/R in Ukraine
Strategic Analysis of Maritime Security and Justice Challenges in the Gulf of Guinea
Lesson Identification on SSR/G in the ECOWAS region - Ghana & Liberia case study
AU / RECs outreach and reinforcement SSR portfolio
Seed funding for AU/REC's Austria project
UN OROLSI targeted support to priority areas of Rule of Law and Security Institutions in the Sahel
Strategic Analysis of Moldova’s Security Sector Reform and International Assistance
Strategic Analysis of Georgia’s SSR and International Assistance
UNDP Somalia - Support to the Development of the Next Generation (SSR) Programmes
Support to UN RCO Niger - S&J Assessment and RCO capacity assessment, and roadmap for improvement - phase 1
UNITAMS Assessment of Rural Courts in Sudan
Core group & International Partners Group in-person meeting
Participation as challenge setter in 2023 C4SI (IHEID initiative) Fall Programme
Panel Presentation to Marshall Centre: “AI and SSGR”
Lecture - Seminar to NATO Defence College
People Centered Approaches to SSG/R
Advisory Note on Promoting Youth & SSR
SSG/R and Migration
What Works Study
Enhancement of ISSAT S&J and Governance Community of Practice
Climate Security and SSG/R - Stocktaking study
Support to UN and WB
ISSAT Helpdesk support to IPGMs – UK Community Policing Programme in Nepal
Stocktaking of Donors HRM programming - Albania mission
International Police Advisors Masterclass 2023
Military TRA for SSR-DDR
German Staff College SSR Training in support of military planning processes & capacity building
Security Sector Governance and Reform Course - UNTSI Ireland
ESDC EAB Support
OIF PVE Training
OSCE academy summer school in Bishkek

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation	Narrative	Progress
Maximise the direct value of ISSAT for OCSM/HMG.	ISSAT Pillar 1 funding has been ‘earmarked’ to support OCSM’s SSR policy, guidance and training development for some time but has been delayed due to the time it has taken to build-up FCDO OCSM SSR team capacity to lead this work, as this work kicks-off in the coming months ISSAT is positioned to directly contribute. This would also be a good moment to explore a potential new UK mandate on SSR and peace processes in line with cross-cutting OCSM priorities and as part of the ISSAT work strand on politics. As OCSM capacity increases, the team also plan to raise awareness among country teams and MOD on the support available through the ISSAT programme, whilst maintaining oversight to prioritise central programme resources and to ensure feedback is captured for performance monitoring purposes.	SSD has increased its staffing capability significantly over the last year, and the programme has an SRO (Senior Responsible Owner), PRO (Programme Responsible Owner) and colleagues working on maximizing the value of mandates to FCDO and of the International Partners Group meetings to growing SSD’s network of likeminded policy leads. ISSAT’s training provision was directly valuable for a range of UK colleagues this year.
Encourage and work with ISSAT to continue attention by ISSAT and IPGMs on specific geographies, thematic issues, and partnerships.	Ukraine and the Eastern Neighbourhood, defence-related reform, NATO engagement, and the further concretisation of the work strand on the politics of SSR, will continue to be high UK priorities for ISSAT and for engagement with IPGMs over the coming year. FCDO and ISSAT should continue to collaborate on developing methodological approaches to political economy analysis and international assistance mapping to further strengthen output quality and navigate political sensitivity.	ISSAT delivered sessions on Ukraine, West Africa and MENA during International Partner Group (IPG) Meetings that took place in December 2023. This involved a Ukraine Assessment piece of work and looking at the issue of governance in West Africa. This was based on recommendations and encouragement from IPGMs to focus on specific geographies and thematic issues, demonstrating that ISSAT continues to be responsive to our geographic and thematic priorities and those of the SSR field more broadly. ISSAT has been slow to pick-up the ‘political economy methodological approaches’ strand but has included it in the 2024 work programme.
Engage with ISSAT and other members of the Core Group to reflect on lessons around the current results framework, and the theory of change and assumptions, and establish improved mechanisms internally within HMG to deliver feedback.	This would be a valuable process in the run-up to the end of the current programme and thinking ahead to the next Strategy and results framework.	We will continue to request this engagement as the programme comes to a close this year and in the context of consultation around the new One DCAF approach.
Explore with ISSAT whether there are greater opportunities for synergies with and to harness the ‘One DCAF’.	There would appear to be opportunities for more joining-up between ISSAT and wider DCAF in line with the objectives of the programme and the interests of ISSAT’s members. For example, ISSAT has agreed to look at opportunities to further strengthen engagement with DCAF’s Gender and Security Division, which would correspond well to the importance the UK attaches to the Women Peace and Security agenda.	DCAF continue to work on its ‘One DCAF’ review and strategy. DCAF will reach out again to partners following the initial consultation phase. They have bought in an external consultant and have had positive feedback in engaging on this.
Set a deadline for finalisation of the DCAF Safeguarding Policy.	ISSAT/DCAF has been responsive to our requirement for a clear consolidated Safeguarding Policy. This is a DCAF corporate-level policy issue. Whilst there has been good progress and it is recognised there are some legitimate reasons why this is taking time, it is a global priority for HMG and identified as high risk in last year’s ISSAT programme audit and should be treated as an urgent priority. A clear deadline should be agreed for putting the policy and implementation arrangements in place within the coming few months.	We have agreed a final deadline with ISSAT of May 2024. We will not be able to develop a further programme without this policy in place.

## D: VALUE FOR MONEY

Key cost drivers and performance

ISSAT is dedicated towards ensuring VFM principles are applied throughout all programming, as well as integrating findings through lessons learned and other learning processes.
The key costs associated with the pooled fund are salaries and associated costs for ISSAT’s staff and advisers, plus fee rates for contracted expertise.  Pre-agreed rates are included in the ISSAT programme of work.
Secondary costs are travel and subsistence costs, temporary accommodation, and event management costs.

Using joint mandates, ISSAT continues to deliver on cost savings through cost sharing. By delivering on training and development to multiple SSR actors, it is able to represent VFM and there is substantial evidence to suggest the programme succeeds in good VFM practices which adds value to UK and international efforts which are greater than the costs of the initial investment.

The business case suggested purchasing technical advice to FCDO to increase donor-influencing capability the access and influence over multilateral approaches to Security and Justice.

Economy:
ISSAT continues to drive value for money by pooling donor funding through its Pooled Trust Fund, which enables economies of scale. ISSAT has a core team and an additional roster of roughly 40-50 people, for which it only pays for services used.

Efficiency:
The support that ISSAT provides to multilateral organisations on a cost-sharing basis is designed to compound the positive effect of wider UK support to these organisations. With better information available multilateral partners can deliver more effectively, meaning UK funding has a higher impact.

Effectiveness:
ISSAT’s continued effectiveness will be monitored through milestones established during the programme inception phase and tested throughout the programme lifetime. Regular discussions of progress against milestone and indicators and feedback from Country Offices will ensure indicators and milestones remain realistic.

ISSAT adheres to IATI transparency reporting standards.

E: RISK

Overview of risk management

There has not been a significant change in the programme-level risk over the course of this year and we continue to rate the overall net risk as minor.

The ISSAT risk register is in line with the OCSM risk appetite statement and strategy and context remains at eager.

- The OCSM completed a due diligence assessment (DDA) refresh in October 2023 of DCAF which provides the corporate platform for ISSAT. The findings showed that ISSAT had adequate controls overall and we were satisfied with the policies that it had in place.
- On risk management, DCAF has circulated a final version of the ISSAT risk policy, which outlines DCAF’s general risk management approach. The policy defines the broad accountabilities and structures DCAF will maintain to manage risk throughout the organisation.
- On Safeguarding: we assess the net risk as moderate however our due diligence assessment and quarterly risk check-ins with ISSAT have highlighted the continued need for DCAF to strengthen their safeguarding policies and processes. Further detail of this can be found in Section F.

The programme is comfortably delivering within risk appetite however, this is due to be reviewed within the next month of this annual review. Noting this, the programme remains a minor risk but will be kept under review.

ISSAT has developed a comprehensive living ISSAT-specific risk register, which was shared with the FCDO and the wider Core Group ahead of the December 2024 quarterly meeting.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

ISSAT will provide a preliminary financial statement for ISSAT in the pooled funders’ report that will be shared with core group members prior to the next quarterly core group meeting at the end of March 2024.

We have an annual contribution to the pooled fund with the finances reported through a living overview which is reported and assessed quarterly, and a pool expenditure report which we request annually to show the progress of finances spent throughout the year.
The gaps in PRO ISSAT programme management at the start of the 2023-2024 financial year meant that the FCDO was late again in making the annual payment in the last reporting year. The FCDO programme team will ensure that measures are taken ahead of the payment deadline in May 2024 to ensure that the payment is made on time.

The process of reviewing and revising the results framework started at the end of 2023 as part of the development of the next ISSAT operational strategy which is due to start in 2025. The UK and other Core Group members will be part of this process.
A key risk that was flagged in the last internal audit of the programme at the end of 2022 is the absence of a safeguarding policy covering ISSAT. A safeguarding policy continues to be in development at the overarching DCAF corporate level, and DCAF has indicated that this will be finalised by May 2024. In the interim, ISSAT continues to review its code of ethics, as well as the obligation of local partners to have formal commitments to safeguarding.

The Head of DCAF’s People and Organisational Development Department recruited an expert to take a safeguarding policy forward. During the gap in the policy, DCAF sought support in these areas from four external experts which included KPMG and PWC and discussed this issue with DCAF’s sister institutions (Geneva Centre for Security Policy and Geneva International Centre for Humanitarian Demining).

The audited financial report will be available to all donors in June 2024.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

There have been numerous monitoring activities throughout the reporting period, including:
- UK participation in International Partners Group and Core Group meetings
- Direct engagement between OCSM and ISSAT directly to outline our strategic priorities and provide guidance
- Programme monitoring through the Living Overview document
- Quarterly regularised risk/programme management meetings, both in-person and online.

This has enabled active programme management, exchanges and decision making on which mandates to fund. These activities have also fed into the evaluation process, and bilateral engagement with other partners and donors has helped to evaluate ISSAT performance. FCDO feedback has been provided to ISSAT on its mandates, training courses and other activities. However, FCDO could deliver its feedback more systematically to ISSAT to allow it to populate its reporting framework. OCSM’s greater capacity will enable this going forward.

We have an assurance process on risk and finance, through our Strategy, Operations, and Performance Group (SOPG).

Evidence

ISSAT is in the process of putting together its latest audited narrative report, which the UK will receive in time for the next International Partners Group meeting in summer 2024. This report will be useful in assessing the quality and breadth of evidence. On independent evaluations, we note that the last one was published some years ago and that they are undertaken for DCAF as a single body, incorporating ISSAT. Nevertheless, we have not seen any negative implications for the programme.

Learning

The risk matrix/management has been a key process for capturing and sharing lessons directly with ISSAT. This has been supplemented by the Living Overview document, ensuring that topics have become broader and align with the FCDO’s objectives. These processes have resulted in more active engagement and responsiveness.
In addition, DCAF is currently working on a One DCAF strategy. While maintaining the independent management of ISSAT, the purpose is to facilitate access to expertise and expand reach, building on both DCAF and ISSAT’s networks. This consultative exercise is providing a useful opportunity for reflections by DCAF/ISSAT and among its partners on DCAF/ISSAT’s comparative advantages, strategic priorities, and ways the collaboration can be strengthened and become even more valuable.
[note] The Geneva Centre for Security Sector Governance (‘DCAF’), under which ISSAT sits, is a multilateral foundation to which we will be providing core contributions under a multi-donor trust fund

Date of last narrative financial report	14/06/2023	Date of last audited annual statement	14/06/2023