## Annual Review
Title: Support to the International Security Sector Advisory Team (ISSAT)
Programme Value £ (full life): £2.7 million		Review date: 09/03/2025
Programme Code: 300614	AMP start date: 01/10/2019	AMP end date: / 31/12/2025

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A
Risk Rating	Minor	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	ISSAT Business Case and Summary
DevTracker Link to results framework:	ISSAT Logical Framework

A. SUMMARY AND OVERVIEW
Description of programme

The FCDO is funding the International Security Sector Advisory Team (ISSAT), a foundation that supports the international community to improve security and justice (S&J), with up to £2.33m of funding over six years. An additional £100k p.a. was allocated for supplementary research for five years of the programme. This was outlined to provide monitoring, evaluation and technical assistance needs on security and justice related priorities, which providers other than ISSAT could best meet, bringing the total business case value to £2.7m over 6 years.

The purpose of the programme is to deliver effective security and justice interventions through ISSAT by providing guidance to help bilateral donors and multilateral organisations to deliver effective and politically informed security and justice responses, based on lessons from the field.

The programme consists of two components:

Component 1 for funding to the International Security Sector Advisory Team

Component 2 intended to fund small-scale security and justice-related research or analysis work outside of ISSAT.

The ISSAT component operates through a pooled multi-donor fund that apportions pooled funders’ contributions across three pillars.
- Pillar 1 is ring-fenced for individual donors’ priorities (which can include joint mandates/co-funded activities supported by the Core Group members).
- Pillar 2 is dedicated to supporting the multilateral system (with the multilaterals also contributing via a cost-sharing arrangement), as well as supporting greater joint engagement by International Partner Group Meetings (IPGMs) around multilateral Security Sector Reform (SSR) support.
- Pillar 3 covers training, knowledge, and project development, including a helpdesk function.
As a founding member of ISSAT, the UK is a member of the ISSAT Core Group of bilateral partners who provide contributions to ISSAT’s pooled fund and is a member of ISSAT’s International Partners Group (IPG) that brings together a much wider grouping of bilateral and multilateral actors active in the SSR field.

ISSAT works with a group of member states and institutions to develop and promote good security and justice reform practices and principles, helping members to build their capacity to enhance the effectiveness and quality of security sector reform (SSR) engagement and programming, and to facilitate the coordination and coherence of international assistance to nationally driven SSR processes.

The nature of the programme means that the indicators used are qualitative and are assessed by the level of feedback received by International Partner Group members. This, and the necessity of Core Group countries then taking action as a result of ISSAT’s research, means it’s challenging to assess the direct change ISSAT’s interventions have led to and the level of success.

The UK-ISSAT relationship and programme management is led by FCDO’s Migration and Conflict Department (MCD).

Key changes to the programme this year:
The business case was extended from 31 December 2024 to 31 December 2025 to allow us to deliver action against new Government priorities, while we prepare a new spending review.

Summary supporting narrative for the overall score in this review

This programme continues to be a unique source of expertise and analysis into SSR and plays a vital role in convening international players in the SSR field, including to build multilateral capability and engage new global south actors. The programme’s design allows for reach and scale in FCDO support and ability to flex, though there continues to be some instances where this approach is challenging to operationalise.

The programme has continued to perform well and has scored an A. It has continued to meet its annual output milestone indicators as set out in the programme’s results framework and is in line with FCDO’s expectations. ISSAT’s proficiency has allowed the programme to flex to the evolving geopolitical context as required and continues to give the FCDO access to high quality expertise to meet new challenges (e.g. technology, climate).

For the output scoring, the review has drawn on the data and explanations that ISSAT provided us in October 2024. The scoring reflects an assessment of both output-level and overall performance.

The programme’s overall risk assessment continues to be minor and demonstrates value for money due to the cost-sharing nature of the programme. Further details on value for money are explained in section D of this report.

Based on the current results assessed in this review, the programme is on track to realise the outcomes and impact statements.

Major lessons and recommendations for the year ahead

Implement process to better monitor how reports and findings produced from ISSAT are being made useful for practitioners
- ISSAT has continued to strengthen its efforts to improve dissemination and uptake of evidence through training, dialogue with partners, requesting feedback, convening discussions. This needs to continue, and FCDO should continue to support this through regular engagement with ISSAT and by: FCDO gathering and sharing feedback with ISSAT to evaluate the usefulness of the reports and findings.
- Both ISSAT and FCDO should engage practitioners from early concept stages.
- ISSAT should ensure that clear executive summaries and recommendations are being brought forward into concept note stage so practitioners have a clearer overview of the contents of the report and can decide how the report will be useful to them and their teams. FCDO should ensure key points and recommendations are made clear when disseminating ISSAT products.
- Both FCDO and ISSAT should take account of emerging lessons from the OECD DAC SSR handbook refresh process.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Figure 1
The programme’s theory of change as illustrated above sets out that the FCDO will work with ISSAT to contribute specialist staffing and programme funding (inputs). In return, FCDO receives advisory support to Security & Justice programming in a range of country contexts; benefits from: improved knowledge, professional development, and improved coordination; and also, consensus between donors and multilaterals (outputs). The FCDO is better equipped to deliver more effective, politically informed and gender-sensitive security and justice interventions (outcomes)

This review therefore assesses that the theory of change remains valid, and no changes are required at the time of this review.

ISSAT has been responsive to supporting UK priorities, fostering collaboration, lessons learning and good practice across the international SSR community, and continues to perform well in line with the objectives of the programme and theory of change. ISSAT also continues to:
1. emphasise improved security and justice outcomes for people as the ultimate objective of SSR, particularly in conflict-affected and fragile states;
2. commit to its data collection with an outcome-level focus and tracks feedback and recommendations from International Partner Group (IPG) members to assess how its efforts contribute to decision-making around SSG/R interventions.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This programme continues to meet expectations and is being assessed as being on track to meeting its expected outcome of the FCDO being better equipped to deliver effective security and justice interventions. The work towards their outcome performance level is timely.

ISSAT continues to monitor its programme delivery risks and clearly report this yearly on risk areas that could impact intended outcomes such as internal staff expert capacity and donor funding.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Accountable, transparent and rights-compliant Security Sector Reform and Governance which contributes to conflict prevention and management, resilience to threats such serious organised crime, hybrid threats, and disinformation, continues to be a key thematic priority within the FCDO/MCD. This programme serves the agenda of both the MCD and priority geographic teams and other thematic departments (such as Open Societies).

MCD’s policy agenda, which includes SSR, stabilisation, peace processes, gender and conflict prevention, is being supported by the pieces of work that ISSAT focuses on and the programme continues to demonstrate that it can respond to UK priorities and provide a cross-cutting mechanism to engage with international partners. This is clearly valued by international partners, as demonstrated by their feedback.

The programme stands to deliver important contributions to SSR guidance and approaches and is the right approach to deliver the outcomes we are looking for on delivering effective security and justice interventions.

Based on this there is a strong argument for continuing the programme.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Advisory Field Support (AFS) for Members' missions - Enhance IPGMs’ capacities to deploy strategic S&J advisors
Output number:		1.1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 - Planned training delivered / 1.1.2 - % of training course participants responding to post-course survey who report that the training contributed to their work performance. / 1.1.3 - Narrative on what the contributions were	Deliver high-quality training for IPGMs	87-98%

In 2021, UK funding contributed to the development by ISSAT of an Introduction to SSG/R E-Learning course, which has now trained over 2,300 individuals. Over 85% of participants in 2023 and 2024, reported that the course content contributed positively to their work.

In 2024 the UK asked ISSAT to organise two pilot courses to ensure that UK staff working on SSG/R would have an interactive opportunity to discuss and learn concepts from an interdepartmental perspective. Two training sessions took place in May 2024 and October 2024 respectively, which targeted UK officials working in different Government departments or international organisations, as well as IPGM representatives from other countries. Both in-person and online courses included a session that reviewed the UK’s approach to security sector governance.

Training sessions included participants from several different countries, providing an opportunity to influence in support of accountable, inclusive, rights-based security sector governance.

Output Title	Knowledge and professional development for member staff
Output number:		1.2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Percentage of training participants who report that ISSAT's training met their expectations	- Number of International Partner Group requests for SSR knowledge and examples	100%
1.2.2 Percentage of participants (out of responses obtained) who report that the ISSAT training contributed to their work performance, (longer-term).	- Number of IPGM requests for SSR knowledge and examples	90%

Knowledge and methodologies are at the heart of ISSAT support to IPGMs. Over the past years, ISSAT's pooled funding mechanism has facilitated the development of a comprehensive toolbox of approaches, methodologies, and best practices, which the UK has significantly benefited from. This mechanism enables ISSAT to pool resources and expertise from multiple International Partners Group Members (IPGMs), fostering innovation and the sharing of knowledge across a wide range of Security Sector Governance/Reform (SSG/R) contexts.

The UK has gained access to a wealth of practical tools and examples that have enhanced its capacity to support security and justice sector development, both in its bilateral engagements and multilateral partnerships. These tools have included tailored assessment methodologies, monitoring and evaluation frameworks, and best practices on thematic areas like gender mainstreaming, climate change, and people-centred approaches to SSG/R. The pooled funding mechanism has thus been instrumental in providing the UK with flexible and high-quality resources, enabling more coordinated and effective interventions in complex and evolving security environments.

For example, to build the capacity and knowledge of staff working on SSG/R, ISSAT developed new learning on Environment and SSG/R. This online course addressed questions such as: why does environmental degradation matter for security sector governance and reform; what roles security sector actors can play in mitigating environmental insecurity and threats; and how can improving security sector governance mitigate the consequences of environmental degradation.

Transmission of learning from Sub-Saharan Africa focused case studies provided the opportunity for local stakeholders to assess the role of security sectors actors in disaster risk management and identify any institutional or legislative changes that might be necessary to better enable them to fulfil their roles. It also provided evidence to reinforce the importance of functional democratic governance mechanisms as part of disaster risk management.

Output Title	Improved co-ordination and consensus between donors, and with multilaterals
Output number:		1.3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.3 - % of ISSAT mandates that bring together multiple bilateral and multilateral GBMs. [Governing Board Members, since revised to ‘International Partner Group Members’].	Improve IPGM approach to cross-institutional or organisational support for S&J Indicators: / 1) Narrative examples of improvement / 2) Improve the extent to which IPGMs cooperate on ISSAT mandates	80%

IPG meetings and discussions in 2024 provided opportunities for exchange and mutual learning between IPG members on priority topics. Issues covered included Ukraine, Africa and the Middle East. In addition, thematic sessions addressed AI and its relevance for the security sector, climate, maritime security, the role of donors such as China, Turkey and the Gulf States as well as the development of feminist foreign policies.

ISSAT reports also support shared understanding and approaches. In 2024, ISSAT undertook a review of current international SSG/R support to Ukraine, including an analysis of existing coordination mechanisms. This report provided important insights to enhance partners’ understanding of the challenges and provide actionable recommendations for improving future programming and coordination structures.

An important added value of ISSAT’s pooled funding mechanism is that it provides International Partners Group Members (IPGMs) with a platform to collaborate on issues of mutual interest. By pooling resources and expertise, IPGMs can jointly address shared challenges in Security Sector Governance/Reform (SSG/R), ensuring a more coordinated and impactful approach. For example, this year, IPG members co-funded these projects: SSG/R training, stocktaking of human resources management systems, ‘what works’ study, assessment of non-traditional Donors interventions in Somalia and Sudan and an assessment of international support and coordination mechanisms in Ukraine.

ISSAT has consistently prioritised fostering joint initiatives, encouraged multilateral dialogue, and driving collective solutions. This collaborative model not only strengthens the coherence of international support but also maximises the efficiency and effectiveness of interventions across diverse regions and thematic areas. Through these partnerships, IPGMs have been able to share best practices, align priorities, and increase their collective influence on SSG/R processes globally.

For example, working in collaboration with NATO, the European Union Partnership Mission to Moldova, as well as other international partners, ISSAT supplied the evidence and observations from its work to feed the methodology and design of Moldova’s national workshop on disaster risk management, civil preparedness, and building resilience and supported Moldova’s security sector reform process.

The Security and Justice Community of Practice (CoP) is a repository for shared knowledge produced by ISSAT and its partners in support of more cohesive approaches. It is intended to keep IPGMs informed about cross-donor engagements and priorities to foster greater exchange and collaboration. The Community of Practice currently consists of 303 members, of which 27 are from the UK, with the majority from the FCDO (21), and the remainder from the Ministry of Defence (3), Army (2), and Police (1). The UK members make up the third largest group on the CoP, preceded by the United Nations (44) and the Netherlands (47), and closely followed by the United States (20) and the European Union (15).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation	Narrative	Progress
ISSAT to strengthen its results framework and the current format of the programme’s log frame to be adapted to be more quantitative.	ISSAT should update its results framework and develop a more robust way to collect feedback and monitor progress against the programme’s expected outcomes. / Currently ISSAT asks IPG members for feedback after training sessions and mandate completion, but there may be instances where members are unable to provide sufficient feedback. This could impact the overall results framework. / We recommended that the results framework be changed from asking for qualitative feedback from core group members to quantitative results that can be better measured and accessed. The log frame should be revised within one month of this review. / The adoption of an amended impact-level statement in the ISSAT pooled fund results framework continues to make it more appropriate and measurable. ISSAT continues to place greater emphasis on data collection at an outcome level. This includes for example efforts to start more systematically tracking the extent of influence and take-up of recommendations contained in ISSAT reports and to assess how ISSAT’s efforts have contributed to bilateral and multilateral decision-making around SSG/R (Security Sector Governance/Reform) approaches and interventions.	In October 2024, ISSAT provided additional evidence which gave a more robust scoring system. / From 2025-29 there will be a new specific results framework managed by DCAF, which ISSAT will align with and contribute to, combining both qualitative and quantitative reporting.

## D: VALUE FOR MONEY

Key cost drivers and performance

ISSAT is dedicated towards ensuring VFM principles are applied throughout all programming, as well as integrating findings through lessons learned and other learning processes.
The key costs associated with the pooled fund are salaries and associated costs for ISSAT’s staff and advisers, plus fee rates for contracted expertise.  Pre-agreed rates are included in the ISSAT programme of work.
Secondary costs are travel and subsistence costs, temporary accommodation, and event management costs.

Using joint mandates, ISSAT continues to deliver on cost savings through cost sharing. By delivering on training and development to multiple SSR actors, it is able to represent VFM and there is substantial evidence to suggest the programme succeeds in good VFM practices which adds value to UK and international efforts which are greater than the costs of the initial investment.

The business case suggested purchasing technical advice to FCDO to increase donor-influencing capability the access and influence over multilateral approaches to Security and Justice.

Economy:
ISSAT continues to drive value for money by pooling donor funding through its Pooled Trust Fund, which enables economies of scale. ISSAT has a core team and an additional roster of roughly 40-50 people, for which it only pays for services used.

Efficiency:
The support that ISSAT provides to multilateral organisations on a cost-sharing basis is designed to compound the positive effect of wider UK support to these organisations. With better information available multilateral partners can deliver more effectively, meaning UK funding has a higher impact.

Effectiveness:
ISSAT’s continued effectiveness will be monitored through milestones established during the programme inception phase and tested throughout the programme lifetime. Regular discussions of progress against milestone and indicators and feedback from Country Offices will ensure indicators and milestones remain realistic.

ISSAT adheres to IATI transparency reporting standards.

E: RISK

Overview of risk management

There has not been a significant change in the programme-level risk over the course of this year and we continue to rate the overall net risk as minor.

ISSAT developed a comprehensive ISSAT-specific risk register which is updated as required. The risk register remains in line with the MCD risk appetite statement and strategy and context remains at eager.

- The MCD completed a due diligence assessment (DDA) refresh in October 2023 of DCAF which provides the corporate platform for ISSAT. The findings showed that ISSAT had adequate controls overall and we were satisfied with the policies that it had in place.
- On risk management, DCAF has circulated a final version of the ISSAT risk policy, which outlines DCAF’s general risk management approach. The policy defines the broad accountabilities and structures DCAF will maintain to manage risk throughout the organisation.
- On Safeguarding: we assess the net risk as moderate. Previously, our due diligence assessment and quarterly risk check-ins with ISSAT highlighted the continued need for DCAF to strengthen their safeguarding policies and processes. In November 2024, ISSAT shared a comprehensive safeguarding policy that included several components including an update to their existing anti-harassment rules and regulations and a new creation of a safeguarding committee. Further detail of this can be found in Section F.

The programme is comfortably delivering within risk appetite however, this is next due to be reviewed within the next month of this annual review. Noting this, the programme remains a minor risk but will be kept under review.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

ISSAT will provide a preliminary financial statement for ISSAT in the pooled funders’ report that will be shared with core group members prior to the next quarterly core group meeting in March 2025.

We have an annual contribution to the pooled fund with the finances reported and assessed quarterly, and a pooled expenditure report which we request annually to show the progress of finances spent throughout the year. All payments to ISSAT in 2024 were made on time.

The programme of work (PoW) for 2025 was presented at the international partners group meeting in September 2024 responding to requests from the Core Group for a more strategic, outcome-oriented document rather than the previous, activity-led approach. The PoW is directly linked to the objectives and results in the DCAF strategy to promote alignment and coherence

A key risk that had previously been flagged in the internal audit was the absence of a safeguarding policy. This has now been addressed with a final policy circulated in November 2024 which included a detailed overview and a framework that reflected best practice. The policy includes a due diligence process, policy architecture and gap analysis and inter agency schemes for disclosure. This safeguarding policy satisfied FCDO requirements and expectations.
The audited financial report will be available to all donors in June 2025.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

There have been numerous monitoring activities throughout the reporting period, including:
- UK participation in International Partners Group and Core Group meetings
- Direct engagement between MCD and ISSAT to outline our strategic priorities and provide guidance
- Programme monitoring through the Living Overview document
- Quarterly regularised risk/programme management meetings, both in-person and online.

This has enabled active programme management, exchanges and decision making on which mandates to fund. These activities have also fed into the evaluation process, and bilateral engagement with other partners and donors has helped to evaluate ISSAT performance. FCDO feedback has been provided to ISSAT on its mandates, training courses and other activities. However, FCDO could deliver its feedback more systematically to ISSAT to allow it to populate its reporting framework. MCD’s greater capacity will enable this going forward.

We have an assurance process on risk and finance, through our Strategy, Operations, and Performance Group (SOPG).

Evidence

ISSAT are in the process of putting together their latest audited narrative report, which the UK will receive in time for the next International Partners Group meeting in summer 2025. This report will be useful in assessing the quality and breadth of evidence. The last independent evaluation was published some years ago and this was undertaken for DCAF as a single body, incorporating ISSAT.

Learning

The risk matrix/management has been a key process for capturing and sharing lessons directly with ISSAT. This has been supplemented by the Living Overview document, ensuring that topics have become broader and align with the FCDO’s objectives. These processes have resulted in more active engagement and responsiveness.

In addition, DCAF have finalised a One DCAF strategy. While maintaining the independent management of ISSAT, the strategy facilitates access to expertise and to expand reach, building on both DCAF and ISSAT’s networks. The learning component is central to ensuring a virtuous circle between proactiveness and policy and there is an ongoing DCAF institutional redesign for effective implementation of the strategy.
[note] The Geneva Centre for Security Sector Governance (‘DCAF’), under which ISSAT sits, is a multilateral foundation to which we will be providing core contributions under a multi-donor trust fund

Date of last narrative financial report	27/06/2024	Date of last audited annual statement	27/06/2024