Annual Review

Title: Strengthening Impact Investing Markets for Agriculture (SIIMA)
Programme Value £ (full life): £19,500,000		Review date: 29 March 2023
Programme Code: / 300632	AMP start date: / 29 March 2019	AMP end date: / 28 March 2025

Summary of Programme Performance
Year	2020	2021	2022	2023
Overall Output Score	A	A+	A+	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business case
DevTracker Link to results framework:	Logframe

A. SUMMARY AND OVERVIEW

Although the agriculture sector is central to the economies of many developing countries, accounting for over half of total employment in target regions, smallholder producers frequently lack sufficient income to invest in climate-resilient technologies, and do not have the market access required to scale their businesses. This locks them into a vicious cycle of increasing vulnerability and lower productivity.

The Strengthening Impact Investing Markets for Agriculture (SIIMA) programme seeks to address this challenge through building a pipeline of investible high-impact businesses that can deliver innovative technologies to farmers and producers in developing countries in sub-Saharan Africa and South Asia, whilst simultaneously providing robust and testable research and evidence to investors. Through this work the programme aims to help address the twin challenges of low productivity, and increasingly, climate vulnerability for smallholders by identifying transformative technologies and bringing them to scale through mobilising additional investment into the sector. The programme also generates evidence on effective pathways to scale, new business models and innovative tools to measure impact.

In this, the programme’s third and final Annual Review, it continues to seek to transform the agriculture sector and livelihoods of low-income small-scale producers, directly improving the lives of 1 million people in Africa and India, by:

- Strengthening markets for affordable and climate-smart technologies in agriculture, by investing in high-impact businesses that can deliver innovative products and services.
- Developing a robust evidence base on pathways to scale for business models and technologies in order to increase the resilience of food systems, including through identifying, mapping and understanding existing flows of private finance into agriculture and related sectors.
- Advancing impact measurement frameworks, to help businesses and investors understand their impacts – including trade-offs between climate, environment, incomes/growth – to ultimately mobilise additional capital into the sector at scale.
- Convening, influencing and mobilising impact investors from across the sector to share knowledge and best practice, develop and trial new ways of assessing impact and collaborate on investments.

Through this work, the programme will deliver two main outcomes:

- Shifting risk perceptions around investing in innovative small- and medium-size enterprises (SMEs) in agriculture and working with farmers or other small-scale producers to increase incomes, build resilience, and reduce climate and nature impacts.
- Mobilising increased financing for the agriculture sector by demonstrating pathways to scale.
After this Annual Review FCDO will complete a Programme Closure Review for this programme, and transition the live components to the new Delivering the Agriculture Breakthrough programme, to consolidate our work in this area. This Annual Review covers the calendar year 2022. At the start of the reporting period, the programme had two workstreams:

1. The Catalysing Agriculture by Scaling Energy Ecosystems (CASEE) partnership with Shell Foundation. FCDO is providing £15m of catalytic funding to the CASEE programme through SIIMA, which is then matched on a one-to-one basis by Shell Foundation in co-investments. CASEE aims to support the scaling of 15 or more high-impact businesses whilst generating industry-shaping research on pathways to scale, operating at the intersection of climate and agriculture and utilising innovation to catalyse both adaptation and mitigation impacts. The programme provides patient grant capital and hands-on business support and technical assistance to businesses providing farmers with access to inputs, finance, markets and productive clean energy assets (such as cold chain solutions, solar pumps, solar dryers and biogas digestors). This component has already generated an impressive track record of success and has supported several innovative businesses that are at the cutting edge of their sectors. As a result, FCDO will be providing a further £10m of funding to the partnership under a new business case, Delivering the Agriculture Breakthrough. The existing CASEE funding under this programme will also transfer to the Delivering the Agriculture Breakthrough programme for the sake of programming coherency. In addition to the funding supplied through SIIMA, CASEE leverages the broader partnership between FCDO and Shell Foundation, with funding from FCDO India (the POWERED programme) and Climate, Energy Water Team in FCDO Research and Evidence Directorate (the TIME partnerships – under the Transforming Energy Access programme).

2. ClimateShot Investor Coalition, with the Climate Policy Initiative and Acumen. Due to the impact of budget cuts leading to the early termination of the Resilient Agriculture Research Engine (RARE) the programme was repurposed to support the ClimateShot Investor Coalition (CLIC). CLIC is an action-orientated coalition of investment leaders focused on mobilising investment into the agriculture sector. The Secretariat is provided by Climate Policy Initiative (CPI) and aims to collectively scale-up and accelerate finance for agriculture and food systems globally with the vision to shift these sectors to a low-carbon, climate-resilient and nature-positive pathway by 2030, thus delivering on the ambitions of the Glasgow Breakthrough Agenda on Agriculture and UK’s COP Presidency priorities on climate and nature. To achieve this goal, CLIC is building a member-driven coalition with a focus on three key outcomes: 1. Greater consensus on priorities for climate and nature finance in the sector. 2. Greater use of evidence-based solutions to reduce transaction costs & risk and improve monitoring & reporting. 3. Increased finance mobilised for the sector globally. The management of CLIC will also transfer to FCDO’s Delivering the Agriculture Breakthrough programme.

Summary supporting narrative for the overall score in this review

This is the third and final Annual Review of the programme, covering the period from 1 January 2022 to 31 December 2022. The programme has scored an A reflecting strong progress toward outcomes, based on logframe targets.

This year CASEE in particular has performed strongly and exceeded many of the lifetime targets of the programme at its mid-way point. This in part justifies the programme’s theory of change and is a reflection of the demand for patient capital in many of the programme’s target markets. However, the level of over-performance was substantive, highlighting the tension between creating demonstration effects on the one hand – where scale and commercial viability are key – and additionality on the other – where the need for concessional or patient capital should be acute. These are issues which will be examined as the component transfers to the Delivering the Agriculture Breakthrough programme.

CASEE achieved its success through supporting portfolio companies to leverage a cumulative £104m through Q3 2022, against an initial target of £60m. Apollo Agriculture (Apollo) - which is an agriculture-focused technology company based in Kenya that bundles together multiple products and services for smallholder farmers, including financing, farm inputs, advice, insurance, and market access, when possible - made a significant contribution to CASEE’s 2022 leverage target, raising almost $47m by itself. This is particularly noteworthy due to the interest the company attracted from atypical impact investors such as Softbank.

Several companies also contributed to significant livelihoods impacts, most notably Sistema.bio (Sistema) and S4S. Sistema – whose primary business involves prefabricated modular biodigester that take organic waste and transform it into renewable biogas - grew significantly through its monetisation of carbon credits. S4S – who deploys its own patented solar conduction dryer, suitable for dehydrating a wide range of harvested crops, including fruit, vegetables, grains, and spices - also grew quickly with their new Village based collection centre (VLCC) model that aggregates produce and then distributes it to female entrepreneurs to process, before S4S aggregates for second level processing and commercial distribution. CASEE helped S4S pilot this new model and subsequently transition towards its full implementation. CASEE also helped S4S secure a partnership with State Bank of India to catalyse access to affordable asset finance for the female microentrepreneurs, thus enabling the unlocking of working capital requirements for expansion in other geographies.

On gender and having made inclusivity a core theme for the programming, 61% of the partners directly funded under CASEE now have either local and/or female founders. To further promote gender equity in the sector, in 2021 CASEE partnered with a fund manager to develop and deploy innovative financial instruments to underrepresented early-stage female founders. In addition, CASEE has developed a network of local researchers has been developed to ensure that expertise is leveraged in the countries where CASEE operates, contributing to the economy. Finally, utilising Shell Foundation resources, the entire CASEE portfolio has access to gender analysis and support developing gender action plans, including dedicated TA support.

Two CASEE partners also delivered major advances in the affordability of their products in 2022:
- Sistema demonstrated biodigester cost reductions of up to 75% through the monetisation of carbon credits, significantly improving income opportunities for the farmers. They now have carbon and RBF contracts in place for 75K units over the next 12-30 months.
- Lorentz realised cost reductions of 30%, significantly improving the affordability of their solar irrigation pumps for farmers, following a successful distributor financing pilot with Shell Foundation that validated a substantial market opportunity and prompted further R&D.
The CLIC component has also performed well in its first year, attracting interest and traction from a wide swathe of the impact investor landscape and beyond. The current membership of CLIC is composed of 32 organisations, representing a range of stakeholders from impact investors, DFIs, bilateral and multilateral donors to TA facilities. The following outputs have been delivered under CLIC this year:

Both Action Group (AG) 1 and Action Group 2 have now been formed and activated. Action Group 1 has a focus on financial innovation, whilst Action Group 2, led by CGIAR, focuses on enabling the impact investing community to step up risk assessment and impact measurement in agriculture & food systems interventions via the promotion of scientific evidence and effective utilisation of tools and methodologies for data collection. White paper publication by CPI on the preliminary findings for the Landscape of Climate Finance for Agriculture, Forestry, Other Land Use and Fisheries (AFOLU). The results of this preliminary study were presented on Finance Day (9th November 2022) at COP27 during an event co-organised by CLIC with IFAD and the Global Innovation Lab for Climate Finance (for which CPI also serves as the Secretariat).

Major lessons and recommendations for the year ahead

The major lesson from this Annual Review is the necessity of setting sufficiently ambitious and stretching goals as part of programme targets. CASEE components in particular substantively overachieved their targets, and whilst this demonstrated an ability to scale and the commercial viability of investments, it did highlight the tension between creating a demonstration effect and the need for additionality. As a result, and as the component transitions to the new Delivering the Agriculture Breakthrough programme, FCDO could seek to challenge Shell Foundation on whether investments made through CASEE are sufficiently additional and intervening in markets where concessional funding can be catalytic. This could include considering geographies, sectors and technologies that have greater additionality. There are pre-existing mechanisms for the FCDO to achieve this, through regular portfolio review meeting, scheduled for later this year..
Another lesson is the importance of flexibility and agility in programme design, combined with strong delivery partners. When part of the programme was forced to close early due to budget cuts, FCDO worked with delivery partners to successfully pivot towards supporting a new intervention through CLIC. The rapid nature with which this happened is a strong example of adaptable programming leading to concrete outcomes.
The main takeaway from the CLIC component to date is that the space of coalitions/initiatives/groups in the agriculture and food system space is crowded, so CLIC needs to identify a niche with clear added value in order to attract members and bring meaningful and action-oriented impact. This has resulted in the idea of setting up a deal room focusing on climate and nature investments in agriculture and food systems, which has attracted interest from various stakeholders including AGRA and ARIC. Whilst the precise design of the deal room is still to be determined, a mechanism to identify and collate a pipeline of investments for agriculture-focused investors – particularly for small-ticket investments – should help address an identified market failure. In addition, impact measurement for investors in climate resilience in the agriculture sector continues to be a challenge.

More broadly, the programme has demonstrated a need for patient capital in its target markets and the importance of holistic, joined-up interventions that target the financing chain, the enabling environment and investors themselves. The expansion of CASEE into a proposition that will support DFI investment is a natural evolution of the component’s scope and is a step towards the increased scale that is identified as crucial in the programme’s business case and theory of change. As this component evolves, it will be crucial to ensure that the lessons learnt from this experience are captured and disseminated and that FCDO funding remains additional.

Recommendations for the year ahead:

- As the CASEE component transitions to the Delivering the Agriculture Breakthrough programme it will be important for the FCDO and Shell Foundation to a) agree sufficiently stretching mobilisation and reach targets and b) ensure that investments are appropriately additional so as to merit concessional financing. Part a) should be achieved as part of the process for agreeing additional funding for the CASEE component through a new Memorandum of Understanding, expected to be completed within the coming months, whilst part b) will be a longer-running conversation and iterative process. A portfolio approach to investment provides the flexibility to support some companies that may not perform well on mobilisation metrics but who nonetheless play an important role in market building.
- FCDO should look to exploit the opportunity that the CLIC component is presenting; it has already achieved credibility with stakeholders and there is clearly an appetite for cooperation and collaboration which the initiative can fill. FCDO should explore ways to further support CLIC and if possible, expand its work programme through creating links with other delivery partners including the Bill and Melinda Gates Foundation, and USAID. These conversations are ongoing but should conclude within the next six months.
- FCDO should work with the Shell Foundation to identify opportunities to improve the component’s research outputs and ensure that there is a strong pipeline of research products with the capacity to influence investment behaviour that can be fed into both the FCDO – where there is increasing demand from the country network for company cases studies operating in their local area - and the wider impact investing environment. There remains a challenge in assessing the overall impact of the component, and what the effects of its interventions have been in aggregate beyond the headline mobilisation and reach figures, so one potential avenue of focus is an assessment of the market changes CASEE has brought about. FCDO and Shell Foundaton have already begun work on addressing this.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme was designed to address four inter-connected barriers that were deemed to be holding back progress on impact investing into agriculture: lack of effective markets to deliver technologies to farmers; a need for better evidence on technology uptake, and business models that can scale; a lack of standardised and cost-effective metrics for measuring and communicating development impacts for the poor; and lack of finance from non-concessional sources due to high perceptions of high risks. Practically, the programme has also ended up operating at the intersection of agriculture and climate and subsequently has incorporated reporting metrics for International Climate Finance.
To address these constraints, the programme has co invested with the Shell Foundation to build a pipeline of businesses operating at the ag-energy-climate nexus in Africa and South Asia. Alongside these investments, the programme works closely with CLIC to build the evidence base needed to maximise impact and drive innovation by creating new tools that enable businesses and investors to measure and communicate their development impacts more cost-effectively.
The ultimate intended impact of SIIMA is a stronger ecosystem of innovative businesses that deliver products and services that improve productivity and climate resilience of poor small-holder farmers in FCDO focus countries. By demonstrating the development impact and financial viability of these businesses, SIIMA aims to help mobilise increased private sector finance into the agriculture sector. The original theory of change is visualised below:
Figure 1 – Theory of Change.

There have been no changes to the theory of change during this period, but over previous periods the programme has changed substantively. The support to the Lean Data Development Platform and the Acumen Resilient Agriculture Fund (ARAF) research programme have been cut, whilst the CLIC component has been brought online. These changes are in part a response to the impacts of COVID-19 and cuts to the aid budget, but are also a demonstration of the programme’s adaptability and capacity to change its focus mid-flight.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to the expected outcomes and impact, having already achieved some of the programme’s lifetime targets. Over the next year the two remaining components of the programme will transition to the new Delivering the Agriculture Breakthrough programme, and this programme will be closed.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme’s relevance has increased since the business case was authored, given FCDO’s current focus on food security, climate and nature (and increasingly the relationship between the two) and the potential of technology and innovation to help address the challenges these issues pose.

The programme has performed extremely strongly over its lifetime and has gone a substantive way to legitimizing its theory of change, and should continue based on its own merits. However, as mentioned previously both live components within the programme will be transferred to the Delivering the Agriculture Breakthrough programme later this year, in order to consolidate the FCDO’s approach to supporting agriculture innovation.

## C. DETAILED OUTPUT SCORING

Output Title	Increased number of farmers with access to energy-related products, technologies or services (CASEE)
Output number:		1	Output Score:	A +
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of smallholder farmers directly served by CASEE partners (cumulative)	110,000	457,833 (to Oct 2022)
1.2. Number of smallholder farmers indirectly served by CASEE partners (cumulative)	330,000	715,444 (to Oct 2022)

Briefly describe the output’s activities and provide supporting narrative for the score.

CASEE has substantively over-performed against its logframe targets for this output, achieving the total seven-year targets for the component in only its third year, and thus scoring an A +. In light of this strong performance the FCDO will have to work with Shell Foundation to establish stretching KPIs as the component transitions to the Delivering the Agriculture Breakthrough programme, and ensure that targets are sufficiently ambitious. Smallholder farmers impacted by CASEE’s investments is a key metric for the overall success of the programme and so making sure that targets are appropriate and stretching is vital to assessing performance. The large increase in the amount of farmers either directly or indirectly served by the programme can be used as a proxy measure of the fact that portfolio companies are beginning to reach scale, one of the key intended impacts of this intervention.
On this measure, CASEE partners directly impacted 457,833 farmers (4.2X of target) through to October 2022, by providing access to inputs, finance, markets, and productive clean energy assets (solar pumps, solar dryers and biogas digestors). Apollo, who directly supported more than 79,000 farmers, and Sistema who directly supported more than 68,000 farmers were particularly strong performers in the portfolio. S4S also scaled significantly, supporting almost 41K farmers.
CASEE partners indirectly impacted 715,444 farmers (2.2X of target) in 2022, by providing access to cold storage at farm gate, reducing farmer risk through access to insurance, and piloting innovative financial instruments to scale impactful early-stage companies with female founders. As in the previous year, the standout performer was Pula, a partner CASEE has supported through three innovative funding rounds. This included piloting Pay-at-Harvest insurance, which was later scaled by BII, and piloting bundling of insurance and PAYGO solar home systems (SHS).
[note] CASEE only counts a conservative pro-rata portion of Pula lives impacted based on other funding the company received.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes to this output during the last year but given strong overperformance the target metrics in the logframe will need to be reconsidered as part of the component’s transition to the Delivering the Agriculture Breakthrough programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no outstanding recommendations relating specifically to this output from previous Annual Reviews, although it will be impacted by proposals to move from cumulative to annual assessment milestones.

In light of the indicator’s strong overperformance it is clear that the targets set were not ambitious enough and underestimated the ability of portfolio companies to reach target small-holders farmers. As a result, FCDO will work with the Shell Foundation to design suitably stretching targets as the component transition to the Delivering the Agriculture Breakthrough programme.

In addition, the impressive performance of individual companies who have delivered an outsized proportion of results demonstrates the importance of a portfolio approach, where strong performers can carry less punchy but more additional investments. As the research approach for this component evolves it will be important to consider the ‘who’ and ‘what’ aspect of smallholder farmers that interventions are reaching; this should include for example greater disaggregation by gender and further research on what farmers spend their increased incomes on.

Output Title	Businesses receive financial and technical support to scale (CASEE)
Output number:		2	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of businesses supported by CASEE (cumulative)	17	Exceeded: 19
2.2. Amount of finance leveraged by CASEE partners (US$ millions) (cumulative)	US$60m	Exceeded: US$128m

Briefly describe the output’s activities and provide supporting narrative for the score.

CASEE is now supporting 19 separate businesses, exceeding its target for this year, and helping to create a robust and varied portfolio with the capacity to deliver strong results. This is an increase of 2 compared to the previous year’s reporting.
On the second indicator, related to amount of finance leveraged, CASEE achieved the seven-year targets for the life of programme. In 2023, FCDO will therefore need to re-establish KPIs for leverage targets that are suitably ambitious and reflect the level at which the programme is delivering. This will be done as part of the transition to moving the component to the Delivering the Agriculture Breakthrough programme.
This strong performance demonstrates the high scalability potential of CASEE portfolio companies, and the efficacy of the Shell Foundation network. Several investments have been made due to Shell Foundation’s introductions including GIF investing in S4S following a 2021 curated investor series that was organised through CASEE. Measured by scalability alone, the programme is delivering on its mandate.
However, the magnitude of the overperformance provokes questions on the additionality of the investments, versus their demonstration effect, and invites reflection on whether these companies required concessional investment from the FCDO. Whilst counter-factuals of this nature are often hard to evidence, it is a useful pointer to consider means by which to increase the component’s additionality through focusing on more challenging geographies and sectors.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes to this output during the last year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no outstanding recommendations relating specifically to this output from previous Annual Reviews, although it will be impacted by proposals to move from cumulative to annual assessment milestones. In light of the output’s strong overperformance and as the programme transitions to the Delivering the Agriculture Breakthrough programme, new KPIs will have to be deployed.

The box below sets out lessons gleaned from across the CASEE portfolio:

BOX 2 – Lessons learned from the CASEE experience:

Platform companies have different rates to scale and fundraise compared to product companies.
Increasingly impact investors primarily want to see hockey stick model growth or projections to consider a company for investment. This type of growth is often easier for platform companies – such as Apollo and Pula – to achieve, in comparison to product companies. Although successful platform companies require a balance between digitisation and strong operations on the ground, often through already established infrastructure such as agri-dealers, they can achieve quicker and often exponential growth especially because changes to a product can be implemented much quicker.
In contrast, it often takes product companies much longer to go through prototyping, finding market fit, and building a product – often repeating a few times – before considering to scale, and therefore growth projections often look different. Despite the need for both types of companies, the product company lifecycle is often less attractive for investors especially in emerging markets – particularly commercially leaning investors – and requires significant upfront patient capital. This is especially relevant in 2022 and 2023 as new CASEE partner EchoVC comments, “….the slowdown in the African Venture market has started and will continue into the new year.”
Not only can carbon financing make the product more accessible for low-income consumers, but it also increases the prevalence of climate-smart products in the market and reduces carbon emissions.
Over the last few years, with CASEE and previously TIME support, Sistema has started selling their carbon credits and utilising carbon financing, making the business model commercially viable. It enables the company to increase product sales by reducing the cost to end users and subsequently reduce the cost of goods sold through economy of scale. Sistema is working with a large corporate that has projected increase of sales by 12X+. According to CASEE, Duke University, and RMI research, a “carbon revenue stream has the potential to buoy SMEs if it were more accessible. A lack of scale and high transaction costs are the primary reasons companies are not generating financial returns from their carbon benefits.” There is an opportunity to further explore climate financing with other companies in the CASEE portfolio. This is especially important considering the increase of climate shocks, which are particularly noticed in the agriculture sector.
It is critical to recognise the importance of the ecosystem for end users and companies when providing support.
Working with companies like KIC and EAF has shown that market access is necessary for cold storage and chain to be attractive or financially viable for farmers. For EAF to provide high-value market access, they need farmers to provide a reliable supply chain, which will ultimately increase farmers’ incomes through cold chain/storage as well as grow EAF. Even if EAF and other such companies do not directly provide the full suite of services such as inputs and microloans, it is necessary for them to provide information or linkages to these other services so that farmers have increased, reliable harvests.

Output Title	Knowledge and evidence generated and disseminated (CASEE)
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of partnerships created with in-country academic researchers (cumulative)	3	Met: 3
3.2.1 Number of third party led evidence and learning outputs disseminated based on the CASEE research workplan (Annual)	2	Met: 2
3.2.2 Number of articles, case studies and portfolio learning reports disseminated based on the CASEE research workplan (Annual)	15	Exceeded: 16
3.3 Events organised by SF to promote CASEE or external events where CASEE work is being presented/promoted to be counted (Annual)	8	Exceeded: 9

Briefly describe the output’s activities and provide supporting narrative for the score.

The CASEE component once again performed strongly, marginally exceeding expectations on half of the indicators for this output. Whilst the component has performed strongly, and outputs have been high quality and relevant, there is further room to ensure uptake and proliferation. This is also the first year of reporting under the new approach to the research section of the log frame, where three of the outputs report annual results instead of cumulative ones. With these changes, CASEE still exceeded log frame targets.
Highlighted insights from CASEE’s blended finance 3rd party research include the following:
[note] Convergence State of Blended Finance 2022 Report
- The need for standardisation of definition and measurement of climate adaptation impact.
- That there are challenges in climate adaptation vs mitigation investments. While climate mitigation investments for emerging markets are also lagging targets, climate adaptation is more challenging due to the added factor of longer time horizons for impact realisation.
- That there is a need for intermediary funds to aggregate smaller ticket sized investments for institutional investors.
The research element of the CASEE component is still somewhat underpowered, and as FCDO and Shell Foundation agree new funding and strategic direction building up impactful and insightful research insights will need to be a central consideration. This will include shifting from intervention-focused outputs, to more strategic work that considers the aggregate impact of issues in the round.
Through collaborating with more organisations on research CASEE work was able to be presented at a wider range of events, including at the AGRF conference, the Rabobank Foundation partnership TA programme, a workshop on climate adaptation evaluations in Uganda, and the launch of the State of Blended Finance Report by Convergence.
Partner-led case studies, articles and portfolio learning reports were also of higher quality due to work with TripleLine, who supported partners with completing their research milestones and provided a quality assurance function. The full range of research completed this year is set out in the table below:
TABLE 2 – Research outputs from the CASEE component:
Number of articles, case studies and portfolio learning reports disseminated in 2022
1	Catalysing Climate Finance for Low-Carbon Agriculture Enterprises – SF
2	How cold chain infrastructure is transforming Kenyan fishing communities – SF
3	InspiraFarms' Cooling-as-a-Service: How to scale cold storage solutions for smallholder farmers in SSA – SF
4	Understanding how solar powered decentralised food processing can increase value-chain efficiency – SF
5	The business potential in going beyond cooling as a service – SF
6	Growing prosperity and building climate resilience for small-scale farmers – SF
7	Does access to inputs, information, credit and markets result in increased income for smallholder farmers? – SF
8	Pay-at-Harvest increases insurance uptake by 14x in Nigeria – SF
9	Empowering women one credit at a time with the W+ Standard
10	Why PayGo solar energy and insurance can improve smallholder productivity
11	30x in 1 year: Insurance pilot with 4k Nigerian farmers leads to a scale-up across 3 countries
12	Exploring the Holistic Impact of Clean Energy-Powered Cold Chain
13	Dedicated Spotlight on Agriculture newsletter to 5,000 sector members
14	State of Blended Finance 2022 Climate Edition
15	Insights on the cold chain needs of Fisherman and Traders in Homa Bay County in Kenya
16	Guarantee Fund as an enabler for new-age agriculture enterprises

CASEE learnings were disseminated through multiple channels, increasing the reach and influence of the programme. Examples of dissemination include webinars such as Catalysing Climate Finance for Low Carbon Agriculture Enterprises, in partnership with Duke University and RMI – with more than 100 organisations registered, including 50 high priority investors – and presenting initiatives at coalitions such as Efficiency for Access.
The CASEE team organised and presented at nine events in 2022 (see table below for details). Several of these events were multi-day or multi-presentation events such as the AGRF conference and the Agri TA working group, which was co-hosted and presented at by Shell Foundation.

Table 3 – Events held under the CASEE component:
	Event	Participate/ Training/ Speaker/ Host
1	Webinar: Catalysing Climate Finance for Low-Carbon Agriculture Enterprises	Research was presented by co-funder
2	Presentation of CASEE Climate Research in Efficiency for Access Investor group meeting	Presenter
3	Presentation of CASEE programme and Rabo partnership (India COVID Response Fund) in the Agri TA working group meeting: FMO office in Hague (2 days)	Organiser of event and presenter
4	Presentation of Rabo partnership (India COVID response fund) in ADB event	Presenter
5	AGRF in-person event: Presentation of CASEE insights (2 panels)	Presenter
6	Impact Alpha Webinar: Presentation as part of a panel discussion about CASEE's work on climate adaptation	Presenter
7	Presentation of CASEE research in CIIC meetings (2 presentations)	Presenter
8	Duke workshop on climate adaptation evaluations in Uganda	Organiser
9	Launch of the State of Blended Finance Report by Convergence. Shared CASEE work (with Rabo Foundation and on climate adaptation) in the panel discussion	Presenter

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There was one minor change to this output during the last year, with the addition of the metric for 3.2.1 to better reflect the evidence outputs the programme is delivering. Three of the indicators have moved from cumulative to annual assessments of achievement in order to provide a more granular view of results. There are no planned changed as a result of this review, although the component will transition to the Delivering the Agriculture Breakthrough programme later this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no outstanding recommendations relating specifically to this output from previous Annual Reviews.

Case study: Pula Advisors

Pula provide accessible, scalable insurance solutions for smallholder farmers by bundling insurance with the inputs farmers already use including seeds and fertiliser. They use technology such as satellite imaging in addition to farm level yield data to determine insurance playouts and collect and analyse farmer data to better help partners understand the needs of farmers. In Nigeria, CASEE supported Pula to pilot an innovative ‘Pay-at-Harvest’ insurance product, which has increased uptake of insurance amongst smallholder farmers from 5% to >70%. Insurance is vital to developing farmers’ resilience to climate shocks; Pula has provided this product insurance to over 5,000 customers, most of whom are farming <2Ha. FCDO’s support through CASEE has been instrumental in enabling Pula to test innovative new products, and ultimately securing additional investments from British International Investment to further scale the product.

Output Title	ClimateShot Impact Investing Coalition (CIIC) launched
Output number:		4	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
CIIC (renamed CLIC) launched at COP27	1	Achieved
1 white paper developed	1	Achieved
Action Group 1 activated	2	Exceeded
Strategic case developed for CLIC	1	Achieved

Supporting narrative for the score:

This is the first (and last) year of reporting under this output, following changes initiated over the preceding twelve months. In FY22/23, building on the partnership between FCDO and Acumen, an existing funding arrangement was extended for one year to deliver and operationalise the UK’s commitment to the ‘Climate Shot’ Global Action Agenda for Agricultural Innovation for People, Nature and Climate and associated ClimateShot Impact Investing Coalition (CLIC).
[note] By way of background, Acumen and FCDO previously signed an accountable grant agreement in April 2019 for £4 million of support from FCDO, with the intention to undertake cutting edge, applied research in behavioural economics to examine the constraints to the uptake and scaling of climate-resilient agriculture. The grant was intended to support the work of impact measurement firm 60 Decibels (60dB) to develop innovative solutions for measuring investment impact on the poor through Lean Data impact measurement projects, farmer panel and polling and by leveraging frontier, Big Data technologies. However, the scope and budget of the Acumen component was reduced in 2021 to £2.63 million due to the impact of COVID and subsequent FCDO budget cuts – please see the previous years’ Annual Review report for details of outputs and outcomes of this earlier phase of work.

This Coalition, known as CLIC, was operationalised this year with the aim to convene leaders in the agriculture investment space to accelerate collective efforts to scale up financing for agriculture and food systems in line with the Paris Agreement’s objectives to achieve net zero emissions, climate resilience and biodiversity. CLIC aims to achieves this through improving the evidence base on impact measurement, increasing the private sector’s role in scaling innovations and through facilitating action-orientated partnerships within the impact investing ecosystem. It has organised around two action groups – one focused on financial innovation, and the other focused on impact measurements. In addition, it will also create a deal room to facilitate the creation of a pipeline of investible opportunities for CLIC members and beyond.

Climate Policy Initiative was secured as the Secretariat for CLIC and 4 main component deliverables were agreed for this year, set out below:

1.	CLIC Technical workplan: Align the strategy with a technical workplan for CLIC.
2.	CLIC Action Groups: Convene AG 1.
3.	Advisory to FCDO: support in developing the strategic case for CLIC as an input to the FCDO Business Case, for continued delivery of the CLIC.
4.	Convening: Formal launch event at COP27.

This component has performed strongly, meeting or exceeding all of its targets and ensuring that CLIC was launched successfully as a credible, viable initiative that has traction in the impact investor landscape.
1 - CLIC launched at COP27 - Achieved
CLIC held its first virtual event, hosted by CPI, on 27th September 2022. The event saw strong participation, with 40 individuals attending from 20 different organisations. The audience was primarily composed of impact investors, fund managers, and Technical Assistance (TA) facilities. In coordination with FCDO, the approach for CLIC’s launch at COP 27 moved away from one single event towards ensuring visibility of the coalition, embedding its representatives and products at several COP27 events. Accordingly, CLIC was present across five separate events at COP27, gaining traction and interest in the initiative:
- Catalysing Investments for Resilient Smallholder Agriculture (9th Nov 2022, IFAD Pavilion). Co-organised by CLIC, IFAD and the Global Innovation Lab for Climate Finance, this event convened key players to discuss bankable opportunities to de-risk and invest in low-carbon and climate resilient sustainable agriculture projects.
- Science to Shape a Climate Smart & Nature Positive Financial System: Launch of the CGIAR Hub for Sustainable Finance (OneSF) (9th Nov 2022, Food and Agriculture Pavilion). Co-branded by CLIC, this event saw the official launch of OneSF. The session presented a first of its kind science-based architecture to enable financial institutions & investors to quantify climate and environmental risk and impacts in food systems investments.
- How to finance resilience for smallholder farmers at scale? The role of regulation, risk disclosure and locally led adaptation (10th Nov 2022, Resilience Hub). In this workshop session, CPI, alongside participants from BNP Paribas, ResponsAbility, the GEF and GAWA Capital identified key barriers to scaling financing for smallholder resilience in the areas of regulation, risk disclosure and locally led adaptation.
- A Framework for Measuring and Evaluating Adaptation to Climate Change for Food Systems: perspectives for finance in the public and private sectors (12th Nov 2022, Morocco Pavilion). Co-organised by CLIC and CGIAR (AG2 lead), this session set out to understand the needs faced by public and private actors in developing and using adaptation and resilience metrics, with the goal of unlocking increased climate financing.
- Breaking down barriers for an Agriculture Breakthrough: Putting the Breakthrough Report recommendations into action (12th Nov 2022, Food Systems Pavilion). This session convened speakers from CPI, Clim-Eat, FARA, CGIAR and WWF to discuss linkages between existing or emerging initiatives and the Agriculture Breakthrough, identifying any challenges or opportunities for implementation.
2 - White Paper Developed – Achieved
The white paper, as agreed with FCDO and aligned to the Agriculture Breakthrough, focused on research tracking climate finance flows to Agriculture, Forestry, Other Land Use and Fisheries globally. The preliminary findings from this study were published on November 4th, 2022 as the Landscape of Climate Finance for Agriculture, Forestry, Other Land Use and Fisheries (AFOLU).. It showed that AFOLU sectors require a nearly 26-fold increase in annual funding, i.e., USD 423 billion annually by 2030 (compared with the annual average of USD 16.3 billion in 2019/20) in order to shift to a low-carbon and climate resilient trajectory. CPI will publish a larger more detailed study by Spring 2023. Current work on this includes public and private sector data gathering to address the identified data gaps from the preliminary study.
3 - Action Group 1 Activated – Exceeded
Action Group 1 focusing on Financial Innovation has been initiated and led by Acumen and as of January 2023 the Council of Small Holder Finance (CSAF) have joined as co-leads. It held its first session on 18th October 2022. In addition to Action Group 1, Action Group 2 was also initiated. This Action Group is led by CGIAR and focuses on enabling the impact investing community to step up risk assessment and impact measurement in agriculture & food systems interventions via the promotion of scientific evidence and effective utilisation of tools and methodologies for data collection.
4 - Strategic Case developed for CLIC - Achieved
CPI provided content to FCDO necessary for the development of the strategic case for CLIC through the technical workplan, analysis of CLIC’s market positioning and of its membership. The technical workplan details CLIC’s overarching goals, KPIs and the short-, medium- and long-term activities, has been finalised following review from both FCDO and Acumen. A summary of CLIC’s theory of change and overarching aims is publicly available in the form of a 2-page brochure available here.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to the output and there are no planned changes. The most significant adjustment in the structure of CLIC has been the decision to make the third action group a ‘deal room’ following consultation with FCDO, Acumen and CLIC members during the development of the strategic case.
From next year CLIC will move to the Delivering the Agriculture Breakthrough programme as part of a consolidation of the FCDO’s work on this agenda.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
This is the first and last year of reporting against Output 4. The main lessons in the development of the CLIC this year have been the importance of clear communication with members and creating the opportunity for active exchanges between them. Finally, the importance of utilising targeted engagement to avoid fatigue from multiple groups became clear. This will all be considered as CLIC continues to develop under the new Delivering the Agriculture Breakthrough programme.
## D: VALUE FOR MONEY

Overall, the SIIMA programme continues to represent good value for money when compared to the Business Case’s Strategic Case and cost drivers remain as expected. The catalytic nature of FCDO’s funding on the CASEE component – combined with the partnership with Shell Foundation – helps ensure strong value for money for that component. Similarly, the expertise and convening power of CPI has ensured effectiveness and efficiency. An assessment of the programme’s performance against the 5 E’s of FCDO’s value for money framework – economy, efficiency, effectiveness and equity (including gender equality and, disability), and overall cost-effectiveness is set out below:

- Economy: For the CASEE component Shell Foundation matches FCDO’s funding on a one-to-one basis, with up to with £15m of its own budget doubling the resources available to CASEE for investment. Shell Foundation does not charge any indirect costs to FCDO and absorbs all overheads associated with the programme from its own funds, given the component a high level of both economy and efficiency. For the CLIC component, utilising CPI as a delivery partner has ensured a high level of traction for the initiative which has meant resources have not been needed to mobilise support.
- Efficiency: By combining processes and resources between the CASEE and TIME partnerships through sharing the FCDO/ Shell Foundation Partnership Manager, Shell Foundation has reduced administration costs for the component. Shell Foundation is also on track to meet the financial forecast for 2022. For CLIC, utilising an existing grant agreement and repurposing it to support the initiative has reduced overhead on the programme, and allowed the component to get off the ground in a shorter time period. Utilising CPI’s existing network and convening power has also reduced the amount of effort required to attract and grow the membership.
- Effectiveness: The programme partners all enjoy strong reputations and convening power within the sector, and engage effectively and frequently with FCDO and other UK-supported partners – including proactive engagement around FCDO’s pivots to climate and nature. Progress toward programme outcomes has been strong, due to SIIMA partners leaning into broader UK and FCDO priorities, including through engagement with the country network (e.g. India and Ghana) and other processes (e.g. providing inputs into the ClimateShot Impact Investing Coalition, or partnering with other FCDO programmes e.g. CASA). Shell Foundation and CPI have also been in regular contact with FCDO including bi-weekly meetings, ensuring the programme is managed appropriately.
- Equity: CASEE has made further progress this year in making its portfolio more inclusive. S4S and Keep IT Cool have both been recognized for and have attracted additional interest from investors due to their gender action plans. A number of CASEE portfolio companies also address systemic barriers for women directly – e.g. S4S which is a decentralised solar food processing enterprise preventing post-harvest crop loss, has a supply chain which consists of 100% female farmers and whose solar dryer systems have been designed with feedback from these farmers. We are in active discussions about expanding the disability aspects of equity under the CASEE component.

Assessment of whether the programme continues to represent value for money

Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, there is sufficient evidence that the programme continues to represent value for money.

E: RISK

Overview of risk management

The programmes overall risk rating remains Moderate. Whilst FCDO is exposed to potentially high reputational risk through the CASEE component – particularly in relation to misuse of funds and lack of oversight of downstream investments, this is mitigated through working with high quality delivery partners who understand the environments they are working in and who have robust processes in place.

The risk matrix on FCDO’s Aid Management Platform has been updated as part of this review, and has been adjusted to reflect that many of the risks occasioned by COVID-19 have rescinded.

Risks are being kept under review by the FCDO programme management and Shell Foundation teams, who meet at least monthly to check on programme performance. This includes assessing risks both in terms of impacts on investees’ ability to deliver against targets, and in terms of budget forecasts. The risk matrix continues to be reviewed on a quarterly basis, or as the need arises. This is complimented by our low-risk appetite for fiduciary, operational, reputational, safeguarding and delivery risks, which are managed through our active engagement with programme partnerships, and adherence to FCDO’s Programme Operating Framework.

The programme’s overall risk has remained steady post-COVID, and it has been able to deliver comfortably within risk appetite. Delivery risk remains low and the highest potential risk impacts are reputational where there is a significant risk to FCDO funding private activity in emerging economies. Mitigation of the risk is managed through in in-depth due diligence on enterprises and entrepreneurs, and downstream mapping. Know Your Customer checks are made prior to grants being paid out and enterprises are required to confirm annually that they adhere to Shell Foundation’s business standards, particularly linked to Health, Safety, Security & Environment as well as Anti Money Laundering, Safeguarding, Bribery and Corruption. The risk of misuse of funds is therefore assessed as low.

As the components in this programme transition to the Delivering the Agriculture Breakthrough programme, the nature of the risks FCDO is exposed to will change slightly – it will be important to incorporate the lessons learned from this programme into the new approach.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery partners for this programme – Shell Foundation, Acumen and Climate Policy Initiative – have performed consistently well across delivery, commercial and financial performance with high-quality and timely reporting that conforms to FCDO’s standards. There has been pro-active engagement with all delivery partners on emerging issues – particularly relating to budget constraints – and forecasting has generally been strong. Delivery partners have shown flexibility with regards to programme management issues and worked with the FCDO to resolve problems as and when they have occurred – including re-profiling budgets when required.

Shell Foundation have also helped to manage changes to key personnel and organisational strategy proactively, helping to ensure continuity in engagement with FCDO. Shell Foundation’s CASEE Programme Manager left their post at the end of 2022, and the CASEE programme was overseen by two experienced members of the Shell Foundation team for the remainder of 2022. Shell Foundation replaced this role through the creation of a new FCDO Strategic Partnership Manager to oversee CASEE and TIME partnerships which was filled in January 2023.
Despite business conditions remaining unpredictable and challenging throughout 2022, with high inflation, supply chain delays and remaining uncertainty about COVID-19, CASEE has continued to outperform on programmatic and research log frame outputs. Three reasons in particular enabled the CASEE portfolio to continue to succeed despite the challenging delivery conditions:
1. Groundwork started in 2021, which was doubled-down on and successfully carried out (e.g. research and partner fundraising);
2. Shell Foundation’s hands-on business support to partners (e.g. support with transitioning business models and fundraising);
3. innovative projects that have become attractive for others in the sector (e.g. climate, and finance facilities).

Financial reports reviewed showed no major concerns.

Date of last narrative financial report	Acumen: February 2022 / Shell Foundation: January 2022	Date of last audited annual statement	Acumen: June 2021 / Shell Foundation: December 2021

Approach to this Annual Review:

This Annual Review was primarily undertaken through a desk-based review by the SRO, built on reporting from delivery partners. Ancillary conversations with delivery partners and recipients of funding were also utilised.

ANNEX 2: CLIC outputs:
	Event/Thought Piece	Event Summary	Location	Date	Reach (# of participants/ interactions)	Link
1	CLIC Update Meeting (webinar)	The inaugural convening of CLIC members and friends to update on progress to date on CLIC’s direction, its structure, and next steps.	Virtual	27th September 2022	147	N/A
2	CLIC: Action Group 1 - Blended Finance for Agriculture and Food Systems (webinar)	The inaugural session for Action Group 1, focusing on Blended Finance for Agriculture and Food Systems. The session was hosted by the AG1 lead Acumen as well as Convergence, with case studies presented by Ceniarth and the Acumen Resilience Agriculture Fund (ARAF).	Virtual	18th October 2022	58	N/A
3	CLIC COP27 Newsletter	A newsletter sent to CLIC members and friends outlining CLIC’s presence at COP27 and the publication of the AFOLU Landscape Preliminary Study.	Virtual	7th November 2022	147	N/A
4	Landscape of Climate Finance for Agriculture, Forestry, Other Land Uses, and Fisheries – Preliminary Findings	Preliminary findings from a Landscape study of global climate finance flows to the agriculture, forestry, other land uses and fisheries sectors. The publication was advertised on CPI’s website, social media, and CLIC’s network.	Virtual	4th November 2022	180	https://www.climatepolicyinitiative.org/publication/landscape-of-climate-finance-for-agriculture-forestry-other-land-uses-and-fisheries/
5	CLIC 2-page Brochure	A condensed 2-page report on CLIC’s mission, theory of change, unique offer, and membership.	Virtual	3rd November 2022	44	https://www.climatepolicyinitiative.org/wp-content/uploads/2022/11/CLIC-ClimateShot-Investor-Coalition.pdf
6	Catalysing Investments for Resilient Smallholder Agriculture	A jointly hosted session by CLIC and the Global Innovation Lab for Climate Finance to bring together investment leaders to mobilise finance into resilient smallholder agriculture globally.	COP27 IFAD Pavilion + Virtual	9th November 2022	100	https://www.youtube.com/watch?v=n5y6IhBm0wM
7	Science to Shape a Climate Smart & Nature Positive Financial System: Launch of the CGIAR Hub for Sustainable Finance (OneSF)	The official launch event for the CGIAR Hub for Sustainable Finance (OneSF), where CLIC was advertised as a partner. The session focused on unlocking capital aligned with SDG impacts enabling Food, Land and Water system transformation. Takeaways from the event will be distributed to a wider audience by CGIAR via blog post in early-December.	COP27 Food and Agriculture Pavilion	9th November 2022	178	https://www.youtube.com/watch?v=S0fzMZ1IiOc
8	How to finance resilience for smallholder farmers at scale? The role of regulation, risk disclosure and locally led adaptation	In this workshop session, CPI, alongside participants from BNP Paribas, responsAbility, the GEF and GAWA Capital identified key barriers to scaling financing for smallholder resilience in the areas of regulation, risk disclosure and locally led adaptation. This was followed by a discussion of basic, near-term, and advanced solutions to these barriers, ultimately to develop a framework for resilience finance at scale.	Resilience Hub	10th November 2022	~15-20
9	A Framework for Measuring and Evaluating Adaptation to Climate Change for Food Systems: perspectives for finance in the public and private sectors / . / .	Co-organised by CLIC and CGIAR (AG2 lead), this session set out to understand the needs and approaches faced by public and private actors in developing and using adaptation metrics, with the goal of unlocking increased climate financing. The event saw two keynote presentations, from the International Platform on Adaptation Metrics and Adaptation Metrics Mapping and Evaluation (AMME) Framework and Acumen Resilient Agriculture Fund (ARAF), followed by a panel discussion	Morocco Pavilion	12th November 2022	~10
10	Breaking down barriers for an Agriculture Breakthrough: Putting the Breakthrough Report recommendations into action	This session convened speakers from CPI, Clim-Eat, FARA, CGIAR and WWF to discuss linkages between existing or emerging initiatives and the Agriculture Breakthrough, identifying any challenges or opportunities for implementation	Food Systems Pavilion	12th November 2022	~40-50

Annex 3 – Previous Annual Review recommendations:

The recommendations from the last Annual Review have been addressed.

Recommendation	Addressed
SIIMA should accelerate its work with DFIs to mobilise additional capital for SMEs.	A proposed expansion to CASEE, which is based on collaboration with DFIs, is in the process of being approved and a strong pipeline to deploy capital has been developed and is advancing.
SIIMA should continue to lean into broader FCDO work on impact investing, including the ClimateShot Investor Coalition.	CASEE has supported FCDO with the development of the ClimateShot Investor Coalition including presenting research and seeking collaboration at two meetings. SF has also had several exploratory calls around a potential deal Room for Adaptation and Resilience (A&R) in Agriculture and Food Systems, and how this could be structured and implemented in practice to have significant impact and be additive to other deal rooms, such as matchmaking type offerings in market. A follow up call will take place early in 2023. / The CASEE expansion is directly advancing FCDO’s commitment in impact investing, including aligning with BII.
Explore further opportunities to engage the FCDO country network	Several Shell Foundation team members and partners have directly supported FCDO country offices and foreign missions, including helping to plan an FCDO ministerial visit to Ghana. A dedicated FCDO/SF partnerships manager, has also been hired by Shell Foundation to manage the CASEE and TIME programmes from January 2023 and will explore further collaboration with FCDO country offices.
Review log frame including choice of cumulative vs annual milestones.	The log frame was reviewed and several deliverables transitioned from cumulative to annual reporting.
Keep reputational risks associated with branding under review.	Outside of COP in 2021, the Shell Foundation brand did not present a significant reputational challenge. Shell Foundation did not participate in COP directly in 2022 and therefore, did not require adjustments.