Annual Review

Title: Strengthening Impact Investing Markets for Agriculture (SIIMA)
Programme Value £ (full life): £19,500,000		Review date: 29 March 2022
Programme Code: / 300632	AMP start date: / 29 March 2019	AMP end date: / 28 March 2025

Summary of Programme Performance
Year	2020	2021	2022
Overall Output Score	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/40384354.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/90000064.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The agriculture sector accounts for more than half of total employment in sub-Saharan Africa and South Asia, but many small-scale producers (farmers, fisherfolk, processors) suffer from low productivity and high vulnerability to climate change. Weak access to markets contributes to high post-harvest losses, which further reduce incomes (preventing investments in more resilient/productive technologies) and increases greenhouse gas (GHG) emissions. SIIMA addresses these problems by building a pipeline of high-impact inclusive businesses that can deliver technologies to farmers and build market linkages at scale, whilst generating evidence on pathways to scale as well as innovative tools for impact measurement – ultimately aiming to mobilise additional investments into the sector.

SIIMA works to transform the agriculture sector and livelihoods of low-income small-scale producers, directly improving the lives of 1 million people in Africa and India, by:

- Strengthening markets for affordable and climate-smart technologies in agriculture, by investing in high-impact businesses that can deliver innovative products and services.
- Developing a robust evidence base on pathways to scale of business models and technologies to increase resilience of food systems.
- Advancing impact measurement frameworks, to help businesses and investor understand their impacts – including trade-offs between different objectives e.g. climate, environment, incomes/growth – to ultimately mobilise additional capital into the sector at scale.

Through this work, the programme is striving for two outcomes:

- Shifting risk perceptions around investing in innovative small- and medium-size enterprises (SMEs) working with farmers or other small-scale producers to increase incomes, build resilience, and reduce climate and nature impacts.
- Mobilising increased financing for the sector by demonstrating pathways to scale.

This Annual Review covers the calendar year 2021. At the start of the reporting period, the programme had three workstreams:

1. Catalysing Agriculture by Scaling Energy Ecosystems (CASEE) partnership with Shell Foundation. FCDO contributes £15m to the CASEE programme, which is matched by £15m from Shell Foundation. CASEE aims to support the scaling of 15 or more high-impact businesses and generate industry-shaping research on pathways to scale. The programme provides patient grant capital and hands-on business support to work with businesses providing farmers with access to inputs, finance, markets and productive clean energy assets (such as cold chain solutions, solar pumps, solar dryers and biogas digestors). Annex A shows the portfolio companies as at end-2020, including many companies that – through the support of Shell Foundation and FCDO – have established themselves as leading innovators in their respective sectors. CASEE aims to help these companies scale by mobilising £110m of additional finance. CASEE leverages the broader partnership between FCDO and Shell Foundation, with funding from FCDO India (the POWERED programme) and Climate, Energy Water Team in FCDO Research and Evidence Directorate (the TIME partnerships – under the Transforming Energy Access programme).

2. Lean Data Innovation Platform (LDIP). LDIP was managed by 60 Decibels and aimed to develop innovative solutions for measuring investment impact on farmer-level outcomes relating to incomes, productivity, resilience and sustainability. Following ODA budget reductions, FCDO has exited from this work, but elements are continuing with new funding from the Gates Foundation.

3. Resilient Agriculture Research Engine (RARE). Acumen managed this initiative focused on behavioural research on adoption of climate-smart technologies in Nigeria, Kenya, Tanzania and Ethiopia, in partnership with the Busara Center for Behavioural Economics based in Kenya. This work is designed to leverage the networks with businesses developed by the Acumen Resilient Agriculture Fund (ARAF), which is supported by the Green Climate Fund and the first equity fund focused on adaptation in agriculture in Sub-Saharan Africa. Following ODA budget reductions, FCDO has also exited from this work, after securing additional funding from the Gates Foundation to continue this work

During the year, the economic impacts of the pandemic led to reductions in the ODA budget, which necessitated significant changes to the programme in early 2021, including the early termination of components 2 and 3 (see section on Programme Management). To reflect these changes, the logframe was reviewed (revisions set out in Annex B).

Given the global pandemic of COVID-19, the low risk of a programme with long-standing relationships with FCDO, and on-going processes around Business Planning, this is a light-touch Annual Review. More detail on each aspect of the programme can be found in the two partner annual reports on which the present Summary Annual Review is based.

Summary supporting narrative for the overall score in this review

This is the third Annual Review of the programme, covering the period from 1 January 2021 to 31 December 2021. The on-going pandemic and the ODA budget reductions presented a range of challenges, in response to which the partners have pivoted effectively. The partners proactively lean into emerging FCDO priority issues and the programme continues to deliver strong VfM for FCDO.

The programme scores an A+ reflecting strong progress toward outcomes, under challenging circumstances, and evidence of programme partners going ‘above and beyond’ in aligning and delivering on UK priorities and programme outcomes. The partners have all stepped up and delivered strong progress toward outcomes around shifting risk perceptions and mobilising finance at scale. The three SIIMA partners’ have been critical in developing the ClimateShot Impact Investing Coalition (CIIC), including through co-creating the Call to Action and subsequently helping to mobilise the CIIC group through their active engagement in CIIC convenings. Shell Foundation’s presentation of our work with Duke University on carbon markets for SMEs in agriculture led to several expressions of interest from other CIIC member to partner on actual co-investments into CASEE portfolio companies – with the visibility and evidence brought by Shell Foundation and FCDO bringing down risk perceptions.
[note] The CIIC, as a priority initiative under the Global Action Agenda for Innovation in Agriculture, contributes to the delivering the Glasgow Innovation Breakthrough goal on agriculture, launched at the World Leaders Summit at COP26.

Progress toward the outcome around mobilising finance comes from Shell Foundation’s growing work with DFIs and investor matchmaking. This involves pioneering new models for bridging the gap between SME and DFIs, e.g. the MOU Shell Foundation has with the U.S. Development Finance Corporation (DFC), whereby the latter pre-commit funding for ventures supported by Shell Foundation subject to reaching certain hurdle (and Shell Foundation plays a hands-on role in support both DFC and the businesses to understand each other). Shell Foundation is currently exploring with CDC/British International Investment an arrangement similar to the DFC model. This work aligns strongly with the Foreign Secretary’s ambitions on economic development and British international partnerships. We recommend in this Annual Review that an extension to CASEE is approved to accelerate this work.

Acumen and 60 Decibels will remain connected to FCDO through the CIIC work, and their work on other RED programmes (e.g. under the Transforming Energy Access programme).

Summary performance by component:
- CASEE had a strong year and continued to outperform on programmatic and research outputs. CASEE brought in three new companies into the portfolio; formally launched the Rabobank Foundation US$55m guarantee partnership (generating 86x leverage for the CASEE contribution; and focused on providing hands-on support and capital to help companies already in the portfolio scale in impact, innovation, and commercial sustainability. The work with Pula to pilot its pay-at-harvest weather insurance model contributed to CDC/BII’s announcement at COP27 to fund Pula through its new Climate Innovation Facility. Working with Apollo Agriculture to strengthen their AI-based credit models helped to improve repayment rates, enabling Apollo to extend the business in a financially sustainable way to reach over 90,000 farmers. The work with Sistema.Bio enabled the company to deliver Emissions Reductions (ERs) through the Gold Standard in Kenya and India (through partial carbon offset projects). CASEE’s work on research and evidence pivoted to FCDO priorities around climate finance and mapping of the investor ecosystem, working with well-established research institutions and other FCDO programmes (e.g. the Commercial Agriculture for Smallholders and Agribusinesses programme). The combination of hands-on venture building, investor convenings, and robust research outputs have reinforced the Shell Foundations strong reputation in the market.
- LDIP (grant managed by Acumen) delivered high profile outputs to help funders, policy makers and businesses to better understand COVID-19 impacts on farmers, and inform better decision making. Over the course of the grant (now ended) 60 Decibels conducted 55 Lean Data projects that catalysed co-funding from eight funders and surveyed over 12,000 farming households. The team proactively sought out these co-funding opportunities (e.g. bringing in funding from MercyCorps to extend the Kenya COVID impacts on farmers work). As a result, for every £ of SIIMA grant funding spent on these projects, the team raised £1.2 of catalytic funding.
- Under RARE, Acumen partnered with the Busara Center for Behavioural Economics (Busara) and eight agricultural platform companies in sub-Saharan Africa to finalise behavioural economics research on how smallholder farmers perceive the effects of climate change. The research focused on farmers’ strategies to mitigate challenges associated with climate change, and why they chose to (or not to) work with agricultural platform companies offering climate-smart solutions. This included interviewing 360 farmers in Ethiopia, Kenya, Nigeria and Tanzania, culminating in a robust industry-facing report, supported by a comprehensive marketing strategy – estimated to have reached over 1,350 impact investors, donors, agribusinesses, agriculture technical assistance providers and practitioners by end-2021.

The recommendations from the last Annual Review have all been addressed (see Table 1). Recommendations around the pivot toward climate and nature are ongoing, as are the discussions around how to best engage with the FCDO country network. During the year, all SIIMA partners participated in a roundtable organised by FCDO on how to step up our focus on climate and nature in our work. Partners responded positively and worked hard to help FCDO land our message on climate-resilient and sustainable agriculture at COP26. The programme should continue based on strong VfM and direct contributions to UK and FCDO priorities around economic partnerships and building pipeline for CDC/BII, strengthening climate-resilient sustainable agriculture, and science and technology partnerships.

Table 1: Progress against 2021 Annual Review recommendations
Recommendation	Status	Commentary
Programme partners should co-develop with FCDO a set of clear influencing goals (by June 2021)	Complete	Shell Foundation and FCDO worked closely together on the Climate Finance and investor mapping research to unlock additional capital for low carbon agriculture. The collaboration ensured the objectives and outcomes were in line with COP26 objectives and FCDO’s CIIC initiative bringing together impact investors.
Review logframe indicators and milestones for 2021 to ensure indicators are meaningful and milestones are stretching (by May 2021)	Complete	FCDO and SIIMA partners worked together to review the logframe targets to ensure they were appropriate. Logframe targets were adjusted for RARE (Acumen) and LDIP (60 Decibels), but not for CASEE (Shell Foundation) – see Annex B for further detail.
Programme partners should build on their momentum in developing strategic research partnerships, and reflect this ambition in research work plans (by May 2021)	Complete	SIIMA partners all built several strong research partnerships in 2021 and throughout the programme (see Outputs section for further detail).
Continue to build networks with FCDO country offices, to explore alignment with country office priorities and scope for providing technical supporting (e.g. with market intelligence) (on-going).	Complete/ Ongoing	Shell Foundation has continued to develop relationships with FCDO country offices, e.g. working with FCDO India to organise launch of the Rabobank US$55m guarantee facility, and coordinating a ministerial visit with the Ghana office. The Shell Foundation India team is supporting FCDO India to showcase CASEE companies to COP26 President in Q2 2022.

Major lessons and recommendations for the year ahead

Key lessons from the year under review:

Evidence is emerging that the model is working, leading to significant financial leverage and impact. CDC/BII’s announcement at COP26 to invest in Pula, through their new Climate Innovation Facility, demonstrates the impact the Shell Foundation model of venture building combined with investor convenings and robust research. Further evidence of interest from the UK investors came from the decision by CDC/BII to invest in Factor E’s new Equator Fund.
[note] Factor E is the clean technology incubator, that was co-founded by Shell Foundation with FCDO support, and has incubated many of the top-performing companies in the CASEE and TIME portfolios that are now scaling (e.g. Apollo Agriculture, InspiraFarms, S4S Technologies and Sistem.Bio.
- Robust research anchored in the realities of hands-on business support can be effective in convening investors around common priorities. The work Duke University and Rocky Mountain Institute has undertaken under CASEE has been an effective ‘calling card’ for FCDO and Shell Foundation to refer to in engaging investors and other stakeholders on the issues around mobilising climate finance, including adaptation finance. Building on the work under SIIMA, in 2020 Acumen Resilient Agriculture Fund (ARAF) partnered with 60dB and the Green Climate Fund to develop a Climate Resilience Toolkit to empower companies to measure their contribution to building smallholder farmers’ resilience.
  [note] Discussions are on-going with respect to turning this into a publicly available tool.
- Partnerships with other FCDO-supported programmes, is extending the reach of the SIIMA programme. The partnership with CASA has been effective in extending the reach of CASEE’s work: Shell Foundation developed an investor mapping research product with primary data on investor preferences, and then partners with CASA for them to disseminate and maintain this work in a database.
- Reputational risks around branding need to be monitored. In the lead-up to COP26, Shell Foundation agreed to reduce its presence in sessions due to sensitivities around brand links to Shell Corporate. Shell Foundation manages this risk proactively by drawing consistent reference to its charitable independence and how that is protected across its various communications activities.
- Strong partnerships and focus on delivery helped to mitigate against impacts of ODA cuts. When the prospect of ODA budget reductions arose, FCDO engaged with its partners including BMGF to explore alignment between SIIMA activities and BMGF strategy. These negotiations resulted in a three-year US$4m project and partnership between 60dB, Busara and the BMGF Digital Farmer Services team. Through this work 60dB and Busara will continue the collaboration started under SIIMA, and leverage evidence generated from the SIIMA grant to conduct additional research on digital farmer services for small-scale producers (SSP) in Nigeria and India.
Key recommendations for the year ahead are set out in Table 2.

Table 2: Annual Review recommendations
Recommendation	Notes	Lead/timeframe
SIIMA should accelerate its work with DFIs to mobilise additional capital for SMEs.	There is an opportunity for FCDO to capitalise on the opportunity afforded by the deepening partnership between Shell Foundation, CDC/BII and DFC, by accelerating Shell Foundation’s investor relations work and drawing out lessons for the investment community (see Box 1). We recommend expanding CASEE funding for this purpose through a Business Case cost extension addendum.	SF to prepare concept note in consultation with FCDO (by April 2022).
SIIMA should continue to lean into broader FCDO work on impact investing, including the ClimateShot Impact Investing Coalition.	A narrative around how this work contributes to the 2030 vision for the Glasgow Innovation Breakthrough goal on agriculture should be developed, to align with broader UK ambitions on climate-resilient and sustainable agriculture.	SF and FCDO (by June 2022, ahead of Agriculture Breakthrough launch at Stockholm +50 or other event).
Explore further opportunities to engage the FCDO country network.	Shell Foundation has been proactive on this but country engagement has been held back by the FCDO/Shell Foundation partnership role (co-funded by SIIMA and TEA programmes) being vacant. Procurement is now underway and we expect the role to be filled by mid-2022.	SF with support of FCDO (engagement strategy to be developed when Partnership Manager is in post).
Review logframe including choice of cumulative vs annual milestones.	The decision was taken during the year to not move to annual targets (as opposed to cumulative), however FCDO and Shell Foundation should revisit this to assess how output milestones can provide a meaningful incentive and mechanism for accountability during the year.	SF to make proposals to FCDO by April 2022.
Strengthen cross-FCDO linkages with Shell Foundation.	Propose to integrate CASEE more closely with the Ayrton fund, given strong alignment of CASEE’s work on energy for productive use. This will require CASEE reporting against ICF, in line with reporting already provided by TIME, but also enable the programme to participate in Ayrton convening/network activities.	CASEE team in consultation with TIME team, by June 2022.
Keep reputational risks associated with branding under review.	Shell Foundation are actively considering such issues and potential mitigations, in close consultation with FCDO.	Shell Foundation and FCDO (on-going).

Description of performance against outputs

This section discusses each output in turn. For CASEE outputs, given the lumpiness of results and decision to present cumulative targets, the judgments on outputs score rely heavily on evidence of quality of delivery (e.g. market shaping, sector influencing, and agility in pivoting to UK priorities) and progress toward outcomes, as set out above.

Output Title	Increased number of farmers with access to energy-related products, technologies or services (CASEE)
Output number:		1	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of smallholder farmers directly served by CASEE partners (cumulative)	60,000	Exceeded: 183,176
1.2. Number of smallholder farmers indirectly served by CASEE partners (cumulative)	230,000	Exceeded: 349,776

Supporting narrative for the score:

- The programme scores an A+ on this output, reflecting the CASEE team’s above-expectations engagement and innovation in building sustainable businesses. In particular the team worked hard to get portfolio businesses back on track when impacted by COVID, and in supporting businesses to make connections with other ecosystem players (technology providers, finance providers, service providers) that enabled businesses to move closer to farmers/small-scale producers and generate greater reach and impact.
- The programme exceeded the indicator milestone target on Output 1.1. CASEE partners directly impacted farmers by providing access to inputs, finance, markets and productive clean energy assets such as solar pumps, solar dryers and biogas digestors. Drivers of outperformance for this output include Apollo and AgroCenta who work directly with farmers through a hybrid of robust proprietary digital platforms and boots-on-the-ground operations, and Sistema.bio which provides farmers with access to biogas digesters, along with credit and after sales service. Apollo has directly supported more than 90,000 farmers; AgroCenta has directly supported more than 32,000 farmers and Sistema.bio has directly supported more than 26,000 farmers.
- The programme also exceeded the indicator milestone for Output 2.1. CASEE partners indirectly impacted farmers by providing access to cold storage at farm gate as well as by reducing their risk through access to insurance. 80% of this KPI has been achieved via supporting Pula, which has to date supported more than 3.3 million farmers to access insurance and build resilience against risk. Origen and S4S have also outperformed in this output by expanding their supply chains to move closer to small scale farmers.
  [note] We have only included 17% of Pula’s 2021 annual KPIs to CASEE to ensure conservative attribution, while for all other partners we have used cumulative numbers.

Output Title	Businesses receive financial and technical support to scale (CASEE)
Output number:		2	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of businesses supported by CASEE (cumulative)	17	Met: 17
2.2. Amount of finance leveraged by CASEE partners (US$ millions) (cumulative)	US$50m	Exceeded: US$79m

Supporting narrative for the score:

The programme scores an A+ on this output, reflecting above-expectations delivery on forging links with (UK-supported and other) investors that have resulted in increased leverage. Of the US$79m that has been mobilise to date, US$47m is equity, US$23m is debt and other commercial instruments, and US$9m consists of grants. This is a strong result given a difficult funder environment with commercial investors showing greater risk aversion during the pandemic. It can be attributed to (1) a robust approach to identifying well-performing businesses with scaling potential; (2) providing portfolio companies with fundraising readiness support; and (3) a strong focus on investor relations and investor convenings.
The programme exceeded its targets on both indicators relating to this output. Since the programme goal for Output 2.1 has been met, CASEE will focus on scaling up the existing portfolio companies, mobilising additional financing, and identifying ecosystem interventions to solve key market barriers. Two priority areas with respect to ecosystem interventions are asset financing for farmers and increasing climate finance for low carbon agriculture enterprises.

Output Title	Knowledge and evidence generated and disseminated (CASEE)
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of partnerships created with in-country academic researchers (cumulative)	2	Met: 2
3.2. Number of research, learning and case study reports disseminated based on the CASEE research workplan (cumulative)	14 (incl. 2 high-quality peer-reviewed outputs)	Exceeded: 25 (incl. 3 high-quality peer-reviewed outputs)
3.3 Number of events organised, attended or facilitated that bring together relevant experts and practitioners to promote CASEE objectives	18	Exceeded: 40

Supporting narrative for the score:

- The programme has exceeded expectations and scores an A+ on this output. The CASEE team has been active in developing research partnerships with credible partners, and effectively worked to align research questions with FCDO evolving priorities.
- Under Output indicator 3.1, two partnerships were developed with local academic researchers to support CASEE partners. One partnership was developed between East African Fruits and the Solidaridad research network, and one was developed between Keep it Cool and Agrocenta and Kenyan researchers that are part of the Environment for Development network of global researchers. These partnerships are already improving the rigour of research led by portfolio partners, while also building capacity of local researchers by providing them with opportunities to undertake research with data from live operations.
- Under Output indicator 3.2, the team disseminated 12 research and evidence outputs during the year (see Table 3). This included a mix of high-quality outputs (including three that were peer-reviewed by industry experts) as well as communications pieces that have been effective in boosting awareness about CASEE. It is recommended for next year to consider separate logframe targets for high-quality outputs and other influencing/communications pieces; and to consider annual targets, to facilitate a view on performance within a particular reporting period.
  [note] For outputs published prior to 2021, please see the SIIMA 2021 Annual Review.
  [note] These communication outputs have received nearly 6,000 views, and have been promoted via newsletters, social media and a range of events and engagements.
- Under Output indicator 3.3, CASEE organised and/or spoke at 14 events in 2021. These included significant investor engagement, through a range of formats designed to bring together CASEE partner businesses and investors, in particular around asset financing, gender inclusion and climate. As a direct result of the sessions, several investors started due diligence on CASEE companies, such as S4S with GIF and GIZ and Keep IT Cool with Accion.

Table 3: CASEE case studies and learning reports published during 2021
S.No.	Title and link to the output	Type of output
1	Understanding Rural Pathway Transitions	High quality primary research report
2	Mapping of agriculture investors: Investor database	High quality primary research output
3	Insights for enterprises and investors from CASEE investor mapping	High quality primary research report
4	FactorE report: Can productive agricultural activities strengthen the commercial performance of community mini-grids?	Partner learning report
5	Pula Report: Can agri-insurance reduce the credit risk associated with solar paygo products?	Partner learning report
6	Brookings blog: Climate finance meets low carbon ag-tech	Blog in a peer-reviewed platform (Brookings)
7	Interview with Efficiency for Access: Improving livelihoods and adapting to climate change by understanding pathway transitions in rural households	Blog: Interview with Efficiency for Access
8	Implications of the Rural Pathways Model as a means of understanding the long-term trajectory of rural households	Video recordings in partnership with CASA, with practical examples of the Rural Pathways model’s application for SMEs
9	Scaling Biodigesters: How Appropriate Financing Can Help This Undervalued Technology Deliver Social and Environmental Impact	Blog in a popular development sector platform (Next Billion)
10	World Economic Forum blog: How finance, ag-tech and more can speed the energy transition - 4 experts explain	Blog in World Economic Forum
11	India COVID Response Programme for Agriculture Transition: Highlights from the launch event	Blog summarizing highlights from India COVID response program launch event
12	Article in Economic Times India highlighting S4S’s impact and growth journey	Article in popular trade media (Economic Times India)

Output Title	Poor farmers increase the adoption of resilient and productive products and services (Acumen-managed).
Output number:		4	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Amount of investment made by Acumen Resilient Agriculture Fund (ARAF) by year.	US$4 million	US$1.8 million 2022 / (with several promising deals expected to close in early 2022)

Supporting narrative for the score:

The programme has met expectations and scores an A on this output. ARAF held its fund final close in June 2021 at US$58m. FCDO’s support of £380k to the fund’s Technical Assistance Facility (TAF) through SIIMA in 2020 sent a strong signal to the private sector, catalysing an additional US$5.5 million USD in commitments from other donors towards the TAF, including IKEA Foundation, FMO, GCF and other DFIs. The work of the TAF has been critical in preparing investments for the fund, as tracked under this Output indicator. While investments made during the year were below the logframe milestone, the profile of deals is ‘lumpy’ and this score reflects that ARAF is engaged in due diligence on several promising deals that expect to be close in early 2022.
[note] The fund is now supported by the Dutch entrepreneurial development bank (FMO), the Soros Economic Development Fund, the French development institution PROPARCO (through FISEA+, the AFD Fund advised by PROPARCO), the Children’s Investment Fund Foundation, IKEA Foundation, Global Social Impact, and other respected investors and funders.

Output Title	Companies refine business models to increase impact on customers; investors better target high impact companies (managed by Acumen and delivered by 60dB)
Output number:		5	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1. Cumulative number of Lean Data projects completed with agriculture companies	40	Exceeded: 55
5.2 Cumulative number of farming households surveyed	10,000	Exceeded: 12,370 (incl. 360 farmers surveyed through RARE)

Supporting narrative for the score:

- The programme has exceeded expectations on this output and scores an A+. Over the course of the grant, 60 Decibels completed a total of 55 Lean Data projects with eight different funders and 23 companies, surveying 12,010 smallholder farmer households. FCDO’s funding catalysed both co-funding (cost share between FCDO SIIMA and the organisation) and follow-on funding (paid for by the organisation) from agribusinesses and investors/funders for Lean Data projects. While 2021 was a wind-down year, strong pipeline at the start of the year resulted in a significant number of Lean Data projects delivered during the reporting period that were funded through follow-on funding catalysed by SIIMA, or paid for through the ARAF TAF which SIIMA funded in FY19/20.
- This work has been critical in providing agribusinesses and organisations with feedback from their farmers that can be applied to operational decisions in the context of the pandemic. The dashboard on farmers’ experience of COVID-19 was used by investors, companies, researchers and influencers in the sector to inform their support of farmers during this difficult time, including by Mercy Corps’ AgriFin Accelerate & Digital Farmer Programs who used the data to “make an unprecedented effort to get support for unconditional and conditional cash transfers to farmers”. In another example, the climate-resilience toolkit developed by 60 Decibels is now being used by ARAF to collect longitudinal data on their farmers’ resilience journey and identify ways in which their investees can improve these.

Output Title	Public dissemination of research and learning outputs (managed by Acumen)
Output number:		6	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of public facing activities that Acumen/ARAF/Lean Data participate in to discuss and disseminate learning from research and learning activities	25	Exceeded: 34
6.2 Number of public-facing knowledge and learning outputs published (excludes peer reviewed journals), by year.	2	Met: 2
6.3 Number of academic articles in peer-reviewed journals published, by year.	0	0

Supporting narrative for the score:

- The programme has met expectations on this output and scores an A. The teams delivered 34 public-facing activities, against a milestone set earlier in the year of 25. This reflects a combination of increased activity in the lead-up to COP, in part catalysed through the FCDO-CCAFS chaired ClimateShot agriculture innovation COP26 campaign (six of the events were linked to COP26) as well as the strong reputation of delivery partners leading to additional engagements/invitations. Over the course of the grant, the team delivered 51 events and knowledge outputs, reaching over 10,000 engagements across the three years of the grant. Acumen also leveraged its relationship with the GCF as an accredited entity, to share the insights from this work at GCF hosted events and COP26.
- Key industry-facing reports landed well with the sector. Acumen’s Resilient. Farmers. report and 60 Decibels’ 8 Things we learned from Kenya farmers during COVID-19 report both generated significant interest in the market. The final deliverable, an agriculture sector benchmark report containing data aggregated from all SIIMA and Lean Data agriculture projects, will be completed in the first half of 2022 due to delays in the data aggregation process. 60 Decibels is in the process of aggregating data from 75+ agriculture organisations whose farmers have been surveyed since 2018, including the 23 organisations that received support directly or catalysed under the SIIMA programme
Risks

The programmes overall risk rating is Moderate.

The risk matrix on FCDO’s Aid Management Platform has been updated as part of this review.
Risks are being kept under review by the FCDO programme management and Shell Foundation teams, who meet at least monthly to check on programme performance. This includes assessing risks both in terms of impacts on investees’ ability to deliver against targets, and in terms of budget forecasts. The risk matrix will be reviewed on a quarterly basis, or as the need arises. Additionally, we have extensive mitigation measures. This is complimented by our low-risk appetite for fiduciary, operational, reputational, safeguarding and delivery risks, which are managed through our active engagement with programme partnerships, and adherence to FCDO’s Programme Operating Framework.

Programme management

Following the ODA budget reductions made in the 2021/22 FY, changes were made to each of the components. For Component 1 (CASEE) the 2021/22 budget was reduced from £3.5m to £1.3m. The programme was also extended from a five- to a seven-year programme, along with re-profiling of the FCDO-Shell Foundation mix of funds, to place a larger share of FCDO funding in outer years.

For Components 2 and 3 (RARE and LDIP) the remaining budgets for years 3 to 5 were cut. A budget of £50,000 was made available to wind-down grant activities in the first two quarters of FY21/22, and Acumen and 60 Decibels were asked to prepare a wind-down work plan and budget forecast for the final six months of the grant, which ended on 30 September 2021. FCDO led discussions with BMGF that resulted in some activities under these components moving into a new grant and being expanded upon through BMGF funding.

The approved budget for 2021/22 FY was £1,404,522, of which £1,020,464 has been spent to date. All partners responded swiftly to the budget cuts and the continuing challenges presented by COVID-19, and made contingency plans and corresponding adjustments on workplans, log frames and budgets. These contingency plans and adjustments included a no-cost extension to the partnership with Shell Foundation under this programme, the partnership was extended by two years. All partners have been very responsive to FCDO during the period, communicating regularly to agree realistic deadlines and expectations and responding well to feedback and guidance provided by FCDO.

Financial reports reviewed showed no major concerns.

Value for Money

SIIMA continues to represent strong VfM for FCDO. The VfM case is largely as documented in the Business Case and includes significant financial leverage and ability to leverage technical expertise of the larger FCDO-Shell Foundation partnership established through the Transforming Energy Access programme, and drawing on Acumen’s and 60 Decibels’ networks and expertise. VfM highlights for the year are presented in Table 4.

Table 4: Selected examples of VfM
VfM indicator	Examples
Economy	Shell Foundation matches FCDO’s budget 1:1 with £15m of its own budget, doubling the resources available to CASEE for delivery. Shell Foundation does not charge any indirect costs to FCDO and absorbs all overheads associated with the programme from its own funds. / By combining processes and resources between the CASEE and TIME partnerships, e.g. sharing the FCDO/ Shell Foundation Partnership Manager, Shell Foundation is able to reduce administration costs for the programme.
Efficiency	Shell Foundation further developed its approach to remote due diligence, which requires more time than in-person due diligence – however the team has made it more efficient and effective by leveraging and deepening its investor networks. / CASEE’s is making rapid progress toward programme leverage targets of mobilising £110m in additional capital (having mobilised £79m by the end of 2021). / All eight organisations who received support under the SIIMA grant co-funded Lean Data projects (AgDevCo, CDC, Solidaridad, CASA, Technoserve, Syngenta Foundation, Shell Foundation, Mercy Corps Agri Fin Accelerate) – showing how far a bit of catalytic funding can go in shifting investors’ interest in impact management. Over the life of the grant, for every £1 of SIIMA funding, 60dB raised £1.2 of co-funding from other investors. / In its second year of operation, ARAF’s investments have already leveraged 1.67x the capital invested in them by ARAF.
Effectiveness	The programme partners all enjoy strong reputations and convening power within the sector, and engage effectively and frequently with FCDO and other UK-supported partners – including proactive engagement around FCDO’s pivots to climate and nature. / Progress toward programme outcomes has been strong, due to SIIMA partners leaning in to broader UK and FCDO priorities, including through engagement with the country network (e.g. India and Ghana) and other processes (e.g. providing inputs into the ClimateShot Impact Investing Coalition, or partnering with other FCDO programmes e.g. CASA) / The 60dB impact benchmarking work and impact measurement innovations (to be published in calendar year 2022) will help drive more impactful investment of development capital through CDC and other UK-supported funds.
Equity	CASEE made further progress in making its portfolio more inclusive. Having made inclusivity a core theme for the programming, 61% of the partners directly funded under CASEE now have either local and/or female founders. To further promote gender equity in the sector, in 2021 CASEE partnered with a fund manager to develop and deploy innovative financial instruments to underrepresented early-stage female founders. / CASEE has developed a network of local researchers has been developed to ensure that expertise is leveraged in the countries where CASEE operates, contributing to the economy. / Through Shell Foundation resources, the entire CASEE portfolio has been invited to undergo gender analysis and support developing gender action plans, including dedicated TA support. S4S and Keep IT Cool have both been recognized for and have attracted additional interest from investors due to their gender action plans in particular. / A number of CASEE portfolio companies also address systemic barriers for women directly – e.g. S4S which is a decentralised solar food processing enterprise preventing post-harvest crop loss, has a supply chain which consists of 100% female farmers and whose solar dryer systems have been designed with feedback from these farmers. / In feedback to the Kenya COVID-19 impact survey, a senior director at MercyCorps noted “We are definitely finding that the 60 Decibels work is the clearest, cleanest, most regular and most comprehensive set of insights we have access to and we are routinely using it to drive support programming around farmer messaging, gender approach, work with banks and other financial service providers, input companies and aggregators.” / Acumen’s research work with Busara provided new evidence on differential behavioural drivers across men and women of take-up of climate resilience solutions.
[note] This includes travel, office costs and supplies, subsistence, event management costs, business-related expenses, and the time of any other staff member necessary to ensure successful delivery of the programme.

Approach for this Annual Review

Following authorisation by the Research and Evidence Directorate Head of Department, the approach to this Annual Review was a light touch review drawing on discussions with the SIIMA team and also the annual reports submitted by partners Shell Foundation and Acumen. These reports covered the twelve-month period to end-December 2021.

The Annual Review was carried out by an internal FCDO team which comprised of Agriculture Research Team’s Programme Responsible Officer (PRO) and Deputy Programme Manager (DPM. Quality assurance was carried out by the Agriculture Team Leader.

Date of last narrative financial report	Acumen: February 2021 / Shell Foundation: January 2021	Date of last audited annual statement	Acumen: June 2020 / Shell Foundation: December 2020

Key documents:

SIIMA Business Case
Annual Report from Acumen
Annual Report from Shell Foundation
SIIMA Annual Review 2021

Annex B: Changes to logframe indicators and milestones

Following recommendation in the last Annual Review, FCDO and programme partners reviewed logframe indicators and milestones.

For CASEE, with respect to Output indicators themselves, two changes were made. First, the 2.1 Output indicator “Number of peer-reviewed papers accepted for academic journals” was changed to “Number of partnerships created with in-country academic researchers”. In consultation with FCDO, it was agreed that fostering partnerships with local academic networks, based in the countries where CASEE portfolio companies operate, would be more valuable for the programme than peer-reviewed papers in academic journals. The new focus on partnerships with in-country academic researchers will help enterprises deliver more robust research reports as well as help local researchers build capacity by providing them access to data and information that can help fill evidence gaps in the agriculture sector. This will eventually lead to CASEE evidence being frequently published in academic journals and discussed in academic forums.

Second, the 2.2 Output indicator “Number of events organized, attended or facilitated that bring together relevant experts and practitioners to promote CASEE objectives” was changed to “Events organised by Shell Foundation to promote CASEE or external events where CASEE work is being presented/promoted to be counted”. This reflects the fact that the CASEE team attends many events to ensure the programme remains relevant and new ideas are added, however events organised by, or where Shell Foundation presents, will have greater impact on CASEE objectives. Therefore, under the revised indicator, only CASEE organised events and events where CASEE is promoted will be counted.

With respect to Output indicator milestones, the decision to not adjust output milestones on a year-by-year basis, but rather to continue to assess performance holistically against the benchmark of intended outcomes by the end of the programme rather than annual targets. Key reasons for this include:
1. CASEE is reducing its work with ecosystem enablers who do not have a direct energy link. Several of these enablers are platform based (Pula, Apollo, and AgroCenta) and therefore have the fastest impact expansion. As these partners graduate from the CASEE portfolio, KPIs will increase slower.
2. Companies go through a growth cycle when working with Shell Foundation. Most companies when they enter the portfolio are at an earlier stage, tracking fewer KPIs. Then after Shell Foundation hands-on support and CASEE capital, these companies perform better and are better able to articulate this performance. 6 of the 17 companies and ecosystem enablers are new to the CASEE portfolio, entering at the end of 2020 and throughout 2021, are at an earlier stage in the growth cycle. Several of the companies that have been in the Shell Foundation portfolio for longer, are being evaluated for graduation. Therefore, KPIs will be ‘lumpy’, and focusing on individual years could detract from the partnerships focus on results for the programme as a whole.
For Acumen-managed components, the below table sets out the changes of logframe milestones following confirmation of ODA reductions. For discussion on actuals vs revised milestones, see the Output section.

Table [X]
	2021 milestone	Revised milestone	Actuals
Output Indicator 2.1: Cumulative number of Lean Data projects completed with agriculture companies, including portfolio companies, those outside the portfolio, and those in due diligence.	55	40	55
Output Indicator 2.2: Cumulative number of farming households surveyed.	12,500	10,000	12,370
Output Indicator 3.1: Number of public facing activities that Acumen/ARAF/Lean Data participate in to discuss and disseminate learning from research and learning activities, by year.	33	25	34
Output Indicator 3.2: Number of public-facing knowledge and learning outputs published (excludes peer reviewed journals), by year.	3	2	2