        Business Case – September 2020

Summary Sheet

Country Development Diagnostic/ Portfolio/ Business Plan Summary: / FCDO Yemen aims: (a) to find a sustainable resolution to the conflict in Yemen, thereby reducing the threat to UK regional interests and our Gulf partners, and reducing the risk of terrorism emanating from Yemen, and b) to alleviate the humanitarian crisis, stabilise Yemen's economy and support the development of more effective and resilient state institutions and society [Yemen Country Business Plan]

Title: / Yemen Food Security Safety Net P rogramme
Programme summary (100 words maximum): / This programme will provide cash transfers to up to 1.5 million of Yemen’s most food insecure households. It will be FCDO Yemen’s flagship programme and the backbone of our humanitarian response. It will spend up to £250 million over 5 years, replacing 3 existing programmes which last year spent in the region of £120 million per year. The programme will continue provision of life-saving cash assistance to those most in need (including women), build resilience to reduce famine risk in the future, and ensure a more efficient, effective and sustainable response to the high on-going needs of this protracted crisis.
What is the rationale for UK Aid spending? (200 words maximum): / Extreme poverty, food insecurity and malnutrition in Yemen have been exacerbated by over six years of on-going conflict, increased frequency of natural disasters resulting from climate change, and the impact of COVID-19 on the economy and livelihoods of the most vulnerable. / A more predictable, coordinated, and longer-term response is essential to address extremely high levels of poverty and food insecurity. Short-term humanitarian financing alone is ineffective in meeting the needs of the increasing number of Yemenis reliant on humanitarian assistance. Providing more predicable support reduces the risk of famine in the future and helps vulnerable communities cope better ensuring they don’t sell assets to survive or stop sending their children to school to save money. / This programme brings together existing programmes that provide cash to Yemen’s most vulnerable, taking a more strategic, longer-term development approach with UN, NGO, and national Yemeni partners. Leading donors’ efforts to bring together cash transfer programmes under one coherent response will improve accountability, deliver better value for money and provide a more predictable and sustainable response to addressing food insecurity.
Programme Value: £250 million		Country/ Region or Sector: Yemen
Department/Country Office confirmation of review processes		Redacted
Contact name		Redacted
Threshold for final approval of Business Case: / FS (via Junior Minister), HM Treasury (via Management Accounts Group), QAU for review of Business Case
Date of Approval of Concept Note:	22/10/2020	Name and role of Approver: Foreign Secretary
Date of Approval of Business Case:	06/08/2021	Name and role of Approver: Foreign Secretary
Programme Code: 301125	AMP Start Date: 20/07/2021	AMP End Date: 31/12/2026
Overall programme risk rating:	Severe
Vault Number:	61501559

## Strategic Case

CONTEXT: The worst humanitarian crisis in the world

After more than six years of continuous conflict since early 2015, the humanitarian crisis in Yemen remains the worst in the world, with food insecurity at its core. Humanitarian need has increased over the years, resulting today in 20.7 million people, 66% of the population, needing humanitarian assistance. Between January and June 2021, 47,000 people are projected to be in famine conditions, while 16.2 million people are estimated to be severely food insecure and in need of urgent assistance.
[note] Yemen Humanitarian Needs Overview 2021, link here.
[note] Yemen Integrated Phase Classification snapshot: October 2020-June 2021 (December 2020), link here.

Food insecurity in Yemen is an affordability crisis, rather than being driven by food availability. Almost 90% of food is imported, and markets function, but people lack the income sources to pay. The economy has shrunk by half since 2015 and the Yemeni Riyal has depreciated by 90% since 2017, further affecting people’s ability to afford enough food.
[note] Commercial imports comprise about 88% of the total available food supply in Yemen, Yemen Food Supply Chain, thematic report, ACAPS, Mercy Corps, December 2020, link here.

Yemen has a long history of conflict, instability and pervasive poverty and inequality. The country faces deep-seated development challenges including state fragmentation, endemic corruption, rapid population growth, high youth unemployment, gender inequality, poor provision of basic services, and a weak economy that depends on declining oil reserves and is now subject to capture by conflict parties. The conflict continues to inflict civilian casualties and cause extensive damage to public and private infrastructure. Today, Yemen ranks 179 out of 189 countries on the Human Development Index and has been the poorest country in the Middle East, even before the conflict escalated. Poverty is deepening, affecting around three-quarters of the country’s population, compared to less than half before the crisis.
[note] Human Development Report 2020, the next frontier: human development and the Anthropocene, UNDP, link here
[note] The World Bank in Yemen, Overview, link here.

The most vulnerable groups are women, children, people with disabilities, minorities, Internally Displaced Persons (IDPs), refugees, and migrants. Women and girls continue to be marginalised, facing unstable livelihoods, insecurity and lack of access to basic services. Even before the current crisis, they faced discriminatory social norms that limited their economic, social and political participation. Since 2006, Yemen has consistently ranked the worst place in the world to be a woman, last in the World Economic Forum Gender Gap Index and highest in the Gender Inequality Index. Conflict and displacement have exacerbated gender inequalities and increased rates of violence against women and girls and early marriage.
[note] Yemen Humanitarian Needs Overview 2021, link here; Amnesty International report 2020/2021 link here
[note] “Women nowadays do anything.” Women’s role in conflict, peace and security in Yemen, Heinze, M and Baabbad, M., SaferWorld, CARPO and YPC, 2017 link here.
[note] In 2019/20 Yemen was again ranked the worst place in the world to be a woman, the only country to experience ‘major deterioration; Georgetown Institute for Women, Peace and Security and Peace Research Institute Oslo. 2019. Women, Peace and Security Index 2019/20: Tracking sustainable peace through inclusion, justice, and security for women, https://giwps.georgetown.edu/the-index/
[note] Ranking 155th in 2020, Global Gender Gap Report 2021, Insight Report, World Economic Forum, 2021, link here.
[note] Gender inequality index, link here.
[note] From the Ground Up: Gender and Conflict Analysis in Yemen, Gressmann, W, Oxfam, 2016, link here
[note] Amnesty International report 2015/2016, 2015, link here.

The conflict has hindered access for the delivery of assistance and basic services. The worst affected areas are in the north-west of Yemen, where battles between de facto authorities and Government of Yemen (GoY) and aligned forces are most fierce. In 2020, intensified conflict brought the number of IDPs to over 4 million. Conflict has made many forms of national service delivery largely impossible. Operational constraints for humanitarian actors include: access restrictions; scarce data; active conflict and severe insecurity; bureaucratic and logistical impediments; and low capacity to deliver assistance, leading to delays or interruption of assistance to at least nine million people some time during the year.

NEED FOR INTERVENTION

This programme seeks to address two key problems:

  - Problem A: Tens of thousands of Yemenis are at risk of starving. People’s resilience, purchasing power and livelihoods have been eroded to the point that they cannot afford enough food to feed their families.

  - Problem B: The current development and humanitarian response is poorly coordinated. Cash transfers, the principal focus of this programme, can help address food insecurity and the risk of famine in Yemen, but fragmentation and poor coordination hamper their efficiency, effectiveness and sustainability.

Problem A: Yemenis are at risk of starving

Food insecurity in Yemen is not only severe but protracted, with a growing risk of famine resulting from people’s vulnerability and chronic poverty.

  1. The longer people are food insecure the more likely they are to have been depleting their assets, ‘making any further deterioration or shock all the worse for them and increasing the negative long-term effects’. In Yemen, millions of people have been severely food insecure for over six years already.
    [note] Viewpoint: Determining Famine: Multi-Dimensional analysis for the twenty-first century, Daniel Maxwell, Abdullahi Khalif, Peter Hailey, Francesco Checchi, 2020, link here.

  1. In the absence of accurate mortality data (which authorities in Yemen do not have the capacity to collect or may even try to suppress), it is unlikely that famine will ever be declared. If it is, it is likely it will only happen after thousands of innocent people have starved. World renowned experts declared in February 2021: ‘Nobody knows the actual death tolls in […] Yemen. But we believe it’s quite possible that future demographers and nutritionists will conclude that hundreds of thousands of people died from hunger and related causes in these countries, and that almost all died in places where there was never an official designation of famine’. It is estimated that conflict has led to nearly a quarter of a million people killed directly by fighting and indirectly through lack of access to food, health services, and infrastructure .
    [note] Hunger deaths aren’t simply about famine or no famine, Daniel Maxwell, Peter Hailey, Abdullahi Khalif, Andrew Seal, Alex de Waal, Nicholas Haan, Francesco Checchi, article in the New Humanitarian, February 2021, link here.
    [note] Assessing the impact of war on development in Yemen, Frederick S. Pardee Centre for International futures, UNDP, 2019, link here.

Food insecurity in Yemen is mainly an issue of affordability, driven by the deterioration of the economy. Dramatic increases in prices mean food is unaffordable for most Yemenis. The Yemeni Riyal has depreciated by over 90% since 2017, as a result food prices have grown by 117% since 2017 and by 30% over 2020. These are compounded by primary and secondary impacts of COVID-19.

More than 40% of Yemeni households have lost their primary source of income. The poorest and most vulnerable (including IDPs, female headed households, widows, older people, and people with disabilities) are affected the most. The Government of Yemen is now largely unable to deliver public services and pay public sector salaries, affecting over a million civil servants. Pre-conflict, 25% of households relied on government salaries, of which 31% were food insecure.
[note] Yemen Humanitarian Needs Overview (HNO) 2021, link here.

Remittances, a sole or primary source of income for more Yemeni families during the conflict, could have dropped as much as 80% in some communities as a result of COVID-19 restrictions which has reduced the ability of Yemenis to work in Gulf countries and send money home to Yemen.
[note] Remittances constitute a substantial share of Yemen’s economy, making 17% of GDP in 2019 (World Bank, link here); and exceeding US$ 3.3 billion annually since 2012 (source: World Bank, link here). They exceed international aid flows and are the largest source of foreign exchange.
[note] ACAPS report to be published. Remittances in Yemen’s economy: regional developments, labour laws and sub-national dynamics. Yemen HNO.

1. The risk of famine is not only driven by an insufficient access to food, but by a broader range of factors primarily caused or compounded by human action: reduced access to health, and to Water, Hygiene and Sanitation (WASH) services, contributing to malnutrition; access restrictions that impede delivery and access to services and assistance; and breaches to protection of civilians.
  1. In 2021, the number of acutely malnourished children is expected to rise by 15% to 2.26 million, and more than a million pregnant women and new mothers, are projected to suffer from acute malnutrition
    [note] IPC_Yemen_Acute_Malnutrition_2020Jan2021Mar.pdf (reliefweb.int)
  2. Over 15.4 million people are without safe water and sanitation, and over 20 million without adequate healthcare. Half of Yemen’s health facilities are not operational due to conflict damage to infrastructure and access constraints.
    [note] Yemen Humanitarian Needs Overview (HNO) 2021, link here.
  3. Access remains highly restricted by parties to the conflict leaving 16.5 million people in hard to reach areas. predominantly where people in acute need are.
    [note] Compared to 5 million people two years ago, with bureaucratic obstacles presenting the most pervasive constraint for the safe, sustained and principled delivery of assistance and protection services.; Yemen Humanitarian Needs Overview (HNO) 2021, link here.
  4. Violations of International Humanitarian Law and human rights are widespread, disproportionately impacting women and children. Conflict has exacerbated all forms of gender-based violence, including child marriage, intimate partner violence, and sexual violence, with most survivors not seeking help for fear of stigma or reprisal. The quality and coverage of response services is weak; government services are poorly resourced, uncoordinated and ineffective, with authorities obstructing specialised programming.
    [note] Services include provision of clinical and psychosocial care, safe spaces for women and children, provision of legal assistance, access to reproductive healthcare, and case management for children and GBV survivors. UNOCHA’s Financial Tracking Service figures show the protection cluster as 18% funded at present, but almost all of this is multi-purpose cash assistance, not specialised protection support.

There is a desperate need for funding of interventions that address food insecurity and the risk of famine, whilst ensuring reform of the economy and a comprehensive political settlement are reached. Humanitarian and social protection interventions are both effective ways to address food insecurity in Yemen and they are both required to tackle the severity and longevity of need. Such interventions should be part of a comprehensive response that addresses other famine risk drivers (e.g. nutrition, protection, health, WASH).

Problem B: The current development and humanitarian response is poorly coordinated

Poorly coordinated humanitarian and social protection programmes risk leaving people behind

In Yemen, humanitarian and social protection systems to tackle food insecurity have been built separately and, as a result, are poorly coordinated. Pre conflict, Yemen had an effective social protection system, established in the mid-1990s and developed over two decades of intensive investments from the donor community and the GoY. Alongside humanitarian and wider development assistance, it helped reduce poverty from 40.1% in 1998 to 34.8% in 2005. However, after war broke out, much of Yemen’s formal social protection system stopped functioning and GoY support stopped altogether. As a result, the humanitarian response scaled up exponentially, with an increasing range of actors and interventions.
[note] Prior to the conflict, Yemen had social assistance, social development programmes, grant and production support programmes, social insurance and social protection programmes targeting those with special needs.

The result is a fragmented landscape of programmes that risks leaving people excluded or not necessarily receiving the type of assistance that is cheaper and works best for their situation.

Humanitarian and social protection interventions duplicate each other due to weak and insufficient coordination, despite increasing realisation of its need and progress. The extent of overlap between respective caseloads is unknown, but anecdotal evidence suggests it could be high (around 30%) despite targeting approaches that seem different. This is because in the Yemeni context of protracted crisis, the overlap between food insecurity, poverty and vulnerability is significant, meaning that humanitarian and social protection interventions are likely to reach the same groups despite using different selection criteria.
[note] Recent efforts for greater coordination between humanitarian cash interventions are leading to tangible progress: for example, the NGOs Cash Consortium of Yemen and WFP have now interoperable enrolment mechanisms. This is a sizeable achievement that will allow comparing beneficiaries lists and avoid overlaps. A Yemen Cash and Markets Working Group (CMWG) is actively working towards harmonisation among humanitarian cash actors (e.g. cash transfer values). But progress is slow, as incentives for change are insufficient. Coherence between social protection interventions is lacking, with currently no central government ministry leading on social protection and no mechanism to coordinate. The degree of geographic overlap or targeting complementarity is not known and targeting mechanisms vary widely. This will start changing in 2021 when a centralised social protection database is established.

It is almost impossible to identify duplications and complementarities in coverage and impact between humanitarian and social protection interventions. Information management systems are fragmented and often not interoperable making it almost impossible to compare recipients lists.

The effects and Value for Money (VfM) of different humanitarian and social protection interventions can hardly be compared, making it difficult to know which ones work better and for which groups, and where they duplicate or increase each other’s impact. This is because monitoring and impact metrics differ between interventions.

Variable sizes of cash transfers between humanitarian and social protection agencies confuse recipients and can be perceived as unfair, with the risk of creating tensions between communities and families.

Cash transfer values can be insufficient to address the severity of food insecurity. The value of the transfers can be insufficient to protect livelihoods or even save lives: the value of the Social Protection Emergency Cash Transfer Programme (ECTP) was deemed too low especially after currency depreciation and has led to the provision of ‘top-ups’. However, these remain below the value required to address the depth of need of most food insecure people.

Cash transfer value is determined by the programme rather than by the level of need. Whether people receive enough cash depends on the institution, the sector it belongs to and the funds it can access, rather than the level of need or a coordinated rationale across actors.

Attention to protecting livelihoods and building resilience is insufficient. Cash transfers are often made when people have already reached high levels of vulnerability, after their assets have been depleted.

Grievances from aid recipients can be missed and therefore not addressed: complaints mechanisms are disconnected and not effective enough, leading to confusion of recipients, lack of reporting and insufficient accountability.

1. Poor coordination between humanitarian and social protection programmes is mainly driven by competition for limited resources, diverging principles that underpin interventions (humanitarian principles versus working with governments) and insufficient alignment between donors.
  [note] Humanitarian cash and social protection in Yemen, CaLP Case study, Ruta Nimkar, Meraki Labs, Cash Learning Partnerships, 2020, link here
  1. To increase their chances to get more funding, aid actors tend to seek to become the go-to agency for parts of the response and become reluctant to share and align their approaches and data with other actors working in the same areas.
  2. Holding to humanitarian principles, including neutrality, can limit engagement with government actors especially in a conflict affected context where parties to the conflict can be compounding humanitarian need.
  3. Donors’ varying funding conditions can be a barrier to coordination (annual vs multi-year funding; preference for cash or in-kind; no requirement for implementing partners to follow common standards).
  4. Coordination is also challenged by the fact it takes place across multiple locations in country (mainly two centres of control: Sanaa’ and Aden), and abroad (Amman, Riyadh etc…), as several actors - including donors like the UK - are not based in country for security reasons.

Greater coordination between aid actors will require reform and incentives. Donors have a key role to play in shifting incentives for reform towards a collective vision, and this is – for example - the aim of the newly formed Cash and Social Protection Donor Working Group in Yemen. The UN Country Team and the World Bank should also play a key role cutting across the humanitarian and development siloes.

Progress has been made recently but it is only a start: UN agencies have commissioned a study on how to make their information management systems interoperable, and a few NGOs’ are working with a few UN agencies on making their information systems compatible. More efforts are needed and those should build on global cash coordination initiatives.
[note] The Cash Consortium of Yemen (CCY) aims to harmonise cash programme mechanisms among its NGO members, and to develop compatibility with UN agencies’ information management systems.
[note] For example the Common Donor Approach (CDA) launched in 2019 and the Joint Donor Statement on Humanitarian Cash Transfers (JDS) and the UN Common Cash Statement (UNCCS, a statement from the Principals of OCHA, UNHCR, WFP and UNICEF in December 2018), for which Yemen is a pilot country.

Insufficient funding makes coordination essential to address the scale of humanitarian need

Each pound needs to deliver maximum possible value. Current humanitarian funding levels are insufficient to address the scale, depth and longevity of need. A well-funded humanitarian response in 2019 helped reverse the risk of famine identified in late 2018. Food insecurity has once again soared after a year of limited funding (57.6% of Humanitarian Response Plan was funded in 2020). Today the famine risk is similar to 2018/2019, however, funding to the Humanitarian Response Plan has only reached 45% so far in 2021 compared to 87% in 2019.
[note] Yemen 2020 | Financial Tracking Service (unocha.org)
[note] As of end of March 2021. Though not all contributions are yet reflected on FTS: Yemen 2021 | Financial Tracking Service (unocha.org).
[note] Yemen 2019 | Financial Tracking Service (unocha.org).

Waiting to treat food insecurity when it is most severe is more costly. The humanitarian response model only treats needs when they are severe, and therefore costly, with no certainty that the treatment will be long enough to reduce humanitarian need. Designed to save lives, most humanitarian interventions are not eligible to development funding and depend mainly on short-term funding (primarily annual). As they target those who have tipped into extreme food insecurity, they offer higher transfer values but are more expensive and difficult to sustain year after year.

Protecting people from falling into severe hunger is cheaper. Social protection transfers are kept low to keep the scheme affordable for the state in the future and ensure sustainable sources of funding from donors in the interim. They protect people at risk of falling into extreme food insecurity (this is proven to be cheaper than waiting for people to become extremely food insecure to assist them) but are less likely to address the depth of humanitarian need.
[note] Economics of early response and Resilience to COVID-19: Ethiopia, Courtenay Cabot Venton, and input from experts on the Social Protection Approaches to COVID-19: Expert Advice helpline (SPACE), 2021, link here; Economics of resilience to drought in Ethiopia, Kenya and Somalia, Courtenay Cabot Venton, 2018, link here.

Better coordinated social protection and humanitarian interventions will stretch aid further. Removing duplications will support more people in acute need, and ensuring complementarities will protect those at imminent risk (which is cheaper). A recent World Bank analysis argues that the number of beneficiaries of all humanitarian and development programmes is more than enough to cover the entire Yemeni population (not accounting for overlaps in interventions), but that coordination is required to reduce duplications and exclusion.
[note] Social Protection at the Humanitarian-Development Nexus, Insights from Yemen, Discussion Paper, Yashodhan Ghorpade and Ali Ammar, World Bank, April 2021, link here.

Coordination is a first step towards a nationally owned and financed response to food insecurity

The long-term vision for addressing food insecurity should be one where we build back better a nationally owned and financed social protection system under the control of GoY. We know this can work and are learning about what works, thanks to current experience of delivering assistance through an existing social protection programme. But this will take a long time and require intermediary steps where humanitarian actors continue playing a core role, as the government is today not able to fund and provide social protection The re-introduction of government policy engagement and management of basic service provision will be challenged by state fragmentation, government instability and lack of capacity, as well as a lack of fiscal space.
[note] In partnership with UNICEF, the Emergency Cash Transfer Programme continues to provide quarterly cash transfers outside of GoY systems to people who are on a social protection beneficiary list.
[note] Yemen – Linking Humanitarian Cash and Social Protection: summary version, Ric Goodman, Christina Frey, Rachael Steller, Zakee Ahmed and Adnan Qatinah, 2019, Better Assistance in Crises (BASIC).

In the meantime, humanitarian and development investments should work together in ways that lay the foundations for a nationally owned system. In a context where the state has limited capacity and motivations which can affect neutrality and impartiality, humanitarian policies and efforts have been largely driven by international donors and implementing agencies. However, this should not prevent humanitarians delivering assistance in ways that can support the re-establishment of government participation and the building of a stronger national system in the future. The first step towards a strengthened nationally owned system is one of coordination between humanitarian and development actors.

FCDO LEARNING AND RESPONSE TO DATE

What we know: cash transfers are likely to be the most effective and efficient way of addressing food insecurity in Yemen

The rationale for addressing food insecurity and the risk of famine through cash transfers in Yemen is strong. In contexts like Yemen, where markets work and affordability is the challenge, evidence shows that cash transfers are more effective and efficient to address food insecurity and the risk of famine than direct food donations or vouchers.

Yemen has one of the largest humanitarian cash responses in the world. It has grown over recent years, following a global trend. By the end of 2020, three United Nations Agencies, 13 International Non-Governmental Organisations (INGOs), and 12 National NGOs (NNGOs) implemented cash and voucher programmes assisting 4.3 million people across the country to address their food needs.This is part of a broader cash programming landscape that addresses a variety of humanitarian needs beyond food security alone.
[note] In 2016, Yemen had the 5th largest humanitarian cash response, representing 4% of the total humanitarian cash assistance provided worldwide. Source: Counting Cash: tracking humanitarian expenditure on cash-based programming, ODI, Development initiatives, 2016, link here.
[note] At global level, cash and voucher assistance has grown in volume (reaching US$5.6 billion in 2019, from $ 2 billion in 2015) and as a percentage of international humanitarian assistance (17.9 % in 2019, up from 7.9 % in 2015); Source: The State of the World’s Cash 2020, cash and voucher assistance in humanitarian ais, The Cash Learning Partnership, 2020, link here.
[note] https://fscluster.org/sites/default/files/documents/cva_dashboard_oct_2020.pdf
[note] Yemen Cash and Voucher Assistance Snapshot (January - September 2020) [EN] | Humanitarian Response

Global and Yemen specific evidence on cash transfers is compelling on their benefits to address food insecurity and the risk of famine. They are an FCDO Chief Economists Office “Great Buy” and are good value for money (more details in Annex 1).

Cash transfers are an effective tool to support food security. Recipients mostly use cash transfers to buy food, meet basic needs (medicines, school costs) and repay debts. The flexibility in their use would be hard to match with in-kind assistance. Monitoring shows that transfers need to be of sufficient size to help the most food insecure people achieve minimum levels of food security and protect their coping strategies.
[note] People receiving food assistance have better food security outcomes than non-assisted households, Source: WFP Yemen | Food Security and Price Monitoring, mid-September 2020..Evidence on comparative effect of different modalities (in-kind, vouchers and cash) is emerging A comparison over three months shows cash can have greater food security outcomes than vouchers or in-kind, but with variations over time. Evidence gathered remains insufficient. Source: WFP Yemen, Monitoring and evaluation Quarterly Report, April – June 2020.
[note] Around 82%of the Emergency Cash Transfer (ECTP) and around 90% of the WFP cash transfer are spent on food, Source FCDO Third Party Monitoring of YeSP and WFP programmes.
[note] WFP monitoring.

Cash transfers in Yemen are highly efficient due to their large coverage. They can be implemented at scale, including in hard to reach areas thanks to a strong infrastructure of financial services and resilient market systems.

Cash transfers have wider benefits. They support the economy and local markets to operate, strengthen, and recover. In Yemen, as in most contexts, satisfaction rates with cash transfers are extremely high (99%) amongst recipient communities as they empower households to meet their specific needs. They can help address Gender Based Violence and the economic pressures that drive most significant protection risks in Yemen, including displacement, child labour, child marriage, recruitment into armed groups, eviction, or accessing health and education services.
[note] UNICEF – FCDO Donor Report on ECT, 15 Feb 2021, Inter-agency joint cash study: Market functionality and community perception of cash-based assistance. Cash and Markets Working Group and REACH, 2017, link here.
[note] Collected papers on gender and cash transfer programmes in humanitarian contexts, compiled by the Cash and Learning Partnership, 2018, Link here.

Cash transfers can have longer-term impacts over time . Regular and predictable cash transfers can help build resilience of poor and vulnerable people protecting them from the impacts of shocks, including the erosion of productive assets, and minimising negative coping practices. They can facilitate livelihood investments that build resilience to future shocks or crises (e.g. petty trading or purchase of small productive assets like small animals).
[note] Understanding the impact of cash transfers: the evidence, Jessica Hagen-Zanker, Francesca Bastagli, Luke Harman, Valentina Barca, Georgina Sturge and Tanja Schmidt, Briefing, ODI, 2016, link here.
[note] Social protection in protracted crises, humanitarian and fragile contexts, FAO, 2016, link here.

Emerging evidence in Yemen shows that Cash for Work can (i) enhance and protect Yemen’s human capital potential through the acquisition of skills; (ii) increase social capital and strengthen community cohesion; (iii) restore access to basic services, and thereby reduce time to access markets, water, healthcare, and reduce the burden on households (particularly female headed households and those with people with disabilities).
[note] FCDO Yemen IMEDA Third Party Monitoring reports – SFD, and indicative findings from IMEDA Impact Evaluation – SFD Cash for Work

There is no evidence that cash transfers are more prone to theft, diversion and corruption than direct food aid. Evidence shows that people spend cash on what they need most and that cash transfers can ‘be less risky than other, more traditional forms of aid spending’ with regards to ‘waste and fraud’. Humanitarian actors in Yemen are largely able to mitigate the risks of cash programming, despite substantial operational and contextual challenges.
[note] Public Accounts Committee (2012), Sixty-Fifth Report, DFID transferring cash and assets to the poor, link here.
[note] CTP in challenging contexts: case study on CTP and risks in Yemen 2015-2018, CaLP case Study, Cash and Learning Partnership, link here.

While there is clear evidence that cash transfers work in Yemen, and a growing body of evidence on the specific benefits and challenges of specific cash interventions, there is a need for greater investment in impact monitoring and evaluations, that also allows comparing the impact and VfM of different cash interventions.
[note] Secondary desk review of cash and markets data for Yemen. REACH and CMWG, 2019, link here.

FCDO response to date

The UK will use its solid understanding of cash programming in Yemen and strong relationships with the key cash actors to help build a more effective and efficient response to food insecurity. To maximise impact and better incentivise cash reform, this programme will bring together humanitarian and social protection interventions currently funded under three FCDO programmes and build on learning to date (details in Annex 2):

1. The World Food Programme (WFP)
2. The Yemen Social Protection Programme (YeSP), delivered by:
1. Yemen Social Fund for Development (SFD)
2. UNICEF/World Bank Emergency Cash Transfer Programme (ECTP)
The Yemen Multisector Humanitarian Response Programme (MHRP) delivered by a consortium of NGOs.

Table 1: Headline results over past years for FCDO funded WFP, YeSP and MHRP programmes.

Results: / Number of people reached with cash programming funded by UK	2018	2019	2020
MHRP	Cash to approx. 2,053,366 people / (over the period 1 January – 31 December 2018)	Cash and voucher to approx. 4,520,327 people / (over the period 1 January 2019 – 31 March 2020)	Cash transfers to approx. 175,000 people / (over the period 1 April 2020 – 31 December 2020)
WFP	Vouchers to up to 760,000 people per month	Cash to up to 567,000 people per month / Vouchers to 1,900,000 people in July to cover gap in funding	Cash to up to 661,000 people per month
YeSP	N/A	ECTP cash to 1,410,472 people per month** / SFD* Cash for Work to 7,834 people over the year	ECTP cash to 1,435,529 people per month** / SFD* Cash for Work to 5,450 people over the year / SFD Cash for Nutrition to 23,118 people over the year
[note] Lower than previous years due to delays in starting extension phase of programme. Numbers will be verified during PCR.
[note] Activities during 2020 predominantly focused on start-up activities for programme extension period with partners as well as beneficiary identification and verification. Nutrition and WASH activities were stopped.

*Funding to SFD’s Crisis Response Plan under YeSP is unearmarked and supports a wide range of activities. We have only included cash results attributable to FCDO funding (calculated at 9% of total results for 2019 and 14.2% for 2020).
** The transfer is made quarterly.

Throughout their lifespan, the WFP, YeSP and MHRP programmes have delivered well on their objectives and on UK priorities as shown by Annual Review ratings and audit results. Where improvements were needed, those were captured in Annual Reviews and acted upon, leading subsequently to better results. This programme will continue building on our learning to date on our key partners and their cash interventions, reinforcing their strengths and supporting them in addressing their weaknesses.

Table 2: Annual Reviews (AR) Scores

AR scores	2018	2019	2020
MHRP	B	A	A
WFP	A	B	A
YeSP	A*	B	A

*From PCR for the previous phase “SFD Phase IV”.

WFP

WFP and its NGO partners deliver one of the largest cash humanitarian programmes in Yemen, providing ‘access to life saving, safe and nutritious food all year to food insecure people affected by crises across Yemen’. UK funding and active engagement is supporting WFP in strengthening their approach to prioritisation, targeting, risk reporting (in particular aid diversion and safeguarding), and monitoring impact (especially on vulnerable groups and disaggregated by modality). This has helped WFP to better manage risk, which includes biometric registrations for the delivery of cash programmes.
[note] In 2021, WFP plans to provide food assistance to over 12 million severely food insecure people through food packages, vouchers and cash transfers. Among them, WFP intends to deliver cash transfers to up to 3.2 million people, increasing from over 600,000 recipients in 2020

MHRP

INGOs and NNGOs deliver a large part of the humanitarian response in Yemen, including cash programming. The UK’s work with NGOs has targeted higher risk areas, given us more granular contextual detail, and led NGOs to apply higher standards of targeting, verification, and monitoring. This also improves our ability to hold larger partners to account. The current phase of the MHRP already builds on significant learning from the prior two phases, streamlining the programme to deliver primarily unconditional cash (demonstrated to have the greatest measurable impact on immediate food security outcomes). We continue to work with NGO partners on targeting methodologies and inclusion issues, financial management, and flexibility and adaptation to changing contexts and new needs.
[note] They perform key functions of WFP programming (beneficiary targeting, verification and much of the monitoring) which helps improve accountability of large UN agencies like WFP. They also deliver their own cash programmes, at increasing scale (e.g. cash components of the Rapid Response Mechanism). Under the coordination of the FSAC, WFP and NGOs aim to reach the whole FSAC caseload for food and cash assistance (12.7 million people in 2021), with harmonised transfer values and eligibility criteria, while avoiding duplications.

YeSP

Only two national social protection institutions continue to operate in Yemen today:

Yemen’s Social Fund for Development (SFD), established in 1997 under Yemeni law, is a quasi-governmental organisation that has a strong reputation for independence and neutrality. SFD’s work improves poor communities’ access to basic social services (education, water, health, rural roads), enhances economic opportunities, and reduces the vulnerability of the poor. SFD is a community-led development organisation supporting Yemen’s poorest and most vulnerable people with cash-based safety nets, restoration and improved access to basic services and assets (e.g. clinics, schools, water points), and economic development opportunities (e.g. through access to microfinance).

Yemen’s Social Welfare Fund (SWF) was established in 1996 through Yemeni Social Welfare Law. Until 2015, it was primarily financed by the GoY (plus a small number of donors) to provide quarterly, unconditional cash transfers to some of the country’s most vulnerable households. This was a remarkable achievement given scarce government resources. However, both the GoY and donor funding stopped when the conflict escalated. In 2017, the World Bank set up the Emergency Cash Transfer Programme (ECTP) to continue to provide quarterly cash transfers outside of the GoY systems to up to nine million poor and vulnerable people on SWF’s beneficiary list, in partnership with UNICEF. The World Bank is strengthening the ECTP and seeking to transition delivery of the cash transfers from UNICEF to SFD as an interim measure to further strengthen national institutional capacity.

UK funding and engagement has supported improvements to the ECTP, for example by topping up transfer values and better measuring the impact it has. For example, FCDO funded cash top-ups have been provided in 2020 and 2021 to address the secondary impacts of COVID-19. FCDO have also supported SFD to review its targeting strategy and develop an action plan to improve its monitoring and evaluation systems, and we continue to work with the World Bank/UNICEF and SFD to ensure better complementarity of their cash programming. FCDO manages these programmes remotely as its teams are not able to be based in Yemen and uses Third Party Monitoring to assess progress and quality, understand impact and extract learning across programmes.

WHAT FCDO WILL DO

The Food Security Safety Net programme will deliver cash assistance to up to 1.5 million of the most severely food insecure households in Yemen on an annual basis, immediately alleviating critical humanitarian need amongst conflict-affected people. This will:

  1. Reduce the risk of famine (Problem A) by ensuring Yemen’s most food insecure and vulnerable households receive regular, predictable cash transfers that help them cover most essential needs, reducing their reliance on negative coping strategies (such as reducing food intake, selling assets, resorting to child labour or marriage, joining armed groups, and displacement) to address food insecurity in the immediate as well as medium and longer-term.

  1. Incentivise reform of cash-based responses to food insecurity in Yemen (Problem B) to build a holistic and coherent response that includes humanitarian and development actors along with national social protection institutions, as a better way of ensuring that aid is more sustainably distributed at scale, meets the needs of the most vulnerable and has the greatest impact. The package of cost effective and mutually reinforcing assistance to the most food insecure and vulnerable people in Yemen will promote household and community resilience and, over time, reduce the number of people in extreme need of humanitarian assistance.

This programme will contribute to delivering the vision of a coherent Yemen humanitarian response, by funding humanitarian and social protection interventions and promoting coherence between them. The expected impact and outcomes of the programme are:

Impact: Reduced humanitarian need in Yemen.

Outcomes:

    1. The most food insecure and vulnerable Yemenis can address their food and basic needs, reducing famine risk and food insecurity.
    2. The response to food insecurity is more effective, efficient, and sustainable.

Beyond the lifetime of this programme, the long-term vision for addressing food insecurity is a nationally owned and financed social protection system. The pathway to this long-term vision is one starting with harmonisation and complementarity between humanitarian cash and social protection interventions, with humanitarian assistance building blocks for the future national system.
[note] Until greater governance stability is reached, analysts argue that it is not desirable to transition directly to a nationally owned system, but to continue investing in a parallel humanitarian system while reinforcing the national social protection programmes. Yemen – Linking Humanitarian cash and social protection (Phase II report), Ric Goodman, Christina Frey, Zakee Ahmed, Rachael Steller, Adnan Qatinah, DAI, funded by BASIC (Better Assistance in Crises), FCDO. October 2019.
Even before the conflict Yemen’s economic and human development indicators were amongst the worst in the world, a return to the pre-conflict state is thus not sufficient. As social protection (including responding to shocks), building resilience and disaster management are ultimately a function of government, the vision of a strengthened government owned and financed social protection system should be the means to address the risk of famine. In the Yemen context, this will however require a number of preliminary steps and take time. This programme will contribute to this vision while recognising that it will take longer than its duration.

Humanitarian aid will remain essential for the foreseeable future, until there is a viable means of delivering development-style support in financial partnership with Yemeni institutions. While harmonisation is important, strategic investments should be directed to building a future national system capable of replacing humanitarian aid. This will mean investing in humanitarian systems that can be coherent with, transition into, or provide the building blocks for future national systems.

This vision entails bringing together existing humanitarian and social protection cash interventions into a coherent Yemen cash response to food insecurity that is more effective, efficient and sustainable because it:

1. Delivers at scale and reaches more people in need.
2. Optimises impact and VfM, avoiding duplications and optimising complementarities.
3. Provides adequate and equitable cash transfers with appropriate layering of cash interventions (higher-value cash transfers to those most in need and lower values to protect and build resilience of the poorest).
4. Empowers the most food insecure and vulnerable through coordinated Accountability to Affected Populations (AAP) systems and beneficiary feedback mechanisms.
5. Ensures timely and quality assessments of needs and context.
6. Measures outcomes to understand impact across cash interventions, also contributing to strengthen the evidence base on how cash interventions deliver food security and resilience in Yemen.
7. Is shock responsive by flexing to the depth of needs and to new shocks.
8. Supports stability and future governance, by strengthening national capacity and supporting the development of a nationally owned and financed social protection system over the longer-term.

The first steps towards a sustainable and nationally owned system require a focus on the six priority areas of the Cash and Social Protection Donor Working Group workplan. These include: 1) adequacy and equitability (harmonisation of cash transfers); 2) targeting the vulnerable (common identification and targeting approaches); 3) value for money (complementarity of coverage); 4) accountability (common feedback mechanisms); 5) measurability (common measurement of results); 6) sustainability (multi-year funding; and linkages to livelihoods programming).

There is no single or linear pathway to building a national shock-responsive social protection system. While global learning and evidence on how to build shock responsive systems in crises are emerging, additional capacity and expertise among national and international partners is required . In a context of conflict, with two sets of authorities (GoY and De Facto Authorities) and a breakdown of public institutions and services, the roadmap for each priority area will need to continuously adapt to the political economy. To provide such ground truthing and real-time data and insights on the ever-changing political reality in Yemen, technical assistance will be critical as part of this programme to support FCDO and partners in designing and implementing the practical steps of the transition to this more sustainable and cost-effective system for reducing food insecurity.
[note] The state of the world’s cash 2020, cash and voucher assistance in humanitarian aid, The Cash Learning Partnership, July 2020, link here.
[note] Shock-Responsive Social Protection Systems research: Synthesis report, O'Brien, C., Scott, Z., Smith, G., Barca V., Kardan, A., Holmes, R., Watson, C. and Congrave, J., Oxford Policy Management, Oxford, UK, 2018, link here; Identifying practical options for linking humanitarian assistance and social protection in the COVID-19 response, Daniel Longhurst and Gabrielle Smith, with Valentina Barca, Karin Seyfert, Simon Little, Calum McLean, Sophie Pongracz, and experts on the Social Protection Approaches to COVID-19 expert advice helpline (SPACE), September 2020, link here.

This programme will have a strong focus on Accountability to Affected Populations (AAP), both ensuring that beneficiaries are engaged in the programme and that AAP systems are strengthened. AAP is notably weak across the humanitarian response in Yemen. Cash reform efforts provide a key opportunity to ensure analysis of food insecurity is informed by Yemeni voices and programmes have strong beneficiary feedback and grievance redressal mechanisms in place to drive accountability and improve programme engagement and effectiveness.

This programme will adopt a flexible approach to ensure that the modality can be adapted to the context (e.g. flexing from cash to vouchers and/or food in-kind if markets do not function any more) and can respond to emerging evidence on what works to support longer-term impact. This will be supported by a technical facility that will help FCDO identify when context changes or evidence warrant adaptations of interventions.

This programme will also adapt to the context the balance between its support to saving lives and reducing future famine risk. In the current context of live famine risk, for the first year of the programme, a greater proportion of results and budget will be allocated to saving lives while still investing in reducing future famine risk to prevent further increase of humanitarian need. For following years, the balance will be revisited based on the context.

WHY SHOULD THE UK INTERVENE?

Strategic fit with UK and Yemen priorities

This programme will directly contribute to key FCDO and HMG strategic objectives, including the UK's enduring responsibility to respond to humanitarian crises. In line with the UK Aid Strategy objective of “Strengthening resilience and response to crises” , the UK Foreign Secretary’s priority on ‘Humanitarian preparedness and response’’ and the UK’s Humanitarian Reform Strategy, this programme will improve the humanitarian situation in Yemen whilst driving a greater focus on strengthening resilience of the poorest and building systems for long-term development financing.
[note] Letter from the UK Foreign Secretary to the International Development Committee stating seven global challenges that UK aid will be focused on: Letter from the Foreign Secretary regarding the future of the UK aid budget (parliament.uk). Statement made by the UK Foreign Secretary on 26 January 2021. Written statements - Written questions, answers and statements - UK Parliament.

The programme reflects global priorities identified in the 2016 World Humanitarian Summit, the Grand Bargain and Wilton Park principles. The focus on cash programming and linking humanitarian cash and social protection is a direct application of the Grand Bargain and contributes to DFID’s commitment to double the volume of humanitarian cash assistance delivered by 2025.

It responds to the Humanitarian and Development pillars of UK NSC strategy for Yemen: alleviating the world’s largest humanitarian crisis and building Yemen's economic resilience and institutional capacity. This programme will play a central role in delivering the second campaign goal of the Yemen Country Business Plan 2021-2022: Alleviate Humanitarian crisis – A well targeted and funded humanitarian response that prevents famine, saves lives, respects humanitarian principles, protects civilians and reduces future need. It will also deliver on the fourth campaign goal: ‘Support Institutional resilience – protect services and Yemeni institutions, prepare for stabilisation and recovery’.

This programme contributes to streamlining the FCDO Yemen portfolio and will be delivered in complementarity with other Yemen FCDO programmes (on-going or in the pipeline), in particular nutrition, protection, economy, security and stabilisation, and monitoring and evaluation.

FCDO comparative advantage, capacity, and partnerships

The UK is one of the largest donors to the Yemen humanitarian and development response, providing over £1 billion since the conflict began. This has also secured considerable influence. The UK has played a key role in combatting hunger and the risk of famine in Yemen over the past years: in 2020/2021, it allocated around 60% of its funding to addressing food insecurity in Yemen.
[note] The UK remains a large donor in Yemen, being the 5th largest bilateral donor in 2021.

FCDO Yemen can rely on the UK’s global leadership on humanitarian programming and on linking humanitarian cash and social protection. FCDO’s greatest area of value-added is its ability to work effectively across humanitarian and development sectors, less constrained by institutional and financial siloes than other donors and agencies which split these. Our added value also resides in our substantial humanitarian and social protection expertise and investments both in Yemen and at global levels, our experience in delivering technical assistance, our reputation for thought leadership and global influence in both these areas, and our experience in building the evidence of what works and using it to inform policy and programming. FCDO is the third largest bilateral humanitarian donor at global level (as of financial year 2020/2021), with a global reputation for thought leadership - including on humanitarian cash, reform, and multi-year humanitarian approaches. FCDO is one of the largest donors of humanitarian cash programmes, and a major social protection donor, especially social assistance (currently supporting 25 countries in Africa, Asia and the Middle East and North Africa).
[note] The UK was the third largest for humanitarian cash-based programming in 2015. Source: Counting Cash: tracking humanitarian expenditure on cash-based programming, ODI, Development initiatives, 2016, link here.

The UK is uniquely placed to promote the reform that will lead to a coherent cash response in Yemen. It has long-standing and influential partnerships with the World Bank and the main bilateral donors, UN agencies and INGOs who fund and deliver cash and social protection interventions in Yemen. FCDO Yemen has been promoting reform through its existing programmes and its funding to WFP since 2010, SFD (part of the current YeSP programme) since 2004, the World Bank/UNICEF ECTP since 2018, and NGOs (currently supported through the MHRP) since 2014.

FCDO has demonstrated its leadership on cash programming and reform in Yemen:

1. The UK plays a key role in cash coordination in Yemen. As well as being an active member of the Cash and Markets Working Group (CMWG), the UK has funded the cash coordinator position since 2017. This investment has delivered tangible progress towards cash reform, through tools harmonisation (starting within the humanitarian sector) and prioritising coordination with social protection actors
  [note] Yemen Humanitarian Response plan 2021, link here.
2. The UK was instrumental in establishing the Cash and Social Protection Donor Working Group in 2020, which we currently co-lead with ECHO and the World Bank. A common vision and workplan set in 2020 will guide collective donor efforts from 2021.
3. Through its bilateral funding and relations, the UK has played a key role in promoting cash programming and supported continuous improvement of standards and quality.

This is the right time to push for greater coherence among cash interventions as our partners increase their ambition on cash programming:
1. By funding and supporting the ECTP, the World Bank aims to preserve the SWF as the national social protection mechanism, at least partially affordable by a government treasury, under appropriate future conditions.
2. WFP intends to increase its cash programming coverage in 2021 through the roll-out of biometric registrations in more areas of the country. This is in line with the Food Security and Agriculture Cluster ambition to scale up the use of cash.
3. The UN has recognised the need to seek complementarities, synergies and greater cost effectiveness through the UN Common Cash Statement (a statement from the Principals of OCHA, UNHCR, WFP and UNICEF in December 2018), for which Yemen is a pilot country.
  [note] Statement from the Principals of OCHA, UNHCR, WFP and UNICEF on Cash Assistance, 5 December 2018, link here.

Combining its development and diplomatic influence gives the UK a unique opportunity to promote reform and deliver greater impact. For example, we will use our existing relationships with Gulf donors (Saudi Arabia, UAE and Kuwait) to encourage them to support the joint donor cash vision. Combined UK development and diplomatic efforts will remain key in pushing for greater humanitarian access and economic stabilisation, supporting the delivery of this and other life-saving programmes.

We will be working with and leveraging the support from FCDO’s central programmes: Better Assistance In Crises (BASIC), Gender Responsive Social Protection (GRSP), Social Protection Approaches to COVID-19 (SPACE) and the regional climate programme (PHENOMENAL) to ensure the programme draws on global best practice. The programme will benefit from BASIC research, a two-year research project, aiming to establish what works in Yemen to address food insecurity and build resilience through cash programming. Yemen is an FCDO resilience pilot: this programme will receive central support from FCDO Conflict, Humanitarian and Security Department (CHASE) to test innovative approaches to building resilience, and in return it will feed into learning across FCDO on good practice and policy for resilience building in crisis contexts.

Compliance with relevant legislation

Compliance with the International Development (Gender Equality) Act 2014 and Public Sector Equality Act, and Disability Inclusion

This programme will have a significant impact on gender equality and be designed in line with the International Development (Gender Equality) Act 2014. It will also comply with Public Sector Equality Act (2010) by ensuring equality of opportunity irrespective of, for example, age or disability.

The gender-related differences in needs of those affected are at the core of the design of this programme. It recognises that women and girls in Yemen are more affected by food insecurity and poverty, with challenges to access the same opportunities as men and boys and higher exposure to violence and discrimination. In targeting the most food insecure and vulnerable, the programme will automatically target women who are most in need. All the interventions this programme considers supporting prioritise vulnerable women among their targeting criteria (women headed-households, pregnant and lactating women, etc). This is reflected in the substantial proportion of women among their beneficiaries (see Annex 3).

The GoY’s 2013 Demographic and Health Survey, published in 2015, found that 3.6% of the population, had some form of disability. This is likely underestimated: survey responses were not verified by medical diagnosis, and global data suggests prevalence of disability to be around 15-20% and much higher in conflict/post-conflict states. An estimated 6,000 people have been left with disabilities – most as a result of a blast, mine, or gunshot.

We will ensure our partners have appropriate responses, in compliance with the International Development (Gender Equality) Act 2014 and the Public Sector Equality Act (2010). All partners will collect and analyse data disaggregated according to age and gender in order to provide quality analysis and evidence to inform targeted interventions. Monitoring and research will bring particular attention to the gender dimensions of cash programming and how cash transfers benefit or not different gender groups and gender dynamics. We will ensure the relevant delivery and accountability mechanisms are gender-sensitive, so that services are effectively delivered to women and their feedback is considered. For example, Cash for Work activities will be adapted to the needs of women (activities designed specifically for women, taking into account childcare requirements). We will ensure partners employ female staff as relevant so that they can effectively engage with female beneficiaries, and that accountability mechanisms are set up to ensure that women have safe spaces to provide feedback.

We will work with partners so that that they include disability in their vulnerability targeting criteria, use the Washington Group questions when identifying people with disabilities, and disaggregate data on key indicators where the benefits are delivered at individual or possibly household level. In line with the 2020-2023 Yemen Gender Strategy, the programme will mainstream gender and disability through gender and social exclusion analysis during procurement, in project design and its results framework.

Compliance with Safeguarding Commitments

In avoiding doing harm, FCDO Yemen will ensure that interventions do not sustain unequal power relations, reinforce social exclusion and predatory institutions, exacerbate conflict, contribute to human rights risks, create or exacerbate resource scarcity, climate change and/or environmental damage, or increase communities’ vulnerabilities to shocks and trends. An Enhanced Due Diligence Assessment will be conducted on all partners. This will ensure they have robust policies and procedures as well as reporting systems in place that protect beneficiaries against sexual exploitation and abuse by humanitarian workers. The needs of women and girls will be particularly considered, ensuring they can collect cash safely. We will ensure partners have a safe reporting mechanism in place for beneficiaries and others to report any allegations/suspicions of abuse. We will work with partners to ensure they strengthen policies where appropriate. Partner agreements will include a narrative setting out FCDO expectations regarding safeguarding considerations.

Compliance with Terrorist Financing Legislation

There is a risk of terrorism and terrorist financing as terrorist groups including Al-Qaeda in the Arab Peninsula (AQAP) and Daesh-Yemen are active in Yemen. It is the policy of FCDO to ensure that no UK taxpayer funds are used to support individuals or entities associated with terrorism. All FCDO partners will be required to make themselves aware of and to comply with the relevant counter terrorist financing legislation. Due diligence and delivery chain mapping will be undertaken on all partners to reduce risk and provide further assurance over the use of UK funds.

FCDO will ensure that the selected partners for this programme have robust policies and monitoring systems to detect, report and mitigate the risks. The enhanced controls (see sections D and E) put in place by FCDO Yemen provide assurance that every effort will be made to ensure UK funding does not reach individuals or entities associated with terrorism.

Conflict Sensitivity

We will work with partners to ensure steps are taken to address conflict sensitivity. There are significant conflict sensitivity challenges associated with delivering programmes of this scale in Yemen and particular risks linked to the politicisation of beneficiary targeting and the diversion of assistance. The de facto authorities have allegedly sought to exert a high level of control over the distribution of food assistance, for example by attempting to subvert WFP beneficiary targeting and seeking to redirect assistance to the front line. There are risks that the de facto authorities will seek to strong arm WFP-managed community committees tasked with compiling village-level beneficiary lists. Conflict sensitivity concerns have prevented the update of the SWF single beneficiary list (ECTP recipients) since the start of the conflict, with the risk of assistance becoming increasingly poorly targeted. In all locations, the question of who is and is not eligible for assistance can prove divisive, and feed into existing conflict dynamics at the local level.

The programme offers an opportunity to act strategically to positively influence conflict dynamics, by bringing cash transfer programmes together and taking a more coherent, long-term approach. These risks and opportunities will be explored in more detail during the mobilisation phase of the programme and mitigated through the establishment of ongoing mechanisms for monitoring and responding to emerging conflict issues (for example, since 2019, WFP has implemented a roadmap to mitigate and manage diversion risks and its delivery is an output in the FCDO funded WFP programme logframe).

Climate Change and Environmental Sustainability

Climate change and environmental factors contribute to Yemen’s humanitarian crisis in multiple ways, compounding the current risk of famine. Domestic agricultural production and in country availability of wheat and cereals - which are dependent on international markets and production – are vulnerable to climate change. The UK’s 2020 Joint Analysis of Conflict and Stability for Yemen identified that competition for natural resources acts as a key conflict driver.
[note] According to a 2020 Climate and Disaster Risk Screening by the World Bank, Yemen is projected to face intensified periods of drought and uncontrollable flooding throughout the year. Whilst Yemen imports 90% of its food, agriculture remains a major contributor to livelihoods and GDP. Both drought and floods have contributed to diminishing domestic crop yields and damaged infrastructure – with up to 5% of arable land lost every year. Yemen’s water availability per capita is the lowest in the world and groundwater aquifers are declining by one to seven meters each year. If water resources continue to deplete then Yemen's agricultural productivity is expected to reduce by up to 40%. Whilst the landscape is complex, these hazards pose a significant threat to Yemen becoming a self-sustainable country, even after a peace agreement is reached.
[note] Yemen is highly vulnerable to future climate change impacts at the global level. By some estimates, up to 60% of current wheat-growing areas worldwide could see simultaneous and prolonged droughts in coming decades. Given its high dependency on food imports, any downturn in global wheat production and subsequent rise in prices would hit Yemen hard

By providing cash transfers of a sufficient value to the most food insecure, this programme will ensure that people can afford the food they need (the cost of which is defined by international markets). UK funding is provided to partners in British pound sterling which allows an alignment of the transfer value with the cost of food, given the exchange rate and food prices have followed similar evolutions. The UK supports the work of the Yemen CMWG which leads in updating the value of cash transfers when inflation has eroded dangerously the amount of food people can afford.

This programme will be delivered with full consideration of climate change and environmental sustainability, including alignment with the Paris Agreement. During the design and mobilisation phases, and when new interventions are considered, we will undertake a climate risk assessment to determine whether a) the programme might exacerbate or reduce the impacts on people from a changing climate, and b) its objectives can be achieved taking into account likely climate variability and change. Appropriate climate indicators will be included in the results framework (e.g. to measure improved climate resilience). When supporting activities with an agricultural or environmental dimension (e.g. some Cash for Work activities), this programme will do so in an environmentally sustainable way: building back greener, not exacerbating water scarcity, exploring climate-smart crops, and using resources sustainably.

This programme offers an opportunity to act strategically to positively influence Yemen’s climate resilience. By strengthening Yemen’s social protection system, this programme will lay the foundation for a more holistic mechanism in future years that responds to climatic shocks, bolstering the recovery and resilience of affected communities. Cash transfers to bring wider resilience benefits could be explored further in outer years with support from the regional FCDO climate programme PHENOMENAL.

## B. Appraisal Case

In this section we will evaluate three different options for delivery of cash transfers to food insecure households in Yemen to achieve the programme objectives (i. Save lives and reduce the risk of famine; ii. Incentivise reform of cash-based responses to food insecurity in Yemen). A greater emphasis will be placed on objective i, as set out in the programme selection criteria in table 3. Given the current context of high famine risk in Yemen, the first year of the programme will allocate twice as much of the programme budget and results on life-saving outputs compared to preventative outputs. For the following years this balance will be revised to reflect the changing context and level of humanitarian need.

It is clear from the Strategic Case that addressing the current lack of coordination between delivery partners providing cash assistance in a context such as Yemen where the political economy is complex and changing, will require concerted capacity and expertise in order to sufficiently incentivise reform through UK funding of cash transfer programmes. Alongside the selected option for delivery of cash transfers, the programme will therefore also fund a Technical Assistance Facility (TAF) to provide support to delivery partners, donors and the FCDO Yemen programme team with the specialist skills, expertise and knowledge to deliver the six priority areas of the Cash and Social Protection Donor Working Group cash reform action plan (see paragraph 39) and ensure the programme delivers on its long term vision of a sustainable and nationally owned social protection system. Given the lack of FCDO staff presence on the ground in Yemen, and the significant data gaps evident, this facility will play a critical function in ramping up UK influence on responding to famine risk and food insecurity and strengthening the evidence base for more effective and cost-efficient programming in the future. An appraisal of the TAF is included in paragraphs 96 - 98 and detailed further in paragraph 207 of the Management Case.

SUMMARY OF APPRAISAL OPTIONS

The three appraisal options have been measured against the counterfactual of not allocating funding to address food insecurity in Yemen. The three options that are appraised are delivery of cash-based assistance by:

International humanitarian agencies

National Yemeni institutions

Both international humanitarian agencies and national Yemeni institutions

Option A. International humanitarian agencies

Finance UN agencies and NGOs delivering monthly Emergency Food Assistance cash transfers. This option would enable us to target assistance to the most food insecure households, including in hard to reach areas accessed by NGOs, and ensure they receive a value of cash that enables them to meet their minimum food consumption needs each month. Due to the higher value of cash transfers this option would however reach fewer households overall. Administration costs of UN and NGO international humanitarian agencies are also comparatively higher and they are not a sustainable long-term solution.

Option B. National Yemeni institutions

Finance national Yemeni institutions delivering multiple cash-based projects to support the most vulnerable and food insecure households. This includes support to Cash for Work projects (providing temporary income and vocational training opportunities), Cash for Nutrition projects (providing women with cash transfers and nutrition awareness sessions), and top-up support to the Emergency Cash Transfer Programme (a quarterly cash transfer supporting beneficiaries of Yemen’s Social Welfare Fund). This option would provide varying values of cash transfers, from larger transfers to meet households’ urgent basic needs, including food, to providing smaller contributions to protect households at risk of falling into extreme food insecurity. It would reach more people in need but target fewer of the most food insecure households with a higher value of cash that is sufficient to meet their basic needs in comparison to option A.

Option C. Both international humanitarian agencies and national Yemeni institutions

Provide financing to UN agencies, NGOs and national Yemeni institutions to support all forms of cash-based assistance outlined in the two options above. The allocation of funding to delivery partners will be determined during the mobilisation phase and informed by technical expertise from the TAF. Year one of the programme will however allocate a greater proportion of budget and results to life-saving rather than preventative interventions given the current live famine risk. This option would capitalise on the strengths of the humanitarian system in delivering cash promptly to those that need it most, whilst strengthening national systems and continuing to support households at risk of becoming food insecure in the future.

Counterfactual: No FCDO funding allocated to food security response

A cessation or sharp reduction in FCDO funding to address food insecurity in Yemen will exacerbate an already dire humanitarian crisis and have fatal consequences, and it is unlikely that other donors will have capacity to increase funding to compensate for any reductions made by FCDO. It will also undermine the investments made through the current WFP, MHRP and YeSP programmes, and compromise the strong partnerships that FCDO has built with the World Bank, humanitarian agencies and national Yemeni institutions. Such a decision would also have implications for the UK’s diplomatic and political stance, running counter to the UK’s global leadership on famine prevention and domestic and global policy commitments which focus on responding to vulnerability where it is greatest.

SUMMARY OF SELECTION CRITERIA

Three selection criteria for appraising the programme options have been identified that align with programme outcomes. The weighting for these selection criteria assumes that the full amount of funding is available each year for delivery of the programme and reflects the relative priority of each criteria. Add line about assessing against different funding scenarios.

Table 3: Programme selection criteria

Programme Selection Criteria		Weighting
1	Save lives. Cash-based assistance is provided to the most food insecure households to save lives. The response is timely, maximises value for money, and effectively manages risk to reduce existing high levels of food insecurity.	50
2	Reduce future famine risk. Cash-based assistance builds resilience and coping capacity of households and communities to address root causes of food insecurity and mitigate future famine risk.	25
3	Improve food security response. Cash reform is incentivised, improving the efficiency, effectiveness and sustainability of cash assistance. Progress is made towards a future nationally owned shock-responsive cash-assistance system that supports chronically food insecure households and can respond to spikes in need.	25

REVIEW OF HOW WELL EACH SELECTION CRITERIA IS ACHIEVED THROUGH 3 OPTIONS

Selection Criteria 1: Save lives - Cash-based assistance is provided to the most food insecure households to save lives. The response is timely, maximises value for money, and effectively manages risk to reduce existing high levels of food insecurity.

OPTION A – International humanitarian agencies

This option specifically targets the most food insecure households with unconditional cash transfers aligned with Minimum Food Basket values, guaranteeing that these households can purchase the amount of food they need and saving lives. International humanitarian agencies ensure cash reaches those most at risk of starvation by targeting assistance geographically according to food security indicators then working with affected communities and local leaders to identify those most in need... There is strong evidence that such unconditional cash transfers are successful in addressing food security in contexts such as Yemen (and they rated by the former DFID Chief Economist as a “great buy” as outlined in the Strategic Case).

Supporting both UN agencies and NGOs in this option is critical for getting UK Aid to the most hard to reach, risk diversification, and accountability. This has been demonstrated by our existing programmes. For example UN agencies such as WFP are able to distribute cash at scale and rapidly respond to unforeseen spikes in need including meeting needs of newly vulnerable or displaced populations., While WFP relations with the authorities are generally good, there have been times when they have been unable to access certain areas, or have not been permitted to implement key changes such as retargeting because of the high visibility and political value of their assistance. Having multiple delivery channels allows us to flex quickly in case of problems with any single channel, and NGOs play an invaluable role in ensuring cash support is accessed by hard to reach communities. NGOs also have a presence where they are delivering assistance and interact directly with the affected populations, which UN agencies including WFP largely do not have. This provides a very valuable channel of information, ground truthing and holding UN agencies to account. NGOs are able to play this role more effectively where they have some independent funding, and when they are our bilateral partners they provide FCDO with more regular and frank information than would otherwise be the case, which has great value in our broader contextual understanding and our ability to effectively influence the humanitarian response in Yemen.

Funding humanitarian institutions to respond to food security is pivotal to FCDO Yemen policy work and UK influence and engagement with the wider response, particularly given the risk of famine in Yemen and the UK’s leadership addressing this globally. Furthermore, funding only one system maximises the available funding for interventions specifically targeting food insecurity and reduces the likelihood of duplication of support to beneficiaries, recognising that cash reform (for example agreement on vulnerability targeting or common beneficiary identifiers) required for effective layering of programmes will take some time to implement.

OPTION B – National Yemeni institutions

This option targets both the most food insecure households (including specifically targeting women and children at risk of malnutrition) and the chronic poor and vulnerable. It provides varying values of cash transfers, from larger transfers (e.g. to Cash for Work beneficiaries) enabling households to provide for their basic needs and save lives, to smaller contributions (e.g. the ECTP) to protect households at risk of falling into extreme food insecurity. This option would therefore have more of a preventative effect by enabling UK funds to reach more people at risk of falling into extreme food insecurity (due to the lower average transfer value) but providing fewer of the most food insecure households with a value of cash that is sufficient for them to meet their basic needs.

As a community development organisation, SFD have long-standing relationships with vulnerable communities in every governorate of Yemen. Working with affected communities and local leaders, they identify households most in need of assistance who are often invisible to non-local actors. SFD’s Cash for Nutrition projects also specifically target women and educate mothers in areas of high malnutrition on how to keep their family healthy. Evidence shows that women are often excluded from access to, or control of, household cash transfers that are predominantly collected by men. Given the combination of high rates of early marriage and low rates of literacy amongst women and girls in Yemen, SFD’s gender-sensitive cash transfers play a unique and critical role in both addressing gender equality but also saving lives of women and children who are often those most at risk of malnutrition.

The ECTP is a long-term source of income for vulnerable households in Yemen. Top-ups to quarterly transfers help respond to rising costs of food and fuel as well as the increased vulnerability of SWF beneficiaries (primarily the chronic poor, the elderly, and people with disabilities) resulting from the conflict and COVID-19. The ECTP is an essential mechanism that goes beyond treating symptoms to prevent already vulnerable households in Yemen from becoming more food insecure and then requiring a higher value cash transfer to survive. As a former national safety net programme, the ECTP continues to work closely with Social Protection Consultative Committees in the North and South of Yemen that include government representatives. The ECTP is therefore more protected from access issues than humanitarian programmes that are required to negotiate access and thus an important option for managing risk in a potential worsening political scenario. The World Bank supporting a transition of the ECTP from UNICEF to SFD later this year provides a key opportunity for maximising synergies between these programmes and, as in Option A, only funding one system reduces the likelihood of duplication of support to beneficiaries.

OPTION C – Both international humanitarian agencies and national Yemeni institutions

Providing funding through both the humanitarian system and the national system capitalises on the benefits of each set out above, providing cash assistance of a value, speed and scale that is critical to responding to high levels of food insecurity and saving lives whilst also preventing vulnerable households from becoming food insecure. Inevitably in committing funding towards both treatment and prevention efforts, this option does mean that whilst the reach is greater, fewer of the most food insecure households can be supported with cash transfers that enable them to meet their immediate basic survival needs than option A .

Both systems will continue to be funded, and by doing the same the UK can use our convening power and leadership of the Cash and Social Protection Donor Working Group to influence other donors to align their funding to this approach and better drive cash reform. In addition to the competition generated through supporting parallel systems, increased joint donor efforts will better incentivise coordination and harmonisation of the two systems, increasing efficiency and cost-effectiveness. Funding both systems also provides an important opportunity to better understand the relative VfM and impact of different types of cash-assistance/delivery partners and adjust programming accordingly as per an adaptive programming approach. It also spreads risk across a range of delivery partners which is important in an unstable context such as Yemen.

Selection Criteria 2: Reduce future famine risk - Cash-based assistance builds resilience and coping capacity of households and communities to address root causes of food insecurity and mitigate future famine risk.

OPTION A – International humanitarian agencies

This option funds unconditional cash transfers delivered by humanitarian agencies. There is strong evidence to suggest that (when aligned to the value of the Minimum Expenditure Basket) unconditional cash can play a critical role in building the resilience and coping capacity of households since cash that is surplus to meeting immediate needs is often used to purchase goods or equipment necessary to generate an income and/or protect their productive assets and livelihoods (e.g. prevent the sale of an asset). Unconditional cash also has the indirect benefit of providing beneficiaries with cash to survive whilst not detracting from time required for caring responsibilities or opportunities to generate additional income. International humanitarian agencies are however largely unable to access World Bank and development finance and, given the likely decline in levels of humanitarian funding following a peace settlement, will therefore be unable to respond to famine risk in the future.

OPTION B – National Yemeni institutions

This option funds both unconditional cash transfers (ECTP) and Cash for Work and Cash for Nutrition projects targeted to households most at risk of food insecurity. Cash for Work projects provide a temporary income alongside short-term work and training opportunities for men and women. A key additional benefit of engaging in work, alongside receiving the cash transfers itself, is improving individual’s resilience and wellbeing, restoring a sense of dignity through engaging in productive activities. Some beneficiaries are able to use the skills gained through these projects to access future employment opportunities, bringing longer-term benefits. However, the potential for longer-term gains remains limited without reinvigoration of the Yemen labour market and such projects also exclude those unable to work due to age, disability or caring responsibilities. Cash for Nutrition projects, in addition to providing gender-sensitive cash transfers, provide invaluable nutrition awareness that support young mothers to make healthy choices for their families helping to address risk of malnutrition in the future.

This option also builds resilience to mitigate future famine. SFD’s Cash for Work projects build resilience and coping capacity at the community level through restoration and provision of essential basic services, promoting local stability and social cohesion. Furthermore, support to SFD and the ECTP preserves and protects these two key national social protection institutions, building institutional resilience of previously State supported institutions at the national level, preserving the State’s ability to respond to food insecurity in the future. The national institutions supported by Option B can also access World Bank and wider development finance, that is likely to increase in Yemen in the future once the conflict ends. The predictability of support provided by permanent state-backed institutions also delivers greater resilience gains since individuals are able to take greater risks in investing in productive livelihood opportunities with the additional certainty and predictability of the support these institutions provide. Furthermore, funding only one system maximises the available funding for interventions specifically preventing risk of future food insecurity and building resilience of Yemen’s poorest households.

OPTION C – Both international humanitarian agencies and national Yemeni institutions

This option offers the potential to ensure that the cash households receive equates to their level of need and vulnerability through supporting multiple types of cash transfer programmes. This would capitalise on the benefits of unconditional cash, Cash for Work, and Cash for Nutrition in building resilience and coping capacity of households and communities outlined in the options above. Supporting both the international and national systems and driving greater complementarity between programmes would also ensure that cash assistance can be better targeted to households at risk of becoming food insecure in the future, as well as preventing households that were previously food insecure from slipping back into life-threatening levels of vulnerability.

The additional focus of national Yemeni institutions on preventing rising levels of food insecurity in the future does mean a trade-off with reaching more of the most food insecure households with high value cash transfers that would be the case under Option A. However, given that the crisis is protracted and funding remains insufficient to respond to the level of need, it is even more imperative to improve understanding on how to best reduce famine risk and preserve and support income generation in Yemen. Addressing these evidence gaps will lessen these trade-offs as the response becomes more effective and efficient. Since the cash assistance delivered by both humanitarian agencies and national Yemeni institutions has the potential to address the root causes of food insecurity and mitigate future famine risk, this option provides a significant opportunity to improve understanding on the most effective, affordable, and sustainable approach to build resilience and reduce reliance on the very costly response to severe food insecurity that could not be gained through option A or B.

Selection Criteria 3: Improve food security response - Cash reform is incentivised improving the efficiency, effectiveness and sustainability of cash assistance. Progress is made towards a future nationally owned shock-responsive cash-assistance system that supports chronically food insecure households and can respond to spikes in need.

OPTION A – International humanitarian agencies

Since humanitarian agencies are the predominant source of cash assistance in Yemen, focusing efforts on reform of the humanitarian cash sector is critical to improving efficiency and effectiveness of cash transfers before conditions for a nationally owned and funded cash-assistance system are feasible. The humanitarian system is also likely to remain operational in Yemen for the foreseeable future and should be strengthened to deliver the shock-responsive element of a nationally owned cash assistance system in the future.

International humanitarian agencies are, however, unable to build a nationally owned cash-assistance system without working with a national actor. Option A is therefore unable to deliver on making progress towards this system aside from reform of humanitarian cash programmes that would be beneficial for any future national system and would reduce the sustainability of UK funding. It would also go against the principles of the UK’s Humanitarian Reform policy and commitments in the Grand Bargain to increase work through national institutions.

OPTION B – National Yemeni institutions

Investing in national institutions is essential to preserve and strengthen these institutions that will be critical to delivery of future nationally owned and funded system. This option presents a strong opportunity to support SFD to scale up their Cash for Work and Cash for Nutrition projects, reaching more food insecure households through a national system than previously. This is also aligned with the World Bank shift to increase support through national institutions, including supporting SFD to be able to deliver the ECTP from late 2021 onwards. Option B presents a timely investment to further support this transition and strengthen SFD as a critical part of a nationally owned shock-responsive cash assistance system in the future. It is the option that invests most in efforts to move towards a future nationally owned social protection system.

This option would however limit our ability to influence other donors, who place most of their funding through the humanitarian system, and be unable to incentivise reform of the humanitarian cash system improving the efficiency, effectiveness and sustainability of what is currently the dominant provider of cash assistance in Yemen. The scope for improving the food security response is therefore limited to the size of the national response, that is unlikely to reach an inflection point with the size of the humanitarian response in the next 5 years.

OPTION C – Both international humanitarian agencies and national Yemeni institutions

The appraisal of options A and B above highlights how cash reform in Yemen requires both humanitarian and national cash assistance programmes to be coordinated and harmonised together. This includes alignment of common approaches to targeting, setting of transfer values, strengthening systems for Accountability to Affected Populations, and development and rollout of common beneficiary identifiers as key reform priorities. Funding both the humanitarian and national system drives competition, further incentivising reform, and capitalising on the future role that each system has to play, as set out above. A future nationally owned cash assistance system will not be based on one or the other but is likely to draw of the strengths of both; therefore Option C that invests in both is critical to bridging the long transition between the current response and a nationally owned and funded social protection system.

OPTION ANALYSIS

The three feasible options have been appraised against the Selection Criteria identified as critical to achieving the programme outcome. They have been scored as follows in Table 4. These scores reflect the rationale set out in the appraisal above. The scores are based on a scale of 1-5 (1 = does not meet criteria, 2 = poorly delivers against criteria, 3 = somewhat delivers against criteria, 4 = delivers well against criteria, 5 = delivers very well against criteria).

Table 4: Option Analysis

Selection Criteria		Weighting	Option A	Option B	Option C
1.	Save lives	50	4	3	3
2.	Reduce future famine risk	25	3	4	5
3.	Improve food security response	25	2	3	4
SCORE		100	325	325	375

TECHNICAL ASSISTANCE FACILITY (TAF)

Since FCDO are not present in Yemen, and in order for this programme to deliver best value for money and build on the UK’s influence on addressing famine risk and food insecurity, additional capacity and capability is required to support delivery partners and donors to incentivise harmonisation of cash assistance as outlined in paragraph 70. Specifically, there is a requirement for researchers, data analysts and technical specialists in humanitarian cash and social protection system reform to:
- Deliver technical aspects of the Yemen Cash and Social Protection Donor Working Group action plan (for example, rollout of a common form of beneficiary identification and alignment of delivery partner Management Information Systems to enable improved targeting and harmonisation between programmes);
- Undertake a longitudinal evaluation of the programme to improve data that enables greater comparability of programme effectiveness.

Consideration has been given to whether these functions could be delivered more cost-effectively in-house though programme funded posts within the FCDO Yemen team or through Centrally Managed Programmes. We concluded that neither option is viable. A Programme Funded Post will not have sufficient technical expertise for conducting a longitudinal evaluation nor deliver on the specialist technical cash reform interventions. There are also not currently FCDO programmes in place for the duration of this programme that could offer such support, and existing programmes are not able to guarantee sufficient capacity to take on delivery of such outputs at the level required. It should however be noted that if the FCDO Evaluation Unit can support a longitudinal evaluation when there is greater certainty of budgets this option will be considered.

Since in-house options are not viable, this programme will include provision for an external Technical Assistance Facility to drive and incentivise improvements to the efficiency, effectiveness and sustainability of cash assistance in Yemen. Third Party Monitoring, joint analysis of beneficiary feedback from delivery partners, and monitoring of food security data will however be undertaken by existing FCDO programmes (FCDO Yemen’s IMEDA programme, the CHASE Resilience Pilot, and BASIC) to reduce costs of this component.

ECONOMIC APPRAISAL

1. A cost/benefit analysis in Net Present Value (NPV) terms, and by extension a sensitivity analysis is not employed in this appraisal. This is principally because we are only confident in being able to accurately estimate FCDO’s direct financial costs. We do not attempt to quantify benefits since, given the highly uncertain operating context and scarcity of recent data available in Yemen, it is likely that assumptions will result in a misleading empirical estimation of the flow of associated benefits. Rather, we offer robust reasoning and evidence to support the case that the potential benefits from the interventions justify the cost.
2. The scarcity of data also means that VfM arguments of the associated interventions continue to be limited. It is a priority for FCDO Yemen to work on building up the data and strengthening the methodologies for assessing the VfM of humanitarian cash transfers and social protection programmes, including in emergencies, which currently focus on effectiveness and speed of response. Designing the methodology for this and undertaking data collection and analysis will be a key function of the programme’s Technical Assistance Facility.
3. Following the options appraisal analysis, we appraise the economic arguments of the preferred option (Option 3) compared to the no intervention option. The optimal choice comprises both elements of options (1) and (2).
Option Resource Costs

The total cost of FCDO planned support for the programme is £250 million over 5 years. Wider costs linked to the interventions are not covered by this and are separate to FCDO’s direct contribution. These costs include:
1. The ongoing costs related to the interventions we plan to support. These are the largest wider costs, for instance the ECTP requires c.$200million/annum to cover 1.5 million households, keeping the current value of the transfers fixed (at 5,000 Yemeni Riyals for a family of 7 per month, or around $8 USD). We have been reassured the Bank will continue to prioritise financing the programme from its own resources (Yemen’s IDA allocation) or externally (e.g. a donor-financed trust fund to support reconstruction and recovery) for the next two years. It is not expected the GoY will be in a position to part–finance these expected costs during this time or in the medium-term.
2. Costs of advisory and programme management support from FCDO Yemen. It is assumed that a team comprising of a full-time Social Development or Humanitarian Adviser, Senior Programme Manager and Programme Officer will undertake the management of this programme, with additional support from other FCDO Yemen Advisers on a part-time basis.
3. Associated costing variations due to the changing macroeconomic situation, such as the exchange rate and inflation. These include changes to the amount of transfer needed to maintain purchasing power and input costs (labour or materials). As FCDO’s contributions are expressed in British pound sterling, this does not affect how much it costs but it does affect how far it goes by affecting the relative value of cash transfers for recipients. Since food prices have mostly fluctuated in sync with foreign exchange rates this is unlikely to be a major risk and with cash reform leading to agreement on transfer values set against Minimum Food Basket costs this will maximise the poverty reducing effects for the target household.

Benefits

The potential economic benefits resulting from a flexible and adaptable programme using both social protection and humanitarian approaches are:
1. Meeting basic needs through cash transfers as a form of income support. Greater impact for people affected by crises, by producing better outcomes at the same cost.
2. Reduced risk of costly response to acute food insecurity in the future by responding earlier (and avoiding loss of productive capital for households) and investing in the resilience of households to manage shocks through shock-responsive social protection systems.

Increased aid efficiency and cost-effectiveness delivered through cash reform, including a more sustainable and predictable response to food insecurity paving the way for a nationally owned and financed social protection system in the future.

Expected benefits derived from meeting basic needs through cash transfers as a form of income support

Global and Yemen specific evidence on cash transfers is compelling on their benefits. They are a FCDO Chief Economists Office “Great Buy” and are good value for money. A rigorous review conducted by the Overseas Development Institute (ODI) of the evidence on the impacts of cash transfers shows that cash transfers reduce monetary poverty; the evidence consistently showed an increase in total expenditure and food expenditure and a reduction in poverty measures. Cash transfers are also an economic multiplier since cash is spent in markets and supports economic activities and invigoration of the local economy (see Annex 1 for more information).

Cash transfers to people support improved outcomes. For example, ECHO and UNICEF found that unconditional cash transfers allow people to buy the goods and services they need through local markets and are characterised by flexibility that would be hard to match through in-kind responses that do not take the varied needs of households into account.
[note] Humanitarian Cash Transfers in the Democratic Republic of the Congo: Evidence from UNICEF’s ARCC II Programme, report
[note] Evaluation of the Use of Different Transfer Modalities in ECHO Humanitarian Aid Actions 2011- 2014, report

The direct economic benefits from Cash for Work projects are similar to cash transfers as both are instruments for income provision (although have small additional costs related to training, materials and supervisory staff costs). Income is generated for targeted individuals, in this case for the exchange of labour. SFD and NGOs expect to create over 1 million working days per year through Cash for Work projects. This type of employment will not lead to transformative economic growth in Yemen. However, the primary purpose of employment created under SFD is to transfer income support during a period of continued economic collapse.

Whilst cash transfers in the global and Yemen evidence are the best option to meet needs (more details in Annex 1), this programme will flex to vouchers or in-kind provision where necessary only if cash provision is not possible. In the humanitarian context where the aim is to meet acute need, if the context does not allow for cash transfers then an alternative is the best VfM option.

There are high rates of return on investments: The World Bank’s support to SWF through its Yemen Emergency Crisis Response Project (ECRP) ECTP is expected to yield a substantial return overall, given its response in an emergency situation. A rate of return of the invested resources is linked to assisting poor families, including mothers and children to cope with famine, and temporarily afford a minimum food intake. It is presumed to be life saving for about 30% of the target group. It therefore yields a calculated return of about 70%, particularly due to the alleviation of famine for mothers and children. This will be even more true for humanitarian cash transfers given their higher transfer value. The Technical Assistance Facility will yield further data on comparative return on investment across partners.
[note] Report No: PAD2402, World Bank.

Expected benefits derived from reduced risk of costly response to acute food insecurity in the future

There will be benefits generated from the programme by decreasing humanitarian need through preventative efforts. Investing in early response and resilience is significantly more cost effective than providing ongoing humanitarian aid. Expected benefits result from the economics of resilience, avoiding costs of humanitarian aid and losses due to negative coping strategies through social protection. This maps onto DFID’s VfM guidance on efficiency and effectiveness.
Expected benefits derived from increased aid efficiency and cost-effectiveness delivered through cash reform

Common systems between humanitarian assistance and social protection enable effectiveness, reduce duplications and offer a bridge between humanitarian and development. The modalities of cash (and food) transfers are common to humanitarian assistance for disaster-affected households and social protection to chronically poor households. They provide a common assistance tool for transitioning smoothly between normal times and crises. Social protection programmes’ architecture for administering long-term transfers could be used during emergencies with potential for a quicker, more predictable, more efficient and therefore more effective response. Likewise, humanitarian systems could be built to last, to be transitioned into national systems. Institutional coordination can provide the necessary ownership and institutional sustainability to support post-conflict transition and long-term development.
[note] Gairdner, D., Mandelik, F. and Moberg, L. (2011) We Accept Cash: Mapping Study on the Use of Cash Transfers in Humanitarian, Recovery and Transitional Response. NORAD Report 10/2011 Discussion. NORAD; Development Initiatives, Global Humanitarian assistance report 2015; Kukrety, N. (2016) ‘Working with Cash Based Safety Nets in Humanitarian Contexts: Guidance Note for Humanitarian Practitioners’. Cash Learning Partnership.; Kuriakose, A., Heltberg, R., Wiseman, W., Costella, C., Cipryk, R. and Cornelius, S. (2012), 'Climate-Responsive Social Protection. Discussion Paper No. 1210', World Bank.; La Rosa, M. (2015), 'Are Social Protection and Safety Nets viable Avenues for Policy Makers for Crisis Response in LICs and Fragile States? Initial scoping study report', ECHO; Maunder et al., 2016, Evaluation of the Use of Different Transfer Modalities in ECHO Humanitarian Aid Actions 2011- 2014, ADE.
[note] Slater, R. and Bhuvanendra, D. (2013), 'Scaling up existing social safety nets to provide humanitarian response: a case study of Ethiopia’s Productive Safety Net Programme and Kenya’s Hunger Safety Net Programme. Fit for Future Social Protection Thematic Study', CaLP, UK; del Ninno et al., 2016; Maunder et al., 2015

1. Social protection approaches, like safety nets, can bring savings in recurrent and predictable crises. Building on work commissioned by DFID in 2013 on the Economics of Early Response and Resilience, a further study found that donors could save 30% on humanitarian aid spending through an earlier and more proactive response that uses safety nets. The study compared a range of investment and drought response scenarios in Kenya, Ethiopia and Somalia and demonstrates that early humanitarian response, safety nets and/or investments in resilience are far more cost effective than responding after households are engaging in negative coping strategies and prices are destabilised. A more proactive response helps households protect their income and assets and manage the effect of shocks. Every US$1 invested in building people’s resilience, through safety nets and/or income-generating activities, will result in up to US$3 in reduced humanitarian aid and avoided losses.
  [note] Cabot Venton, C. (2013). 'The Economics of Early Response and Resilience: Summary of Findings'. DFID, London; Cabot Venton, 2018, Economics of resilience to drought in Ethiopia, Kenya and Somalia, USAID Center for Resilience.
2. There are opportunities to reduce costs by integrating multiple systems, resulting in economies of scale through sharing of information which will reduce duplication. These opportunities for reducing costs are likely to improve economy and efficiency. A World Bank Report comparing humanitarian and social assistance programs in Yemen presents evidence that many households receive benefits from multiple programs whereas several households receive no assistance whatsoever. Exclusion and overlap can be reduced with better coordination between agencies and programmes, including through harmonisation of transfer values and mutually intelligible approaches to geographical and household targeting. Complementarity between programmes can also be increased by institutional coordination.
  [note] Social Protection at the Humanitarian-Development Nexus: Insights from Yemen, March 2021

SUMMARY AND RECOMMENDATION

Option C (both international humanitarian agencies and national Yemeni institutions) is the preferred option. The final budget breakdown by delivery partner that comprise Option C will be determined in the design and mobilisation phase, commissioned after Business Case approval.

We have assessed the options based on the assumption that the programme budget will remain the same for all options. It should be noted therefore that the additional focus in Options B and C on preventing rising levels of food insecurity in the future, building resilience of the most vulnerable, and strengthening national institutions for sustainability of the food security response does mean a trade off with the recommended option reaching slightly fewer of the most food insecure households with high value cash transfers than under Option A. Where possible, cost benefit analysis and VfM data is presented though these will be addressed in greater detail when assessing and selecting delivery partners in the mobilisation phase following Business Case approval.

Although work is underway by the World Bank, humanitarian agencies and FCDO seeking to better coordinate and harmonise cash and social protection programmes in Yemen, it is impossible to forecast the levels of food insecurity in Yemen in the outer years of this programme and therefore the most appropriate safety net interventions. As outlined in paragraphs 205 and 206, the programme will be subject to adaptation and change, depending on the impact and performance of our programmes.

RESULTS AND IMPACTS

Results have been calculated on the basis of a £49.6 million annual spend. It presupposes an average annual spend of £400,000 on the Technical Assistance Facility. For the purposes of results reporting, each delivery partner will be held to account on the basis of the estimated numbers of beneficiaries identified for each funding interval determined during the mobilisation phase.

However, based on the current results of existing programmes, FSSN will aim to:

- Deliver humanitarian cash transfers to 240,000 of the most vulnerable Yemenis on a monthly basis
- Support up to 1.5 million households (up to 9 million people) with top-ups to ECTP quarterly cash transfers
- Support up to 10,700 pregnant and lactating mothers in areas of high malnutrition with monthly cash transfers and nutrition awareness and advice (delivered by 420 community educators employed through the programme) for a period of 12 months
- Support up to 12,000 people with Cash for Work opportunities, delivered in a sustainable manner in line with the climate risk assessment and environmental safeguarding considerations.

VALUE FOR MONEY (VfM)

FCDO uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that UK aid maximises its impact. The assessments (below) show that the proposed option that supports the UN WFP, NGOs, SFD, and the ECTP, demonstrates Value for Money. The programme’s complexity requires ongoing monitoring and analysis of how change is being achieved.

WFP

Economy
WFP are able to guarantee that 82% of cash programming contributions from FCDO Yemen go directly to the beneficiaries. Whilst this figure appears high flattering in comparison to other partners, this is because it is only marginal cost budgeting rather than full cost budgeting that takes into consideration wider costs associated with the programme. We are however confident that overall the amount of cash reaching beneficiaries is comparable to that of delivery partners and this is something that will be further investigated through the Technical Assistance Facility as part of the longitudinal impact evaluation of the programme. Operational and support costs are also clearly outlined in any contribution proposals and WFP are experienced in procuring local suppliers, where necessary, to ensure maximum value for their operation.

Efficiency
WFP is operating at a scale which no other organisation is in Yemen and is therefore able to ensure efficiencies in the delivery of assistance. Using an established financial provider and experienced NGOs to facilitate distributions of cash allows a smaller lead-in time for distributions compared with other modalities, which is critical to addressing urgent humanitarian need. Distributions also support the local economy by guaranteeing revenue for local shops and businesses. As co-chair of the Food Security and Agriculture Cluster (FSAC), WFP can also ensure there is no risk of duplication of effort in the food security response.

Effectiveness
Over the last 2 years WFP have undertaken an extensive retargeting and biometric registration exercise increasing confidence that funding is reaching the right people. WFP’s expansion in cash distribution points over the last six months (an additional 91 over the last quarter) is also likely to improve effectiveness as people no longer have to travel as far to access their cash.

The ‘SCOPE’ – WFP’s beneficiary and transfer management platform - reduces costs by harmonising beneficiary registration (using biometrics), targeting and transfer provision under a common shared platform. Technological advancement has also allowed implementing agencies to replace paper questionnaires with digital equivalents. This has reduced labour intensive data entry costs and requires fewer staff to administer. WFP have also worked in the last couple of years to improve the effectiveness of cash programming by increasing the number of distribution points available to beneficiaries, allowing better and safer access for beneficiaries. FCDO-funded third party monitoring also provides reporting on uses of cash among WFP beneficiaries. It is clear from this reporting that beneficiaries use the majority of cash received for food items, as well as smaller amounts on other essentials, such as healthcare and property rent. The latest WFP monitoring and evaluation reporting also shows that most cash transfer beneficiaries have acceptable food consumption levels, with percentages higher than beneficiaries who receive in-kind assistance. Cash transfer beneficiaries also have a more varied diet compared with recipients of other modalities of assistance, with much greater numbers reported to consume food rich in vitamin A, protein and iron on a daily basis.

Equity
To ensure that assistance reaches those most in need, WFP is currently carrying out a robust and carefully administered retargeting exercise that aims to minimise inclusion and exclusion errors in beneficiary lists and is periodically adjusted to account for changes in food security levels, operational priorities, context or the funding situation. Disaggregated results data supplied by WFP also allows us to see how many women, girls and disabled beneficiaries are being reached with FCDO-funded cash transfers. In terms of gender, WFP state they comply with their global gender policy (2015-20), including improving and systematizing gender analyses and programming.

NGOs

Economy
Within the extension period of the MHRP, INGOs have committed to the target of 68.4% of funds directly transferred to the beneficiary. As of December 2020, Care International were however exceeding this target with an actual year to date figure of 73.9%. As noted in reference to WFP, it should be clarified that it is difficult to compare full cost budgeting (that which NGOs provide us with) with the marginal cost budgeting that we receive from UN agencies such as WFP. It is not possible to carry out a direct comparison on this basis since WFP would likely be significantly worse cost efficiency than NGOs on a full cost basis but appear better on a marginal cost basis, and a case could be made that each is the more appropriate metric. We also think there is scope to improve cost efficiency with NGOs in this programme, notably we are looking at specifying that indirect costs are not to be charged on the value of cash transferred to beneficiaries, which would lead to significantly better cost-transfer ratios.

Efficiency
INGOs have been able to efficiently manage fluctuations in exchange rates and proactively request the use of exchange rate savings to respond to spikes in conflict, such as in Ma’rib early 2021. This allowed FCDO to efficiently pivot to respond to a spike in need without requesting any additional budget, a particularly efficient use of funds in a constrained financial environment. They have also used any additional exchange rate savings, where appropriate, to reach more households with their unconditional cash transfers.

2 years into the MHRP programme, FCDO introduced a new VfM tool looking at input-output efficiency, particularly cost efficiency for each output. This was fully integrated into reporting in Year 3 and allowed for more holistic and fact-based discussions of cost drivers and broader VfM considerations.

Effectiveness
In December 2020, the INGOs reported that cash transfers received as part of the extension period were spent on four major expenditures: food (70%), health care (12%) and debt repayment (9%). The remainder (8%) was used for various other purposes such as shared with others/gifted, fuel, housing/rent/shelter repairs, transportation, education, water, etc. Since receiving the transfers, respondents were asked what they are able to do now that they were unable to before; 39% reported they were now able to afford nutritious food, 10% reported they were able to pay debts, 37% reported improved living conditions and 12% reported that they spent it on health care. 91% of respondents prefer cash transfers as it offers flexibility and freedom to prioritise costs to repay debts or buy medicine etc.

Equity
At the moment WFP reaches only those in major cities with cash transfers, whereas NGOs deliver cash in harder to reach areas with potentially more vulnerable populations. Working directly with NGOs also gives us more transparency and greater assurance of effective targeting and verification of targeting. NGOs are also able to flex and adapt their response to new needs more quickly than WFP. We may also be able to use NGOs to trial new approaches and build evidence, something that is much harder with the large-scale WFP programme.

SFD

Economy
SFD’s operating costs do not exceed 10% and between 80-85% of funds go directly to beneficiaries which is comparable with both WFP and NGOs. SFD has robust procurement processes in place to ensure high quality goods are obtained for the best price.

Efficiency
SFD has also been able to benefit from exchange rate savings to expand existing programming.

Effectiveness
An impact assessment of SFD’s Cash for Nutrition interventions by the International Food Policy Research Institute provided evidence on its effectiveness in improving the nutritional conditions of targeted beneficiaries as a result of both the cash support and awareness messages. The assessment demonstrated that the interventions increased spending on food, decreased the number of children diagnosed with moderate or severe malnutrition, and improved the nutritional status of children in the poorest third of households. There were also positive impacts on knowledge about the importance of early initiation breastfeeding, the problems of qat usage, and how to feed children when they are sick.

Equity
SFD works to benefit all Yemenis. Under YeSP SFD moderately did not meet its 30% target for female case for work beneficiaries. This is partly due to the nature of the cash for work projects, however FCDO are supporting SFD to address this through the development of an inclusion strategy. SFD have also started using the Washington Group Questions to help better understand and improve work on disability inclusion. SFD projects are also designed to support both host and IDP communities and where IDPs do not have national IDs, SFD supports them to acquire new ones, thus facilitating their access to other essential services.

ECTP

Economy
For the ECTP, the World Bank covers all direct costs and UNICEF’s operating costs do not exceed 8% as stipulated in the Contribution Arrangement. 92% of FCDO funds are therefore used to fund the top up to the transfer amount, including a 2.5% transaction fee with the banks.

Efficiency
An active risk register for the ECTP is maintained and regularly updated, with emerging risks informing programming and mitigation measured implemented to ensure that cash continues to be delivered to eligible beneficiaries. Although the project is implemented in a highly volatile environment, over 1.4 million beneficiaries have been able to successfully collect their cash, impacting the lives of over 9 million Yemenis (around one third of the population).

Effectiveness
Third part monitoring conducted during the eighth payment cycle of the ECTP should that 87% of beneficiaries used their cash to purchase food, 60% used their cash for debt repayments 22% used their cash for healthcare. Of the beneficiaries who reported using their cash for debt repayment, the most prominent sources of debt were taking out loans to buy food (90%), to pay for health care (65%) and to pay for utilities (13%).

Equity
UNICEF (currently implementing the ECTP) have started using the Washington Group Questions to help better understand and improve work on disability inclusion. In addition UNICEF have implemented a number of innovative solutions and streamlined real-time monitoring through insourcing the Management Information System (MIS) and developing multiple dashboards providing real-time information on the status of grievances, field monitoring and payment progress, and allowing the programme team to identify challenges and address them in a timely manner.

Measures to reach the most vulnerable (the elderly, people with disabilities and those who are unable to travel) under the ECTP include reserving the first week to serve the remote archipelago of Socotra as well as a home outreach service for the most vulnerable. In areas where socio-cultural barriers to women collecting cash (e.g. restrictions in movement and on interaction between genders) are very strong, there are female-only payment sites and all communications materials (visuals, videos, flyers) show a strong gender balance. 47.8% of beneficiaries paid under the ninth payment cycle of the ECTP were female.

Summary

A recent impact review of cash transfer programmes by ICAI shows that these interventions consistently deliver on their core objectives of increasing incomes and consumption levels for poorest households. FCDO’s cash transfer programmes present a strong case for VfM, given their proven ability to deliver results for the poorest. FCDO has made progress on building a focus on cost-efficiency into programme management.

It is clear from the VfM analysis above that differing reporting methods, data access and protection issues have long hampered the collection of comparable data, nullifying meaningful analysis between different delivery partners and forms of cash assistance. Increased commitment to cash harmonisation (including the UN Common Cash platform pilot in Yemen) as well as technological advancements does however allow for improved data capture, consolidation and interpretation. This will result in better understanding of the costs involved in delivery and enable a ‘like by like’ comparison between different forms of assistance. We will work over the course of this programme to improve metric and unit cost analysis so as to ensure that the portfolio continues to be informed by clear VfM indicators. In time, this will allow us to compare the cost of delivering cash or Cash for Work interventions, and compare with regional or similar context cost comparators, etc.

Work scheduled for the mobilisation phase after programme approval will further enhance our understanding and application of programme cost metrics. We will also continue to drive improvements in VfM over the course of the programme. For example, we will continue to ensure that our partners negotiate the best exchange rates with banks (given the Yemeni Riyal rate volatility which can affect the real value of cash transfer payments). We will also ensure operational costs keep within agreed limits and ensure that partners are able to reach the most vulnerable. Lessons learned will reshape the programme portfolio as appropriate and be shared across the FCDO network and wider humanitarian and social protection community.

On VfM metrics, we will explore the indicators from the following table:

Table 5: Proposed VfM Indicators

VfM measures	Indicator
Economy	Per capita spend per beneficiary / Service delivery agent salary
Efficiency	Method of delivering safety nets, basic services at local level and livelihoods opportunities / Method of collecting data and feedback loops e.g. use of ICT / Targeting accuracy (exclusion/inclusion errors)
Effectiveness	Improvements in capacity of services to deliver quality outcomes
Equity	Number of vulnerable and women accessing unconditional cash and Cash for Work/Cash for Nutrition projects / Improved access to basic services, particularly for those with disabilities / Difference in access to services between the richest and poorest quintiles

THEORY OF CHANGE

Building on the conclusions drawn from the options appraisal and the subsequent additional analysis, the proposed approach is to support Option C as the preferred option with the following Theory of Change (see Figure 1).

With regard to side ‘B’ of the Theory of Change, a key assumption should be noted that achieving the desired outcomes is dependent on political will and change within the wider operating environment. Whilst the Technical Assistance Facility will ensure improved coordination and effectiveness of the interventions funded through this programme, strengthening national systems and improving the overall food security response in Yemen will require broader commitment of other donors, agencies and state actors.
Figure 1: Yemen Food Security Safety Net Programme Theory of Change

## C. Commercial Case

The Food Security Safety Net Programme (FSSN) budget is £250 million over five years. It will deliver against the three programme outputs (as identified in the Theory of Change) through five different partners. VfM will be driven through a combination of direct and indirect contracting routes, dependent on the partner. This will allow for the most effective and efficient delivery of the intervention. Emphasis will be placed on achieving synergies and efficiencies between the different partners of the programme to maximise impact and contribute to cash reform. In this section we outline the proposed funding mechanisms and procurement routes for this intervention. We also set out assurances we have of partners’ capacity to deliver and how value for money (VfM) will be achieved.

Why are the proposed delivery partners and funding mechanisms the right ones for this intervention?

FSSN combines multiple partners delivering cash assistance in Yemen. Delivering through multiple partners in fragile states spreads risk. FCDO has invested heavily in building institutional partnerships and capacity through current programming and FSSN provides an opportunity to capitalise on progress and achievements made to date as well as further strengthening FCDO’s role in the humanitarian and social protection architecture in Yemen. Potential partners are assessed on i) proven ability to reach affected populations and operate at scale in Yemen, including through local downstream partners, ii) technical capability and capacity to deliver cash, and iii) robustness of internal controls in place including risk management, financial management and procurement processes.

This intervention is based on three programme outputs delivered by several agencies and specialised organisations determined through the Appraisal Case to be best suited to deliver the programme outcomes. Bringing the various agencies and organisations together under one intervention will help maximise complementarities, enhance coordination and reduce duplication.

A small allocation has also been set aside for design funding to assist with the initial development and design of the intervention if required. Table 6 outlines the recommended mix of delivery mechanisms, preferred implementing partners and procurement routes.

Table 6: Delivery mechanism by output

Preferred partner	Delivery mechanism	Procurement route
Cash Based Assistance to i. Save lives and ii. Reduce future famine risk Approx.: £247,955,000*
UN Agency - WFP	Monthly Emergency Food Assistance payments.	Indirect – a Contribution Arrangement will be signed under the global Framework Agreement that has been agreed centrally by FCDO’s United Nations and Commonwealth Department and WFP HQ.
National Yemeni Institution - SFD	Short-term additional cash assistance through Cash for Nutrition payments, Cash for Work, Cash for Education and Cash for Social Services projects. / .	Indirect – a Memorandum of Understanding (MoU) will be drawn up between SFD and FCDO using the standard FCDO template.
UN Agency – UNICEF**	Additional cash assistance through the World Bank/UNICEF Emergency Cash Transfer Project Top-Ups.	Indirect – a Contribution Arrangement will be signed under the global Framework Agreement that has been agreed centrally by FCDO’s United Nations and Commonwealth Department and UNICEF HQ.
INGOs	Monthly Multi-Purpose Cash Assistance transfers, Cash for Work projects.	Direct - the selection of implementing partners will be organised through a competitive call for proposals opened to all international and national NGOs. In line with the Programme Operating Framework, Accountable Grants (AG) with the selected supplier(s) will be drawn up using the standard FCDO template.
Technical Assistance Facility to iii. Improve food security response Approx.: £2,045,000*
Commercial provider	Technical assistance to support cash reform, evaluation and learning.	Direct – the Technical Assistance Facility supplier will be competitively selected through FCDO’s pre-tendered International Multi-Disciplinary Programme (IMDP) Framework. The increased use of Framework Agreements is a key part of FCDO’s Commercial Strategy, reducing the timescale for routine procurements whilst ensuring good VfM. The successful supplier will be managed through a commercial contract.
Commercial provider	Assistance with the design phase should this be required.		Direct – a supplier will be competitively selected with the support of a Delegated Procurement Officer.
TOTAL: £250,000,000

*The indicative breakdown for each delivery partner will be decided during the mobilisation phase. Please refer to the Financial Case for more information.
**Funding to the Emergency Cash Transfer Project could also be channelled through a new World Bank Multi-Donor Trust Fund. This option will be considered during the mobilisation phase with due consideration given to the World Bank’s management, oversight and monitoring processes.

Terms of Reference (ToR) for the components that require direct procurement will be developed following Business Case approval. On the basis of these ToR, resulting agreements for NGO partners and the Technical Assistance Facility will have inception periods to further refine programmatic thinking.

All agreements with partners will outline the expected value and timing of planned payments, the timeline for programme reporting and where possible, specific clauses on anti-terrorist financing and FCDO’s zero tolerance for fraud and corruption. Agreements with NGOs, SFD and the commercial contract will also include specific clauses on FCDO’s zero tolerance for inaction to tackling Sexual Exploitation, Abuse and Harassment (SEAH). FCDO’s Memorandum of Understanding (MoU) and Accountable Grant (AG) agreements stipulate that the partner must apply the UN Inter-Agency Standing Committee (IASC) Six Core Principles Relating to Sexual Exploitation and Abuse. While the Framework Arrangement with WFP does not include language on safeguarding, negotiations are currently underway with WFP Headquarters to revise the agreement. WFP have been made aware of their obligations in relation to safeguarding under the existing WFP intervention and as a UN agency are bound by the IASC Principles. Negotiations are also underway to revise the Framework Agreement with UNICEF but under the current YeSP intervention, clauses on the zero-tolerance approach to SEAH have been added to the Contribution Arrangement stipulating that UNICEF must take robust and prompt action in response to any SEAH allegations.
[note] IASC Six Core Principles Relating to Sexual Exploitation and Abuse, 2019 | IASC (interagencystandingcommittee.org)

Partner performance will be overseen by the programme team, with technical support and guidance from a Commercial Delivery Manager. Even where delivery is not by a private supplier, the programme team will apply contract management principles when managing performance. Collaboration and coordination between partners will be critical to the success of this intervention, and one of the indicators by which performance will be measured. It will also help maximise VfM by ensuring interventions complement each other and prevent duplication. Further information on how this coordination amongst partners will be encouraged in the context of wider challenges posed by the political economy of Yemen and programme management challenges related to adaptiveness and decentralised delivery is set out in the Management Case.

What assurance has been obtained on capacity and capability of the organisations to deliver this intervention?

As outlined in the Appraisal Case, partners will be funded to provide cash assistance along with work and training opportunities for the most food insecure households. Funding to partners will support a range of interventions, to be determined during the mobilisation phase. These are likely to include:
WFP – Emergency Food Assistance cash transfers (monthly)
Social Fund for Development (SFD) - Cash for Nutrition cash transfers (short-term monthly cash transfers targeted to pregnant and lactating women and families with children under 5 in areas of high food insecurity), Cash for Work projects, including Cash for Education and Cash for Social Services projects (short-term)
- UNICEF/Social Fund for Development – Top-up payments to World Bank financed Emergency Cash Transfer Project (quarterly, ad-hoc)
- NGOs – Emergency Food Assistance cash transfers (monthly), Cash for Work projects (short-term).

WFP, SFD and UNICEF will be engaged with a minimal lead in time from the current interventions (which are due to end in December 2021) into this successor one. These partners have a proven capacity to deliver, as demonstrated through due diligence assessments, third party verification of results including through FCDO Yemen’s Independent Monitoring, Evaluation and Data Analysis (IMEDA) programme and strong performance under the current WFP and YeSP programmes. Both programmes scored an A in their 2020 Annual Reviews, delivering well against logframe targets despite the emergence of the COVID-19 pandemic in March 2020, continued conflict escalations, access issues, and challenging exchange rate volatility. Findings and recommendations from the Project Completion Reviews for these interventions will be used to inform FSSN programming particularly during the mobilisation phase but also during implementation where there will be an emphasis on continuous improvement to ensure the most vulnerable are receiving cash as efficiently as possible. Bringing these partners under one intervention will help encourage complementarities and maximise impact. FCDO will engage with these partners prior to the end of the current interventions to ensure a smooth transition. There will be no overlap in timings with the current interventions. Key assurances obtained to date on WFP, SFD and UNICEF are set out below.

WFP

WFP has the experience and presence in Yemen to deliver at scale. It is the biggest actor in the UN humanitarian response in Yemen, working to address suffering by providing life-saving assistance to over 12 million Yemenis every month in the form of food baskets, commodity vouchers and emergency cash transfers. FCDO is one of the most important supporters of WFP’s cash transfer programme in Yemen, supporting WFP to significantly scale up its cash programme in the past year, moving approximately 500,000 people in the South from in-kind or voucher assistance to cash. WFP is also piloting the cash modality in the North, fully funded by FCDO.

FCDO has worked collaboratively with WFP to strengthen oversight and enhance controls since 2016 when WFP operations were criticised as unsatisfactory in an internal audit report and by the former-DFID programme team. This collaboration has been reinforced by a Mutual Accountability Framework, agreed with WFP in May 2017, including provisions on enhanced reporting requirements, engagement with donors and Accountability to Affected Populations. Furthermore, an Operational Roadmap to improve WFP’s approach to preventing aid diversion was put in place in 2019 following allegations of fraud (although no FCDO funds were found to be at risk). There is a standalone output in the current WFP logframe to measure progress against the recommendations in the Operational Roadmap. The output indicators include the percentage of beneficiaries who are aware of WFP’s feedback mechanisms, complaints received that are followed up on, percentage of monitoring findings being addressed and the number of beneficiaries who have been biometrically registered. This output scored an A in the 2020 Annual Review indicating strong progress.

FCDO has received further assurances through a due diligence assessment that was undertaken in October 2017 and an enhanced due diligence assessment covering safeguarding policies that was finalised in December 2019. The due diligence assessment will be renewed towards the end of 2021, following approval of this Business Case. Progress against the recommendations in the enhanced assessment, particularly in relation to reporting, are linked to the negotiations that are underway on the centrally agreed Framework Agreement.

An internal audit of the WFP intervention was carried out by FCDO’s Internal Audit Department in 2020. It concluded that the programme’s controls are designed and operate effectively in relation to the risk appetite but there were opportunities to reduce the risk further in specific areas. Key recommendations included strengthening risk management down the delivery chain, encouraging more in-depth reporting from WFP, continued monitoring of progress against the Operational Roadmap, working with WFP to enhance oversight of safeguarding risks, and increased engagement with other donors. We will push for these areas to be covered in our agreement with WFP and are implementing them under our current agreement.

SFD

Established in 1997 under Yemeni law, SFD is a quasi-governmental organisation that operates nationally and is one of the few remaining Yemeni institutions investing in Yemen’s development. With over twenty years of experience it has become a primary partner in Yemen for international donors, including the World Bank and German Development Bank KfW. SFD has worked to gain and maintain the confidence of all its stakeholders, including international donors and the local communities it serves, by protecting its reputation for independence and political neutrality. This has helped to ensure wide reach across the country including to areas which other international partners have difficulty accessing.

FCDO has supported SFD since 2004. Under current programming with SFD, FCDO has commissioned a number of assessments including: an external due diligence assessment of SFD through BDO, an accountancy and business advisory firm, in 2019, an assessment of SFD’s M&E systems and an impact evaluation of SFD’s social safety net and small and micro enterprise development components through FCDO’s IMEDA programme. An enhanced due diligence assessment was also completed by the programme team in October 2018. The assessments have identified a number of areas for improvement which SFD has been implementing including rolling out safeguarding training across the organisation; recruiting a risk management lead and enhancing risk reporting from the branch offices to HQ; drafting a project prioritisation strategy setting out clear targeting criteria; and enhancing terrorist checks on employees, contractors and suppliers. In addition, the World Bank has recently finalised an institutional and operational assessment of SFD. These assessments, alongside those of other donors and our ongoing partnership with SFD under YeSP since 2018 provide sufficient assurances of their capacity to deliver.

The BDO and World Bank assessments have highlighted potential issues with SFD’s governance arrangements. SFD’s Board of Directors is chaired by the Prime Minister, with membership from several Government ministries, civil society and the private sector. It has not met since 2014 due to the conflict and key decisions have been delegated to the Managing Director and the Project Policy Committee which is made up of SFD’s Unit Heads. This has helped maintain SFD’s neutrality but there remains a risk as they cannot fully replicate the role of the Board. Donors led by the World Bank have therefore increased their oversight of SFD’s operations but the risk to SFD’s political neutrality needs continued monitoring. Indeed, the 2020 Internal Audit Report recognised SFD was a “competent partner occupying an unusual position” and one of the key recommendations was that donors provide a more rigorous challenge function, particularly on strategic issues.

The impact evaluation of SFD’s social safety net and small and micro enterprise development components will assess how effectively SFD has adapted these programmes to the conflict situation and how short term, output level, results may contribute to longer-term expected outcomes and impact. The evaluation is expected to generate practical conclusions and recommendations for both SFD and FCDO, as well as provide insights into programming in complex operating contexts which will be relevant to FSSN and the broader humanitarian community. The evaluation will be completed by June 2021.

YeSP scored a B in the 2019 Annual Review due to concerns around the accuracy of SFD’s reporting. This led to a fundamental review of the YeSP logframe in 2020 and institutional indicators were added to incentivise institutional strengthening of SFD in several areas including development of Management Information Systems, risk management, complaints handling, targeting of the most vulnerable, SFD’s engagement on cash reform and social protection system strengthening, and the percentage of beneficiaries with a unique identifier. YeSP scored an A in the 2020 Annual Review and the YeSP programme team is continuing collaboration with other donors to further strengthen SFD’s systems and processes in a number of core areas including inclusion, monitoring and evaluation, procurement and financial management.

UNICEF

Under YeSP, FCDO Yemen has supported four payment cycles of the World Bank/UNICEF ECTP which reaches up to 1.5 million vulnerable households on the SWF beneficiary list with quarterly unconditional cash transfers. FCDO Yemen’s contribution in 2018/19 originally contributed to the base payment amount for beneficiaries. Additional financing in May 2020 was used to accelerate and support a top-up to the value of the eighth quarterly payment cycle to respond to anticipated impacts of the COVID-19 outbreak on Yemen’s most vulnerable households. A further extension to YeSP was secured in December 2020 to support a top up under the ninth payment cycle in light of increased food insecurity.

A due diligence assessment of UNICEF was undertaken in July 2016 and an enhanced assessment covering safeguarding was completed in 2018. A due diligence refresh is currently underway. In April 2019, UNICEF’s Office of Internal Audit and Investigations conducted an audit of the Yemen Country Office covering the period January 2017 to March 2019. The subsequent report cited the ECTP team’s “commendable risk management culture” and “robust risk management processes”, recommending a similar approach for other UNICEF activities in Yemen.
[note] UNICEF, 2019, Internal Audit of the Yemen Country Office, accessed on 20 April 2021, link here

The audit of YeSP that was undertaken by Internal Audit Department in 2020 also covered the ECTP component. A number of recommendations were made in relation to fraud reporting and the programme team has since agreed with UNICEF that they will provide a comprehensive breakdown of all grievances received and subsequent follow up measures six to eight weeks after each payment cycle. It was also recommended that FCDO work with UNICEF and the World Bank to develop a monitoring system for payments that are disbursed to proxy beneficiaries to verify the status of the primary beneficiary.

Over the coming year, delivery of the ECTP is likely to transition from UNICEF to SFD, supported by the World Bank. This transition is in line with the World Bank’s focus on retaining national implementation capacity. It is not possible to transition to SWF at this stage as it is not possible to work through Government systems until the conflict is resolved and a peace deal is in place. SWF staff are however employed to deliver the ECTP, thus preserving the institutional capacity to an extent. To support SFD’s transition to becoming a direct recipient of World Bank / International Development Association (IDA) funding, the World Bank is investing heavily in capacity building of SFD through the provision of technical guidance and support. Under this Business Case, we will channel funding through UNICEF or a World Bank Trust Fund until the transition and then continue to support the ECTP either through SFD or the Trust Fund. SFD will shadow UNICEF staff during upcoming payment cycles and UNICEF will support their capacity building before the transfer.

INGOs

NGO partners for the FSSN intervention will be selected through a competitive process. However, overall performance to date under the existing Multisector Humanitarian Response Programme (MHRP) which is delivered through a range of NGO partners indicates good performance, albeit with some challenges. NGOs have a strong role on accountability. They have demonstrated strong risk management and increasingly stronger financial management and quarterly reporting which is generally on time and to a good standard. Emergency budget lines were used effectively where possible within the FCDO budget, and management of exchange rate fluctuations was done well and proactively which allowed effective reprogramming of funds. Communications between the MHRP programme team and NGOs has been strong overall, however, in some areas could be improved. The programme team has worked with NGOs to bolster financial management and reporting quality to ensure good monitoring of the programme and VfM for UK taxpayers.

The programme scored an A overall in its 2020 Annual Review but the cash output scored a B due primarily to access issues outside partners’ control. These included increasing administrative obstacles in areas under de facto authorities’ control, COVID-19 restrictions and increased conflict in areas targeted under the intervention. Although partners were able to successfully negotiate with authorities, the delay meant fewer transfers were achieved than planned in the reporting period. We will continue to monitor these risks under the current MHRP intervention.

How will value for money be achieved through procurement?

FCDO will not procure any goods directly under this Business Case. The approach to direct procurement of partners is outlined below as well as key considerations related to partners’ procurement policies.

WFP

WFP procurement processes are in line with UN procurement rules. The policies were shared with FCDO as part of the due diligence process in October 2017 and are satisfactory. WFP’s procurement function has evolved significantly over recent years. WFP procurement policies will be reviewed again as part of the due diligence refresh later this year.

SFD

SFD has well established and robust procurement and finance systems in place. All external audits of SFD have been unqualified, providing the necessary assurances that FCDO funds have been separately accounted for and used as intended. SFD has a dedicated Procurement Unit, which is responsible for a range of tasks including ensuring that procedures for subproject procurements are applied; preparing and reviewing SFD’s procurement plan; updating Standard Bidding Documents for civil works, goods and consultants’ contracts; and maintaining a roster of consultants and contractors etc. Work is ongoing with other donors to further enhance SFD systems. Over the coming year, the World Bank will be working with SFD to further enhance procurement regulations, including through contract management training for staff, and KfW will be hiring an auditor to undertake financial audits and audits of SFD’s procurement procedures from 2019 (backwards verification) to 2022. A joint donor/SFD action plan is in place to monitor progress against these actions. This is reviewed on a quarterly basis.

UNICEF

A Central Assurance Assessment of UNICEF in 2020 confirmed that UNICEF has significant and established procurement capability. It noted, however, that UNICEF is still institutionalising VfM within its work, with a VfM policy being drafted and procedures put in place as well as building capacity. The assessment also noted there was scope to strengthen financial reporting to donors. The country-level due diligence refresh which is currently underway will examine how the VfM policy will be applied at the country office level.

INGOs

Selection of implementing partners for the NGO component will be organised through a competitive call for proposals opened to all international and national NGOs. The launch will include a detailed presentation to support the call for proposals explaining the rationale behind the intervention, lessons learned from the previous MHRP intervention, and the expected outcomes and measures of success. This will be supported by the TAF. Bidders will be encouraged to form a consortium where this leads to efficiencies. Given restrictions on travel due to COVID-19, the launch likely to be held virtually with NGO partners based in Amman, Sana’a and Aden joining by videoconferencing. A scoring matrix will be designed to evaluate strengths and weaknesses of the proposals received. The selection criteria will include the comparative advantage of each organisation, proven ability to deliver across Yemen and existing presence in Yemen, gender and conflict sensitivity, and VfM indicators.

Rigorous due diligence assessments will be conducted on the single bidding NGOs and consortium lead NGOs to assess governance and internal controls, financial management, ability to deliver and manage risk, and safeguarding policies. These assessments will also provide assurance that appropriate levels of due diligence have been carried out by all consortium lead agencies and downstream organisations. Spot checks will be undertaken on downstream partner due diligence assessments and further details of the delivery chain will also be scrutinised as part of the due diligence process. Where additional information is required, FCDO will work closely with the lead agency on strengthening our assurances. Action plans will be put in place for any identified weaknesses.

FCDO will hold the NGOs to account for the management and delivery of outcomes through quarterly reviews of the logframe, expenditure reports and by conducting detailed Annual Reviews. Regular meetings will ensure partners manage and alert FCDO to delivery risks such as, early access constraints, enabling collaboration on alternative arrangements. Future payments will only be made after satisfactory reporting of the previous quarter, demonstration of delivery against outputs and evidence of future plans and accurate forecasting.

Technical Assistance Facility (TAF)

The Senior Responsible Owner, supported by a Commercial Delivery Manager, will lead a tender process for the TAF through the IMDP Framework. The IMDP framework includes suppliers with multi-disciplinary teams including Technical Advisory Experts with proven expertise in a range of thematic areas including research, humanitarian and social development and experience working in complex and fragile contexts. The framework has been designed to ensure VfM, allowing for increased supplier participation and competition whilst enabling more efficient procurement processes with regard to the subsequent call-down contract. The suppliers included in the framework have already undergone a procurement process and signed up to FCDO Terms and Conditions.

A ToR will be developed by the programme team with support from an FCDO procurement specialist. In line with FCDO’s procurement policies, the ToR will clearly identify the need with a focus on the anticipated results and impact of the TAF function in gathering evidence on interventions, supporting partners in identifying shared vulnerability targeting, improving understanding of the less tangible benefits of Cash for Nutrition and Cash for Work interventions, supporting our policy work on cash reform and coordination, and ultimately supporting the adaptive programming approach. The ToR will be shared with other humanitarian and development actors as it is hoped the research products will inform their interventions too, in line with wider cash reform objectives. A competition will be carried out to enable the programme team to test the framework suppliers against the ToR.

Supplier bids will be assessed against a range of technical and commercial criteria, with a 60% and 40% weighting respectively. The technical evaluation criteria will focus on the range and quality of expertise presented, utilisation of local expertise, the structure of the proposed team and their technical approach. The commercial focus will include an in-depth appraisal of bidders to clearly identify cost drivers, including rates for short- and longer-term experts, their ability and capacity to manage finances and risk efficiently and effectively.

The IMDP framework has an in-built pre-determined ceiling rate card for ‘job families’ (project leadership, project admin, project coordination and technical expert roles) based on robust market intelligence. These have been agreed up front by all framework suppliers, but the competition may lead to suppliers providing more competitive rates, thus further enhancing VfM. The successful bidder will have to demonstrate significant competence and capability that ensures VfM in implementation. This will include following FCDO procurement standards to drive competition through any procurement that it undertakes.

A Payment-by-Results (PbR) mechanism will be adopted for the successful bidder, to ensure effective delivery of milestones as set out in annual workplans, and ultimately outputs and outcomes. The contract term will be for 24 months initially, with the option to extend for a further two periods of up to 12 months if supplier performance is satisfactory. The contract will be subject to a break point after the first 12 months. Continuation of the services will be based on satisfactory progress of the supplier against the specified outputs.
Design funding

Programme funds may be used to assist with the design of the intervention. A Delegated Procurement Officer will oversee the selection of a supplier through a competitive process. A ToR will be developed by the programme team and reviewed by the Delegated Procurement Officer detailing the outputs the supplier is expected to provide. To avoid any conflict of interest, it will be made clear that the selected supplier’s involvement in the design phase will preclude its involvement in or ability to bid to work on the Technical Assistance Facility.

How will value for money be achieved during implementation?

The Appraisal Case sets out the numerous considerations of VfM. In line with FCDO Yemen’s VfM strategy (due to be finalised by the end of June) we will need to follow up on key issues (cost drivers, monitoring efficiency of unconditional cash transfers and Cash for Work projects) as part of ongoing project monitoring and through the TAF.

The programme team will work with implementing partners to improve tracking, monitoring and reporting of VfM against a range of indicators. FCDO will work closely with partners to ensure that overheads are reasonable and, where applicable, in line with Non-Project Attributable Costs (NPAC). As a first step these matters will be reflected in the final logframe and as part of other routine project cycle management processes, e.g. Annual Reviews and quarterly meetings with partners. Baseline measurements for VfM indicators will be established during the mobilisation phase, before funds are disbursed, to enable judgements to be made about VfM during implementation.

## D. Financial Case

In this section we outline how programme funds will be disbursed and how expenditure will be controlled, monitored, reported and accounted for. We also consider the financial and fraud risks for this intervention and how they will be managed, taking into account partners’ systems and processes.

Overview of costs

The total budget for this business case is £250 million from 2021/22 to 2026/27. With the programme forecast to spend beyond the current spending review period, approval from HMT will be sought. Agreements with NGOs and SFD and the contract for the TAF supplier will include clear break clauses. Agreements with UN agencies will be amended annually upon confirmation of budgets.

The Business Case will be funded by the FCDO Yemen programme budget (RDEL) and is fully ODA-eligible. The programme will contribute to the overall FCDO Yemen Business Plan. The £250 million budget is based on current FCDO cash programming through WFP, YeSP and MHRP. The amount proposed reflects the protracted nature of the crisis in Yemen, the possibility of increased food security needs and continued economic downturns. The required funding for the first year is available within the current FCDO Yemen resource allocation which currently stands at £87 million for 2021/22. Previous resource allocations for FCDO Yemen have been significantly higher at £220 million for 2020/21 and £232 million for 2019/20. While future resource allocations may increase and be sufficient to cover the FSSN budget, we may also need to bid for contingency from the Central Crisis Reserve (where possible) or reduce the number of people reached by the programme.

The indicative budget for the three main outputs is outlined in table 6 in the Commercial Case. The budget for each delivery partner will not be overly prescriptive to provide room for adjustments and the flexibility to adapt to increasing or decreasing needs by allocating funds to respond to emerging priorities and changing political and economic conditions. This flexibility will also ensure the intervention can apply evidence on what works. The initial funding split per delivery partner will be developed during the design phase with a base amount assigned to each partner. This will then be reviewed continuously during implementation and uplifts will be provided to support the scale up of particular activities based on evidence of needs and impact and in line with FCDO Yemen’s resource allocation.

Cost profiling and planning

The funding type and input sector codes for each of the components and delivery partners are detailed below. We recognise that accurate input sector codes help ensure the integrity of our external reporting for statistical, transparency and information purposes. We will review these codes and percentage allocations again at the end of the design phase to ensure the percentage allocations are correct.

Table 7: Funding type and input sector codes per component

Component 1 – Funding to WFP
Funding Type: 109 – Multilateral Organisation
	Input Sector	Input Sector Code	% Allocation
1	Emergency Food Aid, Humanitarian	72040	100%
Component 2 – Funding to INGOs
Funding Type: 2362 - Accountable Grant
	Input Sector	Input Sector Code	% Allocation
1	Emergency Food Aid, Humanitarian	72040	80%
2	Social Protection, Social Infrastructure and Services	16011	20%
Component 3 – Funding to SFD
Funding Type: 111 – Not for Profit Organisation
	Input Sector	Input Sector Code	% Allocation
1	Emergency Food Aid, Humanitarian	72040	40%
2	Social Protection, Social Infrastructure and Services	16011	60%
Component 4 – Funding to UNICEF
Funding Type: 109 – Multilateral Organisation
	Input Sector	Input Sector Code	% Allocation
1	Social Protection, Social Infrastructure and Services	16011	100%
Component 5 – Funding for the Technical Assistance Facility
Funding Type: 104 – Procurement of Services
	Input Sector	Input Sector Code	% Allocation
1	Emergency Food Aid, Humanitarian	72040	50%
2	Social Protection, Social Infrastructure and Services	16011	50%
Component 6 – Funding for the design phase
Funding Type: 104 – Procurement of Services
	Input Sector	Input Sector Code	% Allocation
1	Emergency Food Aid, Humanitarian	72040	50%
2	Social Protection, Social Infrastructure and Services	16011	50%

How will the budget be profiled?

The indicative quarterly budget profile for the first two years and anticipated annual budget profile for the final three years of the intervention are shown in tables 8 and 9 below. Potential delays in the procurement of the TAF and NGO consortia have been factored into the budget profiling for the first year.

We intend for the funding in this business case to be programmed flexibly as the situation changes and adjusted in line with partner performance and the relative impact of different interventions in responding to food insecurity. This will help ensure the intervention remains cost effective.

Table 8: Estimated quarterly budget profile for the first two years of the intervention

	FY 2021/22		FY 2022/23				Total:
	Q3	Q4	Q1	Q2	Q3	Q4
Cash based assistance	£0	£2,500,000	£12,900,000	£12,900,000	£12,900,000	£12,900,000	£54,100,000
TAF supplier	£0	£50,000	£100,000	£100,000	£100,000	£100,000	£450,000
Design fund*	£30,000	£15,000	NA	NA	NA	NA	£45,000
Total:	£30,000	£2,565,000	£13,000,000	£13,000,000	£13,000,000	£13,000,000	£54,595,000

*Funding for design would only be used in FY 21/22

Table 9: Estimated annual budget for the final four years of the intervention

	FY 2023/24	FY 2024/25	FY 2025/26	FY 2026/27	Total:
Cash based assistance	£51,600,000	£51,600,000	£51,600,000	£39,055,000	£193,855,000
TAF supplier	£400,000	£400,000	£400,000	£350,000	£1,550,000
Total:	£52,000,000	£52,000,000	£52,000,000	£39,405,000	£195,405,000

How will funds be disbursed?

All commitments and payments to partners will be made in British pound sterling. Disbursement mechanisms will vary depending on the aid instrument used and we will agree on reasonable disbursement schedules based on annual forecasts as provided by partners. No payments will be made in advance of need.

WFP: We will make quarterly advance payments as set out in the Contribution Arrangement and governed by the agreements in the Mutual Accountability Framework.

NGOs: We will disburse funds to the NGO leads on a quarterly basis in advance, as stipulated in the AG.

SFD: We will provide pre-financing on a quarterly basis upon receiving an official request from SFD, as set out in the MoU.

UNICEF: We will make advance payments as per the terms set out in the Contribution Arrangement. Payment will be made at least six weeks ahead of the payment cycle to ensure UNICEF has sufficient time for currency exchange.

TAF: Payments will be made in arrears on successful delivery of the milestones as set out in the contract. The same principle will apply for the design component in the first year of programming.

How will expenditure be managed and reported?

Delivery partners will be required to provide accurate forecasts of expenditure at the beginning of each financial year. In line with FCDO’s Financial Planning and Budgeting Policy, the programme team will then ensure budgets are profiled monthly across the year on FCDO’s financial systems. This will reflect the timing of the activities being funded in line with resource accounting principles.

We recognise the need to reconcile the adaptive programming approach with the need for accurate budget forecasting and minimal variance. Spend will be closely monitored over the implementation period and recorded on the system as part of FCDO’s monthly finance cycle. Partner forecasts will be revised regularly in accordance with the respective delivery agreements and on a monthly basis where possible.

The programme team will maintain regular contact with partners to ensure that data input as part of FCDO’s monthly finance cycle is accurate and that FCDO is able to identify and monitor the financial impact of any changing circumstances and emerging risks. In addition, partners will submit bi-annual financial reports with detailed expenditures and explanations for any variance as well as progress reports. We will continuously review spending plans over the implementation period to avoid slippage and spending risks and aim for less than 5% annual variances to forecasts. Where significant risks are identified, we will escalate these to FCDO Yemen’s Finance Manager to allow for effective financial management across the Yemen programme portfolio.

Financial and fraud risk assessment

Yemen is a fragile and conflict affected country and delivering cash transfers to a large number of beneficiaries in such a context carries a high degree of risk. In 2020, Yemen featured at 176 out of 180 countries on the Transparency International Corruption Perceptions Index. Partners therefore operate in a context where there is a high likelihood of fraud risk.
[note] Transparency International 2021, Corruption Perceptions Index 2020, accessed 29 April 2021, link here

FCDO Yemen will take all the necessary steps to mitigate risk and ensure the programme adheres to FCDO’s zero-tolerance policy on fraud and UK Counter Fraud/Bribery and Counter Terrorism legislation. We will build on lessons learnt through current interventions including through implementing the recommendations of the 2020 Internal Audit report in relation to managing fiduciary risks. These include: improved aid diversion measures and fraud reporting from partners; ensuring the risk scoring is accurate; increasing third party monitoring coverage and direct beneficiary engagement; working with partners to ensure risks of terrorist financing and corresponding controls are clearly identified on the delivery chain maps; and monitoring risks related to exchange rate management.

The programme team will immediately notify FCDO’s Internal Audit Investigations Section (IAIS) where there are incidences of fraud detected and assist in any necessary investigations. Partners will also be made aware of their obligation to report credible suspicions or instances of fraud either to the programme team or directly to IAIS.

FCDO Yemen will maintain a robust risk matrix to help monitor, track and mitigate key issues. The main financial and fraud risks and corresponding mitigation measures are detailed in the table below.

Table 10: Financial and fraud risks and mitigation measures

Risk	Mitigation
Funds are not used for the intended purpose	Progress reports including breakdown of expenditure will be required from all partners quarterly. These will be reviewed by the programme team and complemented by quarterly partner meetings to discuss progress, risks and mitigation measures. Quarterly reports will be augmented on a bi-annual basis with financial reports. / Annual audits on partners, including certified financial accounts, will examine the effectiveness of control systems and fiduciary management. / Our third-party monitoring programme, whilst not designed specifically to detect fraud, will provide assurance that funds are being used appropriately.
Lack of awareness on UK legislation leads to weak controls, aid diversion and funds being diverted to terrorist groups	FCDO’s MoU, Accountable Grant and contract templates include provisions on counter-terrorist financing, bribery, fraud and corruption. The Framework Arrangements with UNICEF and WFP also reference the zero- tolerance approach toward fraud and corruption. / Fraud will be a standing agenda at all partner meetings, ensuring all partners understand FCDO procedures and requirements to report and act on fraud and aid diversion concerns.
Poor targeting and beneficiary identification lead to fraud e.g. through ghost beneficiaries, payments to ineligible recipients, collusion involving payment agents and community leaders, and double payments to beneficiaries	Attention will be given to appropriate targeting/beneficiary selection, accountability to affected populations including through robust grievance mechanisms, monitoring and evaluation, and a conflict sensitive approach. We will also ensure that robust verification measures are in place to minimise the risk of aid diversion. In addition, aid diversion will be mitigated by ensuring adequate supervision of the payment distribution process through partners’ monitoring mechanisms as well as FCDO’s third-party monitoring. Post-distribution monitoring will also take place. / In terms of current partner processes: / WFP has biometric identification methods in place for all cash transfer distributions related to FCDO funding. There is also strong community engagement and beneficiary selection through village committees. / Under SFD programming, community committees play a role in the selection and identification of beneficiaries. Two factors of identifications are required, including a household card issued by SFD. / Under the ECTP, payments are made to beneficiaries from the SWF list after a rigorous triangulation method of verification. Independent payment delivery agencies with transparent and robust internal controls and oversight procedures are engaged to monitor emergency cash payments to SWF beneficiaries.
Weak financial management and controls gives rise to corruption, fraud and aid diversion	Due diligence assessments of partners will be reviewed on a periodic basis to assess their governance and internal controls and systems, their delivery capacity, financial management and capacity of downstream partners in order to provide assurance that implementing partners have sufficient internal controls to deliver UK Aid. / Existing due diligence assessments for partners indicate robust controls, albeit with the need for some improvements which we are supporting partners to implement. / FCDO has pushed WFP to create their Operational Roadmap which aims to strengthen several areas of their operation to combat aid diversion. Progress against the Roadmap is reported on in the annual review. / As recommended by the BDO due diligence assessment, SFD is collating its various financial processes into a comprehensive financial manual. Over the coming year, the World Bank will be reviewing SFD’s accounting processes to ensure compliance with International Public Sector Accounting Standards. / For the ECTP, the financial management framework clearly sets out expectations on financial management in terms of preparation of accounts and the requirement for audited financial statements detailing the activities funded. Clauses in contracts between UNICEF and payment agencies means if fraud is confirmed, the payment agencies have to reimburse the funds. No funds are channelled through government institutions. / A key component of the proposal assessment and selection criteria for the NGO consortia will include the ability to demonstrate strong systems and controls to both detect and prevent fraud. A due diligence assessment will be undertaken on the selected consortia lead, with a dedicated section on financial management and fraud prevention policies. Where weaknesses are identified, we will work with partners to strengthen controls.
Poor oversight of the delivery chain leads to increased instances of fraud as funds are mismanaged by downstream partners	In line with the Programme Operating Framework, partners will be required to complete delivery chain mapping before funds are disbursed. These will help clarify the flow of funds down to the end beneficiary, identifying all partners involved in programme funded activities. / The programme team will work with partners to identify opportunities for aid diversion and potential fraud enablers at each stage of the delivery chain. We will ensure the risks are managed effectively with appropriate due diligence undertaken down the chain. Partners will also be required to facilitate FCDO’s engagement with downstream partners on an ad hoc basis as necessary. / Delivery chains will be updated at the annual review stage. Any changes to the delivery chain or risk assessment will also be discussed with partners during quarterly meetings. / Field visits undertaken by third party monitors will provide opportunities to examine the how fiduciary controls are working in the field.
Weak reporting systems mean concerns go unreported and beneficiaries do not receive the full payment amount	WFP, SFD and UNICEF have robust and transparent feedback mechanisms in place for beneficiaries and staff to raise grievances, complaints, concerns or any other issue related to delivery. This will form part of the assessment for the NGO consortia too. / Field visits undertaken by third party monitors will report on downstream partner, field staff and beneficiary awareness of the respective reporting mechanisms. / FCDO will continue to remind partners of their responsibilities in terms of reporting fraud concerns either to the programme team or to IAIS.
Funds do not achieve value for money	VfM considerations for each output will be reviewed at the annual review stage. / Banking sector and exchange rate risks will be monitored with the support of FCDO economists and partner exchange rate policies will be reviewed to ensure there are no unnecessary losses to programme funds.

Monitoring, reporting, and accounting for funds

Reporting requirements will be clearly set out in the funding arrangements agreed with partners. Partners will be required to report on expenditure and results achieved based on agreed timeframes. The level of detail required will be realistic, proportionate and obtainable. Formal discussions with partners will be held on a quarterly basis to determine project progress as well as informal discussions on a more regular basis.

Partners will be required to maintain an asset register of all assets purchased using FCDO funding. This will be updated at a minimum annually. The programme team will ensure that assets are disposed of at the end of agreements in accordance with FCDO procedures and in a way that maximises VfM.

Return of funds will be in line with requirements set out in the agreements i.e. unspent funds or remaining interest accrued at the end of the programme to be returned to FCDO.

## E. Management Case

In this section we outline the governance and management arrangements necessary for the successful delivery of this programme, including monitoring and evaluation processes and how the management structure will contribute to the vision of a coherent cash response. We also set out our approach to risk management.

What are the managing arrangements for implementing this intervention?

FCDO Yemen’s Humanitarian and Development Team will have oversight and accountability of the entire delivery cycle of FSSN. FCDO will effectively play the ‘consortium lead’ role in convening partners and coordinating activities and reporting to better incentivise reform objectives. We recognise that the management of the programme will be time intensive due to its adaptive nature and the need for more regular engagement with delivery partners. However, direct management of the programme (as opposed to appointing a fund manager or channelling support through a World Bank Trust Fund for instance) affords FCDO the greatest control of the programme, and direct engagement affords the greatest leverage. It also represents better VfM than alternative management options. We have assessed our capacity to manage up to six delivery partners and have concluded that the administrative burden is manageable. Key individual positions proposed to deliver the FSSN Business Case and ensure the effective management and coordination of delivery partners are set out below:

Table 11: Roles and responsibilities

Role	Responsibility	Time
Senior Responsible Owner (SRO) – A2 Social Development Adviser or Humanitarian Adviser	Oversight of delivery of the programme / Strategic leadership on systems strengthening, programme adaptation, M&E and research through oversight of the TAF component / Lead the Quarterly Programme Board with partners / Co-chair of the Cash and Social Protection Donor Working Group	100% FTE
Programme Responsible Owner (PRO) – / A2L Programme Manager (PM)	Ensuring that the programme delivers results and VfM, and that risks are appropriately managed / Lead set up of NGO consortium / Manage B2 Country Based Programme Officer / Secretariat support for the Quarterly Programme Board	100% FTE
Adviser – / A2 Humanitarian Adviser	Advisory inputs to delivery partners and on cash reform/coordination / FCDO representative at the CMWG and FSAC	50% FTE
Adviser – / A2 Social Development Adviser	Advisory inputs to delivery partners and on cash reform/coordination	50% FTE
B2 Country Based Programme Officer	Support to A2L PM for all 5 components / Lead on financial management / Responsible for risk management, including due diligence and assurance audits	100% FTE
B1 Programme Manager	Support to A2L PM for all 5 components / Secretariat support for the Quarterly Programme Board	50% FTE
A1 Humanitarian Team Leader	Strategic oversight	10% FTE
A2 Results Adviser	Support on results and data disaggregation / Advisory input on TAF component	15% FTE

Additional resources to support decision-making and for technical advice on programme components will be available within the wider FCDO Yemen team as follows:
- Livelihoods Adviser: advisory input across all components; specific support on INGO and SFD components.
- Humanitarian Data Adviser: advisory input across all components; specific support on TAF component.
- Economist: advisory input across all components, particularly related to VfM.
- Conflict Advisor: advisory input on conflict sensitivity
- Health/Nutrition Adviser: advisory input on CfN activities

The team will also draw on support from the FCDO Climate and Environment Department to support partners with their assessment of environmental impacts of programming where necessary e.g. for CfW programming.

Flexible and adaptive programming

As outlined in the Appraisal Case, the TAF will support an adaptable programming approach that enables more deliberate experimentation, learning and adaptation responding to evidence and learning on the most effective approach to address food insecurity and incentivise improved coordination through layering of programmes.

The TAF will also support the FCDO team with ensuring the programme follows principles of flexible and shock responsive programming as appropriate. This will enable rapid scale up or reallocation of resources, or flex in the type of assistance, in response to unexpected shocks and changes in context. For example, flexing from cash to vouchers and / or food in-kind might be required as a last resort if progress in biometric registration is slowed by national authorities, commercial food imports are substantially affected or exchange rate fluctuations require the use of in-kind in order to meet acute humanitarian need and deliver VfM through speed and timeliness of response. Alternatively flexing the programme to increase the proportion of programme funds directed through national Yemeni institutions might be required if the political context makes it impossible for humanitarian actors to access those most in need or if increased stability provides opportunities to further strengthen national systems for the future.

The TAF will support FCDO and partners in delivering cash reform through the following three key functions:

Provide expert technical assistance to FCDO, delivery partners, the Cash and Markets Working Group and Donor Working Group on Cash and Social Protection, that is critical to driving cash reform and helping to better incentivise reform objectives through this programme. Technical assistance will support system strengthening objectives, improve VfM in the short term and support development of a shock-responsive national-owned social protection system over the longer-term. Technical assistance will also be provided to delivery partners on specific programme priorities including gender, inclusion and Accountability to Affected Populations.

Support with the design a decision-making framework for how funds will be allocated between delivery partners. The TAF will lead on the design of this decision-making framework, with identification of clear evidence-based ‘triggers’ instigating changes to this allocation throughout the programme cycle. The TAF will then continue to support the FCDO programme team with on-going independent technical expertise, including reviewing the type and modality of assistance at least annually based on this framework and on-going data collection.

Improve understanding of the relative effectiveness of different interventions/delivery partners. Whilst understanding of humanitarian needs and the operating environment continues to improve, food security assessments are only undertaken once a year at best and significant data gaps around household food insecurity and vulnerability remain. This is an inevitable consequence of access challenges in a highly insecure and politicised environment. The TAF will support to improve the granularity of data and analysis on food security (drawing on Third Party Monitoring provided by FCDO Yemen’s IMEDA programme which has budget built in to support the various programmes in the Yemen portfolio), and a longitudinal impact evaluation. The facility will play a critical role in ensuring data is used to improve the equity and effectiveness of the programme as well as strengthening the wider evidence base on cash-based approaches to responding to food security both in Yemen and globally.

Decision-making authority on whether to amend, augment or abandon interventions based on their sustainability, effectiveness and impact on vulnerable households and the ‘triggers’ outlined in the decision-making framework will rest with the SRO. It is envisaged that decisions on programme flex will be made on an annual basis at least. Data used to inform these decisions are outlined above. Partners will also be consulted during the decision-making process. The PRO will be responsible for ensuring that all course-corrective decisions and the rationale for them are formally documented.

Figure 2: Diagram outlining key relationships and information flows

Programme Governance

In line with the second objective of this Business Case to incentivise reform of cash responses to food insecurity in Yemen, the proposed governance structure will support a holistic and coherent approach to cash interventions and help the shift to more strategic and evidence-based prioritisation of resources and activities. Quarterly Programme Boards, chaired by the SRO and attended by the PRO and programme managers, lead advisers, donor and programme leads from partner organisations, and a representative from the TAF will provide strategic oversight of the programme. The Quarterly Programme Board will establish a coordinated structure to share evidence and learning, monitor progress and discuss course corrective actions, promote synergies, discuss risks in the operating environment and address technical challenges. It will also provide a forum for implementing partners to help identify cross-cutting operational research questions for the TAF component in support of programme objectives and to strengthen the wider evidence base on cash programmes in the Yemen context. Where appropriate, representatives from key cash forums will also be invited to attend. The PRO will provide a secretariat support function for the Quarterly Programme Board and it is envisaged that a high-level Board is held once a year with senior leadership from FCDO Yemen and partner organisations to ensure continued buy-in for reform objectives.

The programme will encourage coordination with other donors and the Government of Yemen and de facto authorities through existing working groups and national steering and technical committees. FCDO will continue to co-chair the Donor Working Group and both the programme team and implementing partners will be required to actively engage in technical meetings led by the Cash and Markets Working Group, the Food Security and Agriculture Cluster and other relevant clusters/forums.

Internal FCDO ways of working will ensure this programme maximises synergies with other FCDO Yemen programmes and is informed by and informs FCDO engagements. In-country oversight of the overall humanitarian response is managed by the Humanitarian Country Team (HCT). The HCT is chaired by the UN Humanitarian Coordinator and includes representatives from donors, NGOs and the UN. FCDO is represented on the HCT by the Deputy Humanitarian Team Leader. Synergies will also be maximised with development partners, including through our strategic relationship with the World Bank.

Mobilisation Phase

A seven-month mobilisation phase is envisaged for the TAF and NGO components (with funding to WFP and SFD to start in parallel where possible). This is designed to allow sufficient time for a tender process for the TAF supplier and for the finalisation of the design of the programme. We propose to utilise design funds as well as the TAF and FCDO’s Better Assistance in Crises (BASIC) centrally managed programme during the start of the mobilisation phase to enhance our understanding on outcomes of different food security interventions and to support decision-making on the amount of funding assigned to each delivery partner at the outset of the programme. Other key issues to be clarified during the mobilisation phase include the design of adaptive and flexible processes, the accompanying monitoring framework and triggers for flex, in close cooperation with the implementing partners and FCDO. This will be essential to ensure that inputs and activities are realistically programmed to deliver outcomes in a complex, politicised and dynamic context.

FCDO’s Procurement and Commercial Department (PCD) will lead the contracting of the TAF supplier. The PRO will lead the selection of NGO partners, the finalisation of agreements with bilateral partners, agreement with partners on governance and coordination mechanisms, finalisation of the programme logframe, the establishment of programme baselines, and ensuring that key monitoring activities and reviews are embedded in the programme delivery plan.

Monitoring, Evaluation and Learning

Monitoring, evaluation and learning will take place continuously at both the project and programme level to ensure robust, real-time evidence supports programming decisions, leading to improved results and impact.

The TAF will provide an integrated monitoring and evaluation function, ensuring high quality technical assurance of the programme, promoting systematic learning across the programme components, strengthening the evidence base for programming and studying the relative impact of different cash interventions and implications for system reform. The TAF will conduct specialist research and studies where necessary, responding to demand of partners and programme gaps, to generate additional learning about the different interventions and their relative impact on strengthening resilience and improving food security outcomes. Due to the size and complexity of the intervention, FCDO Yemen’s IMEDA Programme will also be used to verify outputs and provide assurance on the quality of interventions through spot checks, field visits and the gathering of beneficiary feedback.

As outlined in the Appraisal Case, it is a priority for FCDO Yemen to build on the data and strengthen the methodologies for assessing the VfM of humanitarian cash transfers and social protection programmes, including in emergencies, which currently focus on effectiveness and speed of response. The scale and breadth of this intervention and the integrated monitoring, evaluation and learning function provide an opportunity to address these data gaps to improve VfM and ultimately drive cash reform. FCDO will commission a longitudinal evaluation through the TAF to better understand the long-term outcomes of the intervention on levels of food insecurity and resilience in Yemen. It is expected that the evaluation will use a mix of quantitative and qualitative methodologies. The logframe and theory of change will guide the evaluation questions. It will test the results chain in the Theory of Change, including whether the assumptions are correct; how far the programme has been able to address food insecurity in Yemen; and the extent to which the evidence base has been strengthened. FCDO will ensure that the evaluation approach is guided by the Development Assistance Committee principles, and by FCDO’s Evaluation Policy and ethics principles. FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS) will also be drawn on to quality assure the ToR and proposed methodology. The final report will be reviewed by the FCDO independent quality assurance mechanism before being published on DevTracker.

The programme logframe will be the standard management tool for reviewing performance. It will provide an overarching direction, ensure coherence between interventions and promote reform. Each implementing partner will also have a performance monitoring framework which will feed into the overarching programme logframe. Draft logframe indicators are included at Annex 4 but the final design of the programme logframe and other agreed milestones will be deferred to the programme mobilisation phase, with advice from the TAF supplier and including all implementing partners to set stretching but realistic targets. Indicators to measure learning and the adaptability function as well as contribution to cash reform will also be built into the logframe. In line with the Grand Bargain commitment to “increase the use and coordination of cash-based programming” and the need for more consistent outcome indicators across programming, the programme logframe will incorporate common outcome indicators as identified by the Grand Bargain cash workstream. to monitor the extent to which the cash meets basic needs. Where appropriate, the draft logframe includes indicators that were agreed by various humanitarian stakeholders in 2019. Understanding of how best to monitor cash outcomes is still developing and the Cash Learning Partnership has commissioned a consultancy to support the review and revision of these indicators. It is anticipated that any revisions to the indicators will be complete by June 2021. These will be reflected in the final logframe.
[note] Cash Learning Partnership, 2019, Multipurpose Cash Outcome Indicators – Final Draft for Testing, accessed 29 April 2021, link here
[note] Cash Learning Partnership, 2021, ToR: Consultancy to support the review and revision of the Grand Bargain MPC Outcome Indicators

Partners will provide FCDO with high-quality quarterly monitoring updates. These will indicate whether partners are on track to achieve the target results. A reporting template will be agreed with partners and will include a narrative report on progress made against the logframe indicators as well as dedicated sections on risk management, targeting and beneficiary selection, finances and VfM, conflict sensitivity, Accountability to Affected Populations and feedback on the less tangible benefits of interventions such as improved self-esteem and mental health. Partner reporting will be informed by their post-distribution monitoring. We will push for consistent questionnaires to be used to measure results against the agreed outcomes and to ensure that data from each partner is comparable. We cannot fully craft reporting requirements for WFP and UNICEF due to the centrally agreed Framework Arrangements. However, reports will be augmented by quarterly bilateral meetings with FCDO to monitor progress on the delivery of workplans, assess risks and key challenges to delivery, scrutinise financial management and identify issues that require escalation. These bilateral meetings will help inform the agenda for the Quarterly Programme Board which will convene all partners.

Delivery partners will be required to disaggregate data at a minimum by geography (governorate and district level), age, gender and disability as part of compliance to FCDO’s commitment to leaving no one behind. We will also require partners to collect data on vulnerable groups such as IDPs and the Muhamasheen.

In addition to the agreed monitoring processes, FCDO will monitor overall programme performance through Annual Reviews. The Annual Review will enable the programme team to assess progress against the outputs and whether results are on track, whether the components continue to represent VfM, how the adaptive function has worked in practice and what, if any, corrective action needs to be taken in line with the adaptive programming approach. Annual Reviews will be informed by desk-based reviews, third party monitoring reports, meetings with implementing and downstream partners, engagement with affected populations provided they are not put at risk (through the TAF) and engagement with other key stakeholders.

Partnership Principles

The partnership principles do not apply since we will not be providing funding to the Government of Yemen. SFD, the only national partner, is an autonomous quasi-governmental institution whose management is delegated the responsibility under Yemeni law to determine how it will invest donor funds, while respecting accords approved with its donors.

Risk

The risk appetite for this Business Case is set at Severe. The key risks are set out in the risk register in Table 12. The programme team recognises that residual risks are high for Yemen and require active monitoring, managing and mitigating actions. The PRO will ensure that all risks are addressed as part of the delivery plan, with monthly checks as part of FCDO Yemen’s internal portfolio oversight function.

The Internal Audit Department (IAD) review of FCDO Yemen (January 2021) notes progress made in risk management with our risk maturity being assessed as “implemented”, which is progress against the previous audit which assessed the maturity as “in progress”. Furthermore, IAD noted that the Yemen team is making positive strides to address the contextual risks within the approved risk appetite and is continuing to monitor and react which is crucial to the success of the portfolio.

Table 12: Risk Matrix

Category	Risk	Probability	Impact	Mitigation	Residual risk
Policy and programme	Delivery and quality of activities may be impacted by lack of oversight and limited monitoring ability in operating environment	Highly likely	Major	Ensure programme is reviewed by IMEDA and the TAF. / Liaise with other donors and encourage sharing of TPM reports to increase assurances and cross-check findings. Request that partners share their field monitoring reports too. / Due diligence assessments that are in place have provided adequate assurance of partner's monitoring processes but ensure these are revisited in any due diligence refresh.	Major
	COVID-19 outbreak in Yemen could worsen the humanitarian situation and reduce the impact of the interventions	Likely	Severe	A number of interventions to respond to the effects of COVID-19 are being implemented across the programme portfolio. / Adaptations to the intervention may be required in light of increasing COVID-19 cases e.g. through one off increases in the transfer value to support the resilience of the most vulnerable. / FCDO continue to support WHO COVID-19 response plan.	Major
	Lack of coordination between partners leads to duplication and impedes cash reform objectives	Likely	Major	FCDO to chair Quarterly Programme Board with partners to encourage coordination and assess partner participation in Annual Reviews. / FCDO and partners to engage with various working groups including CMWG, FSAC and the UN Common Cash Group to ensure coordination and maximise complementarities with other interventions. / Logframe to include common cash outcome indicators in line with the Grand Bargain commitments to ensure consistency in data being collected by partners. / A key performance indicator measuring coordination and collaboration will be used to assess partner performance	Major
	Volatility of fuel supplies and prices impact partners' ability to deliver in a cost-effective manner and lead to loss of power in partner offices and projects	Likely	Major	Partners to plan carefully for all projects and consider early procurement using local materials where possible (for CfW). / Encourage partners to move towards solar energy.	Moderate
	Procurement delays mean the TAF is not operational during the first year of programming and essential technical assistance will not be provided during the mobilisation phase	Possible	Major	Procurement will be undertaken using a framework agreement which is expected to take no more than 12 weeks. / Design funds will be used to fund a consultancy to provide technical inputs (the supplier will be selected rapidly as the procurement will be low value). / The programme team will start working on the ToR for the TAF as soon as possible to minimise procurement delays. / Early market engagement will be undertaken to ensure potential suppliers are aware of the opportunity.	Moderate
	Insufficient donor funding for complimentary activities to reduce mortality risks in Yemen (e.g. health and nutrition) reduces the impact of this intervention	Possible	Major	FCDO Yemen will continue to engage with other donors to ensure there is a holistic approach to addressing the humanitarian crisis in Yemen	Moderate
Strategy and context	SFD’s neutrality and operational autonomy could be compromised by political interference, including through the application of the Supreme Council for the Management and Coordination of Humanitarian Affairs (SCMCHA) clauses	Likely	Severe	Discuss regularly with SFD and other donors and if there are any issues then ensure FCDO in the region is able to lobby key actors on importance of maintaining SFD's neutrality. / SFD will convey to SCMCHA that their neutrality cannot be compromised. / SFD will flag any issues to donors so a consolidated position can be agreed if needed. / SFD will continue its conflict sensitive approach, including through programming in all governorates.	Severe
	Further deterioration of wider famine risk drivers (health, nutrition, WASH, protection, etc…)	Highly likely	Severe	FCDO to monitor evolution of famine risk drivers. / Programme team to seek regular updates from partners to better understand how food security and famine risk are being affected by the broader range of drivers. / FCDO to lobby partners for regular real time monitoring of famine risk drivers, to provide information between IPC analyses. / Programme part of a coherence portfolio that addresses key drivers (Yemen FCDO portfolio also addresses nutrition and protection among other critical needs). / FCDO to advocate with other donors for funding of a comprehensive response that addresses the breadth of famine risk drivers.	Severe
	Further macroeconomic instability such as depreciation of the Yemeni Riyal and non-functioning markets leads to unnecessary exchange rate losses and reduces the impact of the intervention	Highly likely	Severe	FCDO economists to monitor economic situation, banking risks and the impact on our programmes. / FCDO lobbies the Central Bank of Yemen (CBY) and provides technical assistance through its economic programming to enact policies to support the stabilisation of the currency. / Programme team to seek regular updates from partners to better understand how they are being affected by changes in prices/import levels/government or CBY legislation. / Partners to engage with FSAC and follow FSAC guidance on food basket amounts and exchange rate management, which is updated to reflect major exchange rate fluctuations. / FCDO to engage with wider humanitarian and development community to better understand and manage currency depreciation. / Partners will be encouraged to negotiate with banks for the best exchange rate. / If liquidity issues impact distribution of cash, partners will be able to flex to vouchers or in kind.	Severe
	COVID-19 disrupts partners' ability to deliver programming and beneficiaries do not receive essential support	Highly likely	Severe	Ongoing engagement with partners to understand COVID-19 impacts on implementation, and their operational and strategic planning for staff and recipients’ safety and security as well as programme activities and delivery. / Cash transfers move to cycle of every two months to limit physical contact with beneficiaries if required.	Major
	Threats to staff safety from state or non-state actors or due to the conflict restricts access and partner presence in project locations	Highly likely	Severe	Safety and security protocols to protect staff and assets are in place and followed. / Continued close monitoring of situation jointly with other actors. / Partners to hold regular consultative meetings with district authorities, local council members and religious leaders to maintain acceptance. / In extreme situations, evacuate staff as per the organisational policy. / Maintain reliable information networks.	Major
	External access restrictions risk damaging the effectiveness of programming by disrupting food/fuel imports.	Highly likely	Severe	Maintain support to UNVIM to keep ports open (through separate FCDO Yemen programme). / Continue to use HMG resource to support political process and Hodeida agreement. / Work to influence GoY policy (e.g. decrees) in order to keep trade flowing at ports. / Partners to maintain coordination with local authorities and logistics cluster.	Major
	Internal access restrictions and restrictions to registration process (e.g. WFP biometrics) reduce the ability of partners to access beneficiaries and implement programmes	Highly likely	Severe	Continue regular and open dialogue with partners to understand internal risks to programming across all governorates. / Ensure partners have strong contingency plans, including the ability to bring the delivery of assistance closer to beneficiaries, and encourage localised delivery where needed. / Ensure partners maintain close working relationships with government ministries and local authorities. / Work together with other agencies to jointly engage with authorities in order to facilitate the access to the beneficiaries and movement to the field. / Support engagement with SCMCHA on red lines. / Encourage partners to support OCHA Access Advocacy work by sharing information on their Access Constraints with the Humanitarian Access Working Group chaired by OCHA Sana’a. / UK to continue support for UN approach to engaging with De-Facto Authorities on partner access and beneficiary registrations	Severe
Safeguarding	Low cultural understanding of SEAH risks and awareness among staff and beneficiaries increases likelihood of cases not being reported and beneficiaries being harmed	Highly likely	Severe	Enhanced DDAs of partners have been undertaken and we will review progress against the recommendations to ensure robust policies are in place. / Partners will need to ensure their complaints/grievance mechanisms have staff who are able to respond to and escalate safeguarding issues as appropriate, including female points of contact. / Beneficiary feedback will be incorporated into TPM spot checks, annual reviews and post distribution monitoring as appropriate. / Safeguarding will be a standing agenda item at quarterly meetings and partners will be reminded of their obligation to report any concerns.	Major
	Lack of clear safeguarding policies leads to staff being perpetrators or victims of SEAH	Likely	Severe	FCDO will push for the requirement that all partner staff, including international staff, undertake training on safeguarding and SEAH as part of induction training and that this is renewed periodically.	Major
	Personal data of staff/beneficiaries is not protected and they are put at risk	Likely	Major	Partner data protection practices will form part of due diligence assessment renewals. / Where partners are not bound by GDPR legislation, the programme team will share information on data protection and encourage best practice.	Moderate
	Programme activities could lead to the spread of COVID-19	Likely	Severe	Partners will be required to have robust risk plans in place on staff health and safety in relation to COVID-19. / Partners will promote awareness as part of all ongoing projects and ensure appropriate social distancing and hygiene measures are in place e.g. at payment sites.	Major
	CfW programmes could lead to adverse impacts on the environment or climate events (such as flooding) could affect operations	Likely	Major	Partners implementing CfW projects will be required to have appropriate environmental safeguard policies in place. / This will be a requirement for NGO partners and SFD. SFD already apply a Social and Environmental Screening Procedure which is documented in its procedural Environmental and Social Management Framework (ESMF) in which projects are classified (A), (B) or (C), A for high, B for moderate and C for no impact. The ESMF handles the expected environmental and social impacts throughout all the stages of the project.	Moderate
	Partner staff and consultants are put at risk due to the conflict situation	Likely	Severe	Partners to monitor security situation both locally and through security briefings from the HCT and ensure clear security processes are in place to protect staff.	Major
	Programme and targeting are not conflict and / or gender sensitive and create unintended negative impacts, including creating new divisions between communities and adding to existing conflict fault lines	Likely	Major	FCDO to work with partners to ensure programmes are informed by gender and conflict sensitivity analysis (e.g. through advisory input with partners). / FCDO to ensure that no UK taxpayer funds are used to support individuals or entities associated with terrorism. Partners and all downstream partners to make themselves aware of, and partners to sign compliance with, the relevant counter terrorist financing legislation. / Partners to have clear communication and outreach strategy in place to minimise tensions between recipients and non-recipients. / Established grievance redress mechanisms are in place. / Consultation with community elders / leaders and community committee to ensure agreement on beneficiary selection. / Coordination with IDPs, host community and clusters to ensure that the assistance reaches the intended beneficiaries and selection criteria are communicated and understood. / Utilisation of partners’ experience in conflict prevention, conflict analysis and Do No Harm approach. / Partners to accommodate women into programming, putting separate arrangements in place to ensure they are appropriately involved at all stages in the programme and benefit equally from activities.	Moderate
People	Partners' management structures and staff numbers do not provide sufficient capacity to effectively deliver programming.	Likely	Severe	Robust due diligence undertaken and reviewed to ensure partners have sufficient capacity to deliver. / Frequently update delivery chain map to understand downstream partner responsibilities. / Meet with downstream partners where possible to understand their challenges. / Press partners to provide updated organogram of their operations.	Major
	Partner capacity challenges inhibits ability to deliver programmes (recruitment of staff, visas, security and reliance on UN for evacuations)	Likely	Major	Reliance on local/regional expertise wherever possible. / Capacity building of partner organisations and national staff. / Political engagement to improve access, including UK messaging to various stakeholders in Sana'a and Riyadh to help unblock visa processes.	Major
	Lack of Board oversight due to SFD's current governance arrangements means management are not being held accountable or forced to be transparent	Likely	Severe	50% of SFD's Board of Directors represent the government. The Board not meeting since the conflict began has helped maintain SFD's neutrality. / As recommended by IAD, FCDO in collaboration with other donors will provide more of a challenge function on strategic issues. / Donors have fed into SFD's next crisis response plan which is currently being developed and will scrutinise the final product. / The World Bank will continue to play a lead role e.g. by organising donor reviews.	Major
	FCDO Yemen does not have sufficient capacity to manage the programme and meaningfully engage with partners and stakeholders, impacting the success of the intervention	Possible	Major	Consideration has been given to the resources required to manage the BC and this has been set out in Table 11 of the Management Case / Gaps in staffing will be avoided by ensuring recruitment to fill vacant posts is undertaken in a timely manner,	Moderate
Financial and fiduciary / (more details in the Financial Case)	Weak financial management and controls gives rise to corruption, fraud and aid diversion	Likely	Severe	Existing due diligence assessments for partners indicate robust controls, albeit with the need for some improvements which we are supporting partners to implement.	Major
	Poor oversight of the delivery chain leads to increased instances of fraud as funds are mismanaged by downstream partners	Highly likely	Severe	Partners will be required to complete delivery chain mapping before funds are disbursed. These will be updated at least annually and will help clarify the flow of funds down to the end beneficiary, identifying all partners involved in programme funded activities and opportunities for aid diversion. / Partners will undertake appropriate due diligence of downstream partners.	Major
	Lack of awareness on UK legislation leads to weak controls, aid diversion and funds being diverted to terrorist groups	Likely	Severe	FCDO’s MoU, Accountable Grant and contract templates include provisions on counter-terrorist financing, bribery, fraud and corruption. The Framework Arrangements with UNICEF and WFP also reference the zero-tolerance approach toward fraud and corruption. / Fraud will be a standing agenda at all partner meetings and partners will be reminded of their obligation to report and act on fraud and aid diversion concerns.	Major
	Poor targeting and beneficiary identification lead to fraud e.g. through ghost beneficiaries, payments to ineligible recipients, collusion involving payment agents and community leaders, and double payments to beneficiaries	Likely	Severe	Attention will be given to appropriate targeting/beneficiary selection, accountability to affected populations including through robust grievance mechanisms, monitoring and evaluation, conflict sensitivity and value for money. / Robust verification measures will be in place to minimise the risk of aid diversion. / Partners will ensure there is adequate supervision of the payment distribution process.	Major
	Programme is unaffordable in outer years and does not meet beneficiaries’ needs as intended	Likely	Severe	50% of future Yemen resource allocations will be allocated to food security, protecting funding for the business case to an extent / The programme team will secure buy in from the FCDO Yemen management team to process cost extensions to the business case should additional funding become available / FCDO Yemen will enhance coordination and engagement with other donors to ensure the overall food security response is sufficient	Major
Reputational	Anti UN and UK media criticism may lead to erosion of public trust, increased interference by authorities and increased security risk to staff	Likely	Severe	Increased monitoring of social media postings. / Increased advocacy and communication to build public trust.	Major

Annexes

Annex 1 – Evidence on Cash Transfers

Annex 2 – Current relevant FCDO Programmes

Annex 3 – Proportion of women and girls, and people with disabilities reached by cash interventions

Annex 4 – Draft logframe Indicators
Annex 1: Evidence on cash transfers

Global and Yemen specific evidence on cash transfers is compelling on their benefits. They are an FCDO Chief Economists Office “Great Buy” and are good value for money.

Cash transfers are effective to support food security. Recipients mostly use cash transfers to buy food, meet basic needs (including medicines, school costs) and repay debts which is critical to maintain their social capital and the ability to borrow again in case of need. The flexibility in their use would be hard to match with in-kind assistance.
[note] People receiving food assistance have better food security outcomes than non-assisted households, Source: WFP Yemen | Food Security and Price Monitoring, mid-September 2020..Evidence on comparative effect of different modalities (in-kind, vouchers and cash) is emerging. A comparison over three months shows cash can have greater food security outcomes than vouchers or in-kind, but with variations over time. Evidence gathered remains insufficient. Source: WFP Yemen, Monitoring and evaluation Quarterly Report, April – June 2020.
[note] Around 82%of the Emergency Cash Transfer (ECTP) and around 90% of the WFP cash transfer are spent on food, Source FCDO Third Party Monitoring of YeSP and WFP programmes.

Monitoring shows that transfers need to be of sufficient size to help most food insecure people to achieve minimum levels of food security and protect their coping strategies . Since food assistance in the north has been reduced to half (for access and then funding issues), food security levels of recipients have worsened. In Yemen, humanitarian cash, voucher and in-kind food transfers are designed to cover the minimum food basket of most food insecure people. Transfers delivered through social protection in Yemen tend to be lower in value to remain affordable by the state, rather than by design.
[note] Source WFP monitoring.
[note] Guidance on measuring and maximising value for money in social transfer programmes – second edition, Philip White, Anthony Hodges and Matthew Greenslade DFID, 2013,Link here.

Cash transfers in Yemen are highly efficient due to their large coverage. Evidence shows that cash transfers can be up to twice as efficient to deliver as food in-kind. The biggest cash transfer programmes in Yemen show efficiencies above 80% (84 to 88 pence out of every pound goes to recipients with 12 to 16 pence covering direct and indirect programme costs).
[note] WFP budget.
[note] Budgets of WFP and YeSP programmes funded by FCDO.

1. In Yemen, cash transfers can be implemented at scale, including in hard to reach areas:
    1. Yemen has a strong infrastructure of financial services based on its historical reliance on remittances and its pre-conflict social protections systems. To deliver those, Yemen has a variety of private, grassroots, financial service providers who have long-standing experience in transferring cash including to rural areas.
    2. Yemen has also developed resilient market systems as a result of remittances inflows into rural areas and its reliance on imports. While markets have been affected throughout the conflict, they have functioned, with almost 90% of Yemen’s food requirements and over 70% of its fuel requirements being imported.

1. Cash transfers have wider benefits:
    1. They support the local economy and local markets to operate, strengthen and recover. Unconditional cash transfer programmes can generate more than $2 of indirect market benefits for each $1 provided to beneficiaries.
    2. In Yemen, as in most contexts, satisfaction rates with cash transfers are extremely high (99%) amongst recipient communities as they empower households to meet their specific needs. Globally, surveys of recipients of cash consistently report greater dignity as a result of the choice afforded to them .
      [note] UNICEF – FCDO Donor Report on ECT, 15 Feb 2021, Inter-agency joint cash study: Market functionality and community perception of cash-based assistance. Cash and Markets Working Group and REACH, 2017, link here.
    3. They can help address Gender Based Violence and the economic pressures that drive most significant protection risks in Yemen, including displacement, child labour, child marriage, recruitment into armed groups, eviction, or accessing health and education services.
      [note] Collected papers on gender and cash transfer programmes in humanitarian contexts, compiled by the Cash and Learning Partnership, 2018, Link here. A study conducted to examine the gender dimension of an EU funded ten-month multi-purpose cash programme (implemented by CARE and Action contre la Faim in 2017) found that cash transfers reduced negative coping behaviours in both female and women headed households and that women households’ heads were empowered with significant decision making power over the use the money in the household. However, the protection and gender dimensions in the impact of cash transfers requires further investment to understanding if those changes last.

1. Cash transfers can have longer-term impacts over time.
    1. Regular and predictable cash transfers can help build resilience of poor and vulnerable people protecting them from the impacts of shocks, including the erosion of productive assets, and minimising negative coping practices. They can facilitate livelihood investments that build resilience to future shocks or crises (e.g. petty trade or purchase of small productive assets like small animals).
      [note] Social protection in protracted crises, humanitarian and fragile contexts, FAO, 2016, link here.

    1. Emerging evidence in Yemen shows the benefits of cash for work (which are cash transfers provided alongside temporary work opportunities) on people’s lives and livelihoods: (i) Enhancing and protecting Yemen’s human capital potential through the acquisition of skills; (ii) increasing social capital and strengthening community cohesion leading to the establishment of Village Savings and Loans Associations that provide capital for households to start small and microenterprises; (iii) Restoring access to basic services, and thereby reducing time to access markets, water, healthcare, and reducing the burden on households (particularly female headed households and those with people with disabilities).

    1. Claims that cash transfers create dependency are unfounded. There is little evidence that cash transfers reduce work effort, rather evidence suggests cash may increase participation and intensity of engagement in work. They are usually a small proportion of household income, and beneficiaries are not ‘unemployed’ but rather engaged in a range of activities (e.g. paid daily labour, agricultural production, petty trading) to meet household needs..
      [note] Understanding the impact of cash transfers: the evidence, Jessica Hagen-Zanker, Francesca Bastagli, Luke Harman, Valentina Barca, Georgina Sturge and Tanja Schmidt, Briefing, ODI, 2016, link here.

There is no evidence that cash transfers are more prone to theft, diversion and corruption than in-kind aid. Evidence shows that people spend cash on what they need most and that cash transfers can ‘be less risky than other, more traditional forms of aid spending’ with regards to ‘waste and fraud’. In particular, ‘electronic payments can improve financial control and reduce risks of fraud or theft, as well as ‘reducing direct and hidden transaction costs’. All FCDO cash transfer programmes incorporate a range of controls to mitigate risks of fraud and corruption. The National Audit Office found that targeting arrangements in DFID transfer programmes were robust, successfully identifying people who met the criteria of need, and that programmes were achieving this even in particularly remote and challenging places. Humanitarian actors in Yemen are largely able to mitigate the risks of cash programming, despite substantial operational and contextual challenges.
[note] Public Accounts Committee (2012), Sixty-Fifth Report, DFID transferring cash and assets to the poor, link here.
[note] DFID: Transferring Cash and assets to the poor, National Audit Office, 2011, link here.
[note] CTP in challenging contexts: case study on CTP and risks in Yemen 2015-2018, CaLP case Study, Cash and Learning Partnership, link here.

While there is clear evidence that cash transfers work in Yemen, and a growing body of evidence on the specific benefits and challenges of specific cash interventions, there is a need for greater investment in impact monitoring and evaluations, that also allow comparing the impact and VfM of different cash interventions.
[note] Secondary desk review of cash and markets data for Yemen. REACH and CMWG, 2019, link here.

Annex 2: Current relevant FCDO Cash Programmes

	Humanitarian Food Assistance (WFP)	MHRP	SFD	ECTP / SWF
Purpose	Emergency food assistance to the most food insecure and conflict affected people.	Prevents famine and addresses humanitarian needs to most vulnerable populations in food security and other areas through provision of conditional and unconditional cash	Reduces extreme poverty and vulnerability and increase individual, household and community resilience in response to the ongoing humanitarian crisis in Yemen	Unconditional cash transfers to the poor and vulnerable to protect them against extreme poverty,
People targeted	Most vulnerable people in communities, as identified by WFP-managed community committees, who compile lists at village level before they are approved at district and governorate level.	Most vulnerable people in communities, as identified by NGO-managed community committees, who compile lists at village level and NGOs largely conduct 100% verification of the lists.	CfW: Unemployed in targeted districts / LIWP: IDPs / CfN: families on the SWF beneficiary list, households with pregnant or lactating women (PLW) and/or children under 5 suffering from malnutrition, households where the mother or child has a disability in high priority districts according to indicators of malnutrition / CfSS: unemployed youth in targeted districts who can deliver education services	Chronically poor and those who are unable to work including people with disabilities, the elderly, orphans and female headed households on the existing SWF beneficiary list.
Number of people receiving cash transfers	1,172,000 people per month as of November 2020.	Peak of about 280,000 people receiving cash in a month in 2021. Varies depending on which transfers are operating in any month.	626,570 direct recipients of cash transfers (55% female) (since 2018)	Approx. 9 million people
Size of the cash transfer (per household per month, assuming a family of 7 people)	$75 [YER 53,000 per month] (GoY areas) / $61 [YER 45,000 per month] (AA areas) / Amount established by FSAC based on cost of minimum food basket, / reviewed every 6 months or when contextual indicators indicate need. Amounts vary according to the size of household (for up to 10 household members).	$75 [YER 53,000 per month] (GoY areas) / $61 [YER 45,000 per month] (AA areas) / Amount established by FSAC based on cost of minimum food basket, / reviewed every 6 months or when contextual indicators indicate need. Amounts do not vary according to the size of household. / Daily rate for Cash for Work is also based on the FSAC food basket. The number of working days required to receive the transfer depends on local wage rates.	CfW: approx. $82 [50,000 YER] per month (up to 6 months) / CfN: approx. $33 [20,000 YER] per month (up to 12 months) / CfSS: up to $100 per month (up to 12 months)	Around $8.4, ranging from $5 to $10 / [Average YER 5,000 per month with amounts ranging from 3,000 YER to 6,000 YER based upon the size of the household]. / Flex to provide top ups to the base amount with additional donor funds.
Total volume of transfers in a year (+ number of rounds)	Transfers are made every month to the full caseload.	Transfers are made to the full caseload each month. UCT is 6-9 months in a year, CfW and other conditional cash is 4-6 months. / Approximately £15m transferred to beneficiaries in FY20.
[note] Exchange rate Sanaa (old notes) 14 April - YETI (acaps.org)
[note] Exchange rate Aden (new notes) 14 April - YETI (acaps.org)
[note] Survival Minimum Expenditure Basket and Setting the Transfer Values, Guidance Note, Cash and Markets Working Group Yemen, October 2020, link here.
[note] Exchange rate Sanaa (old notes) 14 April - YETI (acaps.org)
[note] Exchange rate Aden (new notes) 14 April - YETI (acaps.org)
[note] JMMI – median exchange rate at national level, February 2021.
[note] JMMI – median exchange rate at national level, February 2021.

Annex 3: Proportion of women and girls, and people with disabilities reached by cash interventions

Intervention	MHRP	WFP	ECTP	SFD
Proportion of women and girls among recipients	51% of beneficiaries supported with cash transfers and Cash for Work (CfW) were women and girls / (October – December 2020 / Cash for work only: 29% (October – December 2020)	47% (Nov 2020)	45%	44%
Measures to prioritise women	Women assigned lighter tasks like collection of water and other materials to ensure they were still able to partake in CfW activities. / Women, the elderly and people with disabilities given priority and served first at cash distribution sites. / Partners worked to improve community-level gender dynamics by encouraging female participation.	Targets the most food insecure: (e.g. women headed households, IDP etc…) / Beneficiaries selected by community committees (which include at least one female member) who assess the level of vulnerability	Targets the chronically poor, orphans, and vulnerable children, widows, persons with disabilities, the elderly and female-headed households / Field facilitation supported by social workers, mostly women, to ensure reaching out to female beneficiaries	Measures to enable women to do more cash for work include days allocated for women to work and projects targeted at women with lighter tasks e.g. in agriculture / Cash for nutrition interventions specifically target women
Proportion of people with disabilities among recipients	7% elderly and 3% people with disabilities (December 2020)	1% (Nov 2020)	11% (from post-distribution monitoring sample)	6% (from CfN post-distribution monitoring sample). / 7,540 special needs children were integrated, of whom, 52% were female
Examples of quality measures	Distribution points / close to beneficiaries, greatly decreasing travel distance (and cost). / Distribution points shaded or inside institutional buildings to avoid the heat for those queueing. / Household members unable to partake in CfW activities due to age or disability were alternatively supported through cash transfers. / Elderly or people with disabilities who were able to partake in CfW activities were allocated less manually intensive work where relevant. / For people with limited mobility, teams were sent to disburse assistance directly in their homes to ensure they did not miss out on distributions.	Significant increase in number of cash distribution points to increase access for all beneficiaries.	Home outreach visits undertaken to those who cannot travel.	Home outreach undertaken to deliver awareness sessions under cash for nutrition intervention

Annex 4: Draft logframe indicators

The logframe indicators and corresponding baselines and targets will be finalised in the mobilisation phase. For reference an indicative logframe is set out below which shows the likely achievements required.

Impact: Reduced humanitarian need in Yemen
Percentage of population in need of emergency food assistance according to Integrated Phase Classification (levels 3 – 5)
Outcome: More effective, efficient and sustainable food security response reduces famine risk and food insecurity, enabling the most food insecure and vulnerable Yemenis to meet their basic needs
Percentage of households who report being able to meet the needs of their household (all/most/some/none) i. basic needs, ii. food needs
Percentage of households with an improved Food Consumption Index
Percentage of households with a reduced Coping Strategy Index
Number of beneficiaries that are i. female headed households, ii. people with disabilities
Percentage of IPC 3 and 4 districts reached
Number of cash reform priorities delivered
Percentage of beneficiaries reporting that programmes are safe, accessible and participatory
Number of beneficiaries with improved climate resilience
Output 1: Save lives - reduce immediate famine risk through delivery of cash interventions	65%
Total number of beneficiaries receiving unconditional cash transfers (i. % female, ii. % people with disabilities)
Total number of beneficiaries engaged in Cash for Nutrition projects (i. % mothers with disabilities, ii. % children with disabilities)
Total number of beneficiaries engaged in Cash for Work projects (i. % female, ii. % people with disabilities)
Amount of cash distributed to beneficiaries in USD
Number of districts reached with cash assistance
Output 2: Reduce future famine risk – improve resilience and coping capacity of food insecure communities	15%
Percentage of beneficiaries reporting access to basic services
Percentage of beneficiaries reporting sufficient assets (income/non-income) to meet their basic needs
Percentage of beneficiaries reporting confidence that their support networks would support in crisis
Percentage of beneficiaries reporting ability to adapt to economic, political, social, environmental changes to their context
Output 3: Technical Assistance and M&E ensures interventions are adaptive, better coordinated and more efficient, effective, accountable and sustainable	20%
Number of longitudinal evaluations undertaken by the TAF
Number of project adaptations/improvements made as a result of performance-oriented food security monitoring data and/or qualitive evidence, e.g. reviews, evaluations, and other research
Number of improvements made as a result of VfM indicators/data
Percentage of FCDO funding that is delivered to beneficiaries