## 2023 Annual Review of the Powering Sierra Leone’s Hospital Programme

Title: Powering Sierra Leone’s Hospital Programme
Programme Value £ (full life): 19.95 million over 3 years		Review date: Oct 2023
Programme Code: 301526	AMP start date: / 01/07/2022	AMP end date: / 31/07/2024

Summary of Programme Performance
Year	2023
Overall Output Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	https://fcogovuk.sharepoint.cwthTeam/
DevTracker Link to results framework:

Abbreviations

FCDO – Foreign Commonwealth and Development office
GoSL – Government of Sierra Leone
SE4ALL – Sustainable Energy for All

A. SUMMARY AND OVERVIEW

Description of programme

The goal of the programme is to provide solar energy to public healthcare facilities on a reliable and sustainable basis. The initial phase of the programme is installing facility scale solar photovoltaic (PV) generation supported by battery storage for six hospitals over five sites (in one case increasing the capacity of an existing system). The capacity of clean energy being installed in Phase 1 is around 0.6 Mw and this solar energy largely replaces the use of polluting, unreliable and expensive small diesel generators and the intervention qualifies as climate finance. The benefits of Phase 1 will include providing reliable energy at facilities where there are typically around a thousand births per month and intensive care facilities for babies needing intensive support. Phase 1 was extended during the year to include one additional hospital and 35 Community Health Centres. Design work is also being undertaken to support an additional round of installations to be contracted in 2024-25.
Summary supporting narrative for the overall score in this review.
Installation of the five hospital systems is about to be completed, with three systems scheduled for completion during October and two in the first week of November. This has been achieved despite several external challenges in the project’s first year. Signature of the Memorandum of Understanding (MOU) with the programme implementer Sustainable Energy for All (SEforALL) was delayed by temporary FCDO approval processes in place during the autumn of 2022, and the shipping timeline delayed by FCDO funding restrictions. There was then a disputed national election in Sierra Leone and clearing delays over the election period.
The limited delay to completion of the Phase 1 hospitals, despite delays in signing the financing MOU and the explicit request to delay shipping of the systems, was made possible by the committed and flexible approach of SEforALL, including early preliminary work to identify potential suppliers, and working closely with the FCDO programme team to respond to iterations in funding availability. The programme sub-contractors, EmOne and Crown Agents have developed a strong relationship with the Ministry of Health, and this has allowed completion of all the Phase 1 systems (five systems, supporting six hospitals) around a month later than the date originally planned in the programme logframe.
Delay was intentionally incurred to allow FCDO to respond to organisation wide in-year budget reductions, and this resulted in planned completion being moved to after the general election period (June 2023), which then resulted in minor further delay due to extended clearing timelines until new GoSL Ministers were in post. The efforts by the supplier to minimise delays not caused by them or programme specific issues have been substantial, and getting all systems completed by November 6th is assessed as meeting expectations in this context.
Major lessons and recommendations for the year ahead

One lesson from the Phase 1 installations is that the Ministry of Health is responding faster to the availability of reliable power than expected in terms of adding equipment and capability for supported hospitals. It is recommended that generation and/ or storage capacity is enhanced where needed for these systems, and also that this experience is taken into account in the sizing of future systems and prior discussion with the Ministry of designs is enhanced.

Additional funding for Phase 1 of the programme has been disbursed and a second phase of installations is planned for 2024-25. The budget for 2024-25 should be confirmed as early as possible, and the logframe should be updated once this has been done.

Future design work should include an assessment of water pumping options (recognising that there are technical reasons for often using stand-alone systems without batteries for boreholes, rather than connecting them to facility systems).
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme theory of change is relatively simple. Poor power supply has been identified by surveys as the major infrastructure impediment to improved delivery of healthcare services in Sierra Leone. This impediment manifests in numerous ways, including reduced diagnostic capacity, unfit conditions for surgery and deliveries, reduced sanitisation and negative impact on staff morale. The theory of change is that relaxing the power supply constraint will lead to better healthcare services being delivered, which in turn will lead to improved health outcomes.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to expected outcomes and impact, with commissioning of the Phase 1 hospitals imminent. Data will be collected by the programme in the coming year to confirm the impact in terms of quality of power supply, quality and quantity of healthcare delivered and health outcomes. While the improvement in power should be immediate, improved health services and outcome are expected to build over time as equipment availability and other operational factors respond to improved power supply.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme should continue. Phase 1 has been successfully delivered and the programme is an important part of BHC Freetown’s Business Plan for spending climate finance and capital.

## C. DETAILED OUTPUT SCORING

Output Title	Project Management Design and monitoring
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR.

Indicator(s)	Milestone(s) for this review	Progress
All procurements contracted (EPC, PM Firm, Comms firm)	Procurement of EPC, PM firm and Comms Firm to be completed by Q2 2022	EPC Contract Signed – December 2022 / PM Firm Contract signed – 18th Jan 2023 / Contract signed for communications materials including project video – April 2023 / EPC contract signed within around three months of MOU signature, due to preparatory work by SEforALL.
Project Steering Committee established and meeting regularly (cumulative)	Committee to be formed by Q1 2023	Achieved. Committee formed including representative from Ministry of Health, FCDO, SEforALL, EmOne, Crown Agents. – Meetings happen monthly
Number of hospitals monitored by FCDO during the installation phase(cumulative)	6 by Q3 2023	Achieved. FCDO site visit conducted for 3 Locations in September 2023. Bonthe, Kabala and Kambia. / 3 sites also visited during design stage (Bonthe, Kambia and Kabala).
Lessons learning process	Report to be submitted after completion of project	Due after systems are commissioned.

Briefly describe the output’s activities and provide supporting narrative for the score.

The introduction by FCDO of an additional temporary layer of approval to meet HMT guidance (Autumn 2022), followed subsequently by in-year budget reductions presented significant challenges for the programme, as funds were approved for use in 2022-23 but limited funding was confirmed for 2023-24. Early contracting was key to delivering these limitations but was made difficult by an extended delay to MOU signature while FCDO went through newly introduced approval processes. SEforALL worked effectively to minimise the disruption caused by delayed MOU signature by engaging the market and getting expressions of interest, so that a Call for Proposals could be issued quickly once the MOU came into force.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A Business Case Addendum was approved that allowed additional funding of up to £15 million in May 2023 and an MOU amendment with SEforALL giving effect to this signed on 8th August 2023.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

While early engagement with the Ministry of Health took place, and the concept was met with enthusiasm, balancing new FCDO approval mechanisms with a time limited funding window reduced the time available for consultation with the Ministry of Health on the final selection of Phase 1 sites and the detailed designs. There was a risk that this could reduce Ministry buy-in, but effective work by SEforALL has helped to ensure a strong partnership with active Ministry support to overcome challenges including port clearance. One consequence of the shortened consultation period was limited ability to test with the Ministry assumptions that had been made on the demand response that would occur once reliable power supply was available. It has become clear during joint monitoring visits with the Ministry that more equipment is currently being stored by the Ministry than had been understood. Partly as a consequence of deployment of this equipment some of the Phase 1 hospitals need greater capacity than originally designed if the system is to support the intended level of facility operation without excess demand eroding system performance.

To mitigate this, it is recommended that additional capacity is added where capability and equipment enhancements have increased optimal system size (examples include a new oxygen plant for PCMH and mortuary freezers at Bonthe Hospital). It is also recommended that a more detailed assessment of the likely enhancements the Ministry will make in response the provision of reliable energy supply should be made for future systems, so that system sizing can better accommodate load increases that will occur in the first 1-2 year of operation. While this requires some adjustment to the initial Phase 1 designs, it is in many ways a sign of success for the programme, as it increases the extent to which to quality and scope of healthcare services being delivered at supported facilities is improving.

Output Title	Implementation
Output number:		2	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
Hospitals electrification construction: number of energy systems installed and commissioned	Complete 5 hospitals by Q3 2023	Ola During/ PCMH, Masanga and Bonthe will be completed during October, and Kambia and Kabala by November 6th. Around 95% of works were completed at all the 6 hospitals by the end of September, with completion being delayed into October due to delays in clearing some containers from the port.
Third Party verification of installations completed	Complete 5 hospitals by Q3 2023	SEforALL appointed Crown Agents to provide third party verification that systems installed are of high quality and meet specifications. Verification and commissioning will take place for Ola During/ PCMH, Masanga and Bonthe by November 11th, and for Kambia and Kabala by November 17th.
Number of female engineers trained through the projects.	12	Training to 12 female trainees is ongoing as the project is still on. The STEM trainees have been shadowing different stages of the project since March 2023.

Briefly describe the output’s activities and provide supporting narrative for the score.

The FCDO requested delay in shipping meant implementation necessarily continued through the election period, and there were fairly minor clearing delays that resulted from difficulty in securing signature prior to the announcement of a new cabinet. Despite some initial Ministry of Health concerns about a compressed consultation on final site selection, SEforALL has succeeded in building a strong collaboration with the Ministry, and this was essential to keeping clearing of containers going through the election period.

Late clearance of the final Phase 1 container resulted in sites not being fully completed by the end of September 2023, with three systems being completed in October and two in the first week of November. Around 95% of installation work was completed by the end of September, but equipment in the final container was needed at all sites, so none could be completed prior to it being cleared.

Completion of all sites in October has been assessed as meeting expectations given that it resulted from an explicit request from FCDO to delay shipping, and the view of the Review Team is that SEforALL and the EPC have performed very well to deliver the full set of installation with only a small delay despite changing financial and timing parameters over the implementation period from FCDO.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The main change is around the expected time of final completion of the installation work, which is now expected for October 2023, with final technical validation happening in November 2023. Additional systems have been added to Phase 1 under the recent MOU amendment.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

This is the first review, so there are no previous recommendations to assess.

The logframe should be updated to include systems contracted under the recent MOU amendment, and planned work in 2024-25.

Future design work should include an assessment of water pumping options (recognising that there are technical reasons for often using stand-alone systems without batteries for boreholes, rather than connecting them to facility systems).

Output Title	Communication
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Communications and dissemination strategy developed	1 for Q1 2023	Milestone achieved. Communication and dissemination strategy developed by the PM firm. A campaign video was completed but had not been disseminated at the time of the review due to a communications pause relating to the political situation (but subsequently lifted)., awaiting clearance from FCDO on unpausing project communications post-elections.
Video footage of hospital completed (pre-post and final)	3 for Q3 2023	Milestone achieved. Videos of the hospitals have been shot during the visits by the Comms firm. Communications will include one larger pre/post video for the project, and one video dedicated to Bonthe Island Hospital. Footage has separately been recorded of short interviews of two hospital superintendents by FCDO.
Impact stories and interviews: Number of staff and/or patient feedbacks on system improvements	4 for Q3 2023	Project heads and staff at the hospital have been interviewed by the communications firm, and FCDO directly interviewed the medical superintendents at two hospitals. Communications materials are with the FCDO communications team for approval, following a pause on project communications in the wake of concerns about the June 2023 election.

Briefly describe the output’s activities and provide supporting narrative for the score.

A communications strategy was developed by SEforALL which centred on the contracting of a specialist communications firm, WTYSL. FCDO approved this strategy, but for financial reasons requested that they be brought in at the start of 2023-24, with the contract being signed in April 2023. They carried out two visits in country to capture footage on-site and carry out interviews with key stakeholders. A campaign video was produced in June 2023 and submitted to FCDO for possible publication. Publication was delayed at FCDO’s request as part of a wider communications pause following a disputed Presidential election but will happen shortly. The delayed use of communication materials was in support of wider FCDO policy, and the programme has been careful at all times to align their communications with FCDO guidance and clear publications. As all expected strategies and materials were produced to a high standard and on time, the output has been scored as A – meeting expectations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

FCDO paused most public project communications material. It is expected that a project video as well as additional material will be published in the final quarter of 2023 (Oct-Dec).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

This is the first review, so there are no previous recommendations to assess.

## D: VALUE FOR MONEY

The Phase 1 systems were contracted through a two-stage tender process, with the request for proposals and then several full bids. This was a robust approach to ensuring value for money, and the systems have been delivered within the contracted and budgeted amounts despite some delays requested by FCDO that extended the installation period. SEforALL kept back some funding to allow for any cost overruns, but this has not been needed and has been made available for future. The review team has not found comparable hospital scale installation in Africa that would allow a cost comparison but will work further on this during the coming year.

E: RISK

Regular risk reduction meetings have been had throughout the year and this helped with the overview and management of emerging risks as well as review of existing ones between the various parties in the programme. The June 2023 elections has been a major challenge were most of the equipment procured experience delayed in clearing from the port.

A major risk recognised from the outset was that systems would not be well maintained. The EPC has been contracted to provide maintenance support until March 2025, and SEforALL is engaging with the Ministry of Health on the development of a sector wide approach to maintaining solar systems in health facilities.

Safeguarding risks remain a top priority. A strong assurance regime, through the Programme Manager (SE4ALL) is in place to monitor these risks. However, this is being monitored during construction work, the FCDO team ensured contractors understand Environmental and Social Safeguarding risks (including against SEAH) requirements and to familiarise themselves with potential SEAH risks, improve the identification, management, and oversight of SEAH risks. The team provided links additional resources Safeguarding Guidance to ensure minimum standards expected to protect individuals affected by implementation (partners, workers, beneficiaries in the community) are upheld.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Powering Sierra Leone’s Hospitals programme is built around mutual partnership and cooperation between the various teams within the project to ensure delivery to it best. The partners include SEforALL, Crown Agent, EmOne and the Ministry of Health. This has allowed for complex of issues to be monitored, discussed, and resolved in a timely and responsible manner. FCDO has a monthly and if necessary weekly financial discussion to ensure all is on track for delivery.

SEforALL’s delivery, commercial and financial performance has been satisfactory during the Annual Review (AR) period. Downstream partners have performed well in the AR period. For example, EmOne has delivered all aspects of the technical (civil, electrical and installation) works related to the project.

On Programme Reporting, SEforAll have been hands on throughout the reporting year providing continuous reports on project activity regularly either through monthly Project Management meetings, or monthly narrative reporting. In all instances, there is a robust risk-based approach to engagement between SEforAll and FCDO, with proactive dialogue on risks and issues that can affect delivery.

On Financial Management, the partners have tried to be on track on FCDO variance threshold of +/- 5% throughout the reporting period. Over the review period, SEforALL has continued to perform well financially, albeit under challenging circumstances, to provide timely forecasts and adapt where necessary (such as moving activities to support FCDO’s ODA target). This is very much crucial for a capital programme like Powering Sierra Leone’s Hospitals Programme. The programme budget for the 2022/23 financial was £4.75m of which £2.83m (60%) was disbursed and utilised as per FCDO financial requirement for the period under review.

Monitoring, Beneficiary engagement and Assets Management – Two site visits were conducted during the reporting period. One prior to start of civil and installation works to assess the sites and one during the AR period to assess progress and gather beneficiary feedback on project performance. The AR visit was a collaborative one involving teams from EmOne Contractors, Crown Agents, SEforALL, Ministry of Health and FCDO. Stakeholder feedback from construction to installation phase was largely positive albeit some challenges such as clearing of containers from the Port to project locations which had resulted to slight adjustments in project completion timeline, though that does not significantly impact project delivery.

Currently the programme has no assets.

Date of last narrative financial report	October 2023	Date of last audited annual statement	N/A