## Example schedule
Example Safety Climate Tool survey schedule
Start date | End date* | Duration (days) | Activity | Who
2016-01-04 | 2016-01-04 | 1 | [Project start]
2016-01-04 | 2016-01-05 | 2 | Carry out stakeholder analysis
2016-01-07 | 2016-01-08 | 2 | Set up steering group
2016-01-11 | 2016-01-13 | 3 | Identify and recruit champions
2016-01-14 | 2016-01-15 | 2 | Prepare communications, particularly early messages
2016-01-18 | 2016-01-20 | 3 | Management approval of communications
2016-01-18 | 2016-01-19 | 2 | Prepare survey
2016-01-20 | 2016-01-20 | 1 | Check access to site for users
2016-01-21 | 2016-01-22 | 2 | Print surveys
2016-01-25 | 2016-01-25 | 1 | Brief line managers
2016-01-26 | 2016-01-26 | 1 | Brief H&S unit
2016-01-27 | 2016-01-27 | 1 | Issue initial message
2016-02-01 | 2016-02-01 | 1 | Open survey
2016-02-01 | 2016-02-01 | 1 | Issue survey live message
2016-02-03 | 2016-02-03 | 1 | Update meeting with champions
2016-02-01 | 2016-02-28 | 28 | Monitor responses
2016-02-05 | 2016-02-05 | 1 | Update intranet with responses to date (1st week)
2016-02-11 | 2016-02-11 | 1 | Prepare reminder message
2016-02-12 | 2016-02-12 | 1 | Update intranet with responses to date (2nd week)
2016-02-15 | 2016-02-15 | 1 | Issue reminder message
2016-02-19 | 2016-02-19 | 1 | Update intranet page with responses to date (3rd week)
2016-02-25 | 2016-02-25 | 1 | Prepare for survey closure
2016-02-26 | 2016-02-26 | 1 | Prepare closure message
2016-02-26 | 2016-02-26 | 1 | Update intranet page with responses to date (4th week)
2016-02-29 | 2016-02-29 | 1 | Issue closure message
2016-02-29 | 2016-02-29 | 1 | Close survey
2016-03-01 | 2016-03-01 | 1 | Update intranet page with closure details
2016-03-02 | 2016-03-02 | 1 | Update meeting with steering group
2016-03-04 | 2016-03-04 | 1 | [project end]
*Do not edit
Chart start date: |  | 2016-01-04
Min axis value: |  | 42373 | Do not edit
Formulas:
End date* = [Start date]+[Duration (days)]-1