## Change Log
No | Date | Sheet | Cell ref (if relevant) | Comment | Priority | Assured by | Owner | Comments addressed and updated in appropriate tab | Date
1 | 2025-01-23 | WSH - Reservoirs | C11 & C12 | Correction: '24' reservoirs, previously '25' |  |  | TN | Yes | 2025-01-23
2 | 2025-01-23 | NWT - Reservoirs | C31 | Specified Activity: 'Tube-A-Manchette (TAM) Grouting', previously 'Slurry Trench' |  |  | TN | Yes | 2025-01-23
3 | 2025-02-12 | SVE - Resilience Interconnectors | D18:D19, D26:E27 | The company identified an error in our PCD in query OFW-SVE-014. "UME01_08: Hallgates to Elms Farm" and "UME01_12: Oldbury to Meriden" payment rates did not cover £5.05m transitional allowance. We have increased the non-delivery and time incentive payments for these PCD deliverables. |  | EQ | LS | Yes | 2025-02-03
4 | 2025-02-12 | SWB - Resilience Interconnector | J31:O31 | Changed the deliverable values after response to OFW-FD-SBB-005 and a follow up meeting |  |  | LS |  | 2025-02-12
5 | 2025-02-18 | TMS - PR19 Gated | New sheet | New tab added to show PCD on TMS PR19 Gated scheme |  |  | HK |  | 2025-02-18
6 | 2025-02-18 | WSH - Reservoirs | Row 16-19 | Row removal. 'Reservoir N' in WSH PCD table removed due to Llyn Celyn being funded by third party services (NRW) rather than enhancement. Non-delivery payment rate for this reservoir re-distributed across other reservoirs in this table. Description output measurement and reporting, following removal of Llyn Celyn, updates to 'Description' and 'Measurement and reporting' – previously 24 reservoirs, updated to 23 reservoirs. |  | TN | TN | Yes | 2025-02-19
7 | 2025-02-18 | NWT - Reservoirs | C31 | Non-delivery PCD rate, cellC31 previously 'Slurry Trench to deliver risk reduction', updated to ' Tube-A-Manchette (TAM) Grouting to deliver risk reduction'. |  | TN | TN | Yes | 2025-02-19
8 | 2025-03-20 | SEW - Resilience | J24:K24 | Update to resilience PCD output for SEW WTW4 capacity for an additional process stream, change from 52.3Ml/d in 2029-30 to 52.3Ml/d in 2031-32 to align with our response to the company's representation in the appendix. |  | LS | LS | Yes | 2025-03-20
9 | 2025-03-20 | SEW - Resilience Interconnectors | D23, D41:E41, J59:O59 | Typo error in the deliverable, update 0.005 to 0.05. Update non delivery payments rates (see associated cost model, tab "PCD") |  | LS | LS | Yes | 2025-03-20
10 | 2025-03-20 | SEW - Resilience | J22:O22 | Update service reservoir 29/30 deliverable from 51Ml to 49.75Ml, following an error we have identified in response to a query |  | LS | LS | Yes | 2025-03-20

## Cover
Cover
Water Resilience and Security PCDs
| Model code | PR24PCD109
| Version number: | 4
| File name: | PR24PCD109 Water Resilience and Security PCDs.xlsx
| Date: | 2025-03-20
| For enquiries please contact: | PR24@ofwat.gov.uk
Contents:
| Tab name | Description
| ANH - Resilience Interconnectors | Resilience interconnectors PCD on Anglian Water
| WSH - Resilience Interconnectors | Resilience interconnectors PCD on Dŵr Cymru
| SVE - Resilience Interconnectors | Resilience interconnectors PCD on Severn Trent Water
| SWB - Resilience Interconnectors | Resilience interconnectors PCD on South West Water
| AFW - Resilience Interconnectors | Resilience interconnectors PCD on Affinity Water
| SEW - Resilience Interconnectors | Resilience interconnectors PCD on South East Water
| SSC - Resilience Interconnectors | Resilience interconnectors PCD on South Staffs Water
| SES - Resilience Interconnectors | Resilience interconnectors PCD on SES Water
| WSH - Resilience | Resilience PCD on Dŵr Cymru
| NES - Resilience | Resilience PCD on Northumbrian Water
| SRN - Resilience | Resilience PCD on Southern Water
| YKY - Resilience | Resilience PCD on Yorkshire Water
| SEW - Resilience | SEMD PCD on South East Water
| WSH - Reservoirs | Reservoir safety PCD on Dŵr Cymru
| HDD - Reservoirs | Reservoir safety PCD on Hafren Dyfrdwy
| NES - Reservoirs | Reservoir safety PCD on Northumbrian Water
| NWT - Reservoirs | Reservoir safety PCD on Unitied Utilities
| SRN - Reservoirs | Reservoir saftey PCD on Southern Water
| ANH - Resilience CC Uplift | Climate change uplift resilience PCDs.
| WSH - Resilience CC Uplift | Climate change uplift resilience PCDs.
| HDD - Resilience CC Uplift | Climate change uplift resilience PCDs.
| NES - Resilience CC Uplift | Climate change uplift resilience PCDs.
| SVE - Resilience CC Uplift | Climate change uplift resilience PCDs.
| SRN - Resilience CC Uplift | Climate change uplift resilience PCDs.
| TMS - Resilience CC Uplift | Climate change uplift resilience PCDs.
| NWT - Resilience CC Uplift | Climate change uplift resilience PCDs.
| WSX - Resilience CC Uplift | Climate change uplift resilience PCDs.
| YKY - Resilience CC Uplift | Climate change uplift resilience PCDs.
| AFW - Resilience CC Uplift | Climate change uplift resilience PCDs.
| PRT - Resilience CC Uplift | Climate change uplift resilience PCDs.
| SSC - Resilience CC Uplift | Climate change uplift resilience PCDs.
| SES - Resilience CC Uplift | Climate change uplift resilience PCDs.
| TMS - PR19 Gated | PCD on scheme related to the water supply system resilience programme (WSSRP)
Summary of the model:
Sets out our proposed price control deliverables (PCDs) for Resilience Interconnector, Resilience and Reservoirs.
Quality assurance: This file has been reviewed internally.
Disclaimer:
This model is part of our final determinations setting out the price, service, and incentive package for water companies for the period 2025-30. It should be read together with the other documents and information that we have now published.
Changes since previous published model: N/A

## ANH - Resilience Interconnector
Anglian Water - ANH - Resilience Interconnector
| Company | ANH
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 1dp) of pipeline The following scheme is expected to be delivered: Intra water resource zone transfer by resilience interconnector of 7.5 km length, 395 mm polyethylene pipe [221124 PR24 Additional tables 1-21 v8.5 - ADD21]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| East Suffolk WRZ IPZ | £m/km | 0.88752
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| East Suffolk WRZ IPZ | £m/year | 0.035234 | 0.011745
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| East Suffolk WRZ IPZ | km | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5

## WSH - Resilience Interconnector
Welsh Water - WSH - Resilience Interconnector
| Company | WSH
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 1dp) of pipeline. The following schemes are expected to be delivered: 1) Tywi/SEWCUS transfer main (4.4km) [WSH-DD-08 TOTEX - Enhancement Cost Allowances.pdf p16] 2) Network connectivity improvements (16.7km) 3) River Wye pipeline relocation (0.7km) [WSH60-RS04_-_Increasing_Resilience_of_Tap_Water_Supply_-_Network_Capacity_and_Connectivity.pdf p3] 4) 8 no. of crossing - 5 corssing connections between existing mains and dualling of 3 corssing by means of the provision of a second main [WSH60-RS04_-_Increasing_Resilience_of_Tap_Water_Supply_-_Network_Capacity_and_Connectivity.pdf p4]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Tywi/SEWCUS transfer main | £m/km | 5.0721
| Network connectivity improvements | £m/km | 0.57522
| River Wye pipeline relocation | £m/km | 6.45
| 8 Crossing connections improvement | £m/nr | 0.79773
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| Tywi/SEWCUS transfer main | £m/year | 0.20136 | 0.067121
| Network connectivity improvements | £m/year | 0.022836 | 0.0076121
| River Wye pipeline relocation | £m/year | 0.25606 | 0.085355
| 8 Crossing connections improvement | £m/year | 0.03167 | 0.010557
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Tywi/SEWCUS transfer main | km | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4
| Network connectivity improvements | km | 0 | 0 | 0 | 0 | 0 | 0 | 16.68 | 16.68 | 16.68 | 16.68 | 16.68 | 16.68
| River Wye pipeline relocation | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72
| 5 cross connections between existing mains and dualling of 3 crossing by means of the provision of a second main | nr | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8

## SVE - Resilience Interconnector
Severn Trent Water - SVE - Resilience Interconnector
| Company | SVE
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 1dp) of pipeline. The following schemes are expected to be delivered: 1) UME01_04: Church Wilne GR to Strelley DSR (0.5km) 2) UME01_08: Hallgates to Elms Farm (12.9km) 3) UME01_12: Oldbury to Meriden (15.0km) [SVE_211124 - Additional Data Tables ADD1-21 ADD21]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| UME01_04: Church Wilne GR to Strelley DSR | £m/km | 5.7995
| UME01_08: Hallgates to Elms Farm | £m/km | 3.6271
| UME01_12: Oldbury to Meriden | £m/km | 4.0385
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| UME01_04: Church Wilne GR to Strelley DSR | £m/year | 0.23024 | 0.076747
| UME01_08: Hallgates to Elms Farm | £m/year | 0.144 | 0.047998
| UME01_12: Oldbury to Meriden | £m/year | 0.16033 | 0.053443
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| UME01_04: Church Wilne GR to Strelley DSR | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| UME01_08: Hallgates to Elms Farm | km | 0 | 0 | 0 | 0 | 0 | 0 | 12.94 | 12.94 | 12.94 | 12.94 | 12.94 | 12.94
| UME01_12: Oldbury to Meriden | km | 0 | 0 | 0 | 0 | 0 | 0 | 14.965 | 14.965 | 14.965 | 14.965 | 14.965 | 14.965

## SWB - Resilience Interconnector
South West Water - SWB - Water - Resilience Interconnector
| Company | SWB
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 1dp) of pipeline. The following schemes are expected to be delivered: 1) ROA20 - Mayflower WTW to Littlehempsted WTW (37.2km) 2) COL25 - Brent Tor to Launceston (15.5km) 3) COL22 - Roadford to Coliford via Saltash (Pumping Station, no PCD applicable) 4) WIMX - Cranbrook to Honiton (16.7km) 5) BW01 - Alderney - Knapp Mill pinch points (0.4km) [SBBDD78_L5_CEAPP_Strategic_Interconnectors.pdf p4]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| ROA20 - Mayflower WTW to Littlehempsted WTW | £m/km | 2.5491
| COL25 - Brent Tor to Launceston | £m/km | 1.0726
| COL22 - Roadford to Coliford via Saltash (Pumping Station, no PCD applicable) | n/a | n/a
| WIMX - Cranbrook to Honiton | £m/km | 0.78998
| BW01 - Alderney - Knapp Mill pinch points | £m/km | 5.9163
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| ROA20 - Mayflower WTW to Littlehempsted WTW | £m/year | 0.1012 | 0.033733
| COL25 - Brent Tor to Launceston | £m/year | 0.042584 | 0.014195
| COL22 - Roadford to Coliford via Saltash (Pumping Station, no PCD applicable) | n/a | n/a | n/a
| WIMX - Cranbrook to Honiton | £m/year | 0.031362 | 0.010454
| BW01 - Alderney - Knapp Mill pinch points | £m/year | 0.23488 | 0.078293
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| ROA20 - Mayflower WTW to Littlehempsted WTW | km | 0 | 0 | 0 | 0 | 0 | 0 | 12.2038 | 12.2038 | 12.2038 | 12.2038 | 12.2038 | 12.2038
| COL25 - Brent Tor to Launceston | km | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
| COL22 - Roadford to Coliford via Saltash (Pumping Station, no PCD applicable) | n/a | [6 empty] | n/a | n/a | n/a | n/a | n/a | n/a
| WIMX - Cranbrook to Honiton | km | 0 | 0 | 0 | 0 | 0 | 0 | 16.7 | 16.7 | 16.7 | 16.7 | 16.7 | 16.7
| BW01 - Alderney - Knapp Mill pinch points | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4

## AFW - Resilience Interconnector
Affinity Water - AFW - Resilience Interconnector
| Company | AFW
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified volume (in Ml to 1dp). The following schemes are expected to be delivered : 1) Additional 10Ml (usable) storage at reservoir Hadham Hill 2) Additional 10Ml (usable) storage at reservoir The Hills [AFW101 - Affinity Water PR24 draft Determination Representation.pdf p136-143]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Additional 10Ml storage at the reservoir Hadham Mill | £m/Ml | 0.60023
| Additional10Ml storageat the reservoir The Mills | £m/Ml | 0.59418
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| Additional storage cells at the reservoir Hadham Mill | £m/year | 0.023829 | 0.007943
| Additional storage cells at the reservoir The Mills | £m/year | 0.023589 | 0.0078629
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Additional storage at the reservoir Hadham Mill | Ml | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10
| Additional storage at the reservoir The Mills | Ml | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10
Note on N16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post adjustment?

## SEW - Resilience Interconnector
South East Water - SEW - Water - Resilience Interconnector
| Company | SEW
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 3dp) of pipeline. The following schemes are expected to be delivered: 1) Butler WTW to Warren Street SR (Section A) (3.3km) 2) Butler WTW to Warren Street SR (Section B) (2.8km) 3) Butler WTW to Warren Street SR (Section C) (10.5km) 4) Butler WTW to Warren Street SR (Section D) (7.2km) 5) Groombridge Reinforcement (2.3km) 6) Resilience of Supply for Telham SR (1.0km) 7) Windover SR resilience (0.1km) 8) Interconnectivity - Kilnwood supply SPoF (4.5km) 9) Transfer between Burham and Halling systems (Pumping Station, no PCD applicable) 10) Transfer between Row Dow and Kemsing (1.0km) 11) Interconnectivity - Thanington to Dunkirk (5.5km) 12) Tonbridge to Bloodshots Main Reinforcement (0.3km) 13) RZ4 Sub-Zonal Scheme - Surrey Hills to Fleet (12.9km) 14) RZ4 Sub-Zonal Scheme - Greywell to Whitedown (15.3km) 15) RZ4 Sub-Zonal Scheme - Greywell to Swaineshill (8.0km) 16) RZ4 Sub-Zonal Scheme - Ewshot to Itchel (4.0km)
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Butlers to Forstal - Section A (3.3km) - Ashford improved supply resilience (RZ8) | £m/km | 0.27754
| Forstal to Detling via Running Horse Booster Upgrade - Section B (2.8km) - Ashford improved supply resilience (RZ8) | £m/km | 0.2639
| Detling to Hollingbourne - Section C (10.5km) - Ashford improved supply resilience (RZ8) | £m/km | 0.16382
| Hollingbourne to Warren St - Section D (7.2km) - Ashford improved supply resilience (RZ8) | £m/km | 0.14555
| Groombridge Reinforcement (2.3km) | £m/km | 0.88315
| Resilience of Supply for Telham SR (1.0km) | £m/km | 2.5936
| Windover SR resilience (0.1km) | £m/km | 21.1621
| Interconnectivity - Kilnwood supply SPoF (4.5km) | £m/km | 0.66681
| Transfer between Burham and Halling systems (Pumping Station, no PCD applicable) | n/a | n/a
| Transfer between Row Dow and Kemsing (1.0km) | £m/km | 2.6657
| Interconnectivity - Thanington to Dunkirk (5.5km) | £m/km | 1.2897
| Tonbridge to Bloodshots Main Reinforcement (0.3km) | £m/km | 3.3614
| RZ4 Sub-Zonal Scheme - Surrey Hills to Fleet (12.9km) | £m/km | 1.7753
| RZ4 Sub-Zonal Scheme - Greywell to Whitedown (15.3km) | £m/km | 1.4202
| RZ4 Sub-Zonal Scheme - Greywell to Swaineshill (8.0km) | £m/km | 1.6304
| RZ4 Sub-Zonal Scheme - Ewshot to Itchel (4.0km) | £m/km | 1.4039
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| Butlers to Forstal - Section A (3.3km) - Ashford improved supply resilience (RZ8) | £m/year | 0.011018 | 0.0036727
| Forstal to Detling via Running Horse Booster Upgrade - Section B (2.8km) - Ashford improved supply resilience (RZ8) | £m/year | 0.010477 | 0.0034923
| Detling to Hollingbourne - Section C (10.5km) - Ashford improved supply resilience (RZ8) | £m/year | 0.0065036 | 0.0021679
| Hollingbourne to Warren St - Section D (7.2km) - Ashford improved supply resilience (RZ8) | £m/year | 0.0057782 | 0.0019261
| Groombridge Reinforcement (2.3km) | £m/year | 0.035061 | 0.011687
| Resilience of Supply for Telham SR (1.0km) | £m/year | 0.10297 | 0.034322
| Windover SR resilience (0.1km) | £m/year | 0.84014 | 0.28005
| Interconnectivity - Kilnwood supply SPoF (4.5km) | £m/year | 0.026472 | 0.0088241
| Transfer between Burham and Halling systems (Pumping Station, no PCD applicable) | n/a | n/a | n/a
| Transfer between Row Dow and Kemsing (1.0km) | £m/year | 0.10583 | 0.035276
| Interconnectivity - Thanington to Dunkirk (5.5km) | £m/year | 0.0512 | 0.017067
| Tonbridge to Bloodshots Main Reinforcement (0.3km) | £m/year | 0.13345 | 0.044482
| RZ4 Sub-Zonal Scheme - Surrey Hills to Fleet (12.9km) | £m/year | 0.07048 | 0.023493
| RZ4 Sub-Zonal Scheme - Greywell to Whitedown (15.3km) | £m/year | 0.056382 | 0.018794
| RZ4 Sub-Zonal Scheme - Greywell to Swaineshill (8.0km) | £m/year | 0.064726 | 0.021575
| RZ4 Sub-Zonal Scheme - Ewshot to Itchel (4.0km) | £m/year | 0.055736 | 0.018579
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Butlers to Forstal - Section A (3.3km) - Ashford improved supply resilience (RZ8) | km | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3
| Forstal to Detling via Running Horse Booster Upgrade - Section B (2.8km) - Ashford improved supply resilience (RZ8) | km | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8
| Detling to Hollingbourne - Section C (10.5km) - Ashford improved supply resilience (RZ8) | km | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5
| Hollingbourne to Warren St - Section D (7.2km) - Ashford improved supply resilience (RZ8) | km | 0 | 0 | 0 | 0 | 0 | 0 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2
| Groombridge Reinforcement (2.3km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
| Resilience of Supply for Telham SR (1.0km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Windover SR resilience (0.1km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
| Interconnectivity - Kilnwood supply SPoF (4.5km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.1
| Transfer between Burham and Halling systems (Pumping Station, no PCD applicable) | n/a
| Transfer between Row Dow and Kemsing to support Hartley system (1.0km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Interconnectivity - Thanington to Dunkirk (5.5km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 4.9 | 4.9 | 4.9 | 4.9 | 4.9 | 4.9
| Tonbridge to Bloodshots Main Reinforcement (0.3km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| RZ4 Sub-Zonal Scheme - Surrey Hills to Fleet (12.9km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88
| RZ4 Sub-Zonal Scheme - Greywell to Whitedown (15.3km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3
| RZ4 Sub-Zonal Scheme - Greywell to Swaineshill (8.0km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 7.43 | 7.43 | 7.43 | 7.43 | 7.43 | 7.43
| RZ4 Sub-Zonal Scheme - Ewshot to Itchel (4.0km) | km | 0 | 0 | 0 | 0 | 0 | 0 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59

## SSC - Resilience Interconnector
South Staffordshire Water - SSC - Water - Resilience Interconnector
| Company | SSC
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified length (in km to 1dp) of pipeline or volume (in Ml to 1dp) for reservoir. The following schemes are expected to be delivered: 1) Burntwood resilience (Pipeline) 2) Hanbury resilience (Pipeline) 3) Langley reservoir (Reservoir Augmentation) [24 09 03 - SSC ADD1-21 ADD21]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Burntwood resilience (Pipeline) | £m/km | 0.48234
| Hanbury resilience (Pipeline) | £m/km | 0.39967
| Langley reservoir (Reservoir Augmentation) | £m/Ml | 0.77232
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| Burntwood resilience (Pipeline) | £m/year | 0.020065 | 0.0066884
| Hanbury resilience (Pipeline) | £m/year | 0.016626 | 0.0055421
| Langley reservoir (Reservoir Augmentation) | £m/year | 0.032128 | 0.010709
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Burntwood resilience (Pipeline) | km | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77
| Hanbury resilience (Pipeline) | km | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1
| Langley reservoir (Reservoir Augmentation) | Ml | 0 | 0 | 0 | 0 | 0 | 0 | 5.41 | 5.41 | 5.41 | 5.41 | 5.41 | 5.41

## SES- Resilience Interconnector
SES Water - SES - Resilience Interconnector
| Company | SES
| Enhancement area | Resilience Interconnector
| PCD No. | PCDW16b
| Common requirements | See Section 8.2.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Resilience Interconnectors: Delivery of the specified section of pipeline. The following schemes are expected to be delivered: 1) Interzonal resilience: Headley Reservoir bypass 2) Interzonal resilience: Outwood Reservoir bypass 3) Interzonal resilience: North Looe Reservoir bypass
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Inter-Inter-zonal resilience: Headley Reservoir bypass | £m/nr | 0.13851
| Inter-zonal resilience: Outwood Reservoir bypass | £m/nr | 0.11315
| Inter-zonal resilience: North Looe Reservoir bypass | £m/nr | 0.058525
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| Inter-Inter-zonal resilience: Headley Reservoir bypass | £m/year | 0.0054989 | 0.001833
| Inter-zonal resilience: Outwood Reservoir bypass | £m/year | 0.004492 | 0.0014973
| Inter-zonal resilience: North Looe Reservoir bypass | £m/year | 0.0023235 | 0.00077449
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Headley Reservoir bypass | nr | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Outwood Reservoir bypass | nr | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| North Looe Reservoir bypass | nr | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## NES - Resilience
Northumbrian Water - NES - Resilience
| Company | NES
| Enhancement area | Resilience
| PCD No. | PCDW16a
| Common requirements | See Section 8.1.2 of Price control deliverable appendix
Additional company specific requirements
| Description | The company is expected to deliver: • Installation of chilling facilities for sodium hypochlorite dosing at 44 water treatment works. [NES24 - A3-10 Enhancement Case WN - Climate Change Resilience - Process enhancements.pdf p4] • Installation of dissolved oxygen monitoring for slow sand filters at 5 water treatment works sites allowing the continued sustainable use of them under hot weather conditions. The sites and the expected maintained peak week production capacities (PWPC) are listed in the company's business plan submission. [NES24 - A3-10 Enhancement Case WN - Climate Change Resilience - Process enhancements.pdf p4] • Installation of run to waste systems for the slow sand filters at the above 5 water treatment works.
| Output measurement and reporting | The company should report outturn spend and number of water treatment works with chilling units and slow sand filter upgrades installed under this scheme annually in parallel with the APR. Following successful completion of each relevant installation, the peak week capacity (PWPC), using the same definition as used for unplanned outage calculation and reporting, of each water treatment works should continue to match the above PWPC regardless of elevated temperature conditions.
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Resilience - Hypochlorite chilling systems | £m per nr | 0.687
| Resilience - Monitoring and run to waste | £m per nr | 6.011
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Number of WTW with new hypochlorite chilling systems | nr | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 44 | 44 | 44
| Number of WTW with monitoring and run to waste facilities in slow sand filtration units | nr | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5
* Non-Delivery PCD rate has been calculated on a revised % allocation between the two schemes (50.1% on Hypochlorite chilling systems, 49.9% on Monitoring and run to waste)
The revised allocation is based on company submitted costs in PR24CA31 - W – Resilience "Company schemes table final" minus the £12.194m company requested reduction to the monitoring and run to waste scheme

## SRN - Resilience
Southern Water - SRN - Resilience
| Company | SRN
| Enhancement area | Resilience
| PCD No. | PCDW16a
| Common requirements | See Section 8.1.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Upgrade works at SRN water treatment works 3, SRN water treatment works 4, and SRN water treatment works 5
| Output measurement and reporting | The company should report the % earned value (EV) delivered aginst the the scope of works specified within SRN representation. For WTW3 this refers to interventions identified within document "SRN25 Appendix I – Full Scope & Delivery Schedule" where marked "AMP8" (page 150). For WTW4 this refers to interventions identified within document "SRN25 Appendix I – Full Scope & Delivery Schedule" where marked "AMP8" (page 161). For WTW5 this refers to interventions identified within document "SRN-DDR-027", for all interventions identified in table 15 (page 46). The company must annually report delivery progress of all interventions, and must deliver all of these interventions by 31st March 2030 or non-delivery payments apply.
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions
| Non-delivery PCD rate | Unit | Under-performance
| SRN WTW3 | £m per 1% of earned value of project not delivered | 0.14576
| SRN WTW4 | £m per 1% of earned value of project not delivered | 0.25639
| SRN WTW5 | £m per 1% of earned value of project not delivered | 0.39027
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| SRN WTW 3 | % | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100%
| SRN WTW 4 | % | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100%
| SRN WTW 5 | % | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100%

## PRT - Resilience
Portsmouth Water - PRT - Resilience
| Company | PRT
| Enhancement area | Resilience
| PCD No. | PCDW16a
| Common requirements | See Section 8.1.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Delivery of a new enhanced bypass provision at 13 service reservoirs [PRT07.04 The Isolation and Recovery of Service Reservoirs.pdf p11]
| Output measurement and reporting | None
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Reservoirs with new enhanced bypass provision | £m per reservoir | 0.269
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoirs with new enhanced bypass provision | nr | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 13 | 13 | 13 | 13

## SEW - Resilience
South East Water - SEW - Resilience
| Company | SEW
| Enhancement area | Resilience
| PCD No. | PCDW16a
| Common requirements | See Section 8.1.2 of Price control deliverable appendix
Additional company specific requirements
| Description | South East Water – Additional treated water storage • Delivery of additional treated water storage (across six service reservoirs) totalling extra live storage capacity of 51 Ml [SEW DD2b14 SEW10 Combined Dossiers Option Refs SRN004c, SRN006c, KRN009, KRN011c, KRN012c, KRN016c]. Delivered storage at the service reservoirs identified in company business plan submissions. South East Water - SEW WTW4 upgrades • Additional process stream (third stream) capable of a peak week production capacity (PWPC) of 52.3 Ml/d [SEW DD2b14 SEW10 Combined Dossiers Option Ref SRN003d]. • Installation of cascade aerator system within the bankside storage.
| Output measurement and reporting | The company should report the additional capacity able to throughput the additional stream in terms of peak week capacity (PWPC), using the same definition as used for unplanned outage calculation and reporting.
| Assurance | Companies should provide assurance on the reported data as per the common requirements.
| Conditions on scheme | No further conditions apply.
| Non-delivery PCD rate | Unit | Under-performance
| Resilience - service reservoir additional storage | £m per Ml | 0.482
| Resilience - SEW WTW4 additional aerator | £m per Nr | 7.7952
| Resilience - SEW WTW4 new process stream | £m per Ml/d | 0.69668
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Ml of additional service reservoir storage at 6 service reservoirs | Ml | 0 | 0 | 0 | 0 | 0 | 0 | 49.75 | 49.75 | 49.75 | 49.75 | 49.75 | 49.75
| Installation of a cascade aerator | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Ml/d of peak week production capacity of additional process stream | Ml/d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.3 | 52.3 | 52.3 | 52.3

## WSH - Reservoirs
Dwr Cymru - WSH - Reservoir safety
| Company | WSH
| Enhancement area | Reservoir safety
| PCD No. | PCDW16c
| Common requirements | See Section 8.3.2 of Price control deliverable appendix
Additional company specific requirements
| Description | Delivery of reservoir safety improvements at 23 specified reservoirs.
| Output measurement and reporting | Interventions delivered to meet the new size threshold requirements and recent legislative changes at each of the 23 specified reservoir sites with enhancement funding. This includes upsizing values and pipework, spillway upgrades, and discontinuance/ monitoring. Reporting should include: - Completion status of interventions at each reservoir site. - Description of delivered interventions. - Expenditure per intervention. - Confirmation of compliance with the Reservoirs Act 1975, new legislation, and updated technical guidelines. - Reporting mechanisms accommodate flexibility for site-specific changes, provided equivalent safety outcomes are achieved and spending levels are maintained.
| Assurance | The company should provide assurance on the reported data as per the common requirements. Where the company delivers interventions as originally proposed, we require self-certification at the end of the period. The company will confirm that the funded interventions were delivered as specified, alongside completed works, costs incurred, and alignment with statutory and technical requirements. In cases where substitutions (swaps) occur, the company must provide independent third-party assurance that the substituted intervention achieves equivalent or better safety outcomes and that spending aligns with statutory requirements and technical guidance. The company will justify any substitutions in their end-of-period reporting, supported by evidence of outcomes delivered and expenditure incurred.
| Conditions on scheme | Reallocation of allowances between reservoirs (swaps) are permitted under the following conditions: - Safety outcomes must be equivalent or greater, safety outcomes will be assessed based on compliance with updated technical and legislative standards, such as the Guide to Drawdown Capacity for Reservoir Safety and Emergency Planning (2017). - Total spending must meet or exceed allocated funding. - Swaps must be justified by statutory or technical priorities and require independent third-party assurance verifying equivalence or superiority of safety outcomes
| Reservoir | Activity | Unit | Non-delivery rate (£m)*
| Reservoir A | Intervention to meet drawdown capacity | £m per specified reservoir site | 0.014626
| Reservoir B | Spillway/drawdown intervention | £m per specified reservoir site | 11.8834
| Reservoir C | Discontinuance of site | £m per specified reservoir site | 1.8663
| Reservoir D | Spillway/drawdown intervention | £m per specified reservoir site | 4.4805
| Reservoir E | Intervention to meet drawdown capacity | £m per specified reservoir site | 12.5455
| Reservoir F | Discontinuance of site | £m per specified reservoir site | 2.6132
| Reservoir G | Spillway/drawdown intervention | £m per specified reservoir site | 0.33055
| Reservoir H | Intervention to meet drawdown capacity | £m per specified reservoir site | 0.29935
| Reservoir I | Intervention to meet drawdown capacity | £m per specified reservoir site | 5.2274
| Reservoir J | Discontinuance of site | £m per specified reservoir site | 2.6132
| Reservoir K | Spillway/drawdown intervention | £m per specified reservoir site | 0.74692
| Reservoir L | Discontinuance of site | £m per specified reservoir site | 2.9116
| Reservoir M | Monitoring | £m per specified reservoir site | 0.073132
| Reservoir O | Intervention to meet drawdown capacity | £m per specified reservoir site | 0.14919
| Reservoir P | Discontinuance of site | £m per specified reservoir site | 1.8663
| Reservoir Q | Spillway/drawdown intervention | £m per specified reservoir site | 3.2285
| Reservoir R | Spillway/drawdown intervention | £m per specified reservoir site | 3.8799
| Reservoir S | Spillway/drawdown intervention | £m per specified reservoir site | 2.9584
| Reservoir T | Spillway/drawdown intervention | £m per specified reservoir site | 0.74692
| Reservoir U | Risk assessment | £m per specified reservoir site | 0.039004
| Reservoir V | Spillway/drawdown intervention | £m per specified reservoir site | 4.1314
| Reservoir W | Intervention to meet drawdown capacity | £m per specified reservoir site | 0.74692
| Reservoir X | Spillway/drawdown intervention | £m per specified reservoir site | 5.3016
* Proposed activity cost, calculated post frontier-shift as specified in WSH-DD-08 (£m)
| PCD Outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoir A - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir B - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir C - Discontinuance of site | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir D - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir E - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir F - Discontinuance of site | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir G - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir H - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir I - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir J - Discontinuance of site | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir K - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir L - Discontinuance of site | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir M - Monitoring | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir O - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir P - Discontinuance of site | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir Q - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir R - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir S - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir T - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir U - Risk assessment | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir V - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir W - Intervention to meet drawdown capacity | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir X - Spillway/drawdown intervention | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## HDD - Reservoirs
Hafren Dyfrdwy - HDD - Reservoir safety
| Company | HDD
| Enhancement area | Reservoir safety
| PCD No. | PCDW16c
| Common requirements | See Section 8.3.2 of Price control deliverable appendix
| Description | Delivery of specified reservoir safety improvements at 10 specified reservoirs.
| Output measurement and reporting | Interventions delivered to meet the new size threshold requirements and recent legislative changes at each of the specfified ten reservoir sites with enhancement funding. Reporting should include: -Completion status of interventions at each reservoir site. - Description of delivered interventions. - Expenditure per intervention. - Confirmation of compliance with the Reservoirs Act 1975, new legislation, and updated technical guidelines. - Reporting mechanisms accommodate flexibility for site-specific changes, provided equivalent safety outcomes are achieved and spending levels are maintained.
| Assurance | The company should provide assurance on the reported data as per the common requirements. Where the company delivers interventions as originally proposed, we require self-certification at the end of the period. The company will confirm that the funded interventions were delivered as specified, alongside completed works, costs incurred, and alignment with statutory and technical requirements. In cases where substitutions (swaps) occur, the company must provide independent third-party assurance that the substituted intervention achieves equivalent or better safety outcomes and that spending aligns with statutory requirements and technical guidance. The company will justify any substitutions in their end-of-period reporting, supported by evidence of outcomes delivered and expenditure incurred.
| Conditions on scheme | Reallocation of allowances between reservoirs (swaps) are permitted under the following conditions: - Safety outcomes must be equivalent or greater, safety outcomes will be assessed based on compliance with updated technical and legislative standards, such as the Guide to Drawdown Capacity for Reservoir Safety and Emergency Planning (2017). - Total spending must meet or exceed allocated funding. - Swaps must be justified by statutory or technical priorities and require independent third-party assurance verifying equivalence or superiority of safety outcomes
| Reservoir | Activity | Unit | Non-delivery rate (£m)*
| Reservoir A | Balmforth enhancement works | £m per specified reservoir site | 0.154
| Reservoir B | New spillway/drawdown intervention and post Balmforth enhancement works | £m per specified reservoir site | 1.082
| Reservoir C | Balmforth enhancement works | £m per specified reservoir site | 0.169
| Reservoir D | New spillway/drawdown intervention and post Balmforth enhancement works | £m per specified reservoir site | 6.141
| Reservoir E | New spillway/drawdown intervention and post Balmforth enhancement works | £m per specified reservoir site | 2.03
| Reservoir F | New spillway/drawdown intervention and post Balmforth enhancement works | £m per specified reservoir site | 2.351
| Reservoir G | Post Balmforth enhancement works | £m per specified reservoir site | 0.42
| Reservoir H | Post Balmforth enhancement works | £m per specified reservoir site | 0.169
| Reservoir I | Post Balmforth enhancement works | £m per specified reservoir site | 0.504
| Reservoir J | Post Balmforth enhancement works | £m per specified reservoir site | 0.218
* Proposed activity cost, calculated post frontier-shift as specified in HDD2.3 (£m)
| PCD Outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoir A - Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir B - New spillway/drawdown intervention and post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir C - Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir D - New spillway/drawdown intervention and post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir E - New spillway/drawdown intervention and post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir F - New spillway/drawdown intervention and post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir G - Post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir H - Post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir I - Post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir J - Post Balmforth enhancement works | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## NES - Reservoirs
Northumbrian Water - NES - Reservoir safety
| Company | NES
| Enhancement area | Reservoir safety
| PCD No. | PCDW16c
| Common requirements | See Section 8.3.2 of Price control deliverable appendix
| Description | Delivery of specified reservoir safety improvements at 9 specified reservoirs.
| Output measurement and reporting | Interventions delivered to meet recent legislative changes at each of the 9 reservoir sites with enhancement funding. The company is funded for drawdown capacity improvements at all 9 specified sites with the installation of new siphons. Reporting should include: - Completion status of interventions at each reservoir site. - Description of delivered interventions. - Expenditure per intervention. - Confirmation of compliance with the Reservoirs Act 1975, new legislation, and updated technical guidelines. - Reporting mechanisms accommodate flexibility for site-specific changes, provided equivalent safety outcomes are achieved and spending levels are maintained.
| Assurance | The company should provide assurance on the reported data as per the common requirements. Where the company delivers interventions as originally proposed, we require self-certification at the end of the period. The company will confirm that the funded interventions were delivered as specified, alongside completed works, costs incurred, and alignment with statutory and technical requirements. In cases where substitutions (swaps) occur, the company must provide independent third-party assurance that the substituted intervention achieves equivalent or better safety outcomes and that spending aligns with statutory requirements and technical guidance. The company will justify any substitutions in their end-of-period reporting, supported by evidence of outcomes delivered and expenditure incurred.
| Conditions on scheme | Reallocation of allowances between reservoirs (swaps) are permitted under the following conditions: - Safety outcomes must be equivalent or greater, safety outcomes will be assessed based on compliance with updated technical and legislative standards, such as the Guide to Drawdown Capacity for Reservoir Safety and Emergency Planning (2017). - Total spending must meet or exceed allocated funding. - Swaps must be justified by statutory or technical priorities and require independent third-party assurance verifying equivalence or superiority of safety outcomes
| Reservoir | Activity | Unit | Non-delivery rate (£m)*
| Reservoir A | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 1.312
| Reservoir B | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 11.028
| Reservoir C | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 10.563
| Reservoir D | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 4.368
| Reservoir E | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 3.183
| Reservoir F | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 3.649
| Reservoir G | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 10.563
| Reservoir H | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 6.55
| Reservoir I | New Siphon to deliver drawdown drawdown capacity improvement | £m per specified reservoir site | 11.028
* Proposed activity cost, calculated post frontier-shift as specified in NES22A (£m)
| PCD Outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoir A - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir B - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir C - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir D - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir E - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir F - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir G - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir H - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir I - New Siphon to deliver drawdown drawdown capacity improvement | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## SRN - Reservoirs
Southern Water - SRN - Reservoir safety
| Company | SRN
| Enhancement area | Reservoir safety
| PCD No. | PCDW16c
| Common requirements | See Section 8.3.2 of Price control deliverable appendix
| Description | Delivery of specified reservoir safety interventions at 2 specified reservoirs.
| Output measurement and reporting | Interventions delivered to meet recent legislative changes at each of the 2 reservoir sites with enhancement funding. The company is funded for emergency drawdown improvements and new auxillary spillways at 2 specified sites. Reporting should include: - Completion status of interventions at each reservoir site. - Description of delivered interventions. - Expenditure per intervention. - Confirmation of compliance with the Reservoirs Act 1975, new legislation, and updated technical guidelines. - Reporting mechanisms accommodate flexibility for site-specific changes, provided equivalent safety outcomes are achieved and spending levels are maintained.
| Assurance | The company should provide assurance on the reported data as per the common requirements. Where the company delivers interventions as originally proposed, we require self-certification at the end of the period. The company will confirm that the funded interventions were delivered as specified, alongside completed works, costs incurred, and alignment with statutory and technical requirements. In cases where substitutions (swaps) occur, the company must provide independent third-party assurance that the substituted intervention achieves equivalent or better safety outcomes and that spending aligns with statutory requirements and technical guidance. The company will justify any substitutions in their end-of-period reporting, supported by evidence of outcomes delivered and expenditure incurred.
| Conditions on scheme | Reallocation of allowances between reservoirs (swaps) are permitted under the following conditions: - Safety outcomes must be equivalent or greater, safety outcomes will be assessed based on compliance with updated technical and legislative standards, such as the Guide to Drawdown Capacity for Reservoir Safety and Emergency Planning (2017). - Total spending must meet or exceed allocated funding. - Swaps must be justified by statutory or technical priorities and require independent third-party assurance verifying equivalence or superiority of safety outcomes
| Reservoir | Activity | Unit | Non-delivery rate (£m)*
| Reservoir A | Emergency drawdown imrprovements and new auxillary spillway | £m per specified reservoir site | 13.029
| Reservoir B | Emergency drawdown imrprovements and new auxillary spillway | £m per specified reservoir site | 12.655
* Proposed activity cost, calculated post frontier-shift as specified in SRN-DDR-035 (£m)
| PCD Outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoir A - Emergency drawdown imrprovements and new auxillary spillway | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir B - Emergency drawdown imrprovements and new auxillary spillway | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## NWT - Reservoirs
United Utilities - NWT - Reservoir safety
| Company | NWT
| Enhancement area | Reservoir safety
| PCD No. | PCDW16c
| Common requirements | See Section 8.3.2 of Price control deliverable appendix
| Portfolio Risk Assessment (PRA) | [13 empty] | Measures in the Interest of Satey (MITIOS)
| Description | The Proactive Risk Assessment (PRA) PCD requires United Utilities to deliver specified risk reduction interventions across 18 reservoir sites. For 10 fully funded sites, the PCD mandates the completion of specific interventions as detailed in the Final Determination. For the remaining 8 sites, funding is adjusted to reflect proportional risk reduction outcomes. The PCD includes flexibility mechanisms allowing substitutions, provided safety outcomes are equivalent or better. Reporting at the end of the period will confirm delivery and risk reduction achieved, ensuring customer funding is appropriately allocated and objectives are met. | [12 empty] | MITIOS Spend-Linked PCD ensures accountability for total £77.357m MITIOS actions spend allowance (comprising £42.797 million enhancement and £34.560 million base funding) by linking delivery to total spend, applying underperformance adjustments for shortfalls. Underspend below the combined total allowance (£77.357m) triggers a clawback proportional to the shortfall in enhancement spending relative to the enhancement cap (£42.797m)
| Output measurement and reporting | Output Measure: 1. Delivery of Intervention at specified reservoir Sites (10/18 Sites) - For 10 out of the 18 sites, United Utilities must deliver the specific interventions as specified in UUWR_14, Appendix C, Table 5. - These interventions should align with the technical specifications and cost estimates provided. - Success is measured by completing the interventions as proposed and achieving the expected outcomes. 2. Delivery of risk reduction at specified reservoir Sites (8/18 Sites) - For 8 out of the 18 sites, United Utilities must deliver risk reduction levels as specified in UUWR_14, Figures 7-25 (annual probability of failure). - Success is determined by achieving the risk reduction (annual probability of failure) specified in UUWR_14, Figures 7-25. Reporting Condition: - The interventions completed at each of the 18 reservoirs. - The associated risk reduction achieved at each site and interventions. - Evidence that allocated allowances have been utilised for the intended purpose and that safety outcomes have been met. - Justification for any deviations or swaps, including demonstration that the revised interventions maintain or exceed equivalent safety outcomes. Failure to achieve these conditions or provide adequate reporting will trigger underperformance adjustments as outlined in the PCD framework | [12 empty] | Total spend on MITIOS (£m), requirement to provide end-of-period reporting on the total MITIOS expenditure and completion of statutory-compliant safety improvements
| Assurance | Company should provide assurance on the reported data as per the common requirements. The company must confirm delivery of the specified risk reduction interventions at 8 fully funded sites. For the remaining 10 sites, the company will report on the risk reduction outcomes delivered, alongside evidence of costs incurred and compliance with technical and statutory requirements. Self-certification will be used to confirm delivery, with OFWAT reviewing submitted evidence to ensure the risk reduction measures are achieved as proposed. In cases where substitutions (swaps) occur, the company must provide independent third-party assurance that the substituted intervention achieves equivalent or better safety outcomes and that spending aligns with statutory requirements and technical guidance. The company will justify any substitutions in their end-of-period reporting, supported by evidence of outcomes delivered and expenditure incurred. | [12 empty] | Company should provide assurance on the reported data as per the common requirements. Given there are no pre-specified interventions,the company will provide self-certification at the end of the period, confirming that spending was directed towards relevant reservoir safety activities. Companies will submit a summary of expenditure to demonstrate alignment with statutory obligations and safety outcomes.
| Conditions on scheme | Reallocation of allowances between reservoirs (swaps) are permitted under the following conditions: - Safety outcomes must be equivalent or greater, safety outcomes will be assessed based on compliance with updated technical and legislative standards, such as the Guide to Drawdown Capacity for Reservoir Safety and Emergency Planning (2017). - Total spending must meet or exceed allocated funding. - Swaps must be justified by statutory or technical priorities and require independent third-party assurance verifying equivalence or superiority of safety outcomes | [12 empty] | 1. Spend Threshold: must spend at least £77.357 million, comprising £42.797 million for enhancement and £34.560 million for base allowances, on MITIOS-related safety interventions during the 2025-30 period, or clawback triggers. 2. Use of Allowance: The allowance must be exclusively used for delivering Measures in the Interests of Safety (MITIOS) interventions to meet statutory safety requirements. 3. Flexibility: Variability in annual spending is permitted, provided the total spend meets or exceeds the £77.36 million allowance by the end of the period. 4. Underspend Adjustments: If total spend falls below the £42.797m enhancement allowance, underperformance adjustments will be triggered for the shortfall amount. 5. Reporting Requirements: United Utilities must submit end-of-period reports providing evidence of completed interventions at named reservoirs and MITIOS spend breakdown to demonstrate compliance with the PCD.
| NWT (PRA + MITIOS) Total (£m) | 145.222 | [12 empty] | NWT (PRA + MITIOS) Total (£m) | 145.222 | Post-Adjustment & Frontier Shift allowance (£m)
| PRA - Total (£m) | 102.441 | Post-Adjustment & Frontier Shift allowance (£m) | [11 empty] | MITIOS - Enhancement | 42.797 | Post-Adjustment & Frontier Shift allowance (£m)
| PRA - 10/18 site interventions fully funded (£m) | 63.491 | Post-Adjustment & Frontier Shift allowance (£m) | [11 empty] | MITIOS - Base | 34.56 | Post-Adjustment & Frontier Shift allowance (£m)
| PRA - 8/10 risk reduction sites (£m) | 38.95 | Post-Adjustment & Frontier Shift allowance (£m) | [11 empty] | MITIOS - Total | 77.357 | Post-Adjustment & Frontier Shift allowance (£m)
| Reservoir | Activity | Unit | Non-delivery rate (£m) Post-FS* | [10 empty] | Non-deliver PCD rate | Unit | Under-performance
| Reservoir A | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 2.07 | [10 empty] | £1 clawback per £1 of MITIOS enhancement allowance underspent | £ of enhancement spend | £42.797m - Actual Enhancement Spend
| Reservoir B | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 7.429
| Reservoir C | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 5.115 | [10 empty] | PCD Outputs (cumulative) | Unit | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
| Reservoir D | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 7.404 | [10 empty] | £1 clawback per £1 of MITIOS enhancement allowance underspent | £ of enhancement spend | 0 | 0 | 0 | 0 | 1
| Reservoir E | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 8.525
| Reservoir F | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 7.307 | [10 empty] | EXAMPLE MITIOS SPEND
| Reservoir G | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 3.897 | [10 empty] | Example MITIOS Spend scenarios | Example 1: No adjustment (£77.357 total MITIOS spend) |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Enhancement (£m) | Base (£m) | Non-delivery adjustment (£m)
| Reservoir H | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 4.896 | [11 empty] | Cumulative allowance (£m) |  | - | - | - | - | 77.357
| Reservoir I | Slurry Trench to deliver risk reduction | Specified reservoir with intervention completed | 15.101 | [11 empty] | Cumulative Actual Spend (£m) |  | - | - | - | - | 77.357
| Reservoir J | Tube-A-Manchette (TAM) Grouting to deliver risk reduction | Specified reservoir with intervention completed | 1.747 | [11 empty] | Non-delivery adjustment (£m) |  | - | - | - | - | 0 | 77.357 | 42.797 | 34.56 | -
| Reservoir K | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 6.69 | [11 empty] | Example 2: Underspend (£70m total MITIOS spend) |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Enhancement (£m) | Base (£m) | Non-delivery adjustment (£m)
| Reservoir L | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 2.05 | [11 empty] | Cumulative allowance (£m) |  | - | - | - | - | 77.357
| Reservoir M | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 10.97 | [11 empty] | Cumulative Actual Spend (£m) |  | - | - | - | - | 70
| Reservoir N | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 2.53 | [11 empty] | Non-delivery adjustment (£m) |  | - | - | - | - | 5.797 | 70 | 42.797 | 27.2 | 7.36
| Reservoir O | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 2.38
| Reservoir P | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 5.85 | [11 empty] | Example 3: Overspend (£80m total MITIOS spend) |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Enhancement (£m) | Base (£m) | Non-delivery adjustment (£m)
| Reservoir Q | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 4.48 | [11 empty] | Cumulative allowance (£m) |  | - | - | - | - | 77.357
| Reservoir R | Risk reduction proposed at site | Risk reduction (Yes/No) at specified reservoir | 4.01 | [11 empty] | Cumulative Actual Spend (£m) |  | - | - | - | - | 80
| * Proposed activity cost, calculated post frontier-shift as specified in UUW44 (£m) | [14 empty] | Non-delivery adjustment (£m) |  | - | - | - | - | 0 | 80 | 42.797 | 37.2 | -
| PCD Outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Reservoir A | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir B | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir C | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir D | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir E | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir F | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir G | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir H | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir I | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir J | Specified reservoir with intervention completed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir K | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir L | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir M | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir N | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir O | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir P | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir Q | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Reservoir R | Risk reduction (Yes/No) at specified reservoir | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1

## Sector - Resilience CC uplift
Resilience climate change uplift
| Company | ANH, WSH, HDD, NES, SVE, SRN, TMS, NWT, WSX, YKY, AFW, PRT, SSC, SES
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
N/A
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| ANH spend on water power and flooding resilience | £m | [6 empty] | 12.223
| WSH spend on water power and flooding resilience | £m | [6 empty] | 8.8412
| HDD spend on water power and flooding resilience | £m | [6 empty] | 0.902
| NES spend on water power and flooding resilience | £m | [6 empty] | 9.8567
| SVE spend on water power and flooding resilience | £m | [6 empty] | 20.116
| SRN spend on water power and flooding resilience | £m | [6 empty] | 5.8043
| TMS spend on water power and flooding resilience | £m | [6 empty] | 32.9099
| NWT spend on water power and flooding resilience | £m | [6 empty] | 17.3039
| WSX spend on water power and flooding resilience | £m | [6 empty] | 3.5849
| YKY spend on water power and flooding resilience | £m | [6 empty] | 11.8209
| AFW spend on water power and flooding resilience | £m | [6 empty] | 8.616
| PRT spend on water power and flooding resilience | £m | [6 empty] | 1.3299
| SSC spend on water power and flooding resilience | £m | [6 empty] | 3.7746
| SES spend on water power and flooding resilience | £m | [6 empty] | 1.3383

## ANH - Resilience CC uplift
#VALUE!
| Company | ANH
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.12223
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## WSH - Resilience CC uplift
#VALUE!
| Company | WSH
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.088412
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## HDD - Resilience CC uplift
#VALUE!
| Company | HDD
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.00902
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## NES - Resilience CC uplift
#VALUE!
| Company | NES
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.098567
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## SVE - Resilience CC uplift
#VALUE!
| Company | SVE
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.20116
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## SRN - Resilience CC uplift
#VALUE!
| Company | SRN
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.058043
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## TMS - Resilience CC uplift
#VALUE!
| Company | TMS
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.3291
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## NWT - Resilience CC uplift
#VALUE!
| Company | NWT
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.17304
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## WSX - Resilience CC uplift
#VALUE!
| Company | WSX
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.035849
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## YKY - Resilience CC uplift
#VALUE!
| Company | YKY
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.11821
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## AFW - Resilience CC uplift
#VALUE!
| Company | AFW
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.08616
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## PRT - Resilience CC uplift
#VALUE!
| Company | PRT
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.013299
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## SSC - Resilience CC uplift
#VALUE!
| Company | SSC
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.037746
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## SES - Resilience CC uplift
#VALUE!
| Company | SES
| Enhancement area | Water and Wastewater Resilience
| PCD No. | PCDWW32
| Common requirements | See section 14.1.2 in 'PR24 final determinations - Price Control Deliverables Appendix.docx'
Additional company specific requirements
| Description | Climate change uplift PCD payment is calculated as Total allowance – Spend on the efficient delivery of schemes meeting the climate resilience criteria. This ensures any underspend on the allowance, or the delivery of inefficient schemes that do not meet the criteria, is returned to customers.
| Output measurement and reporting | In addition to the common reporting and the guidance provided in section 2 in "PR24 final determinations - Price Control Deliverables Appendix.docx', the company shall comply with these requirements: - annual climate change risks analysis to demonstrate the rationale for the selected schemes - the scope of the schemes and the physical assets that have been delivered - updates on schemes being substituted, delayed or cancelled
| Assurance | None.
| Conditions on scheme | We outline the criteria that companies must meet for schemes to qualify for funding under the climate change resilience uplift: - Companies must set out what schemes they will deliver for the additional uplift funding. This should include details of the schemes and why these have been prioritised. - Companies should address their biggest risks due to climate change impact. - All additional funding should be spent in the 2025-30 period. - Companies must clearly identify and demonstrate, supported by sufficient and convincing evidence, the causal relationship between the increasing risks and the climate change impact. Schemes delivered under this funding uplift must meet the climate resilience criteria (as listed) and be efficient. Where schemes delivered do not meet the criteria, or we have evidence of inefficiency of spend, funding will be returned to customers at PR29.
| Non-delivery PCD rate | Unit | Under-performance
| spend on schemes for power and flood resilience delivered: | £m per 1% completion | 0.013383
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0

## TMS - PR19 Gated
Thames Water - TMS - PR19 Gated
| Company | TMS
| Enhancement area | PR19 Thames Gated
| PCD No. | PCDW16d
| Description | Scheme related to the water supply system resilience programme (WSSRP) - due to commercial sensitivity and security concerns, only a high level description is provided below. Detailed descriptions have been shared with and agreed by the company directly following the issue of a Notice of intention to change dated 22 February 2024: 1. A1.1 Coppermills Distribution Resilience: construction of a new High Lift Pumping Station (HLPS) 2. A1.2 Coppermills Process Resilience: increase in the capacity and resilience of a Slow Sand Filter (SSF) 3. A1.3 Woodford Tunnel: resilience 4. A1.4 Hampton Source Resilience: install a road barrier 5. A1.5 Hampton Process Resilience: disinfection resilience 6. A1.6 Hampton Distribution Resilience: structural resilience scheme 7. A1.7 Mogden Distribution Resilience: resilience 8. A1.8 Coppermills Contact Tank: design a resilience solution.
| Output measurement and reporting | Delivery of each of the schemes against the milestones will be reported and monitored annually through the existing Annual Performance Report (APR) process or relevant successor. And, delivery of scheme A1.1. against the milestones will also be reported biannually until the project is in contract.
| Assurance | Independent third-party assurers with a duty of care to Ofwat are required to assess and assure completed milestones and forecast performance for remaining milestones, including that the work has been completed and that the achievement criteria in the table below are met.
| Conditions on scheme | There's minor variations in wording for different schemes, however, broadly our February 2024 notice of intent states: Company must deliver the scheme and required outcome of the scheme as set out in the Deliverables table below as agreed at Gate 4 of the Resilience Conditional Allowance process. Delays in delivering any of the deliverables by no later than the relevant Milestone Date will incur delay underperformance payments as set out in the incentives rates table below. Delay penalties will accrue monthly (based on whole months) and total delay penalties for the scheme will be capped at 30% of scheme allowed totex. In the event that either Thames Water notifies Ofwat the scheme will not be completed, or the scheme is delayed beyond the long stop date and Ofwat (reasonably) considers, following engagement with Thames Water, that the scheme will no longer be delivered, we reserve the right, at the Long Stop Date, to return the full funding allowance for the scheme to customers plus a further penalty of a year's delay penalties (calculated based on the total allowance for the scheme). For the avoidance of doubt, this will include recovery of funding provided in the 2020-2025 period and any subsequent price control period. Delay penalties will be applied via an in-period adjustment and in the event we consider non-delivery is likely, we also reserve the right to return the full funding allowance for the scheme plus the further penalty of a year's delay via an in-period adjustment. For scheme A1.2, Thames Water is required to: propose suitable interim milestones (milestones 2 and 3) for our consideration and inclusion in this Price Control Deliverable; and provide the necessary information to allow us to determine related price control deliverable rates. We will agree construction milestones 2 and 3 by 31 July 2026.
| PCD payment rate^ | • Annual delay rate (1/12th to be accrued monthly); • Penalty rate = scheme totex x (relevant WACC + RCV run-off rate) - specific numbers set out in February 2024 notice of intent; • Notice of intent also sets out a 'Maximum delay penalty' and 'Allowed totex to be returned to customers in event of non-delivery'.
^ Specific PCD payment rates were calculated for each scheme's milestone(s) and are set out in our February 2024 notice of intent.
| PCD outputs / Deliverables* |  | 2025-03-31 | 2026-03-31 | 2027-03-31 | 2027-10-31 | 2028-03-31 | 2028-10-31 | 2030-03-31 | 2031-01-31 | TBC | TBC
| A1.1 Coppermills High Lift Pumping Station (HLPS) |  | Contract Awarded and accepted |  |  | Construction Milestone #1 |  | Construction Milestone #2 |  | Scheme delivered
| A1.2 Coppermills Slow Sand Filter (SSF) |  | Contract Awarded and accepted | [6 empty] | Scheme delivered | Interim milestone TBC by 31-Jul-2026 | Interim milestone TBC by 31-Jul-2026
| A1.3 Woodford Tunnel |  | Scheme delivered
| A1.4 Hampton: road barrier |  |  | Scheme delivered
| A1.5 Hampton: disinfection resilience |  |  |  | Scheme delivered
| A1.6 Hampton Thames Water Ring Main (TWRM): | [7 empty] | Scheme delivered
| A1.7 Mogden: resilience | [5 empty] | Scheme delivered
| A1.8 Coppermills Contact Tank Design |  | Scheme delivered
* Detailed achievement criteria are set out in our February 2024 notice of intent.