## Slide 1: Lifelong Learning Entitlement (LLE) Provider Preparation Guide (July 2025)

## Slide 2: LLE Provider Preparation Guide Introduction
FOR ALL PROVIDERS
The LLE will transform the student-finance system in England for all education providers with students receiving funding from the Student Loans Company (SLC). The LLE will launch within academic year (AY) 2026/27 for courses and modules starting on or after 1 January 2027. This guide has been created to help providers with their preparations for the LLE. The content and timeline provided aim to guide your organisation’s preparations for LLE implementation by suggesting topics and actions for you to consider. This is the third iteration of this guide, following the first in May 2024 and the second in February 2025.
The timeline presented in this guide is illustrative and the guide is not intended to be used as a checklist exercise. Its purpose is to support your organisation in planning and implementing the necessary changes to ensure readiness for LLE launch. This guide also sets out when you can expect further policy information and signposts to further information on the LLE. These timings may be subject to change.
Who should read this guide?
This guide is intended for providers in England that are already registered with the Office for Students or will be registered when the LLE launches.
All Providers: review page 3 to improve or refresh basic understanding of the LLE.
All Providers: review page 4 to understand provider eligibility criteria, including the assurance check.
All Providers: review page 5 to prepare for the introduction of the LLE as the new student finance system.
Providers of eligible courses* review pages 6 and 7 to prepare to offer LLE modular provision from January 2027.
All Providers: review Annexe A for further information on the resources available to you in preparing for the LLE.
*Those who currently offer/plan to offer Higher Technical Qualifications (HTQs) at Level 4 or 5 or Level 6 qualifications which align to priority skills gaps and align to the Government’s industrial strategy. See Lifelong Learning Entitlement overview - GOV.UK (www.gov.uk) for more information.

## Slide 3: Ensuring basic understanding of the LLE and how it will affect your organisation
FOR ALL PROVIDERS
1. Read the resources available at the following links to find up-to-date information on LLE:
    Lifelong Learning Entitlement overview - GOV.UK (www.gov.uk) – this page is regularly updated with new information relating to the LLE. To subscribe to these updates, click “Get emails about this page”. Please note, to fully benefit from this preparation guide, it is essential to first read the overview as this guide assumes a basic level of understanding of the LLE.
    Lifelong Learning Entitlement FAQ (slc.co.uk) – this FAQ page will continue to be updated with new information as it becomes available.
    If you have further questions after reviewing these resources and/or you would like to be more involved in our stakeholder engagement activities, you can contact us at LLE.TEAM@education.gov.uk.
    You can find further information on the resources available to you in Annexe A of this guide.
      2. Determine whether your provision will be eligible for LLE funding from January 2027 and whether any of your provision will be in scope for modular funding from January 2027.
      You can do this using the LLE Provider Modular Eligibility Checker, on page 4 of this guide (please also refer to Lifelong Learning Entitlement overview - GOV.UK (www.gov.uk) for further information).

## Slide 4: LLE Provider Modular Eligibility Checker
FOR ALL PROVIDERS
Is your organisation registered with the Office for Students?
Yes
Does your organisation hold a Teaching Excellence Framework (TEF) rating
and/or
an Ofsted rating?
Yes
(TEF Gold / Silver,
Ofsted Outstanding / Good)
* If both ratings are held by a provider, both conditions must be met
No
Your organisation will not be eligible to deliver any LLE-funded provision from January 2027.
See GOV.UK for further information on the OfS’ planned consultation on the regulation of providers in the statutory FE sector.
Yes
(TEF Bronze / Requires Improvement,
Ofsted Requires Improvement / Inadequate)
or
No Rating
Providers interested in delivering modular provision from January 2027 are asked to submit an Expression of Interest to the DfE, subject to the assurance check.
See GOV.UK for further information on the Expression of Interest and eligible modular provision.
Providers interested in delivering modular provision from January 2027 are asked to submit an Expression of Interest to the DfE, alongside additional information demonstrating their readiness, capability and successful delivery of the parent course, subject to the assurance check.
See GOV.UK for further information on the Expression of Interest and eligible modular provision.
Does your organisation offer Higher Technical Qualifications (HTQs) at Level 4 or 5
or
Level 6 qualifications which align to priority skills gaps and align to the Government’s industrial strategy?
(See GOV.UK for further information on eligible provision).
Yes
No
Your organisation’s modular provision will not be eligible for LLE funding from January 2027.
We anticipate that modular provision will gradually expand when appropriate to do so. Subscribe to updates on the GOV.UK page for updates on modular expansion.
Review pages 5, 6 and 7 of this Guide
Review page 5 of this Guide

## Slide 5: What do you need to do to prepare for the LLE as the new student finance system?
FOR ALL PROVIDERS
Now
  Scale of LLE impact
  Which functions in your organisation will be impacted by the introduction of the LLE as the new student finance system?
  For example:
    Your information, advice and guidance on student finance will need to be updated.
    Consider if your course management and attendance management systems accommodate the LLE i.e. dual running on both the current Higher Education Student Finance system (for continuing learners and for those studying at an English provider, domiciled in the UK and funded via their administrations) and the new LLE system (for new learners).
  Define/adjust roles and responsibilities within your organisation for any changes to these functions and ensure resources are allocated/prioritised accordingly. For example:
    Consider nominating an “LLE Lead” or convening an "LLE Working Group" within your organisation, whose role it would be to keep abreast of LLE policy developments and ensure your organisation is on track to deliver through this new student finance system from January 2027.
Summer 2025
Awareness
Familiarise yourself with the recent announcements regarding the LLE, including:
Details of eligibility criteria for modular funding, including the assurance check.
Details on funding for Advanced Learner Loan (ALL) courses.
Maintenance loans and grants.
Subjects in scope of the Priority Additional Entitlement (PAE) and modular provision.
OfS anticipates re-opening registration applications in Summer 2025. See their website for information.
  Course design
Consider whether and how the LLE might impact your organisation’s course design.
Familiarise yourself with the changes to how tuition fee limits will be calculated and ensure your fees for January 2027 onward are compliant with LLE fee limit rules, where applicable.
Confer with your Awarding Organisation, if applicable, following the publication of the results of the ALL transfer.
Review the SLC’s Course Service Definition once published. This will specify all course eligibility requirements.
Contractual/third-party arrangements
Liaise with internal IT teams and third-party IT suppliers to determine whether your student information system and courses management systems will need updating - further information on the requirements for this will be provided by the SLC in due course.
Consider your attendance management and fee-charging policies in accordance with CMA guidance and how this will change for courses starting from January 2027 for LLE students.
Autumn/Winter 2025
Awareness and marketing
Consider whether/how your marketing strategy will need to change under the LLE.
Continue to monitor updates from the DfE, SLC and your mission group representative.
  The Student Loans Company plans to run a series of LLE planning and awareness events later in the year.
OfS expects to consult on regulation of providers in the statutory FE sector in autumn 2025 and DfE expects to consult on learner mobility across LLE-funded provision in early 2026.
Updating your Information, Advice and Guidance (IAG)
Prepare outreach and recruitment information and any other student resources for courses starting on/after 1 January 2027 to include funding IAG for the LLE and credit values, where applicable.
Revise and issue your attendance management and fee-charging policies by the time you start making course offers for courses starting from January 2027 onwards.
Course collection for AY26/27
Prepare for course collection for AY26/27 as usual. Course information for those starting from January 2027 (LLE-funded students) will be collected in early summer 2026.
  Read SLC training and guidance material ahead of course submission.
  Attend SLC’s Courses Management Service (CMS) webinar (details will be shared in due course).
Spring/Summer 2026
Preparing to submit course information for LLE-funded courses to SLC
Register for SLC CMS training sessions (details will be shared in due course).
Read SLC training and guidance material ahead of course submission (this will be shared in due course).
When preparing to submit your course information to SLC, you will need to consider the following:
  Are credit values assigned to all courses, where applicable?
  Is your internal course database up-to-date to reflect what will be submitted to the SLC CMS?
Preparing for attendance management activities
Register for SLC Student Information Service (SIS) training sessions (details will be shared in due course).
LLE course collection for AY26/27 courses starting from January 2027 onwards
Submit full-time, part-time and any modular course submissions for AY26/27 courses starting from 1 January 2027 (for LLE-funded students) to the SLC CMS.
Student application
Deliver essential eligibility, entitlement and application messages for students who will be accessing LLE funding from January 2027. Channels could include direct IAG engagements and/or incorporation of appropriate information and resource signposting into associated communication materials.
Student applications for LLE funding will open in September 2026.
5

## Slide 6: What do you need to do to if you plan on delivering LLE-fundable modular provision from January 2027?
FOR PROVIDERS OF ELIGIBLE COURSES
Now
  Scale of LLE impact
  Which functions in your organisation will be impacted by modular provision?
    For example, admissions, accommodation, student support, career services, marketing and information, advice and guidance may need to change to serve modular learners alongside full-time learners.
  Define/adjust roles and responsibilities within your organisation for any changes to these functions and ensure resources are allocated/prioritised accordingly. For example:
    Will you need to allocate more resource toward handling modular applications, if these are being managed in-house?
    Will you need to allocate more resource toward supporting an increase in student queries regarding IAG or to support Recognition of Prior Learning?
Summer 2025
  Modularising your courses
Consider the following questions on how modular funding may impact your organisation’s course design:
  Which of your courses can be modularised? We are taking a phased approach to providing funding for modules meaning not all courses can be modularised from launch. Phase 1 of modular funding will focus on modules of HTQs, and level 6 courses identified as key to the government's industrial strategy (see GOV.UK).
  Familiarise yourself with GOV.UK guidance on which courses can be modularised, including noting that delivery of modules cannot be franchised.
  It is not a requirement to modularise all of your eligible courses. Consider which of your modules would work well on their own and would attract demand.
  LLE modules must form part of a designated parent course and have a minimum funding size of 30 credits. You do not need to restructure your courses into 30-credit modules. You can bundle two or more modules from the same parent course to meet this minimum. Do you need to create bundles of existing 5-, 10-, 15- or 20-credit modules to meet the minimum 30-credit criteria?
  Are there any employers you wish to partner with to determine local/national skills gaps that could be addressed through modular provision?
  What are the financial implications of delivering modular provision, including profitability and minimum viable student numbers to run a module?
  Consider whether you will need to create or update your credit transfer framework to support your modular offer. This may include reviewing your academic regulations.
  Consider how you may need to adapt your current processes to provide standardised transcripts for your modules. Guidance will be provided in due course as to what the standardised transcript must contain.
  Find out who your nearest provider on the Modular Acceleration Programme is. Consider connecting with them to learn about any localised best practice they may be able to share with you.
Complete your Expression of Interest to DfE
Providers interested in delivering modular provision from January 2027 will be asked to submit an Expression of Interest (EOI) to DfE.
The DfE will then conduct the assurance check on all providers who have expressed interest and DfE will ask for further information in cases where providers TEF and/or Ofsted ratings do not meet the criteria.
6

## Slide 7: What do you need to do to if you plan on delivering LLE-fundable modular provision from January 2027?
FOR PROVIDERS OF ELIGIBLE COURSES
Autumn/Winter 2025
Awareness and marketing
Determine the marketing strategy for any modular provision you plan to offer.
  For example, if you seek to target mature students, do you need to start building relationships with local employers and/or recruitment agents, rather than only relying on existing recruitment channels? Can you leverage your existing employers to create demand for your courses? How will the LLE affect your relationship with any other providers in your network?
Update your IAG to ensure that it accurately reflects modular study and confirms to CMA guidance.
OfS expects to consult on regulation of providers in the statutory FE sector in autumn 2025 and DfE expects to consult on learner mobility across LLE-funded provision in early 2026.
Other Preparation
Determine the timing for intakes for your modular offering. Will these modules be incorporated into the delivery schedule of the full programme and how will this work if multiple intakes across the academic year are not currently offered?
Consider how applications for your modular provision will be administered and how your admissions and registry operations will need adapt to accommodate this.
Consider how your wrap-around support will accommodate modular learners.
Spring/Summer 2026
Preparing to submit course information for LLE-funded modules to SLC
The process for uploading module information will be similar to the process for full courses. Please see page 5 for more details.
Guidance will be provided in due course as to the specific details that you will need to provide when uploading module information.
When preparing to submit your course information to SLC, you will need to consider the following:
  Are credit values assigned to all modules?
  Is your internal course database up to date to reflect what will be submitted to the SLC Courses Management Service (CMS)?
  Preparing data for collection
Guidance will be provided by the DfE and HESA on how to record data on modular provision. You will need to ensure that you are familiar with this guidance and that your student records systems are able to accommodate the return of this data.
Data requirements may develop over time, so you should remain abreast of any advertised changes.
LLE course collection for AY26/27 courses starting from January 2027 onwards
From summer 2026, you can submit full-time, part-time and any modular course submissions for AY26/27 courses starting from 1 January 2027 (for LLE-funded students) to the SLC CMS.
7

## Slide 8: Annexe A: References and further resources
FOR ALL PROVIDERS
  Core resources (regularly updated):
  Lifelong Learning Entitlement (LLE): overview - GOV.UK (www.gov.uk)
  Lifelong Learning Entitlement FAQs (slc.co.uk)
  LLE policy guidance and other updates
  The modular acceleration programme (MAP) - GOV.UK (www.gov.uk)
  Learner-facing resources:
  Skills for Careers (education.gov.uk)
  Background information:
  LLE consultation response - GOV.UK (www.gov.uk)
  Subscribe to updates:
  You can subscribe to the Department for Education’s LLE mailing list by emailing LLE.TEAM@education.gov.uk
  You can subscribe to the Student Loans Company’s LLE mailing list by emailing LLE_enquiries@slc.co.uk
  Sign up for email alerts - Office for Students