## Slide 1: Setting Up and Leading the North Northamptonshire Shadow Authority
Overview of formation and leadership challenges
Notes: AI-generated content may be incorrect. --- This presentation covers the background, structural changes, roles, timelines, challenges, and lessons learned during the formation and leadership of the North Northamptonshire Shadow Authority. Image source: Microsoft 365 content library

## Slide 2: Today's Presentation Agenda
Background and Context of Northamptonshire Reorganisation
Legal and Structural Foundations: The Structural Changes Order and Shadow Authority Roles
Governance and Leadership During the Shadow Year
Core Challenges in Setting Up the Shadow Authority
Lessons Learned and Practical Advice
Notes: --- We will explore the background and context of Northamptonshire reorganisation, legal foundations, governance during the shadow year, key timelines, core challenges faced, lessons learned, best practices, and summary frameworks. Image source: Microsoft 365 content library

## Slide 3: Background and Context of Northamptonshire Reorganisation
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Financial collapse and drivers for reorganisation, Creation of new unitary councils and establishment of shadow authorities

## Slide 4: Financial collapse and drivers for reorganisation
Northamptonshire County Council’s financial collapse prompted reorganisation. ( Max Caller BV report – MHCLG and DFE commissioners… S114s!)
Two new unitary authorities created: West Northamptonshire and North Northamptonshire (2021).
Reorganisation occurred under severe financial and governance stress, Brexit, General Election, pandemic….
COVID-19 pandemic forced scaled-back transition plans and delayed elections to Shadow Authority.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 The financial collapse of Northamptonshire County Council led to the creation of two new unitary councils, North and West Northamptonshire, which vested in April 2021. Shadow authorities were established to prepare essential elements such as constitution, budget, staffing, and service continuity during the transition period. The reorganisation was driven by both financial failure and governance concerns, with a tight timetable complicated by the COVID-19 pandemic. Notably, the division of legacy financial assets and liabilities took years to resolve, highlighting the complexity of the transition . Image source: Microsoft 365 content library

## Slide 5: Creation of new unitary councils and establishment of shadow authorities - a high level timeline
Council Financial Collapse
  Max Caller BV report and Commissioners appointed 2018
  – 2 S114 Notices
New Unitary Councils Established
  Proposal to Government 2018, Structural changes order 2020, vesting Day 2021
  But … Brexit, general election and Pandemic !!
Shadow Authorities from 2020 ( Joint committee before that)
  Shadow authorities were set up to prepare constitutions, budgets, staffing, and ensure delivery of the implementation plan and service continuity – safe and legal for Vesting Day.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Financial collapse of Northamptonshire County Council prompted reorganisation. Two new unitary councils: North & West Northamptonshire (vested Apr 2021). Shadow authorities established to prepare constitution, budget, staffing, and service continuity. Image source: Microsoft 365 content library

## Slide 6: Phased transition timeline and major outputs
Legal and Statutory Preparation
  Government decisions and statutory instruments establish the legal framework for the shadow authority.
Joint Implementation Board Setup
  A board with council leaders and executives oversees the transition and implementation process.
Baseline Work and Audits
  Comprehensive audits on services, finances, workforce, ICT, and assets prepare for smooth transition.
Communication and Planning Outputs
  Early communication ensures continuity, producing a transition plan, governance blueprint, and risk register.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Phase 1: Pre-Shadow Period — “Setting the Ground” (Months -18 to -12) Goal: Prepare for the legal creation of the shadow authority and ensure smooth political and officer transitions. Key Tasks: 🏛️ Government decision made and statutory instrument laid before Parliament. ⚖️ Implementation Order defines the new area, powers, membership, and timetable. 📘 Establish a Joint Implementation Board (JIB) or Implementation Executive made up of Leaders and Chief Executives of existing councils. 👥 Begin baseline work: service mapping, financial due diligence, workforce data, ICT and asset audits. 💬 Early communications with staff and members to set out process and reassure about continuity. Outputs: Draft transition plan and governance blueprint. Agreed principles for collaboration and culture-building. Initial risk register and resource plan. Image source: Microsoft 365 content library

## Slide 7: Summary of high-level transition timeline
Phase | Months | Focus | Key Outputs
1. Pre-Shadow | -24 to -12 | Early planning and programme set up | Proposals agreed, Implementation begins, baseline data and audits, programme design
2. Shadow Establishment | -12 to -9 | Governance setup – shadow elections | Leadership, constitution, shadow budget, interim officers, executive arrangements
3. Design | -9 to -6 | Operating model design | MTFS draft ( size of the gaps !) , senior structure and operating model, Vision and values
4. Implementation | -6 to -3 | Transition delivery | HR, ICT, finance integration , Appointment of permanent officers
5. Vesting Readiness | -3 to 0 | Final testing & communications | Readiness dashboard, Day 1 plan
6. Go Live | 0+ | Launch & stabilisation | Fully operational council
7. Post vesting day transition | 1- 24 | Harmonise and rationalise | One council, foundations for transformation
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 📊 Example High-Level Timeline Summary

## Slide 8: Legal and Structural Foundations: The Structural Changes Order and Shadow Authority Roles
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Statutory and constitutional basis for the shadow authority, Roles and composition of the shadow authority and shadow executive

## Slide 9: Statutory and constitutional basis for the shadow authority
Structural Changes Order
  Defines the shadow authority and shadow executive, establishing legal and operational foundations. Proposes election and civic arrangements
Draft Shadow Authority Constitution inc Code of Conduct
  Outlines the shadow authority's structure, powers, and membership
Meetings and Decision making
  Creation of Leader and cabinet model , Appointment of Key Officers, members allowances, scrutiny arrangements
Executive Arrangements
  Typical issues – Council tax decisions, locations, implementation monitoring, Blueprints for new organisations , CGR, pensions, budgets, corporate plans, vision and values, task and finish panels, S24 decisions…Logos !.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 The full Structural Changes Order 2020 — especially parts defining the shadow authority and shadow executive. The Draft Shadow Authority Constitution (May 2020) — to see structure, powers, membership. Minutes / agendas from the first few meetings of the shadow authority & shadow executive (e.g. 2020 meetings). Reports or reviews by Commissioners (financial oversight) such as the “Fourth Commissioners’ Report”. Task & Finish group terms of reference and how their outputs were handled. Any reports / minutes showing how statutory officers (CEO, s.151, Monitoring Officer) were appointed, interim arrangements, resignations. Image source: Microsoft 365 content library

## Slide 10: Governance and Leadership during the Shadow Year
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance structures and leadership arrangements, Political leadership, culture, and decision-making

## Slide 11: Governance structures and leadership arrangements
  Governance structures defined in SCO with Leadership Arrangements to ensure accountability, transparency, and strategic direction.
  Scrutiny and task and finish groups established to ensure transparency and inclusive decision making
  Collaborative across both new unitaries – joint arrangements – one programme
  Early agreement on the governance structure , roles and responsibilities, Terms of reference
  Visible political leadership for the new organisations
  Strong message on culture
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance in the shadow year Image source: Microsoft 365 content library

## Slide 12: Political leadership, culture, and decision-making
Establishing Stability and Trust
  Create an environment of stability and trust among members from predecessor councils for effective collaboration.
Promoting Shared Vision
  Encourage a shared vision and purpose to unify the new council and guide decision-making collectively and build the new culture and values
Managing Political Differences
  Address political differences and legacy loyalties constructively to foster positive council dynamics and to start well, end well….
Inclusive Leadership Approach
  Model collaborative and inclusive leadership to avoid a takeover culture and encourage participation , build trust in the new arrangements
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 👥 3. Political Leadership and Culture Purpose: Create stability, trust, and collaboration among members from predecessor councils. Promote a shared vision and purpose for the new council. Manage political differences and legacy loyalties constructively. Communicate regularly and transparently with all members. Model collaborative and inclusive leadership—avoid a “takeover” culture. Image source: Microsoft 365 content library

## Slide 13: Resources and capacity
Workforce considerations
Anxiety will be high…plan for change management early… comms and then more comms..
TUPE and Ts and Cs – look for harmonisation on policies if possible…work with Unions early on ..
Build the culture of one team asap… embrace the new but make sure you give a goodbye to the old..
Support staff early on with career pathways and development
Encourage joint working early on to help integration
Strong visible leadership is needed.. Appoint leadership early
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance in the shadow year Image source: Microsoft 365 content library

## Slide 14: Resources and capacity
Financial considerations
Build strong financial information baseline and agree early the financing of transition , agree principles of cost sharing and disaggregation early if possible – one version of the truth, no shocks..
Consider Council tax changes early on – harmonisation and CTRS
Be realistic on the costs of transformation and change and the timing of savings and efficiencies
Manage the transition to the new unitaries collaboratively – S24 , asset and liability divisions
Embed strong financial management from the start
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance in the shadow year Image source: Microsoft 365 content library

## Slide 15: Program delivery and transformation
Day one service delivery – safe and legal
Critical services need to be identified and contingency plans in place to ensure uninterrupted service delivery and safeguarding
Get Blueprints of operating model agreed and look at service designs to integrate departments if possible before vesting day but at least create the basis for change in the future
ICT is a major challenge … legacy systems .. Compatibility. Integration, data migration, cyber….Look to have basics in place day 1 but don’t expect it to be done for a long time .. Architecture ands systems need to be right so don’t rush it .
Stabalise first then innovate …launch a consistent day one identity… ICT readiness assessments and capacity underpin other transitions
Ensure the programme is realistic and resourced to deliver, including change management and comms.. Have a roadmap
Map service delivery early on to identify differences but also areas of commonality to build on
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance in the shadow year Image source: Microsoft 365 content library

## Slide 16: Comms and Engagement
Comms and the more comms !
Consistent messaging across all impacted organisation is key … bespoke to your own organisation but the key messages need to be the same .. Tailored to different audiences
Stakeholder engagement is key to building trust in the new organisation
Engage with members early on vision and values to set the culture and give clear leadership
Be as transparent as possible – meetings in public , use scrutiny to help
Emphasise the key messages but be honest – if the information or answer isn’t available .. Say so.
Maintain one voice for the organisation in the media
Celebrate successes and milestones
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Governance in the shadow year Image source: Microsoft 365 content library

## Slide 17: Core challenges
Financial Clarity
  Addressing legacy debts and asset division to establish a transparent financial baseline.
Governance and Leadership
  Managing interim executives, senior appointments, and pressured decision-making processes.
Workforce and Culture
  Handling TUPE transfers, pay harmonisation, employee morale, and cultural integration.
Service Continuity and ICT
  Ensuring critical services operate safely while rebuilding in-house IT systems.
Transparency Challenges
  Task & Finish Groups operated privately without published minutes, limiting public scrutiny and oversight
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Key challenges faced by the North Northamptonshire Shadow Authority included: Financial clarity: Addressing legacy debts, asset division, and establishing a transparent financial baseline. Governance and leadership: Managing an interim executive, senior staff turnover, and decision-making under pressure. Workforce and culture: Handling TUPE transfers, pay harmonisation, morale, and integrating diverse organisational cultures. Service continuity and ICT: Ensuring critical services operated safely and rebuilding in-house systems. Transparency and trust: Dealing with closed-door task groups and rebuilding public and member confidence. Image source: Microsoft 365 content library

## Slide 18: Lessons Learned and Practical Advice
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Key lessons and practical recommendations from the North Northamptonshire experience, Specific lessons on finance, governance, staff, and communication

## Slide 19: Key lessons and practical recommendations from the North Northamptonshire experience
Financial Baseline First
  Conduct early independent forensic financial reviews and ensure transparency – no shocks.
Safe and Legal Priority
  Prioritise service continuity and legal compliance before implementing broader transformations.
Scrutiny and Transparency
  Embed open governance and meaningful scrutiny to build public trust.
Invest in People and Culture
  Boost staff morale, engagement, and maintain leadership continuity for success.
Communicate Relentlessly
  Provide clear, honest updates to staff and residents to maintain confidence.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 The document distills practical lessons from the North Northamptonshire experience: Financial baseline first: Early independent forensic financial reviews and transparency are critical to avoid crises. Safe and legal before transformation: Prioritise service continuity and legal compliance before pursuing wider transformation, with flexibility to adjust scope due to external shocks like the pandemic. Embed scrutiny and transparency: Open governance and meaningful scrutiny rebuild public trust. Invest in people and culture: Staff morale, engagement, and leadership continuity are essential. Expect long-tail issues: Financial, operational, and cultural harmonisation can take years. Communicate relentlessly: Clear, honest updates for staff, members, and residents maintain confidence .

## Slide 20: Specific lessons on finance, governance, staff, and communication
Financial Transparency and Early Review
  Early forensic financial reviews and transparency prevent long drawn out decisions and set a reliable financial baseline for future decions.
Clear Asset and Liability Agreements
  Legal clarity on asset and liability division avoids disputes and supports smooth reorganisation.
Prioritising Stability over Ambition
  Focus first on safe, legal operations; to form a foundation for transformation plans ver the medium term.
Staff Engagement and Morale
  Early clarity on pay and conditions and HR policies, plus union engagement, reduce staff anxiety , increase retention and boost morale.
Notes: --- This slide references information from the following file: https://harboroughcouncil-my.sharepoint.com/personal/l_elliott_harborough_gov_uk/_layouts/15/Doc.aspx?sourcedoc=%7B526BC7E4-9A34-49C1-9214-209074A9F029%7D&file=LGA%20webinar%20prep%202.docx&action=default&mobileredirect=true&DefaultItemOpen=1 Financial Discipline & Early Transparency The financial collapse of the old county council meant huge deficits, misuse of reserves, and lack of a credible baseline. It took intervention, forensic review to ascertain true finances. Lesson: Don’t wait until the financial situation becomes a crisis. Early forensic financial reviews, full transparency, and recognition of liabilities are essential. The shadow or intervention authority must insist on a reliable financial baseline early. Managing Legacy Liabilities & Asset Allocation Dividing old county council assets and liabilities between the two new unitaries (West vs North) was technically difficult; political stress over fairness; took years to resolve. Lesson: Clear legal agreements at the outset, ideally enshrined in the reorganisation order or transitional documents, about who gets what (buildings, debts, contracts) are vital. Try to avoid long tail disputes. Urgency vs Safe & Legal The “safe & legal plus” approach: Northamptonshire emphasised getting to safe and legal operations by vesting day, but recognised that transformation beyond that would be necessary. COVID-19 forced scaling back of ambitions for what could be done by Go-Live. Lesson: Prioritise what must be in place for legal, service continuity. Build transformation in, but don’t over-load pre-vesting timetable with projects that risk compromising Day-1 stability. Be ready to adjust scope in light of external shocks (e.g. pandemic). Staff, Pay, Terms & Conditions There were concerns from unions that the new unitary councils should not replicate past mistakes; worry over pay harmonisation and conditions. Some staff left amid uncertainty. Lesson: Employee morale, retention depend on early clarity on pay, terms, TUPE, conditions. Engagement with unions and staff is crucial. Uncertainty causes attrition, higher costs for interim cover, etc. Governance & Decision-Making Structures North Northamptonshire Council adopted Executive arrangements with cross-party Advisory Panels; there was debate about which governance model to use (e.g. executive vs committee). The constitution was approved but expected to need review. Planning committees and scrutiny arrangements have been subject to peer review and adjustment. Lesson: Governance model choices matter and may need to evolve. Embedding robust scrutiny, clear decision lines, and reviewing governance once some initial operation experience is gained is helpful. Also hybrid/advisory layers can help include wider views without slowing core decision-making. Shared Services & Outsourcing Prior to collapse, Northamptonshire had relied heavily on shared services (LGSS etc.) for back-office functions. But governance and cost/performance issues emerged: the authority was “hollowed-out,” lacking in its own corporate capacity. After the turnaround, more corporate centre functions were brought back in house. Lesson: Shared services or outsourcing can bring economies but also risks: loss of control, inability to audit, performance issues hidden by partner arrangements. Evaluate what core corporate / strategic functions you need to maintain directly. Secure strong contracts with shared service partners, clear oversight. Communication, Stakeholder Confidence, and Trust The county had a long period of low trust due to financial mismanagement. Building transparency, oversight, scrutiny, regular reporting etc., were part of the intervention’s focus. Unions pushed for protecting staff, residents had concerns over service continuity, especially in more vulnerable service areas like social care. Lesson: For any reorganization, but especially where failure precedes it, restoring trust is vital. That requires transparency, honest communications about what can / cannot be done by vesting day, acknowledgement of past failings, and visible improvements even before Go-Live. Capacity & Resource Constraints The legacy councils had variation in capacity; recruitment/retention issues; some services burdened; also having to build up unified IT/software, dealing with legacy locations, multiple sites. Also, COVID stretched capacity. Lesson: Be realistic about staff capacity, budget pressures, and operational resource constraints. Plan for redundancy/overlaps, but also for gaps. Central resources (corporate centre, commissioning, IT, legal) are critical and often under-estimated. Image source: Microsoft 365 content library

## Slide 21: Conclusion
Managing Complex Reorganisations
Establishing the authority is complex but also exciting and an opportunity to create something better than the sum of its old parts ! .
Strong Governance Importance
Strong governance frameworks are crucial for guiding successful organisational transitions and ensuring safe and legal on day 1.
Leadership and Planning
Clear planning combined with effective leadership drives successful outcomes in reorganisation efforts and ultimately improves peoples lives ….
Notes: The journey of establishing and leading the North Northamptonshire Shadow Authority offers valuable insights into managing complex reorganisations. Strong governance, clear planning, and effective leadership are key to success.